## Table 1
SPARK – North East Link – Primary Package Inspection and Test Plan (ITP)
ITP Title: Earthworks Excavation (Including Subgrade Preparation) ITP Number: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev 0 LOT Number:
Primary Asset Location Code:
Discipline:
Spark NELPP Approval Record
Function |  |  |  | Position |  |  | Name |  |  |  | Signature |  |  |  | Date
Prepared By |  |  |  | Quality Representative |  |  | Abiola Olulana |  |  |  | Abiola Olulana Digitally Date: 20 |  |  |  | signed by Abiola Olulana 22.08.18 16:59:17 +10'00'
Reviewed By |  |  |  | Senior Project Engineer |  |  | Matthew Watson |  |  |  | Wats 2022 16:4 |  |  |  | on, Matthew .08.19 3:18 +10'00'
Approved By |  |  |  | Quality Manager |  |  | Greg Iro |  |  |  | Digita Date: +10'00 |  |  |  | lly signed by Greg Iro 2022.08.22 09:35:30 '
Note:
1. Ensure all Records or Checklist References are attached and that each Inspection Requirement is clearly named, signed, and dated. 2. Ensure every Records or Checklist References attached are legible 3. This Inspection Test Plan may be generic – ensure the requirement is demographically clear to your scope of work 4. Verification Inspections where applicable for the IREA stated as “Witness” or “Hold” shall be formally notified for their engagement and with sufficient advance notice time (i.e. 3 days or as agreed with the Sub-IREA Representative and/or the Nominated Authority) 5. All Nominated Authority Hold Points are Witness Points for Sub-IREA 6. The Sub-IREA representative is not required to physically sign-off on ITPs
ITP – Earthworks Excavation (Including Subgrade Preparation) Document Number: NEL-CNT-SDC-2990-PQA-ITP-0011. Revision: 0 | [7 empty] | Spark PMS Doc# MSF28-2-NEL Rev 3
Management System - Uncontrolled Document when Printed Webuild Source Doc# MSF28-2 Page 1 of 11
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: This ITP covers forming and grading of subgrade | [16 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
1 | Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
1.1 | PE | Construction Package Approval |  |  | PSDR Part F6 2 (a) to (h) | Construction Documentation shall be submitted and approved prior to commencing work at site. |  |  |  | R |  | PW | NR |  |  | HP |  | NR |  | NR | IFU Construction Package InEight Reference: #
1.2 | PE | Design status |  |  | PSDR Part F5, 2(b) & (c)(i) | Design to be IFC prior to works commencing |  |  |  | V |  | PL | NR |  |  | HP |  | NR |  | NR | IFC Drawings InEight Reference: #
1.3 | SE | All Equipment calibrated |  |  | Quality Management Plan Section 11.1 | Equipment calibration certificates filed in InEight Ensure all equipment associated with the relevant works is calibrated |  |  |  | R |  | PW | HP |  |  | HP |  | NR |  | NR | Calibration Certificates InEight Reference: #
1.4 | PE | Survey Set Out |  |  | PSDR Part F4 Section 6 IFC Drawings VicRoads 703.17 IFC Drawings | Clearly mark limit of works; Chainage, offsets, cut/fill level etc. (if required) |  |  |  | V |  | PW | HP |  |  | HP |  | NR |  | NR | Survey Record InEight Reference: # This ITP Lot Map
1.5 | PE | Stabilisation – Mix Design |  |  | VR290.08 | The Contractor shall not commence work until all mix design details including the stabilising binder spreading rates have been presented to the Nominated Authority for review. If the Contractor is required to determine the Design Distribution Rate of the stabilised binder(s), evidence shall be produced to show that the |  |  |  | V |  | PW | HP |  |  | HP |  | HP |  | WP | Mix Design HP Release InEight Reference: #
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: This ITP covers forming and grading of subgrade | [16 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
material properties specified in clause 290.07(a) or clause 290.17(a) as appropriate have been met.
1.6 | SE | Stabilization Material Compliance |  |  | VR 290.05 (a) (b) (c) | Material approved for use in accordance with the relevant design recommendation and specification - Lime - Cementitious Binder All quicklime and hydrated lime supplied to the job shall be provided with delivery docket showing an assigned ALI at the start of each production week. The assigned ALI shall be determined by averaging the six most recent test results for ALI. A test certificate for determination of the ALI shall be made available on request. Lime shall be stored in a moisture free environment and shall be re-tested for compliance with AS 1672.1 if stored for more than 14 days after receipt from the manufacturer The Contractor shall nominate the type, brand and source of cement proposed. GP or GB cement complying with AS 3972 may be used Water added to the material shall be potable water. |  |  |  | T |  | PW | HP |  |  | HP |  | NR |  | NR | Material Approval InEight Reference: # Delivery Dockets Test Certificate
1.7 | PE | Type GP (if required) |  |  | VR290.10 (a) | If Type GP is proposed, the Nominated Authority shall be first notified and |  |  |  | R |  | PW | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference:
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: This ITP covers forming and grading of subgrade | [16 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
[6 empty] | evidence provided to show that the earthworks material can be mixed and compacted to the specified density within the Maximum Allowable Working Time for Type GP Cement. | [14 empty] | #
1.8 | PE | Stabilization Procedure |  |  | VR290.10 | Lime and cement stabilisation procedure must be approved prior to commencement of works |  |  |  | R |  | PW | HP |  |  | HP |  | NR |  | NR | Approved Stabilization Procedure
1.9 | PE | Material Category |  |  | VR 204.06 (c) | Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04 |  |  |  | T |  | PW | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference: # Test Results
2 | Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
2.1 | SE | Subgrade Quality Assessment |  |  | VicRoads 204.06 (d) 204.07 (d) | In situ material below at Cut Floor Level shall be visually assessed to identify the location and extent of excessively wet, unstable and otherwise unsuitable materials. The Nominated Authority must be informed of the location and area of the unsuitable material and its proposed in situ treatment or extent of excavation to the Superintendent for |  |  |  | V |  | PL | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference: #
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: This ITP covers forming and grading of subgrade | [16 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
review. This must be accompanied by a Geotechnical Assessment. Oversize material shall be treated in accordance with clause 204.08
2.2 | PE | Subgrade Quality: Treatment of Unsuitable Material |  |  | VicRoads 204.06 (e) 204.07(b) | Where unsuitable material is encountered the following treatments are available (i) In situ material below Cut Floor, shall be removed to a depth of 400 mm below Cut Floor Level and replaced with conforming Type B material to the underside of the capping or selected material layer, or where no capping or selected material is required, to subgrade level. (ii )Where removal and replacement of material below the Cut Floor Level is not required, the surface shall be loosened to a depth of 150 mm and re- compacted to meet the specified requirements. |  |  |  | V |  | PW | HP |  |  | HP |  | NR |  | NR
2.3 | SE | Stabilisation Preliminary Trial (if required) |  |  | VR290.11 | Stabilisation shall not proceed outside the trial sections until the Nominated Authority has reviewed all aspects of the work. If the Specification requirements are not met for the trial, the Nominated Authority may direct that another trial be undertaken or that the work be re stabilised and presented for re assessment. |  |  |  | V |  | PW | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference: #
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: This ITP covers forming and grading of subgrade | [16 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
2.4 | SE | Stabilization Construction |  |  | VR290.10 | Unless otherwise specified, stabilisation work undertaken each day shall be completed across the full pavement width. |  |  |  | V |  | PL | WP |  |  | WP |  | NR |  | NR | - Daily Work Record - Binder spreading Record
2.5 | PE | Subgrade Quality: Treatment of Rock Subgrade (if required) |  |  | VicRoads 204.06(f) | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Nominated Authority for acceptance. The Contractor shall submit details of any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces to the Nominated Authority for review. Where rock exists in a cut below subgrade level, the material shall be excavated to a depth of not less than 150mm below subgrade (Top of capping) level and all loose material and soil shall be removed from the rock floor. Any resulting depressions lower than 150mm below subgrade level shall be cleaned of loose material and backfilled with 20 mm Class 3, 3% cement treated crushed rock and compact to refusal. A regulating layer of Class 4, 20 mm Crushed Rock shall then be placed above the rock to subgrade level in |  |  |  | V |  | PL | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference: #
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: This ITP covers forming and grading of subgrade | [16 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
lieu of the specified capping or selected material, in layers not exceeding a compacted thickness of 150 mm in accordance with Section 304
2.6 | PE | Groundwater Seepage |  |  | VR 204.06(h) | Where groundwater or seepage is encountered the Contractor shall notify the Nominated Authority and submit the proposed action to be taken to the Nominated Authority for review. |  |  |  | V |  | PL | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference: # Approvals from relevant authorities
2.7 | SE | Fill Construction |  |  | VR204.10 | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority |  |  |  | V |  | PL | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference: #
2.8 | PE | Proof Roll |  |  | VR204.12, VR204.13, VR173 | Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with section 173. Compliance with the test rolling requirements shall be when an area exhibits deformation or springing but still allows for the effective placement and compaction of the overlaying fill material. Arrange for the Nominated Authority to be present during all test rolling. |  |  |  | V |  | PL | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference: # Test Roll Record
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: This ITP covers forming and grading of subgrade | [16 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
Where areas in excess of 20% of the area being test rolled do not meet the requirements, the whole are shall be ripped and re compacted re compacted as specified above, and re presented for test rolling.
2.9 | SE | CBR and Percentage Swell Testing |  |  | VR 204.14 (a), 290.14 (d), Table 204.141 290.15, Table 290.151 | The initial lot of the stabilised material shall be tested to determine the Assigned CBR in accordance with RC 500.20. Unless otherwise approved by the Superintendent, sampling for CBR testing shall be undertaken after field compaction of the initial lot.accordance with treatment of unsuitable material |  |  |  | V |  | X1 | WP |  |  | WP |  | WP |  | WP | WP Release InEight Reference: #
2.1 | SE | Subgrade Compaction and Moisture Content Testing |  |  | VR 204.13, 204.14 (c) Table 204.142 204.15 290.14 Table 290.142 | Subgrade compaction and moisture content testing shall be done to Scale requirements specified by the designer. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer |  |  |  | V |  | X1 | WP |  |  | WP |  | WP |  | WP | WP Release InEight Reference: # NATA Compaction Test Report
2.11 | SE | Subgrade Finish Level and Conformance |  |  | VicRoads 204.03 (g) Table 204.031 | The surface shall be assessed by random levelling and shall comply with the requirements of Clause 204.03(h) The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, |  |  |  | V |  | X1 | WP |  |  | WP |  | WP |  | WP | WP Release InEight Reference: #
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: This ITP covers forming and grading of subgrade | [16 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
except across a crown and water shall not pond at any point.
2.12 | SE | Disposal of Excess Material |  |  | PSDR Part F6 Section 15.2 (b)(xv)(c) | Tracking sheet to be filled out for every load not passing a SPARK weighbridge. |  |  |  | V |  | PL | WP |  |  | WP |  | NR |  | NR | Certified Weighbridge Docket Material tracking form
3 | Post Operations (Include Inspection and Testing)
3.1 | PE | Verification and Lot Records complete |  |  | CQMP Section 8.3 | Progressive monitoring and signoff of Checklists occurs, and test records are collected. Ensure completed work checklists, inspection and test results and Subcontractor conformance records are progressively and permanently saved and stored as soon as possible after they are received. Completed construction lot records are transferred to the project Quality Team for final record verification prior to being closed |  |  |  | V |  | PL | HP |  |  | HP |  | NR |  | NR | This ITP Lot Map
3.2 | PE | NCR Close out (if applicable) |  |  | CQMP Section 8.3 | All NCR’s presented for closure |  |  |  | R |  | PL | HP |  |  | HP |  | HP |  | WP | HP Release InEight Reference: # NCR InEight Reference: #
4 | Quality
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Earthworks Excavation (Including Subgrade Preparation) | [16 empty] | References: Drawing numbers and specifications - VR204, VR290, Construction Quality Management Plan (CQMP), Project Scope and Delivery Requirement (PSDR)
Description: |  | This ITP covers forming and grading of subgrade | [14 empty] | Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0011 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference | Acceptance Criteria |  |  |  | Test Method |  | Test Freq. | Inspection/Verification (Name, signature & date) | [7 empty] | Records/Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority |  | IREA
4.1 | QSR | Identification and control of non- conforming products or services (if applicable) |  |  | CQMP Section 8.3 | Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot |  |  |  | R |  | PL |  |  |  | HP |  |  |  |  | NCR closed with related documentation
4.2 | QSR | Check all quality records for lot closure |  |  | CQMP Section 8.3 | All applicable quality records are complete |  |  |  | R |  | PL |  |  |  | HP |  |  |  |  | Compiled documents (all data reports and records)
Legend:
Responsibility | [8 empty] | Method |  |  |  |  | Inspection / Verification |  |  |  |  | Test Frequency |  | Other
SS: Site Supervisor SE: Site Engineer PE: Project Engineer SPE: Senior Project Engineer GE: Geotechnical Engineer PS: Project Surveyor |  |  |  |  | PSM: Project Systems Manager QSR: Quality Site Rep. STR: Structural Engineer SSR: Site Safety Rep. EMR: Environmental Management Rep. NA: Nominated Authority (Release of HP) IREA: Independent Reviewer (Observer) |  |  |  | V: Verify I: Inspection R: Review T: Test |  |  |  |  | HP: Hold Point WP: Witness Point NR: Not Required |  |  |  |  | PW: Prior to Works PL: Per Lot F: Full or 100% Inspection or Testing X1: Inspect or Test at Specified Frequency X2: Random Inspection or Test |  | QP: Quality Plan RFI: Request for Information NCR: Non-Conformance VC: Verification Checklist XXXX: Sequential Number from Doc Control
DDD – Types: |  | B – Building, C – Civil, G – General, M – Mechanical & Electrical, I – Motorway Operations System (ITS), S – Structure, O – Tolling, T – Tunnel, U – Urban Design & Landscape
Supplier/Subcontractor: (If applicable) |  |  | Name |  |  | Signature and Date |  |  |  | Spark-NELPP REP | [5 empty] | Name | [5 empty] | Signature Date |  | and
Lot closure comments:
Spark NELP QA Rep: Name Signature: Date: