## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | NEL-CNT-SDC-2990-PQA-ITP-0011 Rev 0 - Earthworks Excavation (Including Subgrade Preparation) | itp |  |  |  |  | NEL-CNT-SDC-2990-PQA-ITP-0011 Rev 0 - Earthworks Excavation (Including Subgrade Preparation)
section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint | 1.1 - Construction Package Approval
label | Resp. Person - PE
label | Specification Reference - PSDR Part F6 2 (a) to (h)
label | Acceptance Criteria - Construction Documentation shall be submitted and approved prior to commencing work at site.
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - IFU Construction Package
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Design status
label | Resp. Person - PE
label | Specification Reference - PSDR Part F5, 2(b) & (c)(i)
label | Acceptance Criteria - Design to be IFC prior to works commencing
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - IFC Drawings
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - All Equipment calibrated
label | Resp. Person - SE
label | Specification Reference - Quality Management Plan Section 11.1
label | Acceptance Criteria - Equipment calibration certificates filed in InEight
label | • Ensure all equipment associated with the relevant works is calibrated
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Calibration Certificates
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey Set Out
label | Resp. Person - PE
label | Specification Reference - PSDR Part F4 Section 6 IFC Drawings
label | • VicRoads 703.17 IFC Drawings
label | Acceptance Criteria - Clearly mark limit of works; Chainage, offsets, cut/fill level etc. (if required)
label | Test Method - V
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
textbox | • Survey Record InEight Reference: #
label | • This ITP Lot Map
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Stabilisation – Mix Design
label | Resp. Person - PE
label | Specification Reference - VR290.08
label | Acceptance Criteria - The Contractor shall not commence work until all mix design details including the stabilising binder spreading rates have been presented to the Nominated Authority for review.
label | • If the Contractor is required to determine the Design Distribution Rate of the stabilised binder(s), evidence shall be produced to show that the material properties specified in clause 290.07(a) or clause 290.17(a) as appropriate have been met.
label | Test Method - V
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - Mix Design HP Release
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Stabilization Material Compliance
label | Resp. Person - SE
label | Specification Reference - VR 290.05 (a) (b) (c)
label | Acceptance Criteria - Material approved for use in accordance with the relevant design recommendation and specification
label | – Lime
label | – Cementitious Binder
label | • All quicklime and hydrated lime supplied to the job shall be provided with delivery docket showing an assigned ALI at the start of each production week.
label | • The assigned ALI shall be determined by averaging the six most recent test results for ALI.
label | • A test certificate for determination of the ALI shall be made available on request.
label | • Lime shall be stored in a moisture free environment and shall be re-tested for compliance with AS 1672.1 if stored for more than 14 days after receipt from the manufacturer
label | • The Contractor shall nominate the type, brand and source of cement proposed. GP or GB cement complying with AS 3972 may be used
label | • Water added to the material shall be potable water.
label | Test Method - T
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
textbox | • Material Approval InEight Reference: #
label | • Delivery Dockets Test Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Type GP (if required)
label | Resp. Person - PE
label | Specification Reference - VR290.10 (a)
label | Acceptance Criteria - If Type GP is proposed, the Nominated Authority shall be first notified and evidence provided to show that the earthworks material can be mixed and compacted to the specified density within the Maximum Allowable Working Time for Type GP Cement.
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Stabilization Procedure
label | Resp. Person - PE
label | Specification Reference - VR290.10
label | Acceptance Criteria - Lime and cement stabilisation procedure must be approved prior to commencement of works
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Approved Stabilization Procedure
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Material Category
label | Resp. Person - PE
label | Specification Reference - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | Acceptance Criteria - T
label | Test Method - T
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | • InEight Reference: #
label | • Test Results
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
checkpoint | 2.1 - Subgrade Quality Assessment
label | Resp. Person - SE
label | Specification Reference - VicRoads 204.06 (d) 204.07 (d)
label | Acceptance Criteria - In situ material below at Cut Floor Level shall be visually assessed to identify the location and extent of excessively wet, unstable and otherwise unsuitable materials.
label | • The Nominated Authority must be informed of the location and area of the unsuitable material and its proposed in situ treatment or extent of excavation to the Superintendent for review. This must be accompanied by a Geotechnical Assessment.
label | • Oversize material shall be treated in accordance with clause 204.08
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Subgrade Quality: Treatment of Unsuitable Material
label | Resp. Person - PE
label | Specification Reference - VicRoads 204.06 (e) 204.07(b)
label | Acceptance Criteria - Where unsuitable material is encountered the following treatments are available
label | (i) In situ material below Cut Floor, shall be removed to a depth of 400 mm below Cut Floor Level and replaced with conforming Type B material to the underside of the capping or selected material layer, or where no capping or selected material is required, to subgrade level.
label | (ii) Where removal and replacement of material below the Cut Floor Level is not required, the surface shall be loosened to a depth of 150 mm and re-compacted to meet the specified requirements.
label | Test Method - V
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Stabilisation Preliminary Trial (if required)
label | Resp. Person - SE
label | Specification Reference - VR290.11
label | Acceptance Criteria - Stabilisation shall not proceed outside the trial sections until the Nominated Authority has reviewed all aspects of the work.
label | • If the Specification requirements are not met for the trial, the Nominated Authority may direct that another trial be undertaken or that the work be re stabilised and presented for re assessment.
label | Test Method - V
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Stabilization Construction
label | Resp. Person - SE
label | Specification Reference - VR290.10
label | Acceptance Criteria - Unless otherwise specified, stabilisation work undertaken each day shall be completed across the full pavement width.
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Daily Work Record
label | • Binder spreading Record
checkpoint | 2.5 - Subgrade Quality: Treatment of Rock Subgrade (if required)
label | Resp. Person - PE
label | Specification Reference - VicRoads 204.06(f)
label | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Nominated Authority for acceptance.
label | • The Contractor shall submit details of any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces to the Nominated Authority for review.
label | • Where rock exists in a cut below subgrade level, the material shall be excavated to a depth of not less than 150mm below subgrade (Top of capping) level and all loose material and soil shall be removed from the rock floor. Any resulting depressions lower than 150mm below subgrade level shall be cleaned of loose material and backfilled with 20 mm Class 3, 3% cement treated crushed rock and compact to refusal.
label | • A regulating layer of Class 4, 20 mm Crushed Rock shall then be placed above the rock to subgrade level in lieu of the specified capping or selected material, in layers not exceeding a compacted thickness of 150 mm in accordance with Section 304
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Groundwater Seepage
label | Resp. Person - PE
label | Specification Reference - VR 204.06(h)
label | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Nominated Authority and submit the proposed action to be taken to the Nominated Authority for review.
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
textbox | • HP Release InEight Reference: #
label | • Approvals from relevant authorities
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Fill Construction
label | Resp. Person - SE
label | Specification Reference - VR204.10
label | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Proof Roll
label | Resp. Person - PE
label | Specification Reference - VR204.12, VR204.13, VR173
label | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with section 173.
label | • Compliance with the test rolling requirements shall be when an area exhibits deformation or springing but still allows for the effective placement and compaction of the overlaying fill material.
label | • Arrange for the Nominated Authority to be present during all test rolling.
label | • Where areas in excess of 20% of the area being test rolled do not meet the requirements, the whole are shall be ripped and re compacted re compacted as specified above, and represented for test rolling.
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | • InEight Reference: #
label | • Test Roll Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - CBR and Percentage Swell Testing
label | Resp. Person - SE
label | Specification Reference - VR 204.14 (a), 290.14 (d), Table 204.141 290.15, Table 290.151
label | Acceptance Criteria - The initial lot of the stabilised material shall be tested to determine the Assigned CBR in accordance with RC 500.20.
label | • Unless otherwise approved by the Superintendent, sampling for CBR testing shall be undertaken after field compaction of the initial lot. accordance with treatment of unsuitable material
label | Test Method - V
label | Test Freq. - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - WP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - WP Release
textbox | • InEight Reference: #
checkpoint | 2.10 - Subgrade Compaction and Moisture Content Testing
label | Resp. Person - SE
label | Specification Reference - VR 204.13, 204.14 (c) Table 204.142 204.15 290.14 Table 290.142
label | Acceptance Criteria - Subgrade compaction and moisture content testing shall be done to Scale requirements specified by the designer.
label | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer
label | Test Method - V
label | Test Freq. - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - WP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
textbox | • WP Release InEight Reference: #
label | • NATA Compaction Test Report
checkpoint | 2.11 - Subgrade Finish Level and Conformance
label | Resp. Person - SE
label | Specification Reference - VicRoads 204.03 (g) Table 204.031
label | Acceptance Criteria - The surface shall be assessed by random levelling and shall comply with the requirements of Clause 204.03(h) The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | Test Method - V
label | Test Freq. - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - WP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - WP Release
textbox | • InEight Reference: #
checkpoint | 2.12 - Disposal of Excess Material
label | Resp. Person - SE
label | Specification Reference - PSDR Part F6 Section 15.2 (b)(xv)(c)
label | Acceptance Criteria - Tracking sheet to be filled out for every load not passing a SPARK weighbridge.
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Certified Weighbridge Docket
label | • Material tracking form
section | 3.0 Post Operations (Include Inspection and Testing)
checkpoint | 3.1 - Verification and Lot Records complete
label | Resp. Person - PE
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - Progressive monitoring and signoff of Checklists occurs, and test records are collected. Ensure completed work checklists, inspection and test results and Subcontractor conformance records are progressively and permanently saved and stored as soon as possible after they are received.
label | • Completed construction lot records are transferred to the project Quality Team for final record verification prior to being closed
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - This ITP Lot Map
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - NCR Close out (if applicable)
label | Resp. Person - PE
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - All NCR’s presented for closure
label | Test Method - R
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
textbox | • HP Release InEight Reference: #
textbox | • NCR InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Quality
checkpoint | 4.1 - Identification and control of non- conforming products or services (if applicable)
label | Resp. Person - QSR
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot
label | Test Method - R
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Records/Documents - NCR closed with related documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Check all quality records for lot closure
label | Resp. Person - QSR
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - All applicable quality records are complete
label | Test Method - R
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Records/Documents - Compiled documents (all data reports and records)
holdpoint | AUTHORITY HOLDPOINT