## PAVEMENT RENEWALS – Unbound Gra
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 20240402 ITP_V1 | Rev.: | 1 |  | H | Client Rep
|  | Project: | 20240402_Dunedin Airport ITP_V1 (Pavement Construction Area 1,2,3,3A,4 &5) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
20240402_Dunedin Airport ITP_V1 |  |  | As per Sppecification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Pre-Construction (P&G/Establishment) | [11 empty] | W & I | Supplier
1.1 | General
1.1.1 | Contract Management plans, (including ITP) |  | Project Manager | The Contractor to provide contract management plans as defined in the project specification prior to commencement of works. ITP to be reviewed and updated upon receipt of construction issue drawings/Specification. | Prior to physical works | Project Specification NTC / Email verification approving Contract Management Plans | YES | H | H | H
2 | Site Specific Requirements
2.1 | Construction Pack (SSSP/CBP) |  | SE, FM | Construction Pack including Site Specific Safety Plan developed for work area and issued to Engineer in advance of works. | Prior to physical works 1 per site | Downer/Construction Pack | YES | H | R | H
2.2 | Service Location |  | SE, FM | Complete the Excavation permit process to identify, locate and protect all services. | Prior to Excavation 1 per site/work area | Downer/Excavation Permit | YES | H | R | H
2.3 | Internal Permits |  | SE | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Prior to Excavation as needed | Downer/Internal Permits | YES | H | R | H
2.4 | External Permits |  | SE | Obtain External Permits as required to complete works including but not limited to: Airport Inductions, Close approach, Worksafe Notice etc. | Prior to Excavation as needed | Downer/External Permits | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Shaun Campbell |  | Rowan Tumai
DATE: 24/04/2024 |  |  | DATE: 24/04/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 20240402 ITP_V1 | Rev.: | 1 |  | H | Client Rep
|  | Project: | 20240402_Dunedin Airport ITP_V1 (Pavement Construction Area 1,2,3,3A,4 &5) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
20240402_Dunedin Airport ITP_V1 |  |  | As per Sppecification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
3 | Material, Personnel & Third Party Approval | [11 empty] | W & I | Supplier
3.1 | Construction
3.1.1 | Insitu Subgrade Fill Material |  | SE | AP150 - Duncans Quarry (Abbotsford) | Annually/Project | Project Specification/As per NZTA Specifications | YES | H | R | H
3.1.2 | Insitu Subgrade Fill Material |  | SE | AP65 - - Duncans Quarry (Abbotsford) | Annually/Project | Project Specification/As per NZTA Specifications | YES | H | R | H
3.1.3 | Basecourse Aggregates |  | SE | M4-AP40 - Blackhead Quarries | Annually/Project | Project Specification/As per NZTA Specifications | YES | H | R | H
3.1.4 | Basecourse Aggregates |  | SE | M4-AP20 - Duncans Quarry (Abbotsford) | Annually/Project | Project Specification/As per NZTA Specifications
3.1.5 | Geofabric |  | SE | Installation of geogrid/geocloth (A29/TX160) when instructed by Engineer. AP65 Compacted in layers not exceeding 200mm | Annually/Project | NZTA F/1 TNZ M/3 Notes/As per NZTA Specifications | YES | H | R | H
3.2 | Paving
3.2.1 | Road Asphalt |  | SE | 50mm AC14 | Supplied/approved annually by Engineer to Contract/Prior to AC | Project Specification TNZ M/10:2020/Approved Mix Design | YES | H | R | H
3.2.2 | Road Asphalt |  | SE | 90mm EME2 (Trial Mix) | Supplied/approved annually by ETC/Prior to AC | Project Specification NZTA M32: 2021/Approved Mix Design | YES | H | R | H
3.3 | Pavement Marking
3.3.1 | Standard Marking |  | SE | Standards pavement marking. Paint shall comply with TNZ M7 and shall be on the current Transit New Zealand list of approved paints. | Approved once by ETC/Prior to Line Marking | Project Specification TNZ/LTSA (MOTSAM)/Approved pavement marking quality system | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Shaun Campbell |  | Rowan Tumai
DATE: 24/04/2024 |  |  | DATE: 24/04/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 20240402 ITP_V1 | Rev.: | 1 |  | H | Client Rep
|  | Project: | 20240402_Dunedin Airport ITP_V1 (Pavement Construction Area 1,2,3,3A,4 &5) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
20240402_Dunedin Airport ITP_V1 |  |  | As per Sppecification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
4 | Construction Activity - Excavation/Prep/Pavement | [11 empty] | W & I | Supplier
4.1 | Excavation
4.1.1 | Site Clearance |  | SE, ENG | Unless shown otherwise on the drawings or directed by the Engineer, all vegetation, shrubs, trees under 3m in height, fences and foundations, retaining timbers, abandoned pipes and services, etc over the contract length and within the extent of the earthworks shall be removed off site. All waste will be disposed at DIAL approved location. | Prior to Excavation/clearance works/per site | Project Specification/Pre construction walkover inspection DNZ Field Inspection Record | YES | H | R | H
4.1.2 | Excavation |  | SE | Excavation carried out as per project extents detailed on construction issue drawings. Level as per subgrade requirements below. | Per site specific requirements/as required | NZTA F1 DNZ Field Inspection Record | YES | H | R | H
5 | Subgrade
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Shaun Campbell |  | Rowan Tumai
DATE: 24/04/2024 |  |  | DATE: 24/04/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 20240402 ITP_V1 | Rev.: | 1 |  | H | Client Rep
|  | Project: | 20240402_Dunedin Airport ITP_V1 (Pavement Construction Area 1,2,3,3A,4 &5) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
20240402_Dunedin Airport ITP_V1 |  |  | As per Sppecification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
5.1.1 | Subgrade Suitability Inspection |  | SE, ENG | The Subgrade must be inspected by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient. Where Scala testing is deemed unsuitable by Contractor (hardfill or Service Strike Risk etc). Visual inspection by Engineer supersedes foundation testing requirements - Site instruction required. Should material be determined as unsuitable (highly organic, saturated clay pug etc) Contractor to elevate to Engineer who will determine whether the material is unsuitable or not and agree the extent of the unsuitable material with the Contractor. | 20m where practical Not required for failed visual inspection areas (ie wet pug, highly organic material)/per site | NZTA F/1 Scala Report (CBR 5) 3blows per 100mm Visual Inspection DNZ Field Inspection Record | YES | H | R | H |  |  | W & I | Supplier
5.1.2 | Geofabric installation |  | SE | Installation of geogrid/geocloth (A29/TX160) as per design. AP40 compacted in layer not exceeding 100mm, AP65 not exceeding 200mm and AP150 not exceeding 300mm. | 10,000m3/Project | NZTA F/1 TNZ M/3 Notes IANZ Lab Reports (on request) | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Shaun Campbell |  | Rowan Tumai
DATE: 24/04/2024 |  |  | DATE: 24/04/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 20240402 ITP_V1 | Rev.: | 1 |  | H | Client Rep
|  | Project: | 20240402_Dunedin Airport ITP_V1 (Pavement Construction Area 1,2,3,3A,4 &5) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
20240402_Dunedin Airport ITP_V1 |  |  | As per Sppecification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
5.1.3 | Subgrade formation level - Kerbs |  | SE | Excavation Min 300mm from design lip level (road tie in) allowing for minimum 120mm M440 foundation for kerbs. | Per site specific requirements/Project | Downer NZTA B/2:2005 DNZ Field Inspection Record | YES | H | R | H |  |  | W & I | Supplier
6 | Construction Activity - Pavement Areas
6.1 | Area 1
6.1.1 | Remove top 100mm |  | SE | Rip surface and lime treat subbase | 1 per pavement area | Project Specification Photographic records with measuring tape | Yes | H | R | H
6.1.2 | Subject to Beams Test |  | SE | Backfill or Seal | 1 per pavement area | Project Specification Photographic records and Results | Yes | H | R | H
6.1.3 | Backfill |  | SE | AP40 and stabilise top 200mm | 1 per pavement area | Project Specification Photographic records with measuring tape | Yes | H | R | H
6.1.4 | Surfacing |  | SE | 90mm EME2 (Trial Mix) | Prior to AC/1 per pavement area | Project Specification Approved Mix Design | Yes | H | R | H
6.2 | Area 2
6.2.1 | Remove top 600mm |  | SE |  | 1 per pavement area | Project Specification Photographic records with measuring tape | Yes | H | R | H
6.2.2 | Geofabric |  | SE | A29 Fabric | 1 per pavement area | Project Specification Photographic records | Yes | H | R | H
6.2.3 | AP150 |  | SE | 300mm | 1 per pavement area | Project Specification Photographic records with measuring tape | Yes | H | R | H
6.2.4 | Geofabric |  | SE | TX160 | 1 per pavement area | Project Specification Photographic records | Yes | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Shaun Campbell |  | Rowan Tumai
DATE: 24/04/2024 |  |  | DATE: 24/04/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 20240402 ITP_V1 | Rev.: | 1 |  | H | Client Rep
|  | Project: | 20240402_Dunedin Airport ITP_V1 (Pavement Construction Area 1,2,3,3A,4 &5) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
20240402_Dunedin Airport ITP_V1 |  |  | As per Sppecification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
6.2.5 | AP65 |  | SE | 200mm | 1 per pavement area | Project Specification Photographic records with measuring tape | Yes | H | R | H
6.2.6 | AP40 |  | SE | 100mm | 1 per pavement area | Project Specification Photographic records | Yes | H | R | H
6.2.7 | Surfacing |  | SE | 90mm EME2 (Trial Mix) | 1 per pavement area | Project Specification Approved Mix Design | Yes | H | R | H
6.3 | Area 3 & 3A
6.3.1 | Remove existing surface |  | SE |  | 1 per pavement area | Project Specification Photographic records | YES | H | R | H
6.3.2 | Prep to suit existing kerb and drianage |  | SE | AP150 | 1 per pavement area | Project Specification Photographic records with measuring tape and falls | YES | H | R | H
6.3.3 | Surfacing |  | SE | 50mm AC14 | 1 per pavement area | Project Specification Approved Mix Design | YES | H | R | H
6.4 | Area 4
6.4.1 | Remove top 650mm |  | SE |  | 1 per pavement area | Project Specification Photographic records with measuring tape | YES | H | R | H
6.4.2 | Geofabric |  | SE | A29 Fabric | 1 per pavement area | Project Specification Photographic records | YES | H | R | H
6.4.3 | AP150 |  | SE | 300mm | 1 per pavement area | Project Specification Photographic records with measuring tape | YES | H | R | H
6.4.4 | Geofabric |  | SE | TX160 | 1 per pavement area | Project Specification Photographic records | YES | H | R | H
6.4.5 | AP65 |  | SE | 200mm | 1 per pavement area | Project Specification Photographic records with measuring tape | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Shaun Campbell |  | Rowan Tumai
DATE: 24/04/2024 |  |  | DATE: 24/04/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 20240402 ITP_V1 | Rev.: | 1 |  | H | Client Rep
|  | Project: | 20240402_Dunedin Airport ITP_V1 (Pavement Construction Area 1,2,3,3A,4 &5) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
20240402_Dunedin Airport ITP_V1 |  |  | As per Sppecification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
6.4.6 | AP40 |  | SE | 100mm | 1 per pavement area | Project Specification Photographic records | YES | H | R | H
6.4.7 | Surfacing |  | SE | 50mm AC14 | 1 per pavement area | Project Specification Photographic records | YES | H | R | H
6.5 | Area 5 - Optional
6.5.1 | Mill top 90mm |  | SE |  | 1 per pavement area | Project Specification Photographic records | YES | H | R | H
6.5.2 | Subject to Beams Test |  | SE | Backfill or Seal | 1 per pavement area | Project Specification Photographic records and Results | YES | H | R | H
6.5.3 | Backfill |  | SE | AP40 and stabilise top 200mm | 1 per pavement area | Project Specification Photographic records | YES | H | R | H
6.5.4 | Surfacing |  | SE | 90mm EME2 (Trial Mix) | 1 per pavement area | Project Specification Approved Mix Design | YES | H | R | H
7 | Post Construction (Final Inspection and Handover)
7.1 | Final Completion inspection |  | PM, ENG | Walk over completed with the Engineer/Engineers Representative to review completed works. Noting any minor omissions, transfer to snag list (NCR if deemed necessary) | Each Site (School Zone etc)/Per package of works | DNZ Field Inspection Record Practical Completion Certificate (Per package of works, ie SP1/SP2) | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Shaun Campbell |  | Rowan Tumai
DATE: 24/04/2024 |  |  | DATE: 24/04/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | 20240402 ITP_V1 | Rev.: | 1 |  | H | Client Rep
|  | Project: | 20240402_Dunedin Airport ITP_V1 (Pavement Construction Area 1,2,3,3A,4 &5) | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
20240402_Dunedin Airport ITP_V1 |  |  | As per Sppecification Ref, Procedure Or Method Statement |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
DOWNER | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
7.2 | Construction Record Compilation |  | SE | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Post construction/Per package of works | Records | YES | H | R | H
7.3 | Survey Records |  | SV | Ensure all items have been surveyed and records are assembled for asbuilting | Post construction/Per package of works | Records | Yes | H | R | H
7.4 | Asbuilt Drawings |  | SE | Supplied in accordance with Project specification | Post construction/Per package of works | Records | YES | H | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Shaun Campbell |  | Rowan Tumai
DATE: 24/04/2024 |  |  | DATE: 24/04/2024 |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: |  | Rev.: |  |  | H | Client Rep
|  | Project: | [10 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
[7 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
[7 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Rowan Tumai
DATE: |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: |  | Rev.: |  |  | H | Client Rep
|  | Project: | [10 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
[7 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
[7 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | DOWNER ENGINEER | SUPER VISOR | SUB-CON | OTHER |  | W(5%) | Sub Supervisor
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Rowan Tumai
DATE: |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client