## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Earthworks Cut 12 Rev 1 | itp |  |  |  |  | ITP - Earthworks Cut 12 Rev 1
section | 1.0 Pre-Construction
checkpoint | 1.01 - Approved CWP
label | Method/Description - Document Review
label | Test frequency - Prior to personal starting
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - IFC issued
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Approved SCWMP
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
checkpoint | 1.04 - Investigation nail testing (Pre-construction)
label | Method/Description - Test
label | Test frequency - Pre-construction
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Test results
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Material Compliance
checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
label | Method/Description - Approval
label | Test frequency - Prior to commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Headworks
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Drapery Mesh
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Steel Wire Ropes
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Wire Rope Fittings
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.06 - Delivery of all rock drapery system components
label | Method/Description - Visual
label | Test frequency - each delivery
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Test Certificates, Material Inspection Checklist
section | 3.0 During Construction
checkpoint | 3.01 - Set out extents
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
checkpoint | 3.02 - Verify Machine Control
label | Method/Description - Survey/visual
label | Test frequency - Daily
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
checkpoint | 3.03 - Assess Crest detail
label | Method/Description - Hand augers/ slope assess/Window Samples
label | Test frequency - Prior to Excavation
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.04 - Install crest detail - Soil Nailing
label | Method/Description - Visual Inspection
label | Test frequency - Prior to cutting rock slope
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.05 - Install crest detail - Erosion Matting
label | Method/Description - Visual Inspection
label | Test frequency - Prior to cutting rock slope
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
checkpoint | 3.06 - Install Rock Fall Protection
label | Method/Description - Visual Inspection
label | Test frequency - Prior to cutting rock slope
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Check List
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.07 - Cut Face inspection - Cut Face inspection
label | Method/Description - Survey check by construction team, visual inspection by designer.
label | Test frequency - 100m2 or maximum 5m vertical cut
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, Survey record, As-built
checkpoint | 3.08 - Cut Face inspection - Cut face material verification - Geo mapping
label | Method/Description - Geo inspection and face mapping
label | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports, Face map from geotechnical engineer/geologist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.09 - Install Rock Drape - Set out drape anchorages
label | Method/Description - Geo walk over
label | Test frequency - Prior to drilling
label | Contractor - H
label | Designer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist
checkpoint | 3.10 - Install Rock Drape - Install anchors
label | Method/Description - Drill and grout records. Stressing records.
label | Test frequency - During construction and at end
label | Contractor - H
label | Designer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Rock Drape Checklist
checkpoint | 3.11 - Install Rock Bolts
label | Method/Description - Drill and grout records. Stressing records.
label | Test frequency - During construction and at end
label | Contractor - H
label | Designer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Active Mesh Checklist
checkpoint | 3.12 - Install Rock Drape - Install Drapes/Active Mesh
label | Method/Description - Visual inspection
label | Test frequency - During construction and at end
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist, Active Mesh Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.13 - Production nail acceptance tests
label | Method/Description - Test
label | Test frequency - At Completion
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test results
checkpoint | 3.14 - Production drape anchorage and Rock Bolts tests (acceptance tests)
label | Method/Description - Test
label | Test frequency - At Completion
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test results
checkpoint | 3.15 - Catch Ditch Inspection
label | Method/Description - Visual inspection
label | Test frequency - During construction and at end
label | Contractor - W
label | Designer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist
section | 4.0 Post Construction
checkpoint | 4.01 - Throughout construction period prior to road opening
label | Method/Description - Monitor
label | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Red Line Mark Up Drawings
label | Method/Description - Submit
label | Test frequency - At Completion
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
checkpoint | 4.03 - Operation and maintenance report
label | Method/Description - Submit
label | Test frequency - At Completion
label | Contractor - H
label | Designer - R
label | Client - R
label | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
checkpoint | 4.04 - Final Handover Package
label | Method/Description - Submit
label | Test frequency - At Completion
label | Contractor - H
label | Designer - R
label | Client - R
label | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements