## Table 1
INSPECTION & TEST PLAN
Inspection and Test Plan and Number | [8 empty] | OP06_f01 Inspection & Test Plan Workbook
Project Name | [8 empty] | KiwiRail – North Auckland Line Recovery – CH 128.840 | [5 empty] | Version: | [5 empty] | 2
Date: | [8 empty] | 2024-04-23 | [5 empty] | Approved in RFI#: | [5 empty] | TBC
Documents / Specifications Referenced: | [8 empty] | ENGEO NAL 128.840KM DETAILED DESIGN REPORT PRE-IFC ISSUE
| ITP# | Work Pack Element(s) |  | Drawing / Specification Ref. |  |  | Specification Detail Summary |  |  |  | Acceptance Criteria |  | Test Spec & Frequency |  |  | Control Type i.e. Checksheet / IANZ Records |  | Hold / Witness |  | Internal / External |  |  |  | PS3 Owner |  | Hold / Witness |  | PS4 Owner Sign Off
1.0 PRE-CONSTRUCTION WORKS
| 1.01 | Check IFC Drawings |  | IFC issued |  |  | Ensure latest revision is being used |  |  |  | Correct drawings |  | Prior to works, updated accordingly based on formal correspondence |  |  | Controlled IFC drawings being used – Checkpoint on QA |  | witness |  | Internal |  |  |  | JFC |  | WITNESS |  | ENGEO
| 1.02 | Erosion and Sediment Control |  | ENGEO – Detailed Design Report - NAL CH 128.84km: Section 5 |  |  | The contractor is responsible for protecting earthworks and erosion control measures, and must develop a site-specific Environmental Control Plan (ESCP) that KiwiRail must review before construction begins. |  |  |  | Contractor to ensure effective erosion and sedimentation control measures shall be installed and maintained in accordance with Auckland Council Resource Consent Requirements, and the ESCP. |  | Before construction begins |  |  | ESCP Documentation, Photos, Daily and Weekly Audits |  | HOLD |  | Internal |  |  |  | JFC |  | HOLD |  | ENGEO
| 1.03 | Environmental and Ecological Assessment |  | ENGEO – Detailed Design Report - NAL CH 128.84km: Section 6 |  |  | An ecologist from KiwiRail must be consulted and on-site to assess the site before and during the removal of vegetation and trees in a Significant Environmental Area (SEA). |  |  |  | The contractor to collaborate with the appointed ecologist from KiwiRail and adhere to the proposed controls. |  | Before and during the removal of vegetation and trees in a Significant Environmental Area (SEA). |  |  | Written Confirmation of the Ecologist’s Instructions and Approval, Photos |  | HOLD |  | Internal |  |  |  | JFC |  | HOLD |  | ENGEO
| 1.04 | Pre-start meeting |  | ENGEO – NAL CH 128.84km: Drawing 7 Note 2 |  |  | A pre-start meeting with Engineer and Contractor is needed to ensure understanding of construction methodology, review work plan and methodology for Geotechnical Professional, and ensure safety measures are in place. |  |  |  | Construction methodology agreed between Contractor and Engineer |  | Prior to commencement of works |  |  | RFI for Clarity and record purposes |  | HOLD |  | Internal |  |  |  | JFC |  | HOLD |  | ENGEO
| 2.0 DRAINAGE WORKS | [24 empty] | ENGINEER
| 2.01 | Materials |  | ENGEO – NAL CH 128.84km: Drawing 6 |  |  | All materials as per the design drawings |  |  |  | All materials comply with the drawings |  | Prior to use of materials on site |  |  | Dockets |  | HOLD |  | Internal |  |  |  | JFC |  | witness |  | ENGEO
| 2.02 | Manhole and Pipe Bedding |  | ENGEO – NAL CH 128.84km: Drawing 4 |  |  | Bedding thickness min. 200mm GAP20 |  |  |  | Engineer to confirm GAP 20 compacted to 90% MDD or CIV of 20 with Clegg Impact Hammer (in accordance with NZS 3725:2007) |  | Engineer to check prior to installation of manhole and pipe |  |  | NDM and or Clegg Test Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval |  | witness |  | Internal |  |  |  | JFC |  | witness |  | ENGEO
| 2.03 | Haunching |  | ENGEO – NAL CH 128.84km: Drawing 5 & Drawing 7 Note 1 |  |  | SP20 Compacted in 150mm layers to widest pipe width |  |  |  | Engineer to confirm SP20 compacted to at least 90% MDD |  | Engineer to check every 150mm thick compacted layer |  |  | NDM Test Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval |  | witness |  | Internal |  |  |  | JFC |  | witness |  | ENGEO
| 2.04 | Culvert Trench Backfill |  | ENGEO – NAL CH 128.84km: Drawing 5 & Drawing 7 Note 1 |  |  | Backfill to comprise of GAP65 or geotechnically approved material in max. 200mm lifts |  |  |  | Engineer to confirm GAP65 or GAP40 or PAP40 or PAP 65 approved equivalent compacted to 95% MDD at interface of sub- ballast layer (in accordance with NZS 3725:2007) – for (sub- ballast refer formation items). Subballast layer to be GAP40 |  | Engineer to check every 200mm thick compacted layer |  |  | NDM Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval |  | witness |  | Internal |  |  |  | JFC |  | witness |  | ENGEO
| ITP# | Work Pack Element(s) |  | Drawing / Specification Ref. |  |  | Specification Detail Summary |  |  |  | Acceptance Criteria |  | Test Spec & Frequency |  |  | Control Type i.e. Checksheet / IANZ Records |  | Hold / Witness |  | Internal / External |  |  |  | PS3 Owner |  | Hold / Witness |  | PS4 Owner Sign Off
compacted to 98% MDD or Clegg of 30.
| 2.04b | Culvert Trench Undercut |  | RFI 027 |  |  | Undercut where subgrade is < 70kpa as measured by hand held shear vane |  |  |  | Installed per RFI 027 detail : 300mm ballast, A29 geotextile wrapped. Duragrid 30/30 or TX160 between wrap and bedding backfill. |  | Check Subgrade every 3 pipe lengths (approx. 7.5m) |  |  | Check sheets, photos |  | witness |  | Internal |  |  |  | JFC |  | witness |  | ENGEO
| 2.04c | Wingwall Bedding |  | ENGEO – NAL CH 128.84km: Drawing 5 |  |  | Compacted hardfill min 200mm thk |  |  |  | Engineer to confirm SP20 compacted to at least 95% MDD |  | Engineer to check every 150mm thick compacted layer |  |  | NDM Test Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval |  | HOLD |  | External |  |  |  | JFC |  | witness |  | ENGEO
| 2.05 | Installation |  | ENGEO – NAL CH 128.84km: Drawing 5 & Drawing 7 Note 2 |  |  | Drainage works to be installed in accordance with the design drawings. |  |  |  | Engineer to confirm that the drainage is connected as shown on the plans. |  | Engineer to check prior to backfill of drainage items |  |  | Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval |  | witness |  | Internal |  |  |  | JFC |  | HOLD |  | ENGEO
| 3.0 TRACK FORMATION | [24 empty] | ENGINEER
| 3.01 | Structural Fill (for CBR <3%) |  | ENGEO – NAL CH 128.84km: Drawing 7, CAN- 01,RFI 001 |  |  | 900mm thick structural fill (GAP65 or GAP40 or PAP40 or PAP 65 with geogrid) RFI 001 |  |  |  | Compaction min CIV = 25 (95% MDD) |  | Clegg Hammer Tests Email 8/3/24 from KH Every 250mm with 1st lift calibrated to NDM Every 20m (email 19/3/24 J Thomas) |  |  | Photos, Clegg Test Results |  | HOLD |  | Internal |  |  |  | JFC |  | REVIEW |  | ENGEO
| 3.02 | Sub-ballast (for CBR <3%) |  | ENGEO – NAL CH 128.84km: Drawing 7, CAN- 01,RFI 001 |  |  | 150mm thick sub-ballast (M4-AP40) RFI 001 |  |  |  | Compaction min CIV = 30 (98% MDD) |  | Clegg Hammer Tests Email 8/3/24 from KH Every 250mm with 1st lift calibrated to NDM Every 20m (email 19/3/24 J Thomas) |  |  | Photos, Clegg Test Results |  | HOLD |  | Internal |  |  |  | JFC |  | REVIEW |  | ENGEO
| 3.03 | Construction of formation (ballast) |  | ENGEO – NAL CH 128.84km: Drawing 7, CAN- 01,RFI 001, RFI 028 |  |  | Formation construction as per KiwiRail Standard C-ST-FO-4110 Formation and task instruction C-TI-FO-4207 |  |  |  | KiwiRail Standard C-ST-FO-4110 Formation and task instruction C-TI-FO-4207 for construction compliance. Ballast to be 390- 410mm below top of rail |  | For every section of formation shown on the drawings. |  |  | Survey |  | witness |  | Internal |  |  |  | JFC |  | Hold |  | KiwiRail
| 4.0 POST CONSTRUCTION | [24 empty] | ENGINEER
| 4.01 | Revegetation |  | ENGEO – Detailed Design Report - NAL CH 128.84km: Section 7 |  |  | The slope will be revegetated using native hydroseeding, native shrub planting, or a combination of both, approved by a KiwiRail environmental scientist and ecologist. |  |  |  | Revegetation planting comply with KiwiRail approved corridor planting schedule 2023. |  | Shrubs to be approved by KiwiRail environmental scientist and ecologist before planting or seeding. |  |  | List of native shrub, Written Confirmation from KiwiRail Environmental Specialist |  | witness |  | Internal |  |  |  | JFC |  | HOLD |  | ENGEO
| 4.02 | As-builts |  | ENGEO – Detailed Design Report - NAL CH 128.84km: Section 13 |  |  | Following the construction, ENGEO should be provided with as built documentation to append their MSQA documentation. ENGEO provided with as built documentation of the: -monitoring fence -accessway -drainage -rip rap to append to our MSQA documentation. |  |  |  | As-built approved by ENGEO & KiwiRail (subgrade, excavations, pipe inverts, wingwalls, rip rap excavations & extents, drainage string (culvert, swales etc.) completion levels |  | At ballast handover & at completion |  |  | KR documents: M37c & As-Built Requirements for Culvert Renewals 441048-03-CC-COM- QA-NAL-CU |  | Witness |  | Internal |  |  |  | JFC |  | HOLD |  | ENGEO
| 4.03 | As built Culvert drawings |  | ENGEO – NAL CH 125.603 Drawing 19 |  |  | As built drawings to be provided by the contractor to detail the final construction of the remedial works including any amendments established during the construction |  |  |  | Engineer’s & KiwiRail acceptance |  | At ballast handover & at completion |  |  | KR documents: M37c & As-Built Requirements for Culvert Renewals 441048-03-CC-COM- QA-NAL-CU |  | Witness |  | Internal |  |  |  | JFC |  | HOLD |  | ENGEO
ITP# |  | Work Pack Element(s) |  | Drawing / Specification Ref. |  |  | Specification Detail Summary |  |  |  | Acceptance Criteria |  | Test Spec & Frequency |  |  | Control Type i.e. Checksheet / IANZ Records |  | Hold / Witness |  | Internal / External |  |  |  | PS3 Owner | Hold / Witness |  | PS4 Owner Sign Off
Sub-contractor ITPs (Refer to OP06_f09 ITP Index for Subcontractors)
ITP# |  |  | Work Pack Element(s) |  | Drawing / Specification Ref. |  |  | Specification Detail Summary |  |  |  | Acceptance Criteria |  | Test Spec & Frequency |  |  | Control Type i.e. Checksheet / IANZ Records |  | Hold / Witness |  |  | Internal / External | PS3 Owner |  | Hold / Witness |  | PS4 Owner
Sub Activity 1 (INSERT QA SHEET NAME) | [18 empty] | (ENTER SUBCONTRACTOR) | [5 empty] | ENGINEER
30
31
32
33
34
Sub Activity 2 (INSERT QA SHEET NAME) | [18 empty] | (ENTER SUBCONTRACTOR) | [5 empty] | ENGINEER
35
36
37
38
39
ITP Induction Sign On
ITP Induction Sign-on
Name | [5 empty] | Date |  |  |  | Signature