## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 128.840 - 1.0 PRE-CONSTRUCTION WORKS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 128.840 - 01.0 PRE-CONSTRUCTION WORKS v2
section | 1.0 PRE-CONSTRUCTION
checkpoint | 1.01 - Check IFC Drawings
label | DRAWING / SPECIFICATION REF.: IFC issued
label | SPECIFICATION DETAIL SUMMARY: Ensure latest revision is being used
label | ACCEPTANCE CRITERIA: Correct drawings
label | TEST SPEC AND FREQUENCY: Prior to works, updated accordingly based on formal correspondence
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Controlled IFC drawings being used – Checkpoint on QA
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 1.02 - Erosion and Sediment Control
label | DRAWING / SPECIFICATION REF.: ENGEO – Detailed Design Report - NAL CH 128.84km: Section 5
label | SPECIFICATION DETAIL SUMMARY: The contractor is responsible for protecting earthworks and erosion control measures, and must develop a site-specific Environmental Control Plan (ESCP) that KiwiRail must review before construction begins.
label | ACCEPTANCE CRITERIA: Contractor to ensure effective erosion and sedimentation control measures shall be installed and maintained in accordance with Auckland Council Resource Consent Requirements, and the ESCP.
label | TEST SPEC AND FREQUENCY: Before construction begins
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: ESCP Documentation, Photos, Daily and Weekly Audits
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 1.03 - Environmental and Ecological Assessment
label | DRAWING / SPECIFICATION REF.: ENGEO – Detailed Design Report - NAL CH 128.84km: Section 6
label | SPECIFICATION DETAIL SUMMARY: An ecologist from KiwiRail must be consulted and on-site to assess the site before and during the removal of vegetation and trees in a Significant Environmental Area (SEA).
label | ACCEPTANCE CRITERIA: The contractor to collaborate with the appointed ecologist from KiwiRail and adhere to the proposed controls.
label | TEST SPEC AND FREQUENCY: Before and during the removal of vegetation and trees in a Significant Environmental Area (SEA).
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation of the Ecologist’s Instructions and Approval, Photos
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 1.04 - Pre-start meeting
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 7 Note 2
label | SPECIFICATION DETAIL SUMMARY: A pre-start meeting with Engineer and Contractor is needed to ensure understanding of construction methodology, review work plan and methodology for Geotechnical Professional, and ensure safety measures are in place.
label | ACCEPTANCE CRITERIA: Construction methodology agreed between Contractor and Engineer
label | TEST SPEC AND FREQUENCY: Prior to commencement of works
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: RFI for Clarity and record purposes
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 128.840 - 2.0 DRAINAGE WORKS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 128.840 - 02.0 DRAINAGE WORKS v2
section | 1.0 PRE-CONSTRUCTION
checkpoint | 2.01 - Materials
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 6
label | SPECIFICATION DETAIL SUMMARY: All materials as per the design drawings
label | ACCEPTANCE CRITERIA: All materials comply with the drawings
label | TEST SPEC AND FREQUENCY: Prior to use of materials on site
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Dockets
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: witness
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 2.02 - Manhole and Pipe Bedding
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 4
label | SPECIFICATION DETAIL SUMMARY: Bedding thickness min. 200mm GAP20
label | ACCEPTANCE CRITERIA: Engineer to confirm GAP 20 compacted to 90% MDD or CIV of 20 with Clegg Impact Hammer (in accordance with NZS 3725:2007)
label | TEST SPEC AND FREQUENCY: Engineer to check prior to installation of manhole and pipe
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: NDM and or Clegg Test Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: witness
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 2.03 - Haunching
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 5 & Drawing 7 Note 1
label | SPECIFICATION DETAIL SUMMARY: SP20 Compacted in 150mm layers to widest pipe width
label | ACCEPTANCE CRITERIA: Engineer to confirm SP20 compacted to at least 90% MDD
label | TEST SPEC AND FREQUENCY: Engineer to check every 150mm thick compacted layer
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: NDM Test Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: witness
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 2.04 - Culvert Trench Backfill
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 5 & Drawing 7 Note 1
label | SPECIFICATION DETAIL SUMMARY: Backfill to comprise of GAP65 or geotechnically approved material in max. 200mm lifts
label | ACCEPTANCE CRITERIA: Engineer to confirm GAP65 or GAP40 or PAP40 or PAP 65 approved equivalent compacted to 95% MDD at interface of sub- ballast layer (in accordance with NZS 3725:2007) – for (sub-ballast refer formation items). Subballast layer to be GAP40 compacted to 98% MDD or Clegg of 30.
label | TEST SPEC AND FREQUENCY: Engineer to check every 200mm thick compacted layer
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: NDM Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: witness
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 2.04b - Culvert Trench Undercut
label | DRAWING / SPECIFICATION REF.: RFI 027
label | SPECIFICATION DETAIL SUMMARY: Undercut where subgrade is < 70kpa as measured by hand held shear vane
label | ACCEPTANCE CRITERIA: Installed per RFI 027 detail : 300mm ballast, A29 geotextile wrapped. Duragrid 30/30 or TX160 between wrap and bedding backfill.
label | TEST SPEC AND FREQUENCY: Check Subgrade every 3 pipe lengths (approx. 7.5m)
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Check sheets, photos
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: witness
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 2.04c - Wingwall Bedding
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 5
label | SPECIFICATION DETAIL SUMMARY: Compacted hardfill min 200mm thk
label | ACCEPTANCE CRITERIA: Engineer to confirm SP20 compacted to at least 95% MDD
label | TEST SPEC AND FREQUENCY: Engineer to check every 150mm thick compacted layer
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: NDM Test Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: External
label | PS3 OWNER: JFC
label | HOLD / WITNESS: witness
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 2.05 - Installation
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 5 & Drawing 7 Note 2
label | SPECIFICATION DETAIL SUMMARY: Drainage works to be installed in accordance with the design drawings.
label | ACCEPTANCE CRITERIA: Engineer to confirm that the drainage is connected as shown on the plans.
label | TEST SPEC AND FREQUENCY: Engineer to check prior to backfill of drainage items
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 128.840 - 3.0 TRACK FORMATION | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 128.840 - 03.0 TRACK FORMATION v2
section | 1.0 PRE-CONSTRUCTION
checkpoint | 3.01 - Structural Fill
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 7, CAN-01,RFI 001
label | SPECIFICATION DETAIL SUMMARY: 900mm thick structural fill (GAP65 or GAP40 or PAP40 or PAP 65 with geogrid) RFI 001
label | ACCEPTANCE CRITERIA: Compaction min CIV = 25 (95% MDD)
label | TEST SPEC AND FREQUENCY: Clegg Hammer Tests Email 8/3/24 from KH Every 250mm with 1st lift calibrated to NDM Every 20m (email 19/3/24 J Thomas)
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Photos, Clegg Test Results
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 3.02 - Sub-ballast
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 7, CAN-01,RFI 001
label | SPECIFICATION DETAIL SUMMARY: 150mm thick sub-ballast (M4-AP40) RFI 001
label | ACCEPTANCE CRITERIA: Compaction min CIV = 30 (98% MDD)
label | TEST SPEC AND FREQUENCY: Clegg Hammer Tests Email 8/3/24 from KH Every 250mm with 1st lift calibrated to NDM Every 20m (email 19/3/24 J Thomas)
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Photos, Clegg Test Results
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 3.03 - Construction of formation (ballast)
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 128.84km: Drawing 7, CAN-01,RFI 001, RFI 028
label | SPECIFICATION DETAIL SUMMARY: Formation construction as per KiwiRail Standard C-ST-FO-4110 Formation and task instruction C-TI-FO-4207
label | ACCEPTANCE CRITERIA: KiwiRail Standard C-ST-FO-4110 Formation and task instruction C-TI-FO-4207 for construction compliance. Ballast to be 390- 410mm below top of rail
label | TEST SPEC AND FREQUENCY: For every section of formation shown on the drawings.
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Survey
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: Hold
label | PS4 OWNER SIGN OFF: KiwiRail
checklist | CH 128.840 - 4.0 POST CONSTRUCTION | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 128.840 - 04.0 POST CONSTRUCTION v2
section | 1.0 PRE-CONSTRUCTION
checkpoint | 4.01 - Revegetation
label | DRAWING / SPECIFICATION REF.: ENGEO – Detailed Design Report - NAL CH 128.84km: Section 7
label | SPECIFICATION DETAIL SUMMARY: The slope will be revegetated using native hydroseeding, native shrub planting, or a combination of both, approved by a KiwiRail environmental scientist and ecologist.
label | ACCEPTANCE CRITERIA: Revegetation planting comply with KiwiRail approved corridor planting schedule 2023.
label | TEST SPEC AND FREQUENCY: Shrubs to be approved by KiwiRail environmental scientist and ecologist before planting or seeding.
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: List of native shrub, Written Confirmation from KiwiRail Environmental Specialist
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 4.02 - As-builts
label | DRAWING / SPECIFICATION REF.: ENGEO – Detailed Design Report - NAL CH 128.84km: Section 13
label | SPECIFICATION DETAIL SUMMARY: Following the construction, ENGEO should be provided with as built documentation to append their MSQA documentation. ENGEO provided with as built documentation of the: -monitoring fence -drainage -rip rap to append to our MSQA documentation.
label | ACCEPTANCE CRITERIA: As-built approved by ENGEO & KiwiRail (subgrade, excavations, pipe inverts, wingwalls, rip rap excavations & extents, drainage string (culvert, swales etc.) completion levels
label | TEST SPEC AND FREQUENCY: At ballast handover & at completion
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: KR documents: M37c & As-Built Requirements for Culvert Renewals 441048-03-CC-COM- QA-NAL-CU
label | HOLD / WITNESS: Witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 4.03 - As built Culvert drawings
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL CH 125.603 Drawing 19
label | SPECIFICATION DETAIL SUMMARY: As built drawings to be provided by the contractor to detail the final construction of the remedial works including any amendments established during the construction
label | ACCEPTANCE CRITERIA: Engineer’s & KiwiRail acceptance
label | TEST SPEC AND FREQUENCY: At ballast handover & at completion
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: KR documents: M37c & As-Built Requirements for Culvert Renewals 441048-03-CC-COM-QA-NAL-CU
label | HOLD / WITNESS: Witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO