## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 134.620 - 1.0 PRE-CONSTRUCTION WORKS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 01.0 PRE-CONSTRUCTION WORKS v2
section | 1.0 PRE-CONSTRUCTION WORKS
checkpoint | 1.01 - Check IFC Drawings
label | DRAWING / SPECIFICATION REF.: IFC issued
label | SPECIFICATION DETAIL SUMMARY: Ensure latest revision is being used
label | ACCEPTANCE CRITERIA: Correct drawings
label | TEST SPEC AND FREQUENCY: Prior to works, updated accordingly based on formal correspondence
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Controlled IFC drawings being used – Checkpoint on QA
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 1.02 - Erosion and Sediment Control
label | DRAWING / SPECIFICATION REF.: ENGEO – Detailed Design Report - NAL CH 134.620km: Section 6
label | SPECIFICATION DETAIL SUMMARY: The contractor is responsible for protecting earthworks and erosion control measures, and must develop a site- specific Environmental Control Plan (ESCP) that KiwiRail must review before construction begins.
label | ACCEPTANCE CRITERIA: Contractor to ensure effective erosion and sedimentation control measures shall be installed and maintained in accordance with Auckland Council Resource Consent Requirements, and the ESCP.
label | TEST SPEC AND FREQUENCY: Before construction begins
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: ESCP Documentation, Photos, Daily and Weekly Audits
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 1.03 - Environmental and Ecological Assessment
label | DRAWING / SPECIFICATION REF.: ENGEO – Detailed Design Report - NAL CH 134.620km: Section 7
label | SPECIFICATION DETAIL SUMMARY: An ecologist from KiwiRail must be consulted and on-site to assess the site before and during the removal of vegetation and trees.
label | ACCEPTANCE CRITERIA: The contractor to collaborate with the appointed ecologist from KiwiRail and adhere to the proposed controls.
label | TEST SPEC AND FREQUENCY: Prior to commencement of works
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: RFI for Clarity and record purposes
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 2.0 SITE CLEARANCE | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 02.0 SITE CLEARANCE v2
section | 2.0 SITE CLEARANCE
checkpoint | 2.01 - Site Clearance
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 2
label | SPECIFICATION DETAIL SUMMARY: The Contractor must set out the working area shown on the Construction Drawings, under observation by ENGEO. The clearing extent on the plans must be agreed on- site after pegging the earthworks area.
label | ○ Clearing will not begin until the agreed extent is established through pegging or paint marking by the Contractor and ENGEO. Adequate silt control measures must be installed.
label | ACCEPTANCE CRITERIA: Agreed extent is established by the Contractor and ENGEO.
label | TEST SPEC AND FREQUENCY: After setting out of clearing area and prior to all clearing
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation of ENGEO’s approval
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 3.0 EARTHWORKS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 03.0 EARTHWORKS v2
section | 3.0 EARTHWORKS
checkpoint | 3.01 - Protection of Earthworks and Erosion and Sediment Control
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 3.1
label | SPECIFICATION DETAIL SUMMARY: The contractor is responsible for protecting earthworks, implementing erosion and sediment control measures, and conducting surface drainage within work limits.
label | ACCEPTANCE CRITERIA: The KiwiRail Erosion and Sediment Control Management Plan and associated drawings must be followed for the installation and maintenance of effective erosion and sedimentation control measures.
label | TEST SPEC AND FREQUENCY: Prior to commencement of any earthworks
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Photos, Daily and Weekly audits
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 3.02 - Materials
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 3.2
label | SPECIFICATION DETAIL SUMMARY: The Earthworks Quality Plan must include a mass haul diagram detailing imported materials and their locations for placement. All imported fill must be certified as free of contamination at source, and reported to ENGEO and the Principal before importation.
label | ACCEPTANCE CRITERIA: Approval of site-won and imported granular fill material by ENGEO and or the Principal.
label | TEST SPEC AND FREQUENCY: Prior to fill being imported to site
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Material report & certification, Written Confirmation of ENGEO/Principal’s approval
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 4.0 EARTHWORKS - EXCAVATION | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 04.0 EARTHWORKS - EXCAVATION v2
section | 4.0 EARTHWORKS - EXCAVATION
checkpoint | 4.01 - Removal of unsuitable material
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 4.1
label | SPECIFICATION DETAIL SUMMARY: All unsuitable material removed prior to filling
label | ACCEPTANCE CRITERIA: Inspection and approval by ENGEO that all unsuitable material removed prior to filling
label | TEST SPEC AND FREQUENCY: Inspection prior to filling
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Photos, Written Instruction/Confirmation from ENGEO
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 4.02 - Fill Benching
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 4.2
label | SPECIFICATION DETAIL SUMMARY: To ensure proper filling, any sliding slope with a steeper slope of six horizontal to one vertical (ten degrees) must be benched before filling, while slopes shallower require scarification. ENGEO should assess cut and fill slopes for additional recommendations.
label | ACCEPTANCE CRITERIA: Cut and Fill Slopes to be assessed by ENGEO. Any additional recommendations to be implemented when required.
label | TEST SPEC AND FREQUENCY: Inspection of all cut and fill slopes
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Photos, Written Instruction/Confirmation from ENGEO
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 5.0 EARTHWORKS - FILL | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 05.0 EARTHWORKS - FILL v2
section | 5.0 EARTHWORKS - FILL
checkpoint | 5.01 - Site-won Material
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 5.1
label | SPECIFICATION DETAIL SUMMARY: Site-won materials used as engineered fill must be free of topsoil, organic matter, and rubbish, with a maximum particle size of 100mm, and mixed or crushed efficiently.
label | ACCEPTANCE CRITERIA: Material compacted to achieve like for like with surrounding soils, and/or shear vanes of > SU=100 kPa and 12% air voids. Standard of compaction may be re-assessed and specified onsite by ENGEO if applicable.
label | TEST SPEC AND FREQUENCY: Testing every layer (250mm) to be completed by ENGEO. Relaxation of testing frequency may be taken at the discretion of ENGEO
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Test Results, Written Confirmation of ENGEO’s approval
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 5.02 - Imported Hardfill for the Toe Buttress (if required)
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 5.2
label | SPECIFICATION DETAIL SUMMARY: Hardfill (imported) for the toe buttress (if required) shall comprise a graded, unweathered, durable, crushed rock product (AP65) approved by ENGEO, with a grading suitable for compaction
label | ACCEPTANCE CRITERIA: Hardfill product approved by ENGEO
label | TEST SPEC AND FREQUENCY: Prior to hardfill being imported to site
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Material Test Results/Certs, Confirmation of ENGEO’s approval
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 5.03 - Hardfill Testing
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 5.2
label | SPECIFICATION DETAIL SUMMARY: Hardfill placed and compacted in 200mm lifts and tested.
label | ACCEPTANCE CRITERIA: Hardfill compacted to 95% of the Maximum Dry Density (MDD)
label | TEST SPEC AND FREQUENCY: One test per 500m3 of hardfill placed with not less than one test per 500mm lift of filling for each fill area
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: MDD Results, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 5.04 - As-builts
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 8
label | SPECIFICATION DETAIL SUMMARY: The contractor is required to provide ENGEO with as-built information for a MSQA Geotechnical Completion Report, including surveying items before filling, which should form a hold point in the construction sequence.
label | ENGEO to receive as-built drawings for:
label | ○ The depth of filling placed including all benching, undercuts, and shear keys and counterfort drainage, underfill drainage and swales.
label | ACCEPTANCE CRITERIA: As-built approved by ENGEO
label | TEST SPEC AND FREQUENCY: Items to be surveyed before filling. As-builts to be provided upon completion of works
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: As-builts
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 6.0 COUNTERFORT DRAINAGE | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 06.0 COUNTERFORT DRAINAGE v2
section | 6.0 COUNTERFORT DRAINAGE
checkpoint | 6.01 - Review of Drainage and Fill Materials
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 6.2 ENGEO – NAL 134.620km: Drawing 4
label | SPECIFICATION DETAIL SUMMARY: Drainage and fill materials installed within the site to the detail provided in the design drawings.
label | – Geotextile Class C (Bidim A29 or equiv),
label | – Perforated Subsoil Drain ((Megaflo 170, Novaflo Hi-way grade 160mm or approved equiv)
label | – Angular no fines drainage rock (7-20mm or 40-20mm drainage)
label | ACCEPTANCE CRITERIA: Drainage and fill materials approved by the Geotechnical Engineer.
label | TEST SPEC AND FREQUENCY: Prior to installation of drainage and fill materials
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Material specs/certs, Written Confirmation/Approval from Geotechnical Engineer
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 6.02 - Review of Location and Setout
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 6.2
label | SPECIFICATION DETAIL SUMMARY: Counterfort drains installed within the site in the locations provided in the design drawings
label | ACCEPTANCE CRITERIA: Locations agreed between the Contractor and Geotechnical Engineer
label | TEST SPEC AND FREQUENCY: Prior to commencement of counterfort drain works
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation/Approval from Geotechnical Engineer, Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 6.03 - Installation of Counterfort Drains
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 6.2 ENGEO – NAL 134.620km: Drawing 4
label | SPECIFICATION DETAIL SUMMARY: Installation should be undertaken in short sections (<5m lengths) and during period of dry weather The Counterfort Drainage will consist of a 500mm wide trench, 2m deep, tapering up to outlet into the reformed swale adjacent to the rail formation.
label | ○ The counterfort drainage should be lined with Geotextile, have a perforated subsoil drain at the base, and be backfilled with angular, no fines drainage rock.
label | ○ The Geotextile should fully wrap the drainage material, and the excavation should have a minimum cohesive soil cap of 0.5m thick
label | ACCEPTANCE CRITERIA: Counterfort drains installed as per the drawings and specifications. Installation approved by the Geotechnical Engineer
label | TEST SPEC AND FREQUENCY: Post earthworks fill and Prior to filling counterfort drain
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation/Approval from Geotechnical Engineer, Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 6.04 - Flushing of Drains
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 6.2
label | SPECIFICATION DETAIL SUMMARY: The invert level of outlets must be aligned with the design drawings' levels to ensure proper drainage throughout the design life.
label | ACCEPTANCE CRITERIA: Drains are operational and proved by the Geotechnical Engineer.
label | TEST SPEC AND FREQUENCY: For every section of drain installed
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation/Approval from Geotechnical Engineer, Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 6.05 - Observation of Flushing Point and Outlet
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 6.2
label | SPECIFICATION DETAIL SUMMARY: Flushing point and outlet to be observed
label | ACCEPTANCE CRITERIA: Flushing point and outlet observed by the Geotechnical Engineer.
label | TEST SPEC AND FREQUENCY: For every section of drain installed
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation/Approval from Geotechnical Engineer, Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 6.06 - As-builts – Surface and sub-surface drainage
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 8
label | SPECIFICATION DETAIL SUMMARY: The contractor is required to provide ENGEO with as-built information for a MSQA Geotechnical Completion Report, including surveying items before filling, which should form a hold point in the construction sequence and proof of function of the counterfort drainage.
label | ENGEO to receive as-built drawings for:
label | ○ The location and invert of all surface and sub-surface drainage
label | ACCEPTANCE CRITERIA: As-built approved by ENGEO
label | TEST SPEC AND FREQUENCY: Upon completion of works and prior to any filling
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: As-builts
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 7.0 INSPECTION AND HOLD POINTS (IN ADDITION TO WHAT HAS ALREADY BEEN LISTED ABOVE) | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 07.0 INSPECTION AND HOLD POINTS (IN ADDITION TO WHAT HAS ALREADY BEEN LISTED ABOVE) v2
section | 7.0 INSPECTION AND HOLD POINTS (IN ADDITION TO WHAT HAS ALREADY BEEN LISTED ABOVE)
checkpoint | 7.02 - Drainage and Counterfort Drainage
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 7
label | SPECIFICATION DETAIL SUMMARY: ENGEO inspection of completed drainage and counterfort drainage
label | ACCEPTANCE CRITERIA: Approved by ENGEO
label | TEST SPEC AND FREQUENCY: For every section of completed drainage works
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation of ENGEO’s approval, Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 7.03 - Finished Surfaces
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 7 ENGEO – NAL 134.620km: Drawing 4
label | SPECIFICATION DETAIL SUMMARY: ENGEO inspection of the finished surfaces prior to revegetation (may also be required for survey purposes as required by ENGEO). Revegetation in accordance with KiwiRail Corridor Schedule (2023).
label | ACCEPTANCE CRITERIA: Approved by ENGEO
label | TEST SPEC AND FREQUENCY: For every section of finished surface prior to revegetation
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation of ENGEO’s approval, Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 7.04 - Hydroseeding
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 7 ENGEO – NAL 134.620km: Drawing 4
label | SPECIFICATION DETAIL SUMMARY: ENGEO inspection of completed hydroseeding. Hydroseeding in accordance with KiwiRail Corridor Schedule (2023)
label | ACCEPTANCE CRITERIA: Approved by ENGEO
label | TEST SPEC AND FREQUENCY: For every section upon completion of hydroseeding
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Written Confirmation of ENGEO’s approval, Photos
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 8.0 FORMATION | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 08.0 FORMATION v2
section | 8.0 FORMATION
checkpoint | 8.01 - Structural Fill
label | DRAWING / SPECIFICATION REF.: N/A
checkpoint | 8.02 - Sub-ballast
label | DRAWING / SPECIFICATION REF.: N/A
checkpoint | 8.03 - Construction of formation (ballast)
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL 134.620km: Drawing 5 CAN-01,RFI 001, RFI 028
label | SPECIFICATION DETAIL SUMMARY: Formation construction as per KiwiRail Standard C-ST-FO-4110 Formation and task instruction C-TI-FO-4207
label | ACCEPTANCE CRITERIA: KiwiRail Standard C-ST-FO-4110 Formation and task instruction C-TI- FO-4207 for construction compliance. Ballast to be 390-410mm below top of rail
label | TEST SPEC AND FREQUENCY: For every section of formation shown on the drawings
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: QA Checksheet(s), Photos
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 9.0 CULVERT – DIRECTIONAL DRILLED | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 09.0 CULVERT – DIRECTIONAL DRILLED v2
section | 9.0 CULVERT – DIRECTIONAL DRILLED
checkpoint | 9.01 - Materials
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL 134.620km: Drawing 8
label | SPECIFICATION DETAIL SUMMARY: All materials as per the design drawings
label | ACCEPTANCE CRITERIA: All materials comply with the drawings
label | TEST SPEC AND FREQUENCY: Prior to use of materials on site
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Dockets
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: witness
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 9.01 - Installation
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL 134.620km: Drawing 8
label | SPECIFICATION DETAIL SUMMARY: Drainage works to be installed in accordance with the design drawings.
label | ACCEPTANCE CRITERIA: Engineer to confirm that the drainage is connected as shown on the plans.
label | TEST SPEC AND FREQUENCY: Engineer to check prior to backfill of drainage items
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 9.02 - Wingwall Bedding
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL 134.620km: Drawing 8
label | SPECIFICATION DETAIL SUMMARY: Compacted hardfill min 200mm thk
label | ACCEPTANCE CRITERIA: Engineer to confirm SP20 compacted to at least 95% MDD
label | TEST SPEC AND FREQUENCY: Engineer to check every 150mm thick compacted layer
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: NDM Test Results, Photos, QA Checksheet(s), Written Confirmation of Engineer’s Approval
label | HOLD / WITNESS: HOLD
label | INTERNAL / EXTERNAL: External
label | PS3 OWNER: JFC
label | HOLD / WITNESS: witness
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 9.03 - As built Culvert drawings
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL 134.620km: Drawing 8
label | SPECIFICATION DETAIL SUMMARY: As built drawings to be provided by the contractor to detail the final construction of the works including any amendments established during the construction
label | ACCEPTANCE CRITERIA: Engineer’s & KiwiRail acceptance
label | TEST SPEC AND FREQUENCY: At ballast handover & at completion
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: KR documents: M37c & As-Built Requirements for Culvert Renewals 441048-03-CC-COM-QA- NAL-CU
label | HOLD / WITNESS: Witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checklist | CH 134.620 - 10.0 POST CONSTRUCTION | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 134.620 - 10.0 POST CONSTRUCTION v2
section | 10.0 POST CONSTRUCTION
checkpoint | 10.01 - Revegetation
label | SPECIFICATION DETAIL SUMMARY: The slope will be revegetated using native hydroseeding, native shrub planting, or a combination of both, approved by a KiwiRail environmental scientist and ecologist.
label | ACCEPTANCE CRITERIA: Revegetation planting comply with KiwiRail approved corridor planting schedule 2023.
label | TEST SPEC AND FREQUENCY: Shrubs to be approved by KiwiRail environmental scientist and ecologist before planting or seeding.
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: List of native shrub, Written Confirmation from KiwiRail Environmental Specialist
label | HOLD / WITNESS: witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 10.02 - As-builts
label | DRAWING / SPECIFICATION REF.: ENGEO Technical Specification – NAL 134.620km: Section 8
label | SPECIFICATION DETAIL SUMMARY: Following the construction, ENGEO should be provided with as built documentation to append their MSQA documentation.
label | ENGEO provided with as built documentation of the:
label | – monitoring fence
label | – drainage
label | – rip rap to append to our MSQA documentation.
label | ACCEPTANCE CRITERIA: As-built approved by ENGEO & KiwiRail (subgrade, excavations, pipe inverts, wingwalls, rip rap excavations & extents, drainage string (culvert, swales etc.) completion levels
label | TEST SPEC AND FREQUENCY: At ballast handover & at completion
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: KR documents: M37c & As-Built Requirements for Culvert Renewals 441048-03-CC-COM-QA- NAL-CU
label | HOLD / WITNESS: Witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO
checkpoint | 10.03 - As built Culvert drawings
label | DRAWING / SPECIFICATION REF.: ENGEO – NAL 134.620km: Drawing 8
label | SPECIFICATION DETAIL SUMMARY: As built drawings to be provided by the contractor to detail the final construction of the remedial works including any amendments established during the construction
label | ACCEPTANCE CRITERIA: Engineer’s & KiwiRail acceptance
label | TEST SPEC AND FREQUENCY: At ballast handover & at completion
label | CONTROL TYPE I.E. CHECKSHEET / IANZ RECORDS: KR documents: M37c & As-Built Requirements for Culvert Renewals 441048-03-CC-COM-QA- NAL-CU
label | HOLD / WITNESS: Witness
label | INTERNAL / EXTERNAL: Internal
label | PS3 OWNER: JFC
label | HOLD / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: ENGEO