## Structure
Tier 1 |  | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Resource to use
St Johns, Summerset
Belcanto Manufacturing
Block A
Level 4
Level 5
Stage 1
existing tiers |  | Tier 4: Tpye 1a
|  | Tier 5: Lower Left - 308 | Checklist - Complex
new tiers start here |  | Tier 5: Lower Right - 309 | Checklist - Complex
|  | Tier 5: Upper Left - 408 | Checklist - Complex
|  | Tier 5: Upper Right - 409 | Checklist - Complex
Type 4
|  | Tier 5: Lower Left - 410 | Checklist - Complex
|  | Tier 5: Lower Right - 411 | Checklist - Complex
|  | Tier 5: Upper Left - 510 | Checklist - Complex
|  | Tier 5: Upper Right - 511 | Checklist - Complex
Stage 2
Type 1b
|  | Tier 5: Lower Left - 406 | Checklist - Complex
|  | Tier 5: Lower Right - 407 | Checklist - Complex
|  | Tier 5: Upper Left - 506 | Checklist - Complex
|  | Tier 5: Upper Right - 507 | Checklist - Complex
Type 1c
|  | Tier 5: Lower Left - 412 | Checklist - Complex
|  | Tier 5: Lower Right - 413 | Checklist - Complex
|  | Tier 5: Upper Left - 512 | Checklist - Complex
|  | Tier 5: Upper Right - 513 | Checklist - Complex
|  | Tier 4: Type 7 | Checklist - Complex
|  | Tier 5: Lower - 414 | Checklist - Complex
|  | Tier 5: Upper - 415 | Checklist - Complex
Stage 3
Type 2
|  | Tier 5: Lower - 405 | Checklist - Complex
|  | Tier 5: Upper - 505 | Checklist - Complex
Type 3
|  | Tier 5: Lower Left - 404 | Checklist - Complex
|  | Tier 5: Lower Right - 404 | Checklist - Complex
|  | Tier 5: Upper Left - 504 | Checklist - Complex
|  | Tier 5: Upper Right - 504 | Checklist - Complex
Type 5
|  | Tier 5: Lower - 403 | Checklist - Complex
|  | Tier 5: Upper - 503 | Checklist - Complex
Stage 4
Type 6
|  | Tier 5: Lower Left - 401 | Checklist - Complex
|  | Tier 5: Lower Right - 401 | Checklist - Complex
|  | Tier 5: Upper Left - 501 | Checklist - Complex
|  | Tier 5: Upper Right - 501 | Checklist - Complex
Type 6a
|  | Tier 5: Lower Left - 402 | Checklist - Complex
|  | Tier 5: Lower Right - 402 | Checklist - Complex
|  | Tier 5: Upper Left - 502 | Checklist - Complex
|  | Tier 5: Upper Right - 502 | Checklist - Complex

## Resources
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
checklist | Balcony Build
section | Casette Assembly
checkpoint | All parts free from defects and damage
Button |  | Pass, Fail, N/A
textbox | [5 empty] | Add Comment
checkpoint | Frame squareness
Button |  | Pass, Fail, N/A
label | Measure Diagonals and compare
label | Diagonals to match +/- 2mm
textbox | [5 empty] | Add Comment
checkpoint | Verify all parts and fixings have been fitted as per drawings and schedules
Button |  | Pass, Fail, N/A
textbox | [5 empty] | Add Comment
checkpoint | Bolt Tightness
Button |  | Pass, Fail, N/A
label | Frequency: Every Bolt Nut Washer
label | Torque Wrench: M8 Bolts to 22Nm (yellow marker)
label | M10 to 44Nm (blue Marker) M12 to 77Nm (green marker)
textbox | [5 empty] | Add Comment
section | Soffit Check
checkpoint | Soffits Level - rear angle support added
Button |  | Pass, Fail, N/A
textbox | [5 empty] | Add Comment
checkpoint | Rivets / Screws: Correct Sizes and Integity
Button |  | Pass, Fail, N/A
label | Visual Check: all mounting points
label | Frequency: Every Rivet / Screw | [6 empty] | Comment : I'd like the result to look like this with a count field for Checkpoint completeion
textbox | [5 empty] | Add Comment
checkpoint | Joints Tight
Button |  | Pass, Fail, N/A
label | All soffit panels pulled tight to each other
checkpoint | Gutter Section Assembled
textbox | [5 empty] | Add Comment
checkpoint | Surface Finish
Button |  | Pass, Fail, N/A
label | No imperfections visible beyond 3m
label | Frequency: Every Soffit Panel
textbox | [5 empty] | Add Comment
section | Balustrade Check
checkpoint | Balustrade Kit Prepared
Button |  | Pass, Fail, N/A
label | All Parts included
label | Correct for Lower or Upper Type
textbox | [5 empty] | Add Comment
section | Decking Check
checkpoint | Preforated sheets fitted where applicable
Button |  | Pass, Fail, N/A
label | Site fitted sheets included in pack
label | Correct for Left or Right Side Unit
textbox | [5 empty] | Add Comment
section | Completeion Check
checkpoint | Site pack compiled
Button |  | Pass, Fail, N/A
label | Preforated sheets, Gutter, Tile edging angle and Balustrade Kit packed
label | Correct for Upper or Lower Type
label | Correct for Left or Right Side Unit
textbox | [5 empty] | Add Comment
Final checkpoint | Balcony Labeled
Button |  | Pass, Fail, N/A
label | Attache and Sign QA label
label | Label states Type, Side and Upper / Lower designation
textbox | [5 empty] | Add Comment