## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Enviro HP1200+850TC |  |  |  |  | Yes | Enviro HP1200+850TC | 042583d7-67d9-4f13-bbdf-9a87e50e20a8
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | f92c4f5e-82a2-5ee6-9ecd-dfb6c0db098f |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | 6b412408-d673-5912-bd10-c95b0169b767 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 470e1600-cd00-5a51-ae0d-60fca9d07ffe |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | e673bcfa-1f4d-5784-92e7-e299708970ce |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | e1657dd0-2246-5fde-ac28-9eda014b8ed5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | df14b197-33d8-5933-ba34-acdfc03e9f0e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat - Mix and Apply Enviro 850TC with brush or new roller (spray application optional) Re-apply as required or determined by the Specification
label | b5bb0801-d5cf-57e0-b9e1-88e2094fce4c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | b2358d66-2cc3-5252-8514-4555374fa43a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | 200P Ultra V01 |  |  |  |  | Yes | 200P Ultra V01 | 050c0976-f931-4e13-abdc-eb98f9232f89
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 8bf8049f-541c-5dec-a91a-e0076e222535 |  | textbox | ITP No.
text | 6bfd893c-8d8d-5ecc-ab89-7569a6830e80 |  | textbox | Revision No. & Date
text | eeb63688-9f05-5c73-a702-30ef7122e65b |  | textbox | Prepared By
text | c1c7332d-f454-546c-8560-c98b53871379 |  | textbox | Reviewed By
text | 48f012bc-8129-5126-b904-84b3ac897257 |  | textbox | Approved By
text | 5bb3b702-a603-5f36-bbc4-ec402dfa85ce |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Shield
label | 53263a52-18c8-5f70-b582-b40870dd76e2 |  | note | Records - Time stamped photograph
select | 271a82c3-ba2c-59a8-88ad-13c49248ebe5 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex FC
label | 26ea71b6-15e8-598c-a5a2-8c3c08715d7b |  | note | Records - Time stamped photograph
select | e0a7173d-00c6-55bf-a7b1-adaf59259b49 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 200P Ultra
label | f9b49a28-d79e-5e12-bebf-1daa9d12ca59 |  | note | Records - Time stamped photograph
select | 4b86d52d-a854-5430-81b6-ca16c94c2e63 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 6fb8cb5c-35b8-5d2e-ba27-b05314b4d1ba |  | note | Submit samples for approval as per Specific Material Requirements.
label | c0c39b02-161d-5df7-a29a-cf57e07e24f2 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | f37a3c24-5897-5221-a50c-8ee4816e43bb |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | b8446ec8-2453-5e57-825d-f40e1f682417 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 25367a9f-2d2d-57cc-851a-193cf265331f |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | c455e862-ac3a-53fc-9ee2-d2fcd06cce6f |  | note | Records - Time stamped photograph
select | ed88965e-ea13-5ccd-bdf2-adce640324a4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 71885b43-ccc4-58c3-9daa-87163637ed18 |  | note | Obtain clearance for work initiation.
label | ebf2494d-6d01-505e-8d20-877a93fbe849 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 09615970-4504-5e54-95ec-806949bc7f7e |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | b1113e38-7052-5b6e-8b26-820bad48eeb1 |  | note | Records - Time stamped photograph
select | f82dcb2e-48ec-5892-b09d-c2bb69de848b |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | fc19b574-849d-5240-aaee-8298b6ee29e7 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | bce6548f-0e0e-5f23-99b3-f28fec2e5cdd |  | note | Records - Time stamped photograph
select | 349a4787-e5d9-5b6c-9300-eaae5dbe4f4b |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 1197488a-48a4-53f2-969b-c194e26cf5fd |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | ed763f59-8576-53fc-bd05-1a340f673c21 |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | d853df90-9e03-529a-a2a5-108497cd04c0 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 86e9df03-c6da-5d21-bbf2-0061f60732ab |  | note | Records - Time stamped photograph
select | 52e348d9-83f7-51a4-854b-9e04da35b6a1 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | 44c83cb6-4e10-5d96-9588-94222c2456c2 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 927a9cfb-2daa-528c-8b76-c2861b792f61 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | cba16a60-1dbb-5e11-9ce6-11b4cddd4de4 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 9172796b-0d66-5ed1-992e-844438640298 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 21ee1e19-aff3-5d87-8506-a0f41962c276 |  | note | Records - Time stamped photograph
select | 0eed3625-0c76-5038-9a64-4bb2a29ab81c |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | f225dce4-d5ec-5992-934c-a62ad612147a |  | note | Ensure Surface is prepared to receive primer application.
label | dc9d7dc8-4821-5168-89b4-b8adb6fc6f83 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 41d5b9f5-d5b1-52ad-a206-62f2bc0ecaf5 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 9c24f3e0-cda1-5775-87d3-7dc563e2935b |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 8dc785fd-5849-56eb-8f32-dc6f99bf7a28 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | d993e4dc-ba77-5a44-aa47-a9d6fa944cb9 |  | note | Records - Time stamped photograph
select | 1ba7911e-adee-5126-bd5a-ecb62effc4af |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Shield Product TDS
label | 5128d1a0-b280-54d1-a6c4-153042df69ce |  | note | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | 80014ebe-8c44-52bd-9468-2678ee4dbe6d |  | note | Records - Time stamped photograph
select | 5f74b39e-e2ad-57bf-b651-a8b905f99e30 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Shield Product TDS
label | ff917656-8691-5a8a-8d1e-f25ec26e0c43 |  | note | Apply within 10-35°C
label | 23b195ec-a596-567d-ba6a-72ba1b45aae5 |  | note | RH must be 0-85%
label | e900bdd0-bffa-571b-bf95-dd1e7ade7b0e |  | note | Screenshot - Temperature and weather forecast
select | 1351a434-3e3c-5ac7-aa38-d500f4d0e295 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro Shield Product TDS
label | 99cbb6a2-d3be-5d99-839d-e381e2b59df5 |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 8ea85e55-9c4a-5e5b-afa6-9da24c2e0e7e |  | note | Mix for 5 minutes or until uniform.
label | 3d03b4a1-dbb2-5963-aafc-68db1e4b55e3 |  | note | Allow to stand 5 minutes after mixing and then mix again for a minute.
select | 4386869a-84f2-5119-8905-5527acf7977a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Shield Product TDS
label | ed461660-98b1-5c6e-b8a3-df83a69e6ed0 |  | note | Apply primer using a brush or roller.
label | dab92e41-45a2-5aca-bbb9-238693b3d0f8 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
label | 01e324e7-4188-5adc-9d73-a1a4c58c8a4d |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | c71d6db1-6660-5517-a2eb-f18865ddb45c |  | note | Records - Time stamped photograph
select | 9fcbc418-29e7-51ad-bf9a-9489a4ad6c82 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | fa66b444-1ba3-511e-b588-5c24d6453241 |  | note | Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 2380358e-85c8-5810-ab0a-2b0f381aafc5 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 810c4307-958e-52d3-b0c2-92d3f66a7d5e |  | note | Allow to be tack free prior to over coating with membrane coats.
label | 2ae9b72f-707e-5508-af5c-abd23b025c78 |  | note | Records - Time stamped photograph
label | aee8fb86-4601-5107-9b2c-e9546ba5cc3b |  | note | Records - Thickness with fillet gauge
select | b2b8cfcc-f9c8-5533-b89b-a8ed256ad68e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman bond breaker inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 200P Ultra Product TDS
label | 494e7477-e8ed-58f3-8990-456e140db13b |  | note | Apply within 10-35°C
label | a206edf2-0156-5d45-bc18-29f85557f0c8 |  | note | RH must be 0-85%
label | f6dc4358-d526-56b7-adf0-b47910235ee6 |  | note | Screenshot - Temperature and weather forecast
select | e5ab4f1a-e383-5a35-9cb1-92fb8f15834c |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - 200P Ultra Product TDS
label | 095ae891-4185-5c4e-a005-97add4bacda7 |  | note | • 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | e139d0c5-7701-559d-8763-c6edc75950c3 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - 200P Ultra Product TDS
label | dd5e087a-1dc0-5a79-a7c8-bc6ab85b9b41 |  | note | • 200P Ultra to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | 95dae775-74ac-5cc5-b2b8-829462a91be6 |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | 3c008728-fd12-5f50-b095-c9bbdff793d1 |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | f9336a01-1bb9-5bb7-8ba4-4d6cd2675d04 |  | note | Records - time stamped photograph
select | 59b0ab16-8223-59df-b888-4a2b7bd61af4 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checkpoint-group |  |  | section | SECOND BASE COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 200P Ultra Product TDS
label | 5638c458-1e2e-55f0-a86a-92ab145f5a5c |  | note | Apply within 10-35°C
label | 06a3f156-d5c1-5f4c-b215-24c614e5b454 |  | note | RH must be 0-85%
label | 7e7799c6-4d43-5071-81f0-64294cca4daa |  | note | Screenshot - Temperature and weather forecast
select | 9ce59582-40b9-58ae-9074-226f61bb4aef |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - 200P Ultra Product TDS
label | 2dbef502-84af-572b-907b-3f541afa32de |  | note | 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | e90cdb40-7779-5bb5-ae99-75fb8023621b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - 200P Ultra Product TDS
label | 84e0a3d4-96c4-547d-bc0f-e4cfd1945384 |  | note | 200P Ultra to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | 43b05fac-03e8-5078-a9f7-afcd024c751c |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | d4f3fa87-8bfd-502e-a327-1c84d0d7fb04 |  | note | Allow membrane to cure for 3 days prior to testing.
label | c2867e4e-5cad-5b8d-afc7-005fcd203ca5 |  | note | Records - time stamped photograph
select | ab5a31b4-38e7-5c08-a25e-b6922227e6c7 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 386ea325-c873-5cd9-9b24-07e9f7c16588 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 033880c4-7081-5c47-a240-f814964b7437 |  | note | Records - time stamped photograph
select | 26178662-febd-5007-9cfa-a7e50e4c16f8 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | 532bd01c-8ec4-59cc-89ce-509fba7f7255 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 9b2db5b5-c147-5b51-a3a0-00e5218652ee |  | note | Records - time stamped photograph
select | 62a72c48-a560-5767-add3-39d7520ad8b8 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Flood Testing
label | ef4beef2-d953-5420-bffe-9a837e69e95b |  | note | Mark water level and conduct a 24 hour flood test for internal wet areas
label | faca497c-f9bd-506e-bf34-4d98088bbb08 |  | note | Records - time stamped photograph
select | a38ce732-b95e-53a9-829d-727e455d2b5f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checklist-flat |  |  | checklist | Enviro Hydrostatic 1 |  |  |  |  | Yes | Enviro Hydrostatic 1 | 091ecff1-da4c-4365-b2a1-4e643c56990c
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 983d6238-321f-5e1a-9a56-679b7c510119 |  | note | Specification / Standard: AS4654.2-2012, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | e7cd1139-879c-51d1-bc9e-cdddcc19e689 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | cfa72c1a-6041-55c7-a7d2-04579a7abc40 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Primer application - Lightly Spray areas to receive Hydrostatic 1
label | aef3a423-d73c-56a7-8021-7585251ce957 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply first coat of Enviro Hydrostatic 1 by brush or roller Use Enviro Joint Band in floor-wall junctions and general movement joints
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply second coat of Enviro Hydrostatic 1 by brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Epoxy RC / Ultra Tuff |  |  |  |  | Yes | Enviro Epoxy RC / Ultra Tuff | 1318bc3f-3eff-40ac-b572-49052424fcc3
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | f7e51a7b-d53b-5e48-ab80-d9de7c43b511 |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | 6b09c6dd-50cf-5cad-a200-9333f05a47a7 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 501f7b51-a135-5926-bd6c-8e560992e2a0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Cutting - Make sure that adjoining ends of intersecting waterstop segments are cut extremely straight
label | aa94131a-886d-5a0f-8cd3-d6a125e77ca6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 625547e5-6d23-5dde-a43e-da207b91e55f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Epoxy Application (1st coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
label | 68419e7b-eff9-5088-8c64-4fbf82d7728d |  | note | (If no aggregate is required, 1st coat of epoxy can be diluted with 10% xylene
label | e90cc86c-301c-582a-b132-746456dc65cb |  | note | If aggregate is required, broadcast at correct coverage while 1st coat has been applied and is in it's wet state prior to curing
checkpoint-status |  |  | checkpoint | Epoxy Application (2nd Coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Enviro 700X V1.0 |  |  |  |  | Yes | Enviro 700X V1.0 | 14eb502d-3f68-4f61-a6ce-55640a8f055f
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 87e65c91-7b68-5310-af73-b26fbee25f6a |  | textbox | ITP No.
text | 34b9e350-ee60-58dc-b215-b59fdfb02ade |  | textbox | Revision No. & Date
text | e2ce1d94-f00a-5e0e-8819-b5d5427b949e |  | textbox | Prepared By
text | b43cea91-2f2a-5eb1-a61c-6a38d17cc87b |  | textbox | Reviewed By
text | ecbdef1b-a5c2-501a-9fa4-4ed7c6e6b59b |  | textbox | Approved By
text | e1a0f824-2969-5c83-a852-b28da724e188 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex Pro
label | b852c9d7-9487-526d-aecf-67923841253f |  | note | Records - Time stamped photograph
select | 92a04eb9-c17b-5bdf-8022-2deb6de2228f |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | 4e04ddd2-ca14-5b8f-8ba9-db3533e68f6d |  | note | Records - Time stamped photograph
select | 568eb1be-aef9-51e5-9883-18973b2aad2a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 700X
label | 48a8f90b-1e8a-542c-b510-a46aae08c829 |  | note | Records - Time stamped photograph
select | f3455359-ef68-559d-b27d-98adf7d63832 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | d3c6bdec-f061-5750-b0e8-1d3d94a95ca6 |  | note | Submit samples for approval as per Specific Material Requirements.
label | 5171d4c8-87d7-5f94-a9f9-8bcc766d5133 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | a80a15fb-fc9e-5770-8bbe-63eb3e4f682a |  | note | Sample Approval Ref
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 5d69d16f-5e6a-52dc-94d2-d709e77d58ca |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | f58c83de-8fee-53bf-9d6c-139c27606883 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 7c6ad560-b277-5fb7-b884-a089f5607446 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 7a804f34-ea05-56b2-9a71-fd77740fe9cd |  | note | Records - Time stamped photograph
select | d4485d89-6953-5ca9-a7aa-274a0b24ed05 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 7cce6fc1-23e3-524a-ad7d-80448c2cdd56 |  | note | Obtain clearance for work initiation.
label | 4c493887-9b9d-5f69-8e33-d512c5b987ad |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 5f5deb02-a087-5a76-89af-04c154266e35 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | ec338a3f-68f5-5aff-b082-8f09ba47ed6a |  | note | Records - Time stamped photograph
select | d4a10c0c-8892-59a7-82e4-d4815a932a94 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 79e20cd7-5a28-51a0-9770-eb7a9b7f02c1 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | 9ae84ce0-a1bd-50dc-847d-88143b1fdb6b |  | note | Records - Time stamped photograph
select | 96cc545f-e2ab-5f98-bd6b-a4e6e6d34e5e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 21af6f3b-2bd4-52ef-b255-b0287eddd939 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | 18e10f81-adf7-55b7-9ffb-a8f07594cf7f |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | e146befd-01f4-5925-b8ba-7903a094af85 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 5c4f1565-8d02-5e3d-bd81-7433f18b2ed0 |  | note | Records - Time stamped photograph
select | 4bbbae17-bdb9-5a53-93ff-7472e37fb506 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | c96ebdce-02fb-57a6-936c-ec91012ccfa6 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | dc7ad5a2-a3e0-5726-9343-d092c1044d45 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | e3ae8f7b-68e1-58b4-a6fa-f0c34ad2a092 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 47f440d9-d7c9-563d-bc6b-fd9b97cf6a73 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | d36f7f88-98e3-58a3-84bf-e55400817330 |  | note | Records - Time stamped photograph
select | 1dbbc85f-79fa-58e5-9565-24f3c923fd34 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | 5102c300-d540-524e-bd61-aebacbfee632 |  | note | Ensure Surface is prepared to receive primer application.
label | 93c40def-de53-5b8c-9e41-a4125a1866bf |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | b4d47da4-c744-54ec-804f-8a28b92f6c7a |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | bb031dd4-c371-588a-af4d-166530646ed8 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 7f1523a8-6b85-565e-a4f9-c154f0278539 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 9136c5de-abfa-5a95-9c93-b1b4ba87875c |  | note | Records - Time stamped photograph
select | c3bbaf25-a36b-598f-b8f1-8b63b2dd497a |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | 54ad968b-bce5-5d45-84c6-398fd8a1a6d6 |  | note | Ensure Surface is prepared to receive primer application.
label | 599a0280-fc44-5e64-8e83-d41ec2efa70f |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | a596ecca-6cef-5627-b62d-7b553ad5c5b9 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | a7300891-d03f-5cf2-a8f3-9d9ee6647ec2 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 2153e184-5202-5fe2-ad06-ec246527f124 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | 02b17268-37a0-5920-aada-e9460f3e21de |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | b0696ea1-5627-5ab1-a312-32e3823195b0 |  | note | Records - Time stamped photograph
select | 06ca84e6-5f55-5050-9bdf-e9b2c2fd8d60 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 9c329917-4192-5080-8258-90f87fc94b73 |  | note | Apply within 5-35°C
label | c5589271-3ac2-58d2-9bf4-21c7c435a2bd |  | note | RH must be 0-85%
label | 17743667-da6b-5517-8368-41b3700f20d0 |  | note | Screenshot - Temperature and weather forecast
select | 3aeba620-dec3-51d6-ba49-d421679710eb |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | 0d8d7b4b-bac8-5bd5-82b6-f66334bedb54 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | b62f959a-cfbb-5d44-af3f-313d5eabc0bd |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | b7ef0bfd-ecef-5a10-b581-f248a308e11d |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | f8399b05-a981-5a11-977a-478085550f96 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | 076fa037-58c9-503b-a6a9-cf7f9dde4a7e |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 422a6828-7211-57e8-93db-a4511b48afb4 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 571d3483-b400-553e-b611-24cad8d1f1e4 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 722e7bd3-eeaa-5503-838a-9d402d110502 |  | note | Records - Time stamped photograph
select | 556ef9d9-1792-5586-9ae4-1129a54416ef |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | 52fe28ed-202e-520b-aad7-b296e64e7504 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | b4181ade-57cd-543c-8ea0-190e3fdc2173 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | cafdc463-59bf-5caa-8da9-f3454a28a414 |  | note | Bond breaker to be tack free prior to coating.
label | c6f58f24-0123-5395-ab94-02c225524ba2 |  | note | Records - Time stamped photograph
label | ebde83f2-510d-56b5-84d2-bcc35714aa11 |  | note | Records - Thickness with fillet gauge
select | 1e0a49ce-e9f8-5dd5-b39d-982adb762968 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | a425ea8a-e459-518e-9ddd-1cda5263d42c |  | note | Apply within 5-35°C
label | b0e748f5-1629-550d-ad0a-f4d696b50d78 |  | note | RH must be 0-85%
label | ca815c69-225c-5512-8707-09b651012206 |  | note | Screenshot - Temperature and weather forecast
select | 52ebba3a-af27-5851-b05d-6ac9bf6fbf00 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 187fbbdc-337a-5805-8196-c39fbc229db4 |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 25e7e202-50fa-522c-81d3-6caf97ee899d |  | note | Records - Time stamped photograph
select | c6cc35cf-594f-529a-8f0b-b50bafa52979 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | eea4052d-b7b5-5f98-8fa4-9b6cdc2cd2cd |  | note | • 700X to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | fa94b9ae-a6d5-53a1-ba79-7973769df2d2 |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | a2a0a41d-c52c-5937-b3d6-67c29e81062e |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 1597cbfd-3b5d-596a-8d8f-f3de66dc65a2 |  | note | Records - time stamped photograph
select | eb3ab580-3a00-52fd-a1bb-4b86a30ce6ea |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | ENVIRO 700X - SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | 45e0fcfb-1e5e-50a8-aa58-4b1f7618db3f |  | note | Apply within 5-35°C
label | da63e75e-a552-5278-9194-b4d6b883156f |  | note | RH must be 0-85%
label | 49065873-126e-5dc1-9158-3d0d77247b72 |  | note | Screenshot - Temperature and weather forecast
select | 76bca100-0613-5cd5-837a-0dd7ef23411c |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 77ab2295-45b6-58b1-8cb0-1bb6df7aaa3a |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 040a1850-061f-5a3f-b995-f9ea5e627b33 |  | note | Records - Time stamped photograph
select | c8819489-e187-590a-b6ec-29cb984dad54 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | dacc2263-eae4-5db3-9125-5d1cb63282f0 |  | note | • 700X to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | 618eb451-7925-5fc7-80a7-36c0674d718e |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | c96d8958-7847-5d71-8635-d2479405db6c |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 177a6365-7667-5960-8473-0224c670fd6f |  | note | Records - time stamped photograph
select | 8adaf006-2f99-5581-87f2-dddd10f67060 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor Second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | ff3cc332-b87e-5299-a6b9-77d28d9e0eac |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | a00e0f51-11a1-5483-aa76-81affdde62c1 |  | note | Records - time stamped photograph
select | 42aca190-5a7c-56dd-a057-a30fb5c8d426 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | c7a3f27f-5e63-590a-990a-b2aa5a78a841 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 83f7ddbf-5f36-53dc-a1a4-42632a2e3a38 |  | note | Records - time stamped photograph
select | f1d0c4cb-3262-5f0b-89e0-07e47c4ec6c4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | 2cf31767-04d9-52ed-b72e-e6d460845a48 |  | note | Conduct Electronic Leak Testing ( ELT) on area membraned
label | ed1c133f-502c-57f3-ad23-ea83aec6f13e |  | note | Records - time stamped photograph
select | 834f6bfe-2e0d-5cd5-a471-acad53bc0191 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING- EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | 15043794-2d96-580a-bb34-39667afceaa3 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | cd03f1e1-61b3-5c46-9551-7db8d9501c27 |  | note | Records - time stamped photograph
select | f3d52266-e334-5b0b-8e47-b2aedf97c7e1 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-sectioned |  |  | checklist | Enviro Clad V1.0 |  |  |  |  | Yes | Enviro Clad V1.0 | 164a11a9-4781-417c-99ef-775199a17e9a
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 4c1e4d8b-de70-5270-858f-732a6fd179f6 |  | textbox | ITP No.
text | ab35990d-2b9b-53ea-a9b9-67047bb36153 |  | textbox | Revision No. & Date
text | 52af26fe-b1f1-5ad9-9dd8-22230717089f |  | textbox | Prepared By
text | ee7de774-5091-593a-abaf-c589a1d45de6 |  | textbox | Reviewed By
text | fdbcb7ee-8507-561c-8eec-24e96e2b07ec |  | textbox | Approved By
text | 505da682-d432-57ea-a936-4f47a1115365 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Shield
label | b6e54c33-3b4f-5435-8aac-ddd6593e57de |  | note | Records - Time stamped photograph
select | 871b57b3-3b80-50f2-9381-9e4ec468354a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex FC
label | 7438cd9f-b514-5cd3-83d1-0870dd51e994 |  | note | Records - Time stamped photograph
select | 58ebaf11-d035-53ad-b91d-e62e01d40d62 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Clad
label | 2a81dabc-2f0e-50ff-91bd-269013cf5641 |  | note | Records - Time stamped photograph
select | 991ead6a-fe08-54a2-a8e7-6955caf1bd67 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | ce77453a-3c10-507a-8ebc-a4113d5928fb |  | note | Submit samples for approval as per Specific Material Requirements.
label | dbad506f-e491-5b51-b1dd-2d7ebccc227b |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 8d924ed1-fd93-569f-a2d7-e6b335f95f2d |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | b70ae807-247b-550a-a52e-f5e2ea779425 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 0b478016-0ea7-59b2-aa56-a1cc766227c4 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 1157e6a2-2d2e-5beb-9892-08bfb6e2fbd2 |  | note | Records - Time stamped photograph
select | ac97ef68-a362-515c-82aa-e4dc637406b9 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | a0bce86f-41d3-5592-a9d2-256162d07ecd |  | note | Obtain clearance for work initiation.
label | 8a5ef42c-84f8-5135-bd95-486631d91462 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | e7816fc4-67d6-5e00-8f65-50a1c98707a7 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 7ea34972-a251-5898-a932-b7e2b6327dbf |  | note | Records - Time stamped photograph
select | f01e6527-ac1f-5214-bf3c-0b1679dd87b4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 1733c331-6aeb-50dc-a32b-8cb39cdc9676 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | ce2f164b-f44d-5c44-959f-d808cf4180b1 |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | 6395825f-e79f-5f80-9b4b-2a2d8ad81075 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | aa573e73-e866-5356-86a5-bec2749b901a |  | note | Records - Time stamped photograph
select | 1abf3945-38d1-5d97-8644-65e22492ebc5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | fa2d712c-91aa-5c3d-bcae-a5bf45c52180 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | b4e26752-8765-52d7-853c-9fa52a87e2c8 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 5d6f41d4-15d6-5daf-af61-3d6e8e91aece |  | note | Records - Time stamped photograph
select | 3a73333f-6646-5412-ad93-3559edc10285 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | af801355-6771-597d-9038-84f472011968 |  | note | Ensure Surface is prepared to receive primer application.
label | 05bba607-88f3-5266-b5e8-d8085ac58cf5 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | f451aa0a-1f66-5bb8-ab34-3aa8b6fac161 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | b0ffe173-09dc-59a5-a516-5fe457ce82d9 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 127e4412-9aa5-5994-a1bb-90001044102b |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 827fd484-e697-5ae5-a8fe-16be1773fd31 |  | note | Records - Time stamped photograph
select | 2f95cfc9-bcac-5ce9-a563-2760c8188279 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Shield Product TDS
label | ffff3856-0c23-5f43-a3be-3448f70ce246 |  | note | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | 691a45b4-5bb7-5364-ac5d-adc14e5ebdb5 |  | note | Records - Time stamped photograph
select | 7c8c9701-fa5e-5c13-b8e0-4ea8af2d9e7f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Shield Product TDS
label | 206bb24b-60f7-5235-999e-74111d96324d |  | note | Apply within 10-35°C
label | 642ce0fc-d610-5cf7-b0ea-6418bbf69b73 |  | note | RH must be 0-85%
label | 7764faed-2fae-5a15-96a1-f018661ad73e |  | note | Screenshot - Temperature and weather forecast
select | bebd19fb-60fc-5026-a3a0-5c94a145aeb0 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro Shield Product TDS
label | 5c071bed-98e0-5eb7-bbd7-d175bc9e1184 |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | a08c6a5e-1cc5-55bd-b653-fd873e4f34b8 |  | note | Mix for 5 minutes or until uniform.
label | 4c22b448-3a17-5f3d-8f08-63e43d76cb2f |  | note | Allow to stand 5 minutes after mixing and then mix again for a minute.
select | ede5bf9c-550c-57bd-a9ad-8b6b74570dd0 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Shield Product TDS
label | 1b0ed537-019a-5c75-ba71-98ddba7e7ca8 |  | note | Apply primer using a brush or roller.
label | 9751d78d-94e4-5344-9492-829f06d30432 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
label | 8847f4ff-df09-5946-92b9-94fa7abd10fa |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 68112dfa-e454-5ea7-a693-0e3e4b586bb7 |  | note | Records - Time stamped photograph
select | 64e80e7d-453e-52d7-9387-6c62df4fcfcb |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | 68bb424c-0de9-57b6-8d19-d1e012be56e2 |  | note | Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | cf0afdfe-9ffc-5420-a199-41d868694d56 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | b9e1a8fb-078c-530e-b7c7-050d04edde65 |  | note | Allow to be tack free prior to over coating with membrane coats.
label | f3ffa249-10fd-5ea8-bfa4-6e62ee01b47a |  | note | Records - Time stamped photograph
select | 0c744db5-da69-5424-a411-0191fd8b7ee8 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman bond breaker inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Clad Product TDS
label | 39984855-a3e8-50a3-a533-55778dd230b4 |  | note | Apply within 10-35°C
label | 7da2fa59-c4d3-594c-b6bd-3e59d1d57ecb |  | note | RH must be 0-85%
label | 3f5a8143-d112-5a4c-8843-4911ef887c61 |  | note | Screenshot - Temperature and weather forecast
select | 24a3397a-782f-5f54-9c8d-37351825a739 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro Clad Product TDS
label | a0a7fab7-e6e3-5a1c-8fc2-9fda54607c9f |  | note | • Enviro Clad should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | 5405e61f-5ee5-51c0-856f-55f1cf42238b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Clad Product TDS
label | 296c81c6-966b-57d7-8e40-df9a1790646c |  | note | • Enviro Clad to be applied by roller on substrate and detailed with a brush
label | 275bdc0b-f963-5bf8-a8ae-9a8557868458 |  | note | Coating to achieve a wet film thickness of 600 micirons
label | 84fef2d4-0e7c-54c0-8b89-f77b007e1b6d |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 065dd8ea-1942-5461-906e-28870a4d1052 |  | note | Records - time stamped photograph
label | bf4a5e7d-913a-5a93-b793-d0a439c5bc6b |  | note | Records - Wet film thickness reading
select | 799d9d79-a14a-5611-a312-8fca442e66ca |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checkpoint-group |  |  | section | SECOND BASE COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 200P Ultra Product TDS
label | fd56a279-d1ba-51df-be12-27a86adff882 |  | note | Apply within 10-35°C
label | 8a5de68b-6919-542c-9d16-3fc27d437821 |  | note | RH must be 0-85%
label | b4dda4ce-6491-50b3-9c5f-ecd0dc6d9da9 |  | note | Screenshot - Temperature and weather forecast
select | 14810a78-d69b-56a7-94d2-d6f6306152b8 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - 200P Ultra Product TDS
label | 828f2831-a099-5b70-9363-849bf6bcf341 |  | note | 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | cdfb9248-bff9-5ec9-bcad-81d4a8761df8 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - 200P Ultra Product TDS
label | f56319fa-5afc-5c4d-b4d8-a3c3ec843fde |  | note | • Enviro Clad to be applied by roller on substrate and detailed with brush
label | b096599f-6c23-542b-97ec-a47d4da4dd00 |  | note | Records - time stamped photograph
label | bdf9ec66-f65b-5bd0-b4f7-766b7238f849 |  | note | Records - Wet film thickness reading
select | f1966b9f-18e4-5b51-ae78-36ca4d985543 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | ec31d57f-4bcc-5aa5-96d8-a4d4567d39e8 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 15ac4d52-82f3-5319-9c12-88b4396a9a5c |  | note | Records - time stamped photograph
select | 9b3cc5c4-43fb-5df5-8cf2-0a59ce51120f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman base coat inspection sign off
checklist-flat |  |  | checklist | Enviro HP1200 + 700X |  |  |  |  | Yes | Enviro HP1200 + 700X | 2c3c9aa2-f94b-40b1-a23f-a70eeb1f168e
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | e0ca0e40-80c7-5ba1-90d2-f3a3390a396b |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | 29d9b8ad-838b-567c-a1ca-f9ba2dd86df2 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X
label | ca777f10-3e3f-5ad8-b811-73e787cb3708 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply primer (Enviro Epoxy B-LV / Enviro Prime P2 / Enviro Shield) using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X
label | 6bfdfa59-9d6a-5e0b-b011-952d51a47739 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. HP1200 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT. (2 coats)
label | 63a3478b-047b-5c02-b9b6-47f63e15531b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed Enviro 700X to ensure the membrane is not damaged
checkpoint-status |  |  | checkpoint | Top Coat. Enviro 700X should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat
label | 5d1a6503-796b-5331-a62d-d77765e21179 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test
label | ac56fb5d-4146-5354-9315-4a5b0ada4168 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Polyseal ITP - Roller & Spray Applied |  |  |  |  | Yes | Polyseal ITP - Roller & Spray Applied | 36765db2-d78c-4794-b5dd-71db13232634
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 3e440281-b0c1-5cd4-a95e-3530adafb9fe |  | note | The installation and testing of waterproofing membranes must be in line with AS4654.1, AS4654.2, AS4858, AS3740 and the Multiplex project Specification
checkpoint-status |  |  | checkpoint | Item no. 1 Product Procurement
label | 70b8398b-4c15-579a-94fe-9a5583de8bab |  | note | Refer to attached Manufacturers TDS - Check Use by dates, correct product, quantities etc.
label | 81d5e748-bb70-531e-aefa-451978162377 |  | note | Uploaded relevant TDS
label | 41fff0e0-9167-5454-b64e-184d3993c7f5 |  | note | Frequency: Ongoing
label | ba5c5830-1a7d-5432-9503-387b05da1b94 |  | note | Record Kept: Polyseal Procurement
label | 0348063f-739c-5acf-ac9d-9337ca06a700 |  | note | Inspection Type: Site Inspection by Applicator
label | 3153e522-392f-57cc-9d8f-239cb9421457 |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740, Manufacturers Technical Data Sheet
label | 270bd334-f5bd-532c-a664-403037014e85 |  | note | Inspection Procedure: Documentation
label | 76f5a3a1-db78-5e3e-85c3-9dbc9677ae0d |  | note | Inspector Signature attached below
holdpoint |  |  | signoff | REQUEST SIGN OFF
checkpoint-status |  |  | checkpoint | Item no. 2 Check Substrate/Work Area
label | 2ec31230-59d7-5403-832d-f66f8948f8ab |  | note | Applicator Inspection - Concrete sound and level, Trowel Finished, Are there voids or leftover formwork. Drains installed and covers removed and installed by others, Pipes and conduits spaced 100mm apart and extend up minimum 100mm. NCR any unacceptable items.
label | 4cdd5182-3211-5ff1-965e-6211ba1f265e |  | note | Record Kept: Polyseal site specific CONQA web app
label | 7c8613ad-eb09-5e31-b18c-0eed375d2bf8 |  | note | Inspection Type: Holdpoint
label | 95d78ff8-323a-5428-8b87-36f93ee69fe0 |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740, Manufacturers Technical Data Sheet
label | e8bf8a72-5460-57b0-aa82-4a1a7b99b99c |  | note | Inspection Procedure: Polyseal site specific CONQA web app, Site visit by Polyseal QA representative
label | a3fc0c7a-cc74-50fb-a3bc-5e4b966b9d46 |  | note | Inspector Signature from Polyseal attached below
label | 670e0915-669e-5dcb-bf66-fb2a5f5a30e0 |  | note | Inspector Signature from MPX attached below
holdpoint |  |  | signoff | REQUEST SIGN OFF
checkpoint-status |  |  | checkpoint | Item no. 3 Repairs by others if items above are not rectified by Polyseal
label | db709fe2-b9ab-58b2-8c5d-8cf1dc931b60 |  | note | Repairer to Liaise with Polyseal regarding suitable/compatible repair methodology
label | ee70523d-79f8-5697-9372-e283088837dd |  | note | Frequency: Each location
label | bf5582f5-b9fe-50a4-ba2b-ab1e6106a9d7 |  | note | Record Kept: Polyseal site specific CONQA web app, Other party's inspection report (if provided)
label | 92455720-09b5-5f40-958c-32f2cca28674 |  | note | Other's inspection report uploaded below
label | 78ea7ed4-1730-553b-bd3e-7e0342cea3a8 |  | note | Inspection Type: Witness
label | 7f6ba3d4-7c7d-5827-891d-34a7e13436dc |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740, Manufacturers Technical Data Sheet
label | 3f4bbd95-26a3-58f7-9a12-bfb38c3c7fd8 |  | note | Inspection Procedure: Polyseal site specific CONQA web app, Site visit by Polyseal & MPX QA representative
label | 4d3bae90-bac3-5572-bc8f-39f1a880d655 |  | note | Polyseal
checkpoint-status |  |  | checkpoint | Item no. 4 Prepare Surface: Abrasive Grinding
label | af7c83c8-7dc9-56ab-9904-60b7ff58d4fb |  | note | Free substrate of dirt and debris where required.
label | 23ad9e96-9047-5850-ab77-22328fc49a5b |  | note | Measure surface profile using the Digital Surface Profile Gauge (e.g Elcometer gauge) and checking the surface achieve minimum 75micron profile to substrate.
label | 057fdeb5-222d-5fc9-b82d-ae4a486a46cf |  | note | Frequency: Each location
label | 016c0f3b-38b3-5d74-a0cb-d37a4e4e59ab |  | note | Record Kept: Polyseal site specific CONQA web app
label | dd1ccd4f-6efe-55f6-a27b-5f8ef3841f90 |  | note | Inspection Type: Surveillance
label | 9d7b940e-8c7d-58c7-bae9-6512a4a94ac7 |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740, Manufacturers Technical Data Sheet
label | aa98af9b-5f1d-580d-a9ff-fb7aae602659 |  | note | Inspection Procedure: Polyseal site specific CONQA web app, Pre Inspection checklist in CONQA web app
label | 0c7b9cc4-e0bd-5298-9de6-832580db0edd |  | note | Inspector Signature from Polyseal attached below
checkpoint-status |  |  | checkpoint | Item no. 4 Apply Primer
label | 10f1d3d4-6d12-50e8-a21d-6fd0e45f7613 |  | note | Record atmospheric & substrate conditions & notate in QA Documents. Humidity <85%, Delta >3⁰, Air Temp 5-40⁰.
label | 061d1e1a-666e-5779-987b-db54eb2d6e29 |  | note | Frequency: Each location
label | 4aacaac6-1a99-54fe-8de7-c272a9e00bc0 |  | note | Record Kept: Polyseal site specific CONQA web app; refering to photos of primer batch number and atmospheric information
label | 013d2a65-d1da-57c9-a1b4-b82a926cffe2 |  | note | Inspection Type: Holdpoint
label | 71e92492-1ceb-5ed5-a2d2-a7181c007f3b |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740, Manufacturers Technical Data Sheet
label | cdd8c861-b153-5730-bfc9-80acea53c071 |  | note | Inspection Procedure: Polyseal site specific CONQA web app
label | 30f5580a-8511-5768-bc26-efb5c92e7c54 |  | note | Inspector Signature from Polyseal attached below
label | 149e8cf6-6b5f-5b0b-8cc0-251fa1e6062a |  | note | Inspector Signature from MPX attached below
holdpoint |  |  | signoff | REQUEST SIGN OFF
checkpoint-status |  |  | checkpoint | Item no. 5 Polyurethane Fillet to Junctions between elements (Penetrations/Construction Joints/Floor to Wall/PT Pans)
label | f0d5d1e1-1032-5513-9ad3-c1f5476fb733 |  | note | Polyurethane Cove to any junction or where two different substrates meet. (10mmx10mm cove)
label | dfd063df-b108-5eae-864e-6a832ce0272d |  | note | Frequency: Each location
label | b4739a50-e37e-5444-8db8-d9fff913223e |  | note | Record Kept: Polyseal site specific CONQA web app; refering to photos of membrane batch number and atmospheric information
label | 74637ad4-da56-5ece-a00d-a7fa35f128a5 |  | note | Inspection Type: Witness
label | 06f7bdde-94db-5283-a8de-f21caf8bae5a |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740, Manufacturers Technical Data Sheet
label | 51ef099f-dedb-5cc3-968f-fa4838d055ae |  | note | Inspection Procedure: Polyseal site specific CONQA web app
label | 55540baf-f09b-5543-b7f8-82118a5f2f79 |  | note | Inspector Signature from Polyseal attached below
checkpoint-status |  |  | checkpoint | Item no. 6 Apply Membrane
label | 2c7c430c-2b1a-5b1e-8c26-a51d1603e831 |  | note | Record atmospheric & substrate conditions & notate in CONQA web app. Humidity <85%, Delta >3⁰, Air Temp 5-40⁰, Check WFT regularly, Pull off and DFT test 1 per 300sqm, Holiday testing to requested area
label | c63a1bab-86a4-5b4f-adda-4dd96f9809fa |  | note | Frequency: Each location
label | 0e8ef9e2-acdf-55da-869b-51ee087e38b3 |  | note | Record Kept: Polyseal site specific CONQA web app; refering to photos of membrane batch number and atmospheric information
label | 8860af7b-c2b9-5f40-93e7-8d025abac591 |  | note | Inspection Type: S
label | c48cbe67-8771-5d97-8e62-bd7dc46588a8 |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740, Manufacturers Technical Data Sheet
label | 518d3bca-46e5-509f-a879-8ad2f02f02e3 |  | note | Inspection Procedure: Polyseal site specific CONQA web app
label | 233c66b6-6431-5fd7-8342-b49248c5721b |  | note | Inspector Signature from Polyseal attached below
checkpoint-status |  |  | checkpoint | Item no. 7 Carry out Dry Film Thickness test & Holiday Testing & Pull Off Test
label | 9813c992-7537-5ce2-9a77-31a1e0e9d09e |  | note | Repair any defects found using patch and repair method specified in procedures.
label | bfd17d33-99cb-5e78-9979-293197977ea4 |  | note | Frequency: Test required location
label | f4ea24fc-de47-5d35-8153-a804eddfea93 |  | note | Record Kept: Polyseal site specific CONQA web app; refering to photos of specific test
label | e459ad39-670a-5683-a4f7-c8ebc9c1395b |  | note | Inspection Type: Holdpoint
label | b5ea1be7-4b3d-5fad-b5c1-d093faa8eeb1 |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740, Manufacturers Technical Data Sheet
label | da6b4853-50d8-5f20-a1fd-4bdc35ee6372 |  | note | Inspection Procedure: Polyseal site specific CONQA web app, site inspection conducted by Polyseal Leading hand and MPX supervisor when required
label | ccc6674c-6086-573f-9438-e4eddbc6840d |  | note | Inspector Signature from Polyseal attached below
label | 337727b8-f3cc-5763-8299-7acfb11fccc2 |  | note | Inspector Signature from MPX attached below
holdpoint |  |  | signoff | REQUEST SIGN OFF
checkpoint-status |  |  | checkpoint | Item no. 8 Handover QA docs
label | 1fca47f0-97c0-5e02-8760-f47bc0e316b1 |  | note | Once membrane is complete and QA documents reviewed by MPX and Polyseal sign off area as finished
label | 4c584c46-6aeb-5270-b0f2-8a8a210977a7 |  | note | Frequency: Completion of block/zone
label | 99fed15e-e36f-5197-b116-8db375da571f |  | note | Record Kept: Polyseal site specific CONQA web app
label | f6d6f0fa-9c4f-5085-b8f3-45333d20b031 |  | note | Inspection Type: Surveillance
label | 241e5043-2242-5bec-86e0-e6e0be5e7e7d |  | note | Spec / Standard: AS4654.1, AS4654.2, AS4858, AS3740
label | 8fb7e5b0-ceff-51c3-9fe9-8be226410909 |  | note | Inspection Procedure: MPX QA document handover procedure
label | ce2619a1-395a-590e-8d1b-8213072537b2 |  | note | Inspector Signature from Polyseal attached below
label | e7404f37-5efa-566c-85d9-5458b52014de |  | note | Inspector Signature from MPX attached below
checklist-flat |  |  | checklist | Patching and Handover to Bondek |  |  |  |  | Yes | Patching and Handover to Bondek | 384f7a3c-1748-4ce8-b970-212d69b40b32
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | aa3cb9bb-6d9e-5b32-a07d-4b4444381f36 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check membrane - Check for damages to membrane.
label | b6ae40ae-7a3b-5195-9118-0a840264bdc8 |  | note | Attach Photo of damages
checkpoint-status |  |  | checkpoint | Patching. Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT. Or Apply Enviro 700X.
label | 709927be-0306-5685-b322-c28752b2e230 |  | note | Attach photo of patching.
checkpoint-status |  |  | checkpoint | Lapping to blockwork prior to bondek being laid. Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT. Or Apply Enviro 700X.
label | ce5d5d41-ee99-572d-9f08-025e07cbfd5c |  | note | Attach Photo of lap to blockwork.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+900 |  |  |  |  | Yes | Enviro HP1200+900 | 41a77c2b-38df-44b4-966c-f5f80ba871df
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | b0b95391-58dd-59fa-81ab-cfcc45c0b011 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | a341b579-6669-5c17-9e7f-dc5cebfa0a57 |  | note | Attach Photo of substrate
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 8deb82ad-da40-599d-9e09-85dec441232c |  | note | Attach Photo.
checkpoint-status |  |  | checkpoint | Moisture Content Test.
label | ad8f45f6-a820-5681-9b4b-0950c64e0643 |  | note | Attach Photo of moisture reading or enter moisture reading in comment section
checkpoint-status |  |  | checkpoint | Check label on drum to ensure correct material is being used
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 86ec9ee4-374a-59b6-b29e-50635bafcc52 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | be736658-261b-5754-b710-6a86d10aa051 |  | note | Visual inspection, ensure adequately cured.
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
checkpoint-status |  |  | checkpoint | Mixing. Mix HP 1200. Mixing by way of 1:1 mix ratio (by volume) in heated plural component spray equipment such as Graco E-10 or EXP-2. Both low and high pressure spray equipment can be used for the application of Enviro HP1200.
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT.
label | e52bbb52-1a04-580f-97bb-4cdaa7b3e5fd |  | note | Attach photo.
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | da6df8f6-6cf5-510f-83ef-099ed9ea9356 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Wear Coat - Mix and Apply Enviro 900 with brush or new roller (spray application optional) Broadcast aggregate uniformly to the wet Enviro 900 within the timeframes specified
label | 0c290203-5a38-5a7d-b3ca-d185cdf4bc6e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat Mix and Apply Enviro 850 with brush or new roller (second coat optional pending specification)
label | 18d0f7e2-bfb5-52e6-867a-11df42b62740 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | DFT Testing
label | a375d51b-8f0a-5495-9425-bfff921eabeb |  | note | Attach Photo. Enter DFT reading on comment section.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+Shield |  |  |  |  | Yes | Enviro HP1200+Shield | 492b2969-01a7-40b0-83ec-c4114ec95cba
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 174204bf-e5ee-5fba-b5ec-2e3ed67e100a |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 08078cde-49b8-593f-a3c1-413dcd79b518 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) and prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 2a92f274-cb5a-5095-9310-14fd9563f7e0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Check label on drum(s) to ensure correct material is being used
checkpoint-status |  |  | checkpoint | Apply primer (Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | 4a95bf97-bea6-5318-96d4-da9af90948d3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking/ Joints. Apply bondbreaker at junctions
label | 05f1ddda-ca03-5cee-b0bf-714399bedf7e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing. Mix HP 1200. Mixing by way of 1:1 mix ratio (by volume) in heated plural component spray equipment such as Graco E-10 or EXP-2. Both low and high pressure spray equipment can be used for the application of Enviro HP1200.
label | 4c9ecaf3-075b-56c0-8ce6-8660b1934d00 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Application. Spray on Enviro HP1200. Achieve 1.5mm DFT.
label | 8356fdcd-8867-5645-a084-d3e93c1c022c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | 0bfdc2a9-b1a8-5b20-9c14-414e71a78ed6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over if applicable.
checkpoint-status |  |  | checkpoint | Check Screed (areas where applicable) moisture test if required, Enviro Shield is moisture tolerant.
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro Shield with a brush or roller.
label | 73dd952c-4478-5052-8053-f01cd5d4b2df |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro Shield with a brush or roller.
label | ed2acd38-75c3-5af3-a155-938259807531 |  | note | label
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Enviro BSM V1.0 |  |  |  |  | Yes | Enviro BSM V1.0 | 5614c9db-35da-4e38-a747-a1c9510c4231
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 68fe7e95-f059-5264-86a7-e41cd66e05ca |  | textbox | ITP No.
text | 22d2d90f-25db-5e4c-82e7-349a26282765 |  | textbox | Revision No. & Date
text | f0469602-b1f4-5efa-8c32-cfc4c53e0ccf |  | textbox | Prepared By
text | 35e45697-0d2c-52d1-9f6a-ba4eb50a02ad |  | textbox | Reviewed By
text | 937cca6c-68c5-5779-a5b6-460a11481716 |  | textbox | Approved By
text | 7ef022f5-5fb3-5071-bd20-9fe2674b3438 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro BSM
label | 4dda983e-76f7-51ef-ac6e-044873143abf |  | note | Records - Time stamped photograph
select | 6e682470-2c69-54b1-8ce2-e494b65cf238 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Epoxy Grout 100
label | 43837305-55ca-556b-9cbc-69493bdbe9e0 |  | note | Records - Time stamped photograph
select | 406f4c83-24e9-5998-b510-2f66fbfe743a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 700X
label | 9298e06f-875f-5b39-8cad-a473d235982b |  | note | Records - Time stamped photograph
select | 823b7fc4-8035-520e-97aa-174646e6ee31 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Envro Flex FC/ Sika FC
label | 51c8542d-b0ee-5c89-a1ae-2f4240f9a38b |  | note | Records - Time stamped photograph
select | b9db5367-f444-5a10-869e-b05895fa6d30 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor and Site Engineer/Foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | 03ee53c8-40b1-5064-bc4c-9c1befd6d4a2 |  | note | Enviro BSM to be stored upright in dry, cool conditions out of direct UV and weather. Maximum storage temperature is 45°C.
label | 406e3541-5b3b-5469-a788-bfe8bd4f22e4 |  | note | Screenshot - Temperature and weather forecast
label | 0392ef1f-3db8-5341-8fac-e0306391905a |  | note | Records - Time stamped photograph
select | 306d18b7-1dbc-5a35-87e7-e5dca6a12da7 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection Sign Off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | a10dc566-1da6-58a2-866c-ed24650feea7 |  | note | The substrate should be sound and even, thus preventing movement or subsidence during concrete placement. |  |  | `
label | 77a4edca-c87f-5787-91e5-3f3f5f897e6f |  | note | The substrate in which BSM is to be installed should have no protrusions, gaps or voids greater than 10mm. Penetrations such as plumbing and electrical pipes should be stabilized to prevent movement during membrane and concrete placement.
label | 0c67d8d0-6729-5019-a5e3-ef522062526d |  | note | For horizontal membrane placement, ensure that the substrate is sound, especially when installing over compacted fill so to avoid displacement from traffic or pouring of concrete.
label | 70429150-d883-5ec2-b037-7d4b17dd8527 |  | note | For vertical placement, ensure substrate is sound to provide required support for membrane during concrete placement.
label | c22345c7-1a27-5a2b-bb49-5c79852df830 |  | note | Records - Time stamped photograph
select | 7a080703-b2ac-555d-84bd-86b1fcc40c54 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection- Sign Off
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 6a8146ad-2607-5bee-ae1c-39cb3a178c92 |  | note | Submit samples for approval as per Specific Material Requirements.
label | 2b70c47d-9995-5ca2-805b-4d66ce69e44b |  | note | Sample Approval Ref.
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | dce40751-782d-5e7d-ba9b-0d0193f617cf |  | note | First of type of inspection conducted prior to commencment of works taking place.
label | db511336-681f-572f-8361-62251e98a7a0 |  | note | Document Ref.
holdpoint |  |  | signoff | Sample Submission / First of type inspection - Site Engineer Sign Off
checkpoint-group |  |  | section | APPLICATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | Horizontal application
label | b3acb2bb-0dde-5411-976a-ae843eb1d3b4 |  | note | For horizontal applications, Enviro BSM should be placed with the coloured protective layer facing upwards and the white HDPE layer facing the substrate. Stagger end laps of each run to avoid a build-up of layers.
label | 1919977f-39ef-58b3-b8d1-f1a2a3df35da |  | note | Overlap each previous sheet by 75mm ensuring membranes overlap edge is positioned correctly. Ensure the back of each subsequent roll is clean prior to overlapping and once in place remove the plastic film (on the overlap section) to bond the sheets together.
label | cf7def19-fa00-56d2-aab8-79c7f676ff27 |  | note | Ensure a complete bond with no creases by using a heavy roller across overlap areas. Once overlap bond is complete the plastic film can be completely removed.
label | 4e47907d-d287-5f69-9c3b-979317092334 |  | note | Records - Time stamped photograph
select | 107b9246-dda3-519f-8892-db664400d0af |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection- Sign Off
checkpoint-status |  |  | checkpoint | Vertical application - Witness Point
label | f62f8c1b-1965-5bd4-9a9e-42122e4ae1a8 |  | note | Enviro BSM should be mechanically fixed to the substrate using (substrate dependent) fixings with the coloured protective layer facing the concrete pour.
label | f55af3a6-6382-54cb-9ef4-a0dfc30beb55 |  | note | These fixings should only be placed in the overlap section of the membrane and have a low-profile head so that the sheet overlaps can lay flat and rolled evenly for optimum adhesion.
label | 4b5e8d2a-6f99-572a-8e1b-a93d348fdb03 |  | note | Overlapping in vertical applications should be done in the same manner as horizontal applications ensuring subsequent sheet is overlapped by 75mm, adhered, and mechanically fixed correctly before proceeding with the next.
label | 669c98f6-3ff2-56fd-af4b-ad8f8142e93c |  | note | The plastic film can be removed immediately in vertical applications. All cut edges and roll ends should be overlapped by 75mm, be clean and dry and sealed with Enviro BSM SeamTape.
label | dd2def66-caf9-53c0-892a-5b4378ba69e4 |  | note | Records - Time stamped Photograph
select | 5788eff6-3c9d-5064-954e-d6149f1404c4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Builders Application Review
holdpoint |  |  | signoff | Site Engineer/ Foreman Inspection - Sign Off
checkpoint-group |  |  | section | DETAILING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Reo Bars
label | 8770b17c-9d27-55aa-bd0f-ac5259938f74 |  | note | Ensure bars are chemset and fully cured prior to detailing.
label | e8e5b53c-6eaf-53ed-ac6f-4114cd0751de |  | note | Use Flex FC/ Sikaflex FC to caulk around reo bars and overcoat with Enviro 700X.
label | cd73380f-6c35-5517-b340-2124a86c46c7 |  | note | Membrane to return out minimum 50mm.
label | eea6c1df-d295-554e-bad0-11fd8343fa72 |  | note | Records - Time Stamped Photograph
select | 8c6c52ee-dd56-5ae8-b574-1d134a1fe64c |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Pile Caps
label | 6bd8bb3a-67da-5beb-ac61-2741684403f6 |  | note | Pile cap to be encapsulated with Enviro epoxy grout 100 achieving minimum 50mm finished height.
label | 7d890802-58d2-5e6a-ad42-42c2e0614224 |  | note | Records - Time Stamped Photograph
select | 12d214a0-57fb-5ec4-8cbe-46b4b11e26a3 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Sub columns
label | 72ee2c34-c0cc-5f9a-b078-c1194b591006 |  | note | Sub columns joints to be caulked and overcoated with Enviro 700X terminated minimum 100mm high and 100mm lapping on BSM sheet.
label | 6c3606bb-5a7d-53aa-ae49-b743b64fdadc |  | note | Records - Time Stamped Photograph
select | c4648a2e-bb0d-586c-95a6-37e12232bf12 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Service Penetrations
label | d5cc9510-5355-57e5-aba5-bd836303d38a |  | note | Service penetrations to be caulked around with Enviro flex FC/ SIka FC.
label | b2956fa8-d590-5a79-b450-9fa910e49af3 |  | note | Records - Time Stamped Photograph
select | efc985cd-4534-59ce-8645-417a173ca443 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor Inspection - Sign Off
checkpoint-status |  |  | checkpoint | Builders Detailing Review
holdpoint |  |  | signoff | Site Engineer/ Foreman Inspection - Sign Off
checklist-sectioned |  |  | checklist | Enviro HP1200+800TC V1.0 |  |  |  |  | Yes | Enviro HP1200+800TC V1.0 | 5ef7c5ad-1dde-4c02-97f4-1d9f1f76d994
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 3c694b2c-c959-5c77-ad7e-7c6c6b841f7a |  | textbox | ITP No.
text | 63bf2f0e-4033-50cf-af0b-86ef7e7d6fe3 |  | textbox | Revision No. & Date
text | 91bd5f27-98e1-5a39-9787-91fb5b4b2115 |  | textbox | Prepared By
text | f34f4d69-16f2-50d1-b7c4-fabe2c178bed |  | textbox | Reviewed By
text | 2c696b0e-ee75-5be7-b864-c495a245057b |  | textbox | Approved By
text | b293a4c3-8c8c-5292-b15a-0b0da323b732 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | 979265b8-6bb9-5b02-ab45-9b49d90b989a |  | note | Records - Time stamped photograph
select | 7bd7e2d0-8bb7-5795-8c7a-c6e9af62d6ec |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Sika Flex FC/ Enviro Flex FC
label | 7c798ba4-643e-5562-9159-7ce1d6031baf |  | note | Records - Time stamped photograph
select | 7c6a71a0-deab-5822-b58b-f257db58bf8e |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro HP1200
label | cabd3104-5c34-5bc2-84e4-e28a4116fef3 |  | note | Records - Time stamped photograph
select | 10bc5688-f797-5169-b973-bdd9fcba6038 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 900 PUR
label | e094e936-3973-589d-a71a-054e8c9d1b11 |  | note | Records - Time stamped photograph
select | 791699a6-38aa-5b1f-9130-a402bf397dda |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 800TC
label | 88316839-3c6b-56d7-a15e-0a564c5668fd |  | note | Records - Time stamped photograph
select | dfb25ebe-0ebe-50e2-91fc-5cca8eead70a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 3e679d6c-8ea2-5ef8-84cc-795b7c95431a |  | note | Submit samples for approval as per Specific Material Requirements.
label | 02587a10-404e-5cf4-9db5-6f4fef8d151f |  | note | Records - Subcontractor Contracts Admin Confirmation
label | 1cd22931-678f-5894-a93c-6ee1d428445d |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | c4a42539-82ab-5f4b-bb18-5e4e4d1db80a |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | 36befb10-b92c-5a76-bc17-c0e7338d561e |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 8fa7b53a-b3e8-56d4-9f34-9afc0465e0c6 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | b9904a1a-9226-5b11-9af0-c8e6417ff68b |  | note | Records - Time stamped photograph
select | 77408d11-5c6e-5894-8db8-5bc4906e994f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 895b2a9d-5d81-539e-90d8-8084a5037528 |  | note | Obtain clearance for work initiation.
label | 35ff15c1-dbed-52c2-ad2d-563dc1f2bc63 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 69a956cd-0acf-5dfe-86fd-56dd13d73244 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 247afef4-6e5c-5529-b469-b1d8959f33a5 |  | note | Records - Time stamped photograph
select | ecee74d4-bdff-59ca-a260-3b84fc38830d |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 5f12385b-1f9a-5a0a-912f-2a6d8986753c |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | 65f50955-c477-5cd7-a039-65cb774d1e81 |  | note | Records - Time stamped photograph
select | 8fb6fc3e-202e-54c1-bcd2-162ac9dd2d64 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 98779d7c-7140-5822-9ae1-ab3e22a548be |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | c03cb8fd-3e2a-5890-928c-27a0eb64d55e |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | f23c40ee-2aa0-529f-8138-996b4f47b886 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 5b1d15c3-2098-55a5-bf05-18daf85769f4 |  | note | Records - Time stamped photograph
select | 87b240fe-4218-50cf-ae53-5f6e0a1b693a |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | 1e2197ef-52a8-5472-a659-5cae50a04c92 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 8e7b5c22-e3ee-5d77-afe0-5fb70faa49b2 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | d8aed63f-c653-54e5-bf7b-e0deb61fec88 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | e0251e0e-8798-5824-8a26-bd9202860e11 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 0596d00c-f632-50f7-9510-d62a2571973c |  | note | Records - Time stamped photograph
select | 6652d8f2-6d6e-5b7e-aa9e-92b70059f1ae |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | 79895bec-2548-5b29-9c12-26942676e36e |  | note | Ensure Surface is prepared to receive primer application.
label | 62b1b9cf-461c-5e21-9ff3-9b0e914c5cef |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | bf10b33f-06e8-576e-bb34-280f591248dc |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | ab670afe-182a-593f-b09c-085442970523 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | e1a975f0-3050-534e-a7de-0d630057d8c4 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | c1abeb6f-13cf-53e2-9298-0886ba6c13ea |  | note | Records - Time stamped photograph
select | 0b7f56f0-6235-591a-b89f-4c8f6d4c67d9 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | 851e66dd-b1c8-5e8e-a740-1b10ba8c928d |  | note | Ensure Surface is prepared to receive primer application.
label | 9a5a1b36-1398-51c0-86e2-bb5092ffa8c9 |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 1c6edaa8-d09d-5dbb-be29-378b242f07a9 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | f303fd23-4375-5a7c-b13f-2a39ad07af56 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 30241c00-095d-5754-954d-fddb4214caf4 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | cd244bab-a2c6-5792-adbe-d2dd4176a67b |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | e0c45834-bfdd-5a54-bbd1-bd324be024ff |  | note | Records - Time stamped photograph
select | 35676b4c-26c4-5bb8-bce9-b6f9fcc65c83 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 2978cf5c-7a56-50e1-bcf2-8309876bd543 |  | note | Apply within 5-35°C
label | 8664d6d0-6714-5574-bc22-f44acde7673c |  | note | RH must be 0-85%
label | 41ebc8e1-c630-5f96-beaf-cb99dfbd090d |  | note | Screenshot - Temperature and weather forecast
select | 459f9432-33b1-5bb9-a547-976e771dde7a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | a6169534-9918-5fdf-ae01-e3cafb574772 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | b7e906d9-8959-549c-9936-112197c3063e |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | 313da0d3-890a-50c7-96da-128f52fb4ba6 |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | f553c9ce-9c3e-5bf3-8b82-9b8ebd19b1d2 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | 414d99ef-9eeb-50d3-9d60-a3676b6d84bf |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 412dab85-ad77-5b66-b009-b0e8537542ab |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 9d6e812e-032f-5f16-8aad-d26c7fc208f0 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 41f8dd1f-6811-5221-900a-334dc99a5c8f |  | note | Records - Time stamped photograph
select | b1328787-b592-5474-b199-1f5b510c6d56 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | 7906813a-0e9d-59b3-bae3-04d6a018f798 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 494f0425-503a-5305-9277-71484e2cfebe |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 05a1d3b2-4283-5c6b-9d67-25d678bbdb9f |  | note | Bond breaker to be tack free prior to coating.
label | af582b73-ad72-58c5-9d18-82372f6761f1 |  | note | Records - Time stamped photograph
label | 9c54e1c2-e2c6-5629-8ef8-ffe33bdd8242 |  | note | Records - Thickness with fillet gauge
select | b6a98c49-e69a-54ea-a9dd-5a6754e98936 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
checkpoint-group |  |  | section | BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - HP!200 Product TDS
label | 2aa04793-0d0e-515c-93c1-a4be88c88c26 |  | note | Apply within 5-35°C
label | 4de94224-35e3-505d-92df-72f239704922 |  | note | RH must be 0-85%
label | 5fc813c4-4abc-5f6b-9b5c-65d747593538 |  | note | Screenshot - Temperature and weather forecast
select | 9e836fba-e2d5-5683-9c7f-002adf563bca |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - HP1200 Product TDS
label | c09b6c38-06bb-5d89-9782-448ea3104638 |  | note | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
label | f411dcd6-4b21-51ab-ae00-a10616baf1aa |  | note | Mix Part B thoroughly with a mechanical power mixer before use
select | 72a18d1c-77f1-540f-b256-2fbdb4ac8ee8 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- HP1200 Product TDS
label | c152500f-7936-5f26-a052-2de27acc16cb |  | note | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing
label | 56e2c7ba-3a99-5795-af21-d78fede5cb17 |  | note | Records - time stamped photograph
select | 66fdd4e4-1a43-56f6-b8e2-b793e554c3e1 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 9ddd5169-fc74-5e6f-8426-c5d60e156d76 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 7944f33c-b4f9-5ac0-adf2-d26c451fa4c0 |  | note | Records - time stamped photograph
select | 0823a64f-8912-5f8a-a257-f8bdc7973db7 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | c19a587f-f486-5d07-b501-59dd077a6c99 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 57dc1c7e-c8f7-58b4-9515-e7d453959e89 |  | note | Records - time stamped photograph
select | 31cdd15d-8897-553c-a41e-5c7a82700e75 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | 8b594d92-1317-5b07-95c7-08d4b03120db |  | note | Conduct Electronic Leak Testing ( ELT) on area membraned
label | cb663322-8651-5b10-bb87-fe03c26c12e7 |  | note | Records - time stamped photograph
select | 12f51491-5874-57cd-b1f4-ecaa14da47c0 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | HOLDPOINT - Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | HOLD POINT - Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | WEAR COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro 900 product TDS
label | fdab6e41-ba53-5f54-bb4d-e77b179fc49c |  | note | Apply within 5-35°C RH must be 0-85%
label | 3b55d11f-e46a-519b-a1ac-5d51c2cdedd7 |  | note | Screenshot - Temperature and weather forecast
select | c1606599-a8f9-58e9-a6bc-08590f245719 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing of Product - Enviro 900 product TDS
label | b2374e37-39af-5ba9-bc78-a120581a9ed8 |  | note | Mix Part A and Part B separately, before combining.
label | 5b8745cc-2daa-5e1d-8a14-bbd829e4be0b |  | note | Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
select | d63c499f-f3d9-5a25-ae09-db878713d773 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro 900 product TDS
label | c523cd4a-7cdd-5b72-87c7-59fbd9a87bc5 |  | note | Enviro 900 to be applied by squeegee, roller or brush to finished membrane.
label | 6ae4ec7a-b9f4-595b-82e3-70026211554d |  | note | Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes.
label | 0669022a-085f-522f-8a34-7552a69c0501 |  | note | Records - time stamped photograph
select | 30b61d0c-cae9-579e-97c9-323cae47f3e4 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor wear coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman wear coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | FIRST TOP COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro 800 product TDS
label | f9a9956f-e673-5c2c-b926-0ab8ae532b73 |  | note | Apply within 10-35°C
label | 0b12bb3c-3ee2-522b-9e5c-e3ca0a6e4c79 |  | note | RH must be 0-85%
label | 477e5b91-a44e-56b1-a93e-0a5a045bdc58 |  | note | Screenshot - Temperature and weather forecast
select | f36b68f0-9e84-5967-b1b7-4bed787ce042 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro 800 product TDS
label | 450f73c3-29cb-5d01-ab97-adb53ddafee6 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume.
label | 213013fd-601c-5d2f-ab82-8b67845c6837 |  | note | Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | d161a99f-28b3-58b4-b5dc-9ed68cdf3316 |  | note | Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application - Enviro 800 product TDS
label | ee3305de-cc9c-593d-9caf-99f1fc9333cb |  | note | Enviro 800TC to be applied by roller or brush to finished membrane.
label | 9ea24b53-12fc-514c-88a5-17f7a5b3efea |  | note | Allow coat to sufficiently dry ( 24H) before proceeding to the next coat.
label | d77fb3d7-2fcf-58b5-a1f0-3d4cf446941a |  | note | Records - time stamped photograph
select | 450c39b2-5c3e-5a2f-aa1c-8206bf3fcad6 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first top coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first top coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | SECOND TOP COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro 800 product TDS
label | 5d98f037-c9f8-52fb-bf56-111f42a9bd5d |  | note | Apply within 10-35°C
label | 4fa59f22-cd25-5dac-88c9-c4741c980aef |  | note | RH must be 0-85%
label | 9a114f63-356f-553e-845b-fb51a735178f |  | note | Screenshot - Temperature and weather forecast
select | c5395087-e661-5700-9056-836340d30410 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing - Enviro 800 product TDS
label | 5c1c0e5d-ed3e-5c8e-81dc-1365333cf269 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume.
label | b485c9d9-3477-5830-a7d6-db4beed65d32 |  | note | Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | b4f3156d-3c99-56ea-9b79-b24bc3cf52b4 |  | note | Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application - Enviro 800 product TDS
label | 21ad6b73-7588-5e03-88c9-7d32273b4a8c |  | note | Enviro 800TC to be applied by roller or brush to finished membrane.
label | ab20ac86-0233-5cb3-a257-5a9e9cedfc99 |  | note | Allow coat to sufficiently dry (24H) before proceeding to the next coat.
label | ef2445ef-127d-5b3a-aab8-8a94bbbda3f1 |  | note | Records - time stamped photograph
select | 7c8e9001-89c3-573f-a776-6b1364df38ef |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second top coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second top coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING- EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | aed1cec1-1d7e-5a52-834e-6eb0e2224ba9 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | e22c7f5d-c86e-5245-be51-f095c70f58e1 |  | note | Records - time stamped photograph
select | 555788a2-7196-5520-8d88-1b9c3adf88d5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-sectioned |  |  | checklist | Enviro Systems Checklist - Enviro B-LV+HP1200+900PUR+800TC |  |  |  |  | Yes | Enviro Systems Checklist - Enviro B-LV+HP1200+900PUR+800TC | 697683ad-9b52-4c30-a600-f2c101bf4757
checkpoint-group |  |  | section | Batch Detail Number of Products
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | f2e90e12-74f2-5483-9ed4-cd3048c57f7a |  | note | Record Batch Number
checkpoint-status |  |  | checkpoint | Sika Flex FC/ Enviro Flex FC
label | f26ca467-6341-5bf2-aedb-bef693b02b0e |  | note | Record Batch Number
checkpoint-status |  |  | checkpoint | Enviro HP1200
label | dd0bd381-4103-58eb-a008-a08f18a9ad37 |  | note | Record Batch Number
checkpoint-status |  |  | checkpoint | Enviro 900 PUR
label | 0bebaa64-c43e-5e3d-8b20-a71d58927a43 |  | note | Record Batch Number
checkpoint-status |  |  | checkpoint | Enviro 800TC
label | 4f059535-e843-5860-b32c-2c9872ef4db6 |  | note | Record Batch Number
checkpoint-group |  |  | section | Pre Commencement
checkpoint-status |  |  | checkpoint | Material Management & Storage - Witness Point
label | 4c990b5b-b2b9-5b5f-8679-f3dfc182ff3d |  | note | Store materials in a dry, clean place away from direct sunlight.
label | 245ba9e4-eac7-5b12-9b8f-ef416e5151d2 |  | note | – Record by time stamped photograph.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - Witness Point
label | 122c3138-43ce-5ae1-a974-24faecde0ad5 |  | note | Obtain clearance for work initiation.
label | 502a628c-4e4a-5273-ab62-e03a9eb17bef |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 5a9561b9-9a23-5f7c-a444-4bd7645ddcce |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 61ce50dc-c4a2-5daf-867f-a9d867527fe7 |  | note | – Record by time stamped photograph.
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - Witness Point
label | c59156b0-ce03-5e0a-a998-1851888a67e9 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | 2944537f-53da-5d71-8fb3-65a9a0e45e87 |  | note | – Record by time stamped photograph.
checkpoint-status |  |  | checkpoint | Falls in Substrate - Hold Point
label | 8031fa6b-8f22-5961-87f4-bef450fd2393 |  | note | Builder to confirm compliant falls; minimum 1-100 falls.
holdpoint |  |  | signoff | Foreman to confirm falls - Signature
checkpoint-status |  |  | checkpoint | Cracks in Substrate - Witness Point
label | 39af2c13-47f8-5690-a520-d7cbce2b8e0d |  | note | Ensure no substrate cracks greater than 1.6mm.
label | f8c8c3c7-b549-54d6-9230-518c30fa29cf |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 814a4202-a4ab-5276-a977-4063c5a2964f |  | note | – Record by time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders Pre-commencement Sign Off
holdpoint |  |  | signoff | Witness Point Sign off
checkpoint-group |  |  | section | Substrate Preparation : AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preparation - Witness Point
label | 49024212-ad31-51d4-9db9-045f4701328e |  | note | Ensure Surface is prepared to receive primer application.
label | 85188d19-7063-52fe-a653-5ccf0bd87fa9 |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 0069031a-7320-5896-b4af-169b5e2711ba |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 499fb8a5-b999-5f47-a6c7-016f716246ab |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | a7e49d71-e600-5ec5-be0c-159cc18cb8c3 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 6561ea8d-4117-5ec0-af39-4d94fbc658c3 |  | note | – Record by time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders Substrate Preparation Sign Off
holdpoint |  |  | signoff | Witness Point Sign off
checkpoint-group |  |  | section | Epoxy B-LV - Prime Coat
checkpoint-status |  |  | checkpoint | Moisture Content - Witness Point
label | 9f40879d-a2cc-5bc3-a1b6-55d068fb2f12 |  | note | Check Moisture content of substrate, not to exceed 6% ( Min.1 test per 10m2.)
label | 3b26686e-b90d-5bef-a973-3cbcf482d98b |  | note | – Record with Tramex Moisture Reader
label | 8f1607a0-f30b-5369-b6f8-285649cd77d4 |  | note | – Provide time stamped photograph
checkpoint-status |  |  | checkpoint | Weather/RH - Witness Point
label | 28e6273d-0ee3-5b12-8df9-3e6e65082972 |  | note | Apply within 5-35°C
label | f4cdf996-063e-5e88-923c-4d79527423e0 |  | note | RH must be 0-85%
label | 10bd58d0-09bb-5315-84ad-2e56dc2694c3 |  | note | – Provide screenshot of weather reading.
checkpoint-status |  |  | checkpoint | Product Mixing - Witness Point
label | 7ede3af2-6960-583c-aec5-a7879308ba1a |  | note | Mix Part A (12L) and Part B (6L) separately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | 0ffd91fb-eb2a-50a2-8f46-6df19ccc8dc2 |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | 3da40e1d-cd52-541e-beb5-b28401c16d42 |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Primer Application - Witness Point
label | ac0acda5-5392-5705-ae6c-719e09faef10 |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | f9853ed7-2d08-5abf-b718-687a6e2bdf62 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
label | acf9becc-f2cf-5f22-8066-78ce10ca7768 |  | note | Apply one coat of Enviro Epoxy B to achieve a minimum Dry Film Thickness (DFT) of 75 microns.
label | 1324c451-6240-5a34-a021-f965f631f42b |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 02cf4001-0050-59ab-a4b3-d6a5683e18b5 |  | note | – Record by time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders Prime Coat Sign Off
holdpoint |  |  | signoff | Witness Point Sign off
checkpoint-group |  |  | section | Bond Breaker
checkpoint-status |  |  | checkpoint | Primer Application - Witness Point
label | 9e6af487-0a58-551a-9fbc-55b151654b2a |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 172061d6-6665-5c2c-80e2-e1259c5cda32 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 2567b727-3dc2-559e-b0ac-9020ee861a25 |  | note | Bond breaker to be tack free prior to coating.
label | 8229ff8d-35f8-59b7-9624-759446598a98 |  | note | – Record thickness with a fillet gauge.
label | 625a121a-f7f1-564f-bb29-1eeeaa892153 |  | note | – Provide time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders Bond Breaker Sign Off
holdpoint |  |  | signoff | Witness Point Sign off
checkpoint-group |  |  | section | Enviro HP1200- Base Coat
checkpoint-status |  |  | checkpoint | Weather/RH - Witness Point
label | 945d02da-efb7-5f63-afe2-51a9cdaf59db |  | note | Apply within 5-35°C
label | 9100b031-d85f-5945-a31d-d8652a46c342 |  | note | RH must be 0-85%
label | 9eb345aa-7965-5df1-828e-bfa70a72b077 |  | note | – Provide screenshot of weather reading.
checkpoint-status |  |  | checkpoint | Product mixing - Witness Point
label | e271e34c-0661-5891-813b-360617fea5db |  | note | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
checkpoint-status |  |  | checkpoint | HP1200 Application - Witness Point
label | 7b565402-3adb-549a-8299-f47b77d34bf4 |  | note | HP1200 must be sprayed using high pressure plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing.
label | 18d824dc-5096-5d07-98c1-d7f2f851df2a |  | note | Mix Part B thoroughly with a mechanical power mixer before use.
label | 8e8adab1-bd79-5681-95f7-a8c37b5a722c |  | note | – Provide time stamped photographs.
checkpoint-status |  |  | checkpoint | QA TESTING - Hold Point
label | c76781c0-b01a-56c4-a1a6-f7800821aa6e |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 96e889b6-db22-52b9-85df-253dc23192b4 |  | note | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2)
label | 52372401-6c34-5573-95df-492c3288c013 |  | note | – Conduct Electronic Leak Testing ( ELT) and rectify as required.
label | 53f49db0-0c32-59aa-a23d-25abadfc1b92 |  | note | – Record DFT with Positector.
label | 032a7674-bcf0-5aa9-b53c-d3b1126fa1c5 |  | note | – Provide time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders Base Coat Sign Off
holdpoint |  |  | signoff | Witness point sign off.
checkpoint-group |  |  | section | Enviro 900 PUR- Wear Coat
checkpoint-status |  |  | checkpoint | Weather/RH - Witness Point
label | c31e8dc6-7ea1-5f16-99e4-5282de1793a3 |  | note | Apply within 5-35°C
label | 6678f416-9a50-5171-a74f-ebb29467b652 |  | note | RH must be 0-85%
label | 020623c8-c035-5d13-907b-94ee4d31666d |  | note | – Provide screenshot of weather reading.
checkpoint-status |  |  | checkpoint | Mixing of Product - Witness Point
label | bc496c33-8f59-5dff-9917-0e6b8e64e5c0 |  | note | Enviro 900 has a mix ratio of 2.2:1 (A:B).
label | e0ed4aa3-f0a9-562d-970f-7aa5fbf44dc1 |  | note | Mix Part A and Part B separately, before combining.
label | a861b14b-c839-5d9a-b171-b2e4d3affc88 |  | note | Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
checkpoint-status |  |  | checkpoint | Application - Witness Point
label | 138bebe0-4c9c-5d72-a1bd-a53a1b313d29 |  | note | Enviro 900 to be applied by squeegee, roller or brush to finished membrane.
label | 90751276-979e-5120-8416-ed4b74b15130 |  | note | Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes.
label | 2fa37ed9-0f6a-5520-9523-d5ccd486e9b4 |  | note | – Provide time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders Wear Coat Sign Off
holdpoint |  |  | signoff | Witness point sign off.
checkpoint-group |  |  | section | Enviro 800 TC
checkpoint-status |  |  | checkpoint | Weather/RH - Witness Point
label | 7e67940f-5b93-5f35-b634-8af4fad63a42 |  | note | Apply within 10-35°C
label | 7f6ee8d1-05d2-57db-b1ca-35da93141cff |  | note | RH must be 0-85%
label | 31328c2a-c397-5d42-aa01-cd51fec892c7 |  | note | – Provide screenshot of weather reading.
checkpoint-status |  |  | checkpoint | Mixing of Product - Witness Point
label | 94a34b8c-edce-5ecb-9c38-faf6e48cdd95 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume.
label | e7be3db1-51ef-543e-971d-11cce8492944 |  | note | Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | e8a1198b-c0c0-5623-bab5-99d458a5b207 |  | note | Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application - Witness Point
label | 0dc7709a-e0b7-5115-b8d8-4620cebb3342 |  | note | Enviro 800TC to be applied by roller or brush to finished membrane.
label | 68e1a944-e4d8-53ea-8754-da60f88ccbd1 |  | note | Allow coat to sufficiently dry before proceeding to the next coat.
label | 660a235d-308f-5232-a783-eb805b6fae44 |  | note | – Provide time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders First Coat Sign Off
holdpoint |  |  | signoff | Witness point sign off.
checkpoint-group |  |  | section | Enviro 800 TC - 2nd Coat
checkpoint-status |  |  | checkpoint | Weather/RH - Witness Point
label | 0200521f-3505-5158-af4d-ac2744946848 |  | note | Apply within 10-35°C
label | 16b886b9-4c41-52fb-8bba-98cd8d2cf51c |  | note | RH must be 0-85%
label | 81daba60-a5f2-5682-883d-ee70b7211d87 |  | note | – Provide screenshot of weather reading.
checkpoint-status |  |  | checkpoint | Mixing of Product - Witness Point
label | add0d27f-5910-52b6-baaf-b9cf4e41d45b |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume.
label | f170041f-f99b-5484-a312-ef5e8b1319ff |  | note | Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | ae367d0e-18ce-5273-b973-ec879ab25720 |  | note | Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application - Witness Point
label | 9deb9f86-68ea-538a-97d4-00c8d6fb0d91 |  | note | Enviro 800TC to be applied by roller or brush to finished membrane.
label | a3bc873b-d6d3-5cda-8191-b35327154047 |  | note | Allow coat to sufficiently dry before proceeding to the next coat.
label | 19b2850d-0ca7-5599-bf3b-4ff170c37989 |  | note | – Provide time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders Second Coat Sign Off
holdpoint |  |  | signoff | Witness point sign off.
checkpoint-group |  |  | section | Detailing
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - Witness Point
label | 0bfcb49b-5653-5190-bc2d-2de17696220a |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | 2edb005a-0cbb-52c7-a488-5df650466d3b |  | note | – Provide time stamped photograph.
checkpoint-status |  |  | checkpoint | Builders Detailing Sign Off
holdpoint |  |  | signoff | Witness point sign off.
checklist-flat |  |  | checklist | Enviro Shield / Prime P2 / Epoxy B-LV |  |  |  |  | Yes | Enviro Shield / Prime P2 / Epoxy B-LV | 6a720614-992f-43d2-a87f-8f06de78d07c
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 9164262d-d38e-52f8-98b6-e6a834dd7ece |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Screed (moisture test if required, Enviro Shield is moisture tolerant.)
label | 0c3ce548-5c29-5f63-8b7f-a140a9120a0c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro Shield with a brush or roller.
label | 387a9af1-85a1-508e-9783-8220f568f33b |  | note | Visual
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro Shield with a brush or roller.
label | 38884111-a8fb-5c00-ad5c-976a45403f49 |  | note | Attach photo
checkpoint-status |  |  | checkpoint | Protection board. Install Elmich Versidrain 8 Geo. Applicable to planters only
label | f237a5fe-3677-504d-bba2-42424b70e992 |  | note | Attach photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X + 800TC |  |  |  |  | Yes | Enviro 700X + 800TC | 7465e183-0831-476a-be6b-0de986cff1ee
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 05aade64-061e-59a3-b8b1-2eff05eb2316 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | 433b1232-6967-57a3-8780-e4eb9dbf5e48 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X.
label | 4b28f759-503a-54cc-aaa8-5253c2fb10e3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply primer (Enviro Epoxy B-LV / Enviro Prime P2 / Enviro Shield) using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X.
label | 5aca5a43-364d-5f96-bdd4-f28a98a0fff8 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. Enviro 700X should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT. (2 coats).
label | 5e0d5017-bc35-5a98-b156-c999d9516733 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed Enviro 700X to ensure the membrane is not damaged.
checkpoint-status |  |  | checkpoint | Top Coat. Enviro 800 TC should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat.
label | 9da28fb6-1609-59ea-b378-6159e7615e2c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | 1edc9a1d-369f-56ed-9d9d-7923080d058c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Enviro HP1200 V1.0 |  |  |  |  | Yes | Enviro HP1200 V1.0 | 86f31228-a2bb-4b25-b1ba-b0ce562b638c
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 94725bd3-369e-56d2-a655-0db80384ff9a |  | textbox | ITP No.
text | fd6efd01-9b08-5356-8cdc-9c309d823ad4 |  | textbox | Revision No. & Date
text | e5edf8d5-4fd7-5de3-afe5-f85b4abffa2d |  | textbox | Prepared By
text | 9b204194-b7af-5415-9cfc-670875e1dc90 |  | textbox | Reviewed By
text | b0ef4712-0402-5dc1-bbbe-3b7824ede646 |  | textbox | Approved By
text | dee06efc-c32b-5a67-a253-dca05ada5846 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | 0afb7336-56d8-5029-b900-6bd009129331 |  | note | Records - Time stamped photograph
select | 87cd7e2a-2d7b-5bcd-82c2-f5855219f247 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Sika Flex FC/ Enviro Flex FC
label | 917a4b14-8223-5d54-a673-6397f9cfca98 |  | note | Records - Time stamped photograph
select | 2d0d39a0-1b80-5a54-a37d-1270f303a3ad |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro HP1200
label | 42779e27-ff30-52af-b74b-144a3f7583c1 |  | note | Records - Time stamped photograph
select | d585e112-db0f-5fc8-a971-b281fe57ec01 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 900 PUR
label | 28e49637-e16a-5e8b-9852-924a652d5597 |  | note | Records - Time stamped photograph
select | e24eadbf-3d65-5aec-b0d4-366c78b3da8a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 800TC
label | 0ea196b8-2557-5308-bdec-3c9943dc6a75 |  | note | Records - Time stamped photograph
select | 16d1e4ed-1f36-55dc-bb54-005fbcceaa34 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | a46cf6dc-38a6-5549-90cc-1a75544b282a |  | note | Submit samples for approval as per Specific Material Requirements.
label | dcc9faf8-49ed-54fd-8648-8e1ccf82eef2 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | 44ff0ae7-3ccf-5987-a652-38a225654a58 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 5853ab10-a279-51ee-8697-f4302d3c5029 |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | 334c234f-7033-5a22-bf22-c4e69a32d428 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 71af0db5-c98b-5d0c-bc4a-55c8f5505adc |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 76616a99-a222-5ce4-85f9-d97709b565e4 |  | note | Records - Time stamped photograph
select | 9f98e673-3227-5416-a759-34d64054c135 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 9bb31b46-d07a-559b-b63d-1b172c6c1c9c |  | note | Obtain clearance for work initiation.
label | acc33e65-5944-5d96-9b62-1ce2f63ffa61 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | dfe78e1e-ec9d-5c95-8d2b-fe49ca0406e1 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | f60836ce-7416-5ff5-93cc-3f7e5de1e7cc |  | note | Records - Time stamped photograph
select | ceefd1a0-9d3e-57de-98e5-22a0d1b5772e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 0376d19d-9de3-566d-85c7-b76d54c06c10 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | cebd0837-6ec3-5d39-a548-be035a119527 |  | note | Records - Time stamped photograph
select | eef99008-e794-557b-af54-349849ce403c |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | b27e267f-cd09-5b4e-99f0-4b538c35a9c1 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | b7bed64d-4f0e-522e-bc04-7fe510d19377 |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | 0e825374-f8c1-50ca-a9cc-46bcf2702b77 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 7667afdc-3a3c-5624-9855-f95c8d589f0d |  | note | Records - Time stamped photograph
select | 00db9bbe-8eb8-5161-8c90-e10a356e86f0 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | e2dc1914-8564-5e01-8721-704eb1613a32 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 5795b59e-50c4-5b63-bf9c-123be409ef90 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | f207650e-dd0f-5883-8a1f-d045d3a042ef |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 924ee844-5a3e-5eae-8af5-748b2fc35898 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 29b49db2-29fd-592b-afe2-48435e853bff |  | note | Records - Time stamped photograph
select | 755640c6-7aa6-5ff5-8114-0500eafda702 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | 80f39cd4-5ed2-5496-b170-3ba60f981d82 |  | note | Ensure Surface is prepared to receive primer application.
label | 033ad453-bd67-5fd3-8ae0-3f41c921f46a |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 127e9a07-cb29-5ef9-a68d-65aa3b67c1fc |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 2585d043-63e5-5ab5-a80b-b738bfabaeb2 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | d593f000-af97-5de4-a4ca-2aee1b902df5 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | d4899e80-9e04-5ba3-bb56-7db4c5bb54ee |  | note | Records - Time stamped photograph
select | 3943b6ed-5787-53bd-a914-2eb7aaaaafd3 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | 15135040-f945-5745-80ad-1559c69a03ce |  | note | Ensure Surface is prepared to receive primer application.
label | b0b00f51-3b21-542d-881f-9167ff463098 |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 95504290-8660-59db-a1e5-4490da16f423 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | e262b743-6b78-53c7-b9c6-87caa0886829 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 3171e538-439e-5fe0-aedd-270a07e05e09 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | 94a5d982-4f6d-525f-bd9c-92f5c5ecc73d |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | ee673852-d40a-5160-bc59-b7964ad19005 |  | note | Records - Time stamped photograph
select | 72800a1b-f492-5363-8e3a-53ab2289db76 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 4c69fdaa-44e9-597b-8fa6-f839d93c13e2 |  | note | Apply within 5-35°C
label | 6de3f45f-75d1-5bff-a185-66d2d0d2646e |  | note | RH must be 0-85%
label | f2eabdc3-5266-5c95-87dc-19a7a4166c08 |  | note | Screenshot - Temperature and weather forecast
select | 04f22acb-0c9a-5db8-b4f9-b154653c176e |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | 49283950-4d44-540d-bae8-25b4265a7ac9 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | 74027b4e-abb5-5a1a-beea-8d9f151e1d18 |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | 5a9566fc-de86-508f-868d-d67d3553e26c |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | 57f21608-8daf-50aa-bacf-8caa12edc845 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | 7a08e99e-721d-574b-a185-1f92c5718fac |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 308ad322-cac0-5cc8-b547-37d2b2cef779 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 661a5939-39a9-5c9c-8ecc-706170b92dc7 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 5c91ca7e-48c3-508f-9dcc-c0c3a51e8a98 |  | note | Records - Time stamped photograph
select | 541e973f-4096-57e0-9d42-747637b07803 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | b8b49882-530b-5b34-a3a9-55a4b029df60 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 4463c036-4dd8-506c-830c-e2ee79760a3d |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | cf93cfe7-b847-50b9-b0f5-740d9f6ed773 |  | note | Bond breaker to be tack free prior to coating.
label | 3e0037a5-831c-5ecd-a90e-4989233cf90f |  | note | Records - Time stamped photograph
label | 24f0b347-56ec-5297-a2d0-3aa4015a71a6 |  | note | Records - Thickness with fillet gauge
select | 4aec454b-1acf-5fde-8aa7-676274623f68 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
checkpoint-group |  |  | section | BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - HP!200 Product TDS
label | a92f0824-a589-5106-9d22-a7dd1fd02af2 |  | note | Apply within 5-35°C
label | d70bc5f3-ab3f-5541-bb67-43a0dde264e5 |  | note | RH must be 0-85%
label | 322b4e23-2821-58b6-a3f0-e4643c960bff |  | note | Screenshot - Temperature and weather forecast
select | 11785fb1-ea1d-5208-aeca-350b52903325 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - HP1200 Product TDS
label | ec5f2416-38eb-5b35-abb3-a4efec0457c5 |  | note | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
label | e7301ae5-2382-537d-b880-c5a68741b02f |  | note | Mix Part B thoroughly with a mechanical power mixer before use
select | 84ed08f2-f654-5e31-942f-04203a2e08e1 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- HP1200 Product TDS
label | 34e6a669-93c1-5704-8ee2-46a06df4fea3 |  | note | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing
label | 400b8b66-0de9-51c9-9b82-49a5307d5785 |  | note | Records - time stamped photograph
select | 4faafbd1-68b8-5151-9993-ca67750eda11 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 9190c1a3-e77e-5a81-ae82-133cec13736d |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 57813cf6-9641-5698-a2a0-d8a103b02838 |  | note | Records - time stamped photograph
select | dbbebf5c-2d16-5de5-b4f4-2bb9fa2941f5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | 5818f0c7-a865-55d2-90a3-63088a37cef8 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 9a3d0502-be4c-555d-a704-83c0c7c57d47 |  | note | Records - time stamped photograph
select | 070680fc-3ff4-52cf-9e30-66ff1510e8fe |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | dac36beb-17cc-55dd-b65e-138bad70f3bb |  | note | Conduct Electronic Leak Testing ( ELT) on area membraned
label | 04376728-1da2-5dae-92a2-392b63e75f41 |  | note | Records - time stamped photograph
select | e857169f-c29e-5eb9-872c-e6eb79433cfb |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | HOLDPOINT - Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | HOLD POINT - Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING- EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | 2a1c2edc-c432-5f1f-96c1-3a71bbaa3d48 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | e72ee952-c071-51da-b27c-a39d4f7c5ecf |  | note | Records - time stamped photograph
select | b6659b6c-ccc1-54d2-88cd-ba0c18efdea3 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-flat |  |  | checklist | Envirosystems 200P - Internal Wet Areas |  |  |  |  | Yes | Envirosystems 200P - Internal Wet Areas | 8814a5e8-022b-47dd-a703-c9b885743964
checkpoint-status |  |  | checkpoint | Batch Number
label | 9f069c61-6524-5359-b996-74e3a8f66219 |  | note | Record batch number Min 1 photo
checkpoint-status |  |  | checkpoint | Floor Substrate
label | 18ac8119-47b9-59dd-8860-9ad920701f26 |  | note | Surfaces must be clean, dry and free from all loose particles including dust, laitance, grease, or any foreign matter. All loose particles including dust, laitance, grease and other contaminants such as spray paint, coatings and curing compounds and the like should be removed by grinding or similar. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary. Cracks bigger than 1mm to be reffered to engineers for treatment methodolgy. Min 2 photos
checkpoint-status |  |  | checkpoint | Puddle Flanges
label | d2b1a297-73b5-51ef-98cc-011ee0df213b |  | note | PVC Puddle flanges to be recessed into substrate so that they finish flush with the substrate. Min 2 photos
checkpoint-status |  |  | checkpoint | Wall Substrate
label | 77854394-c29d-5622-acfa-179e5d3a79ac |  | note | FC sheeting to be installed to manufacturers specifications (i.e. maximum 6mm gap at floor / wall junctions) FC sheet and nails to be set with manufacturers base coat. Masonry substrates must be rendered /skimmed. Min 2 photos
checkpoint-status |  |  | checkpoint | SFL
label | c42d82b7-1e27-59be-a221-02ca79f00875 |  | note | Falls in the substrate to drains to prevent ponding water outside of shower (1:100). Falls in the substrate to drains to prevent ponding water inside of shower (1:80). Falls in the substrate to drains to prevent ponding water in a bathroom designed as an unenclosed shower (1:80).
checkpoint-status |  |  | checkpoint | Holdpoint
label | c9432170-5bb8-5475-9668-0d6bf3efc6e3 |  | note | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Moisture Content-Tramex Moisture Reader
label | 12dd2607-73ea-5e20-b34b-805c40a6cff2 |  | note | Enviro Shield -Max 6.9% Enviro Prime WB - Max 4.5% Record and mark reading on tested area ( min 3 tests ) 3 photo of Markings on tested area and Tramex reading.
checkpoint-status |  |  | checkpoint | Primer Application
label | 8983ac41-b814-5ad1-8b3d-955dcb40022d |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base). Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Mix for 5 minutes or until uniform. Allow to stand 5 minutes after mixing and then mix again for a minute. Apply 1 coat of Enviro Shield between temperatures of 5-35C with a brush and roller. Visually check product is cured before proceeding to the next step. Same applies for Enviro Prime WB above. Min 2 photos of primer applied. Min 1 photo of temperature reading prior to application.
checkpoint-status |  |  | checkpoint | Fillet and Bondbreaker
label | ef5ecd1f-6731-56f9-afca-2f23b7c55797 |  | note | Surfaces must be clean and dry. Apply the sealant firmly into the internal corner or joint and tool to the required cove size as per the relevant Australian Standard. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal. Allow to be track free before proceeding with membrane application. Visually check product is cured before proceeding to the next step. Min 2 photos. Min 1 photo with coving testing tool.
checkpoint-status |  |  | checkpoint | Wall Membrane Application
label | 5eb11dfe-9564-5d29-9016-021edcee1f14 |  | note | Enviro 200P Ultra can be applied using a brush or roller in temperatures of 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.6mm. Prefabricated waterproof collars to be installed and incorporated into waterproofing membrane around all plumbing penetrations. Visually check product is cured before proceeding to the next step. Min 2 Photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | Floor Membrane 1st Coat
label | 5cc9b051-c2c6-5a54-a599-b7857a8df1ae |  | note | Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Enviro 200P Ultra can be applied using a brush or roller in temperatures of 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.5mm. Visually check product is cured before proceeding to the next step. Min 2 photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | Floor Membrane 2nd Coat
label | 4c32cf0c-4d98-57d3-ad09-64d5e2883f50 |  | note | Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Enviro 200P Ultra can be applied using a brush (Min 150mm upturns) or roller in temperatures between 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.5mm. Visually check product is cured before proceeding to the next step. Min 2 photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | QA Testing
label | c0454de7-adca-5f9d-9941-21680f9e03f9 |  | note | Thickness testing of application to the recommended DFT to manufacturers instructions( 0.6mm walls 1.0mm floors 3 tests on floor/ 3 tests on walls.) 24 hour Flood testing. 6 photo of markings of testing on susbtrate and Positector reading Min 1 photo of Flood testing
checkpoint-status |  |  | checkpoint | Holdpoint
label | 12d5926e-1b11-54e6-98a5-19b9a7cd946d |  | note | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | Enviro HP1200+900+850TC |  |  |  |  | Yes | Enviro HP1200+900+850TC | 8e47e9be-266a-4197-91db-d0b8a6c37ae7
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | fa75f3d7-7a33-5649-9b46-eccdc88e139c |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | 2fe5199e-0796-5e29-bdb2-b3b732f66448 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 84696d0d-9d86-5ca4-bbb5-d8534458bcb2 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 31118ff4-dbc9-5402-9c01-5c9c11aa5dce |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 0666e7a8-c43f-5c33-8915-c6ab0ed06a6a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | adf76b15-eb4f-54e0-8e8a-13efa4cd23ec |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | 151a4877-e4df-557b-b8e4-b3453ea67e47 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Wear Coat - Mix and Apply Enviro 900 with brush or new roller (spray application optional) Broadcast aggregate uniformly to the wet Enviro 900 within the timeframes specified
label | c0d0dba9-4041-54d0-bfee-ffdc845cadbf |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat Mix and Apply Enviro 850 with brush or new roller (second coat optional pending specification)
label | 589a013f-5e89-52a6-9140-f8e835f0ee82 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro CSH |  |  |  |  | Yes | Enviro CSH | a984781d-000c-4dd1-a452-a250d50e8235
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | ef203c01-8940-544a-8e26-14d9649d91cb |  | note | Specification / Standard: Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate. (moisture test if concrete not fully cured) and prepare surface using a scraper or grinder and vacuum or sweep residual debris.
checkpoint-status |  |  | checkpoint | Check for cracks/defect in concrete.
label | 062cb138-e192-5cfb-ae52-0bedb2e38ae9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Perform mechanical profiling / shot blasting to concrete
label | 56a5635c-18df-5f2b-9673-9634bdbe3601 |  | note | Visual
checkpoint-status |  |  | checkpoint | Spray Enviro CSH concrete surface hardener and moisture barrier, first application
label | 6cba7882-338a-5c0c-887a-6b095dd39d05 |  | note | Visual
checkpoint-status |  |  | checkpoint | Spray Enviro CSH concrete surface hardener and moisture barrier, second application
label | e217aed1-546c-5f13-82a4-28565b9bc660 |  | note | Visual
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
label | 22783937-b7ff-5560-ac28-966f0c18ff8c |  | note | Attach Photo.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Enviro Ultra Tuff V1.0 |  |  |  |  | Yes | Enviro Ultra Tuff V1.0 | ae0a0487-d6a5-4063-94cc-86d9345a56bb
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 0e432987-7a05-5b0e-b046-15244c90a7ba |  | textbox | ITP No.
text | 9db0406a-0288-5653-94af-ad9ce561d2b2 |  | textbox | Revision No. & Date
text | a3a1221c-4d3e-58cd-aaa7-7294a2920410 |  | textbox | Prepared By
text | c6427406-f084-5dc5-9521-a6dbd3ccbe91 |  | textbox | Reviewed By
text | 86d4b25f-3824-5fc3-9d65-c6c9f907e02e |  | textbox | Approved By
text | f4b4f363-0410-5ba7-99e0-317180f7e123 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | e64cff10-5dc7-5585-959d-b9f9f442308b |  | note | Records - Time stamped photograph
select | bd15fe32-9d35-54ba-a234-8a3d0a083743 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro Ultra Tuff
label | bd283232-2937-54e3-94dc-aab211e49450 |  | note | Records - Time stamped photograph
select | c3cc8bb1-621e-5a42-9672-ac75aaebd972 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 188726b7-99ec-5a3d-a6b9-f8eea2107a30 |  | note | Submit samples for approval as per Specific Material Requirements.
label | 844519bd-0c59-55fb-8266-f66d4fe54a04 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | 8d697f6c-c89e-5e93-8b3a-e18cb5be1f1b |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 3b1ba64b-b947-5106-bec3-ba4890d0376e |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | 22326173-5120-5cff-961f-bf1c0d15514a |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 0d17c72a-f5be-5225-8ca7-24817729f059 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 657a9cd9-d30a-5d6e-9040-cdcb3740d3cb |  | note | Records - Time stamped photograph
select | f01dca8a-9538-5eb2-8116-dfd47197cd9b |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | fb7361f0-baf3-588f-92c3-8f76daddbfc3 |  | note | Obtain clearance for work initiation.
label | 14c976cb-7446-5703-abd5-cb654961c1d5 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | a3b3f574-c5d2-5850-b2d2-5a582a64ee4a |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 22f35c1a-2dc3-5c44-92dd-0f1efc155ebb |  | note | Records - Time stamped photograph
select | 5ff16eef-799d-525c-916d-7dbc60560352 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | be04fd09-3ca5-5d7f-8b68-32cbf2787451 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 2cdd03a5-6645-5325-82bf-88111035eae0 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | 187c8105-dc38-5b86-9827-67f50b4e942e |  | note | Ensure no substrate cracks greater than 1.6mm.
label | face0b12-d38a-588f-9863-1ff20690187e |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 2f3d8fbe-2348-57fc-8f1d-4977f3b1d440 |  | note | Records - Time stamped photograph
select | 018dd6f7-fc78-574c-be3a-de4cfe1e582d |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | f73029b7-d7d9-52d4-b718-2080b7068adc |  | note | Ensure Surface is prepared to receive primer application.
label | 8155cb7b-1023-552b-9586-44c6050501e5 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | a0554454-1068-5d6d-a41b-8d5d25d1b002 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 65830d99-860e-5c14-9cd9-8e15d42098f4 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | a667fa36-98e7-5a4b-a088-d3552389f205 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | cc42f9e4-53d0-5e48-bf59-6e5bf6cab88b |  | note | Records - Time stamped photograph
select | f2d86980-7b0f-5085-9adb-32c44d3079b7 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | bbd26e6e-4046-573a-af7e-c388529e373c |  | note | Ensure Surface is prepared to receive primer application.
label | e13b9b9a-3149-50be-9f3c-e35d33fa173b |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 9a7a99bc-7f65-5aff-ba27-f9b9231657f1 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | d5bddf98-5298-575a-8a0a-b11d1272186a |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 74ea621e-27d1-5499-a320-ab4a0a9bc81d |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | d979540a-ace6-566f-84d6-77230418c2ab |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | c4615d40-b6d2-5b65-9a1d-e040b15ad253 |  | note | Records - Time stamped photograph
select | 2b7ede86-3db5-56eb-b5ad-7c02763ba803 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 6b92e4bb-e703-5a1d-a47c-358e664418d5 |  | note | Apply within 5-35°C
label | 3bea77be-5cac-541b-a15d-567839fd9950 |  | note | RH must be 0-85%
label | cd522ab2-d977-5bcd-bffd-ad72ebb6e702 |  | note | Screenshot - Temperature and weather forecast
select | ee755af7-7619-5483-87fb-d978f305a0f4 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | b4121da7-1488-5ea9-841a-b1eb133be2b9 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | 228060fa-d409-54ba-90e9-a6c9fd0cbf9d |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | e2b921f1-905f-5cf1-b3f9-d74b59251d86 |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | 7d903179-7589-5a42-9726-273e5a434f1f |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | a59821f9-948a-50ff-b02c-7675c665d8be |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 51b1db2d-f556-52df-a14b-381de2912efc |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 93443f4b-851d-5213-802e-476a35fcf8b2 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 5677ff60-2b00-56d0-a2ab-af8fc062abc9 |  | note | Records - Time stamped photograph
select | ec86ed42-33a5-549a-9cf0-34520835833e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | EPOXY COVING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Coving - Enviro Epoxy B product data sheet
label | aa80f82d-6ed8-5581-9efa-3136dbb429e3 |  | note | Mix Sand plus Epoxy B according to the works' design specifications to create minimum 75mm coving
label | 50912137-da2a-55ea-8e85-796d981ef31f |  | note | Records - Time stamped photograph
select | 2d3ff96b-7eaf-54e0-801d-4160b0c32d65 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Coving inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman inspection sign off
checkpoint-group |  |  | section | FIRST EPOXY COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Ultra Tuff Product TDS
label | 821356cc-878f-5950-b7e4-fcfb04e1acc8 |  | note | Apply within 5-35°C
label | 5323485f-7475-56dc-ba4c-068f86942a51 |  | note | RH must be 0-85%
label | de6cb11f-50e3-52e8-96e2-dfa4b8a4152d |  | note | Screenshot - Temperature and weather forecast
select | fbf4fb86-e352-5d22-8095-0aa5475d3a1b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Ultra Tuff Product TDS
label | 4cdac9fa-bb63-5d8c-a017-574dd0dfbfd7 |  | note | When using a colour pack add to Part A and mechanically mix until uniform. Add Part B and re-mix until components are uniformly mixed. Colour Packs Rations: 1 pack to make a 8L kit and 2 for the 16L kit.
label | 0cadba3c-f70a-58cf-8e55-6ea1a466567d |  | note | Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for 3mins prior to application.
label | 7698d28c-9814-5ed7-a33a-484ca4fe63db |  | note | Records - Time stamped photograph
select | fa6a4d50-c2e4-51b7-bc46-4c72fa72de94 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- Enviro Ultra Tuff Product TDS
label | 470aa1aa-8af1-516b-af74-422b9055c9f6 |  | note | Enviro Ultra Tuff can be applied by brush or roller to minimum dry film thickness of 250 Microns
label | d9527122-f0be-55b0-9638-afedc6d15285 |  | note | Broadcast selected aggregate and allow to cure for 24 hours prior to second coat
label | b91a6b91-beec-5cf6-8f3b-48eba8a54135 |  | note | Records- wet film thickness reading
label | 7b5d8b21-e5e8-5ac2-9049-942c433c5675 |  | note | Records - time stamped photograph
select | 2ca52918-ce5e-56ff-baf4-807ea6598685 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first epoxy inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first epoxy inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | SECOND EPOXY COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Ultra Tuff Product TDS
label | 99d9566b-ac00-5ec4-be35-37211d68eed0 |  | note | Apply within 5-35°C
label | ea601ac8-ce61-5884-abfd-c032c36f1a8d |  | note | RH must be 0-85%
label | 49fb3e26-8375-5b57-804d-d2e8b52cb1ff |  | note | Screenshot - Temperature and weather forecast
select | ace1fe7c-dde7-57c6-863c-70d12789e780 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Ultra Tuff Product TDS
label | add9c94f-848b-57f8-8b4f-aabd091f118a |  | note | When using a colour pack add to Part A and mechanically mix until uniform. Add Part B and re-mix until components are uniformly mixed. Colour Packs Rations: 1 pack to make a 8L kit and 2 for the 16L kit.
label | 231f6974-1382-523e-bbbf-2a615a4ae780 |  | note | Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for 3mins prior to application.
label | 04185d97-aa5b-5a63-a84b-1e95e0ad50a6 |  | note | Records - Time stamped photograph
select | 46abf0c7-f49c-51a7-bd97-4db6e8cc315b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- Enviro Ultra Tuff Product TDS
label | d3c16b7a-2f41-5273-abdc-5b8d36da1e81 |  | note | Enviro Ultra Tuff can be applied by brush or roller to minimum dry film thickness of 250 Microns
label | cfae4e12-2dbb-57a0-b7b1-e0f0147c9f25 |  | note | Records- wet film thickness reading
label | 03414d9d-1918-5709-918b-ede4647cdc24 |  | note | Records - time stamped photograph
select | a4c4a3eb-3049-5e47-991e-3dbceaec275d |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second epoxy inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second epoxy coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 197191bd-f1c3-5d54-af32-8d7622df8fdd |  | note | Inspect after installation of reinforcement/finishes to check for any damage to coating and rectify as required.
label | f6565312-0f2a-502a-bf10-32acd7ccb05f |  | note | Records - time stamped photograph
select | d96eb5ca-3638-5bd5-b98f-9796b41ed059 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-flat |  |  | checklist | Enviro Flex 2 Part |  |  |  |  | Yes | Enviro Flex 2 Part | b31cfe90-cafd-425b-ad19-21eea711e261
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 8d15868b-f31d-5efc-8bc0-372d475ddd74 |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | f630fd03-9280-588c-9adf-ba9f6e048081 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 2af44354-51e1-5b83-830d-a9cc75265bcb |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | a171eb7f-76e6-5127-866c-09a4a84aade3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 9d30574b-415b-570e-bae3-38006281e792 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Apply Enviro Flex 2 Part using a brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Apply Enviro Flex 2 Part using a brush or roller
checkpoint-status |  |  | checkpoint | Flood Testing (if required)
label | 0ea5ea6b-01d5-55b9-9cc8-0d57c91a98be |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Enviro B-LV+700X |  |  |  |  | Yes | Enviro B-LV+700X | cf1a8acf-ef18-4573-a959-90a106de22c3
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | e2f17ce5-373e-5f6d-b578-5138deae40b6 |  | textbox | ITP No.
text | 71b981a9-a3cb-503a-a851-e1076b1a99c8 |  | textbox | Revision No. & Date
text | a881a32b-8616-5397-9330-f66410fa6f73 |  | textbox | Prepared By
text | 479579c5-3a77-5a1e-8360-60016dc429fa |  | textbox | Reviewed By
text | aca10e0a-9a82-564a-a19d-abddb4c4cf82 |  | textbox | Approved By
text | 853c849b-c1f8-5180-8905-26eb3c8afa5e |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex Pro
label | a9ca7168-8954-582c-91f8-85b9b3b3a3e8 |  | note | Records - Time stamped photograph
select | 1b07a1f8-4f7a-5b92-b28f-3dbbd5fa8eee |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | 9f48ab6f-d0ee-5e63-924c-166f80c9100d |  | note | Records - Time stamped photograph
select | 7b4c224b-3973-5ec5-bd28-f2f83f93b91b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 700X
label | 1d2b1190-7b01-5c48-9bdc-f103c7b7338a |  | note | Records - Time stamped photograph
select | adb66ce0-5cc3-59ff-80b0-9c66a8669652 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 250NS
label | d60b26b1-eba8-5c4f-9834-5945e0b9a9e2 |  | note | Records - Time stamped photograph
select | 23f6705f-1540-5230-93ef-ad2edac0e2c5 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 4d6ac5bb-8360-52db-a000-68913d90365b |  | note | Submit samples for approval as per Specific Material Requirements.
label | 8c504867-4d95-5062-8b20-614b369fae36 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | c401bda4-18fd-50a5-9ac0-1d99c7924190 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 66d2b773-1b62-5ce5-b335-350347a87aaa |  | note | First of type of inspection conducted by builder prior to commencement of works taking place.
label | f4176983-06ba-58dd-b089-a7e0d6560e29 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 58c27aaa-6d91-5222-b2cb-70e26bb132e0 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | cf4d8106-645d-5dfd-b4f9-0fa8a06e24b5 |  | note | Records - Time stamped photograph
select | b0b53783-5454-5b95-8c54-8bb96ff3efce |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | d3778849-ca69-5767-821d-3fa6077b6617 |  | note | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
label | c1b99446-2172-5171-be79-e91a80996b76 |  | note | Records - Time stamped photograph
select | a664831b-9a00-5f48-a3cd-2a225bbe9f24 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 1c2fb462-ee2d-5f47-a366-3c2dae608285 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | 1f467c8c-d965-5156-ad51-09c646bb2d2e |  | note | Records - Time stamped photograph
select | 8e0a51a9-df5a-54e9-a3a8-e064f66f74a9 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | 3048f41c-3fca-58f8-bd24-5bd59f890d65 |  | note | FC sheeting to have max 6mm gap at floor/wall junction. Sheets to be set with manufacturers base coat, including all nails, penetrations and corners. Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | 30402f74-0813-5d6e-8cbf-62cee5a1ce09 |  | note | Records - Time stamped photograph
select | 1977e6f5-3e24-5ea7-aea5-165fd61ab0e0 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | 8b835dad-4f2a-532e-a020-94d43193231a |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | 171514a2-c411-5d01-b6cd-cfe9160e0d1d |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | c710dc50-1159-5228-a7f2-ca3165cc4584 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | f4a3aa91-fcf3-5cf3-8d20-cd164640b224 |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | c9c26c43-4c67-508c-a3fb-ef68abfbf617 |  | note | Records - Time stamped photograph
select | 90ff455e-c244-5fc8-a53d-60876e020685 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPARATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preparation - AS 4654.2-2012
label | 8a89569a-1ba2-54d0-a99c-a612f1e887d0 |  | note | Ensure Surface is prepared to receive primer application. Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | b490704f-60f2-5945-8309-a4e55e71e492 |  | note | Records - Time stamped photograph
select | 84b669e7-a4df-51e5-9d00-ead53e449d58 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preparation inspection review
label | 266867b5-e944-5146-8333-6e5a6adca270 |  | note | Ensure Surface is prepared to receive primer application. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | 08b3a0e9-4d64-5019-be6f-5bd57c64bcb7 |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | 304a9c34-c101-507a-99d3-2f980e2806c0 |  | note | Records - Time stamped photograph
select | 7c55917e-7e60-5810-999d-da45ab756ffd |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | aba13571-4882-5c8c-a39a-c2a2e0c0bb54 |  | note | Apply within 5-35°C RH must be 0-85%
label | fe4ce5a2-c8a6-57eb-af0d-0f1147156a41 |  | note | Screenshot - Temperature and weather forecast
select | 073f281c-9b1a-5715-b2ad-97f392487dc0 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | 334429a3-ace3-5531-9733-60263debcc9b |  | note | Mix Part A (12L) and Part B (6L) separately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | 98e4605a-6cc1-54ca-acce-781f66bbce18 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | 787053b7-162a-5845-a320-0ddeba010b1b |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 270de5e5-31b7-5f5f-803e-ed87f21c5bf7 |  | note | Records - Time stamped photograph
select | 9cbc7d5c-ed00-5672-9e49-acbce0ba6a21 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER - EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | b0a79035-ae9c-599f-95e0-bbfa87480911 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Bond breaker to be tack free prior to coating.
label | 4e63ec6b-7fe1-5719-9995-1a48738b3584 |  | note | Records - Time stamped photograph
label | 473b5a1c-5c28-5d51-9930-391ab75fa62b |  | note | Records - Thickness with fillet gauge
select | 67a67338-7c6a-5af1-ac16-e5b570dc412e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | 9e823208-a2c8-5e20-a400-6ca7496ab965 |  | note | Apply within 5-35°C RH must be 0-85%
label | 9c72265f-53da-52ba-83a6-d6335f0d5514 |  | note | Screenshot - Temperature and weather forecast
select | 6de45fd9-d974-53bc-b441-1575aa903acd |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 8f490dc4-6d40-5b99-8e60-09c6f1d12585 |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 7976a2ff-bafe-5e94-b4b6-695ae90ea3e5 |  | note | Records - Time stamped photograph
select | 4b62392d-2aca-59b1-bad0-7d5cc5ab0cc5 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | 627ad14d-88c4-5055-a197-b07f47b9ccfc |  | note | • 700X to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | 2773edf0-8421-5b4f-9643-7add684d8def |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | 85eb0971-10ca-5fe9-abc6-08899fcee7cc |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 8eaff8d2-affe-542a-bdd6-7fde11f30f4f |  | note | Records - time stamped photograph
select | a6c00395-1336-5065-bdee-8092e0b12384 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | ENVIRO 700X - SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | 05c3cb60-963d-565b-934c-da8121733736 |  | note | Apply within 5-35°C RH must be 0-85%
label | 66cfc7f6-7f03-598e-8c9a-92ec5d3d763f |  | note | Screenshot - Temperature and weather forecast
select | 013600df-4aa1-529a-83e8-60701f0a54bf |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 4fbb9d25-2021-5a5a-beea-1bdbc1a2f18d |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 0190e8e2-08af-5a75-8698-1d66cc6ccb54 |  | note | Records - Time stamped photograph
select | f32ef58e-88c4-525f-9f02-0d4999237240 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | 46f4eb23-b3c9-59f6-bcbe-7477a7a47a82 |  | note | • 700X to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | 5eb2fa5e-faf1-52a3-afcd-970eefb99f4f |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | 2529a416-9956-5e2d-8507-62678650762c |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 1e09b061-0aae-5ebe-bbc2-2a1f2e4a1ee4 |  | note | Records - time stamped photograph
select | 245f0bf0-d448-5608-a5f7-69826492c0ac |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor Second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 0e072034-edd8-5898-8d98-f09cf288745a |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 200884c2-200f-5964-8366-f8ca71f1fb71 |  | note | Records - time stamped photograph
select | 9557887d-cca7-5238-9b95-ae0074b40776 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | 4d9d4ce5-23de-52f0-8eb0-6f676e700227 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 9cc1d2a8-1f04-5f45-b085-078258081126 |  | note | Records - time stamped photograph
select | ba47e571-0652-5020-a67c-09a6981b50dd |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | 9d7d9e2d-baee-5f51-a3e6-5d4a6224a624 |  | note | Conduct Electronic Leak Testing ( ELT) on area membraned
label | 6d9a19cd-d060-5ad7-b421-2742d663a008 |  | note | Records - time stamped photograph
select | 072d39cd-d8cc-5554-b2c6-9d277b89da79 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | 988f9f36-5ef9-52b3-8ef6-be59cabf66c8 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | bccfc498-b104-5007-8c46-dc91edfac53a |  | note | Records - time stamped photograph
select | 432fb273-2337-5373-ab69-e83be6eac9f5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-flat |  |  | checklist | Enviro 700X + 250NS |  |  |  |  | Yes | Enviro 700X + 250NS | cf686ef7-3512-4068-b2ad-62cbecd68641
checkpoint-status |  |  | checkpoint | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint-status |  |  | checkpoint | Batch Number
label | 5647d21c-8882-5435-b6e1-25e4e2e953bc |  | note | Record batch number
checkpoint-status |  |  | checkpoint | Substrate crack and falls inspection
label | 64d5aa11-a9dc-5cfb-9a92-262bd787b922 |  | note | Obtain clearance for work to commence. Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. for non metal surfaces: ICRI CSP-4 to CSP-6 for metal surfaces: ICRI CSP-1 to CSP-2.
checkpoint-status |  |  | checkpoint | Substrate crack and falls inspection
label | f3cae420-d405-5dbc-856a-7898d106b5fe |  | note | Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.Live cracks to be referred to engineers for treatment methodology. Builder to approve falls on substrate(Min 1:100) prior to application of membrane.
checkpoint-status |  |  | checkpoint | Moisture Content
label | 59590a22-9d09-5c49-a13c-8dc45a59db4e |  | note | Note. min. 3 tests per 15m2 Enviro Epoxy B-LV up to 6.9% Enviro Prime P2 up to 5%
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Ambient temperature and RH
label | ccc5c49d-074f-5a81-afba-98e78cf2bdf7 |  | note | Reading twice a day- every 4 hours Mirvac to confirm temperature between the ranges of 5-35 degrees celsius prior to application of membrane. RH must be greater than 50%
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Mechanical Mixing
label | 736cfc08-9290-547d-9a79-60578a2b3fdb |  | note | If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint-status |  |  | checkpoint | Applying primer
label | d9ef6538-662f-57cb-b421-bad2cd5a5bbd |  | note | Using a brush or roller apply the chosen primer. Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it. Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint-status |  |  | checkpoint | Seal/apply bondbreaker at junctions hob/floor
label | ed0f9a51-db0c-5475-8194-25ef502babfd |  | note | Apply Enviro Flex Pro to form smooth 15mm flexible cove to all internal corners, penetrations and joints.
checkpoint-status |  |  | checkpoint | Application of Enviro-700X
label | 4da1cc15-257b-5c6f-80ee-2dbd7b5181d4 |  | note | Mix Bucket at low speed( 400RPM) until thoroughly mixed. Apply two coats of 700X. Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint-status |  |  | checkpoint | QA Testing
label | b529af9d-fa4d-5ffa-b2e0-726b7e9ade2c |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. 5 tests per 15m2 Holiday/ spark testing of area.
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Application of 250N-S Top Coat
label | 8f2be010-5e15-58b2-8cbb-0c3bae19002f |  | note | Mix Bucket at low speed( 400RPM) until thoroughly mixed. Apply 1 coats of 250N-S Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint-status |  |  | checkpoint | Protection of membrane edge
label | 9991ae75-8701-5965-996e-e76b66651c66 |  | note | Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
holdpoint |  |  | signoff | Completion of Work Element
checklist-flat |  |  | checklist | Enviro HP1600 |  |  |  |  | Yes | Enviro HP1600 | d5b9c9d2-54ec-4c13-80cf-c6bbbaafd0ca
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 98325ff4-0ca8-5fec-9bb8-c609bc685700 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 19e1d874-0290-5497-993d-cacef013458c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 723a8146-b54d-587f-b2e3-c8c6266784a0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 2b0104d7-7ebb-55e8-8f8f-409816643ed5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 62fbd0f9-a3ff-5fdc-bd19-6b3ba787fe72 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1600 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | cb29721a-c50e-56e3-a19f-c3b032fcf48e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Enviro 700X + 250NS 1.0 |  |  |  |  | Yes | Enviro 700X + 250NS 1.0 | de4bd4da-f648-4309-a289-65b9de4104dd
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | e3007d7f-101f-545c-9277-366c5d14b44a |  | textbox | ITP No.
text | 060595e3-f92d-518c-8ceb-994ea7f24d38 |  | textbox | Revision No. & Date
text | a47c53c1-28fc-559c-ba94-c157ff73a35f |  | textbox | Prepared By
text | 5f059ab4-9a09-5541-b103-3aec04ea7677 |  | textbox | Reviewed By
text | 60866230-8659-59d7-b2f5-72d0daf81a95 |  | textbox | Approved By
text | e6902c0c-6694-5bcb-bf39-85320fc371a0 |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex Pro
label | e293524a-089b-5cb6-817f-089ee05f1320 |  | note | Records - Time stamped photograph
select | 70bbcaa5-5620-5a70-b58c-6aa083b6b18a |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro B-LV
label | eee8bf13-701c-55f7-bf37-1c2cb3d1ccba |  | note | Records - Time stamped photograph
select | 6b798daa-2b41-5e4b-a446-95ad76b32e9f |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 700X
label | 0d99b989-2829-53c9-8e4f-42f51c9e5064 |  | note | Records - Time stamped photograph
select | a34fab65-fb38-50d0-a261-752765736af7 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro 250NS
label | ba6a458a-d50a-542e-8f67-2f38bf60859b |  | note | Records - Time stamped photograph
select | 95870546-913e-5b5d-aa6e-9247d684c4a9 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 3ddabded-427b-5c94-b938-7a6fd80872f4 |  | note | Submit samples for approval as per Specific Material Requirements.
label | 55cf6181-1300-513a-94ed-3fe311c1c756 |  | note | Records - Subcontractor Contracts Admin Confirmation
label | 286a86db-bebe-529b-84e1-d52d87e85b99 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | 5c652d13-80f2-52ec-9527-db0b1e6b666d |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | 8cc6ae76-8412-5c80-b62c-0c78669ce45f |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 229b1f2a-7e9f-50c4-98bc-32defdfebb04 |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | 843fb8ed-e209-5542-9d5c-214eea9726a0 |  | note | Records - Time stamped photograph
select | b3d561dc-479c-53fa-a7e5-8798f2c63393 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | 8ef9e2de-5f75-554e-a4e2-fd54cbcab08e |  | note | Obtain clearance for work initiation.
label | eb5bfb73-ce69-5a02-904d-62c89ac6aa5f |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 5e9d9ab2-2e96-598e-af55-f9bb10a516ac |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | 78b963da-415d-5fdd-b313-9ec312a5d570 |  | note | Records - Time stamped photograph
select | dbdbd997-0f52-5c28-8aa6-b5f8b76544d7 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | 7c9760f3-ab0a-572d-bf07-d9d3606c1a8f |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | 60bd819c-2396-5a92-bde4-bb05c8632c9f |  | note | Records - Time stamped photograph
select | 68e814e0-3b56-54c2-a26b-ff7a6872212f |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | b8eb1206-3533-5fd9-823d-d387dbf5ab01 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | 078b7911-7727-5865-bb5e-d22d9c77621a |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | 2a75098e-e595-5f2c-8753-d9343f9b98e3 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | cb7152c8-df6d-59df-a30e-8ff0b0117266 |  | note | Records - Time stamped photograph
select | 41352753-d749-598a-995f-a9e5960376bf |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | 58e323be-f347-57e1-b720-97c1bb0b9dd6 |  | note | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
label | b8571748-1e48-5ea0-a3fc-134a15035869 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | a0909787-4878-50a9-86f5-82a28c0a13ad |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 86f60568-c137-57fa-a802-42c000b2461b |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | a7e95e82-af76-563e-9445-6f82932bd5d4 |  | note | Records - Time stamped photograph
select | d75559fd-e073-51a5-a96e-96c6b7103aaf |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | f5cfa46d-cc2d-580c-8375-fae63eaeb587 |  | note | Ensure Surface is prepared to receive primer application.
label | 35d684e8-d9fb-5cb1-99a0-e50ff3927166 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 2ab97271-3960-5472-a55f-83c2d312af84 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 6959092b-cc90-5749-a2e8-d9792e5f9c75 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 2cc7ed35-a83b-5396-956a-1d8420d05a9c |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 5e9a5f4e-d205-5517-b6fd-f5404e24b55f |  | note | Records - Time stamped photograph
select | d7b6f59f-55fc-5ea7-92aa-8cda671913ba |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
label | db170fc3-351e-5d51-9099-2739e096cafe |  | note | Ensure Surface is prepared to receive primer application.
label | 2bac230f-2f02-52be-8162-f3c63852ca82 |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | a1b6f6cf-2b27-5eb4-ac9a-ba5436293567 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | fb7042c0-3374-57a0-a918-61066a97be08 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | af5f7399-e2f4-53e0-a360-b7d81301b66a |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | PRIME COAT- EACH LOCATION
checkpoint-status |  |  | checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | 954119a9-9aa3-5f5d-8d85-a02b19715eba |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | 00413e37-39d4-59c8-a40a-4cdb1da384f9 |  | note | Records - Time stamped photograph
select | 6baceca7-2336-5407-93f3-ee6c7f0b83f4 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | 85c55890-e792-5de0-bd69-847ab0ca0cfa |  | note | Apply within 5-35°C
label | 5c276fed-ed32-574a-a847-bcd07ecf3d15 |  | note | RH must be 0-85%
label | 8b9a88a2-077a-5dd6-9d6f-afcaddc0f355 |  | note | Screenshot - Temperature and weather forecast
select | 01f7ea4a-5bcb-522d-a5c1-e080b6ae0947 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | 59d245d9-f9d3-5683-b764-02f5083aaed7 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | c46fe92f-9ca8-5685-94ec-46186e80d929 |  | note | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | ab7949d5-ee6a-5366-a069-dd9cfa65267e |  | note | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | ea7b9c52-36cb-5b5f-b75f-bb48e8373aef |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | ea883414-c549-55ba-96e3-415d1fe66a83 |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | 143aaf61-9d1e-5ce6-8daf-0fad40b6ae89 |  | note | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | 6e2636df-16a7-5d53-8b1c-a40f8be20af7 |  | note | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | 0bc94d28-6178-5f61-ab53-2a4f4577d054 |  | note | Records - Time stamped photograph
select | 8f244b20-e137-5fa3-88e4-f2e4b597bd63 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Priming Inspection Review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | BOND BREAKER- EACH LOCATION
checkpoint-status |  |  | checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | d7239a6f-144a-5d06-afb2-14669b3972e3 |  | note | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 2bfa7dd9-8750-59d9-b784-eab92bc70453 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 5b2806d7-2986-5fed-b2dd-fc1d3cdcf422 |  | note | Bond breaker to be tack free prior to coating.
label | 6f291ebe-87d2-5861-9d50-a57d7e0d6fd2 |  | note | Records - Time stamped photograph
label | 0ed24b45-eb3b-5cff-b7b6-734de74ff02d |  | note | Records - Thickness with fillet gauge
select | 933219fc-e461-5d26-80e0-75ae75447ed0 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman bond breaker inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman inspection sign off
checkpoint-group |  |  | section | FIRST BASE COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | 4fce58a4-85bb-55ab-9168-deb449994032 |  | note | Apply within 5-35°C
label | 2094bc88-7675-5cd7-ac12-368d278fbebd |  | note | RH must be 0-85%
label | 3a10c03b-0e26-50de-a8af-eddbd912cb61 |  | note | Screenshot - Temperature and weather forecast
select | 9551c6c7-c1a3-5373-b753-56c8b145a179 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 5e5d1c6b-9c4c-52a0-8152-b14a3e1f5d8e |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | a36a2a76-614d-5705-9550-2ee482c4092c |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | ae598013-766c-5de3-bbe3-bf661019f486 |  | note | • 700X to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | d398fe3b-3210-5e38-8b0c-f317dab5a3d7 |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | d267e1a8-33e1-59ad-930a-f088cce4fb2a |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | 3d3bc4dc-0c43-5a35-9bbd-d9c8afe08076 |  | note | Records - time stamped photograph
select | 6d5f98a6-5419-5288-8ecc-d94e0ea3cf13 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | ENVIRO 700X - SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH - 700X Product TDS
label | 0ff77458-408c-5d8e-8b8d-44f96162ec47 |  | note | Apply within 5-35°C
label | a9b6a5ab-a129-5b69-b2b3-fc93f218d66a |  | note | RH must be 0-85%
label | 28fbaa2a-f0ce-56a9-9782-a34948912587 |  | note | Screenshot - Temperature and weather forecast
select | 1c220c83-9554-5a7b-8535-4cc62d159400 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Product Mixing - 700X Product TDS
label | 1a58fd5f-f488-5165-ba27-14f762140383 |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | 1b5663f4-1074-56ca-ac00-772bb6867dff |  | note | Records - Time stamped photograph
select | 8815edaf-45ec-5ee9-96a4-fb654fca26b5 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Application- 700X Product TDS
label | 2f7f13f2-d568-5786-9054-effcc27be7e3 |  | note | • 700X to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | 545cf603-8532-55ab-abea-a7f00fe69976 |  | note | Minimum application requirements set forth relevant Australian Standards to be followed
label | ff27f98e-f374-59f5-b1b4-3eab124991a9 |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | d62036bb-bff5-5fea-8cfa-64a32885d947 |  | note | Records - time stamped photograph
select | 307712fb-4669-5e8b-b26c-c1543fa93e5b |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor Second base coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Second base coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | QA TESTING - EACH LOCATION
checkpoint-status |  |  | checkpoint | Inspection
label | 664a8917-342d-5501-ae83-c57187f4f003 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | f21eaf99-4adf-5880-aeba-be5b4ac7ee68 |  | note | Records - time stamped photograph
select | ab4b0373-a005-528b-87bd-afca87bf23b9 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Thickness Testing - Delfasco Positector
label | c07944d1-c073-52b0-ae44-45975dec2d94 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 1a62b0c5-d482-5f51-828c-630497d1bb4c |  | note | Records - time stamped photograph
select | cffd0697-d0f4-5050-9bc2-220cc488e034 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | ELT Testing - Delfasco Holiday Tester
label | f8489c09-1293-5d5a-8d3a-8da42b3eac82 |  | note | Conduct Electronic Leak Testing (ELT) on area membraned
label | cab29b5e-e7ca-5688-80ff-b67c87bbb122 |  | note | Records - time stamped photograph
select | eec87432-bf68-5f7a-a4a0-ee7658981c5c |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman QA inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | DETAILING- EACH LOCATION
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing - AS 4654.2
label | a03d6d1e-cedf-5986-9563-bf69968ab52d |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | c327a573-fe73-5f60-b47d-604e8e267ce3 |  | note | Records - time stamped photograph
select | 4bd15d9b-106e-5a5b-b070-850b5bb4f168 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman Detailing inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | FIRST TOP COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 250NS PRODUCT TDS
label | 22a0444f-aa62-5578-969a-fabc66ecc614 |  | note | Apply within 5-35°C
label | 90361f81-7e08-50fb-9428-11e5332267a3 |  | note | RH must be 35-85%
label | 92ad9857-6bc4-555c-935c-0340b05a751e |  | note | Screenshot - Temperature and weather forecast
select | f3f989b4-e2c7-5570-a82f-c5c39215dfd7 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing- 250NS PRODUCT TDS
label | c4269b44-5730-5fbb-abe6-d5e7258cc015 |  | note | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
select | 15b3db66-61b5-56cb-a6e6-af2ab581f955 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | APPLICATION - 250NS PRODUCT TDS
label | cb220963-5c6a-5eba-be5f-3daebbeb39ff |  | note | • 250NS to be applied using roller and brush.
label | 6f357246-b4b2-5aeb-93fd-2aae623698ca |  | note | • Ensure Product is cured for 24 hours prior to second coat.
label | 5a5857e1-d69c-562e-9b28-07d824c48b55 |  | note | Records - time stamped photograph
select | 5c5175d0-48e6-592a-995e-e12f3e8d1d08 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first top coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first top coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | SECOND TOP COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Weather/RH - 250NS PRODUCT TDS
label | 64653848-a28f-5f7c-a7e2-2515e551f102 |  | note | Apply within 5-35°C
label | 9603e68c-9d4e-5b5b-9b3e-9fdfe8137d90 |  | note | RH must be 35-85%
label | 599aeeda-90ad-5043-af4f-bfb2faac0179 |  | note | Screenshot - Temperature and weather forecast
select | 90745838-7e1b-542f-a156-eb54bbc4745f |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Mixing- 250NS PRODUCT TDS
label | 57d0ce18-9c74-5ddf-a065-e462424d0b2e |  | note | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
select | 083c06f0-8a36-533e-9c38-e031af2b0ceb |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | APPLICATION - 250NS PRODUCT TDS
label | 63daab2b-d288-578d-9f05-66ccef517e31 |  | note | • 250NS to be applied using roller and brush.
label | 48e3904c-5716-5c0e-b993-8b878beb355e |  | note | • Ensure Product is cured for 24 hours prior to second coat.
label | 24c3f504-5445-5523-9ea4-6806f6514a20 |  | note | Records - time stamped photograph
select | 7d2e196b-2fbc-5053-bd36-3236f8b17ad0 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second top coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-sectioned |  |  | checklist | Sealer V1.0 |  |  |  |  | Yes | Sealer V1.0 | e090525f-618b-4ea6-98a1-d057baed003a
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Attach any relevant documents or photos
text | 9a9f8d53-73c4-508b-8f2a-f1e8b281a41b |  | textbox | ITP No.
text | 054ed12e-91a0-5444-8081-c234431c6520 |  | textbox | Revision No. & Date
text | 817d8986-c5a4-58d7-8ac9-dcea522221d6 |  | textbox | Prepared By
text | fed66dab-f5fa-5738-af46-7321e8b9ce9d |  | textbox | Reviewed By
text | b5acea57-7930-5bde-9c65-b597eec7140a |  | textbox | Approved By
text | abc369d6-cada-5cf6-bb29-e5b5d6242f9c |  | textbox | CIDD Alerts
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
checkpoint-status |  |  | checkpoint | Enviro Seal WB
label | 6a79fe94-0442-5750-a0be-5b8a8431582a |  | note | Records - Time stamped photograph
select | 0fbde961-9f60-558f-93c7-e863dacad104 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Enviro CSH
label | 2e088cb7-bafe-51df-88ed-64406c97e400 |  | note | Records - Time stamped photograph
select | f63ee8a1-d291-58ab-8f40-d46c5ef13850 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Site engineer/foreman batch inspection review
holdpoint |  |  | signoff | site engineer/foreman sign off
checkpoint-group |  |  | section | PRE COMMENCEMENT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Samples Submitted
label | 8a6edd7b-f5fa-529c-8403-0adbcfd78c35 |  | note | Submit samples for approval as per Specific Material Requirements.
label | b0c920f0-b09e-5b11-ad5b-ce6abe57c0d1 |  | note | Sample Approval Ref.
holdpoint |  |  | signoff | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
checkpoint-status |  |  | checkpoint | First Of Type Inspection
label | e44b1cac-6615-55dc-8207-52574f2930db |  | note | First of type of inspection conducted by builder prior to commencment of works taking place.
label | c01460d5-5b1b-54d6-a494-2cb5854130a5 |  | note | Records - Site Engineer/ Foreman Confirmation
holdpoint |  |  | signoff | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
checkpoint-status |  |  | checkpoint | Material Management & Storage - Envirosystems TDS
label | 0fa92cbe-b9d0-5c5e-b739-2d014d243a2f |  | note | Store materials in a dry, clean place away from direct sunlight as per TDS
label | c659018f-7729-5ed5-9bf5-de086bca7a2d |  | note | Records - Time stamped photograph
select | fc0e316a-b4c0-552b-81f7-978116b343af |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | edcdb43f-e8e9-54c2-b0f4-903431ad0d46 |  | note | Obtain clearance for work initiation.
label | 6724bea6-480d-51ad-a91f-a333b00c1314 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | ab336e77-fc6d-514a-a4ed-9dce2d77f5bd |  | note | Patching products must be fully cured as per PDS before applying the membrane.
label | d9202f12-5876-5a2c-ad55-654a512a1a79 |  | note | Records - Time stamped photograph
select | e0d96745-b9bf-53a5-ab4a-0e688f933947 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Cracks in Substrate - AS2870 Table 2.10
label | 47da9490-4b60-5fa4-9b7c-02e86994a1fe |  | note | Ensure no substrate cracks greater than 1.6mm.
label | 6a1bf96e-efff-534c-9728-60998836958c |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | 75447aa9-da3d-5348-b05a-a01673029227 |  | note | Records - Time stamped photograph
select | f4020fb2-af60-5619-b537-22aad3d62a6e |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman pre commencement inspection review
holdpoint |  |  | signoff | Site engineer/ foreman inspection - sign off
checkpoint-group |  |  | section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint-status |  |  | checkpoint | Substrate Preperation - AS 4654.2-2012
label | df0e0dd8-4946-5b3b-8852-c6f4366cdbda |  | note | Ensure Surface is prepared to receive primer application.
label | 66f5e7b4-4b2f-5df1-8469-0d66751e2a51 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 399876a6-f24e-5b49-9c3e-9f751c142e04 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 4d594018-8f55-56b4-b030-31407e7805df |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 6da8a6c1-b632-5518-a9a4-40423c426dae |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | 78339314-5df1-59f2-8d46-b331917f7aa6 |  | note | Records - Time stamped photograph
select | 351ee60f-8fc1-5bf9-90ef-93c281dc8ec5 |  | dropdown | Inspection | Surveillance point, Witness point
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site engineer/foreman substrate preperation inspection review
holdpoint |  |  | signoff | Site Engineer/Foreman Inspection sign off
checkpoint-group |  |  | section | FIRST SEALER COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Application
label | 98f0d9fa-05a9-5491-a3a2-b68338d7599d |  | note | Spray or roll concrete Sealer on substrate
label | acde0429-5f91-5b24-9956-fadd33bfc90e |  | note | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | b1d20ebc-83a4-51c7-9113-21f764ed400f |  | note | Records - time stamped photograph
select | adf80c57-1dd5-5c77-87dc-4da6be2e10a4 |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor first Sealer coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman first sealer coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checkpoint-group |  |  | section | SECOND SEALER COAT - EACH LOCATION
checkpoint-status |  |  | checkpoint | Application
label | 54d77952-20bc-5927-914c-dc525854f80a |  | note | Spray or roll concrete Sealer on substrate
label | eef49155-c39a-588c-9ba1-eed2df43cdac |  | note | Records - time stamped photograph
select | a99bd96a-d2d2-5dc2-b908-2cba7621a15d |  | dropdown | Inspection | Surveillance point, Witness point
checkpoint-status |  |  | checkpoint | Subcontractor second Sealer coat inspection review
holdpoint |  |  | signoff | Subcontractor inspection sign off
checkpoint-status |  |  | checkpoint | Site Engineer/foreman second sealer coat inspection review
holdpoint |  |  | signoff | Site Engineer/foreman inspection sign off
checklist-flat |  |  | checklist | Enviro P2 + HP1200 |  |  |  |  | Yes | Enviro P2 + HP1200 | ef5ee10e-b1bc-46b3-b90f-8bfdba33de6a
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | bd76f65e-1cf3-55fa-ac87-e116894a189b |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | fff0b211-e332-5a9c-81a5-e9edf3a3f271 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X
label | 50074435-fe3d-56b8-a165-26a44b3c81ca |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply P2 using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X
label | 1371ee11-0768-52d7-b33d-5439938dacc6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. HP1200 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application
label | 7ee72644-9dda-5ad3-8089-7ddae4d12aa0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed waterproofing system to ensure the membrane is not damaged
checkpoint-status |  |  | checkpoint | Top Coat. should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat
label | 6e00f212-fdb6-5a7b-b144-be0dcf615d13 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test
label | 268d572b-df5a-54d5-8695-7fca8e1a29f5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X + 200P |  |  |  |  | Yes | Enviro 700X + 200P | fe1316a2-8167-4840-b564-d6cca99e716a
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 99f53c71-c6bc-5256-8310-7dd33e33295c |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | c7e35c37-1d32-53e9-a74a-0649a1f0b6f5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 49e8c85d-d989-58c9-955b-cc07d7d980c0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer (Enviro Shield/Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | cc2940ac-eb26-5ab7-a900-0036c66b25c3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking. Apply Enviro Flex FC junction fillets (where applicable)
label | d6c67b46-4d34-5a4a-8cc7-a1882b5ec965 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. Mix Enviro 700X thoroughly using mechanical mixer. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT.
label | 34c7be94-32ec-5972-a361-fa74fcae153e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Flood test when applicable.
label | 9cc1c40e-6679-5299-aae7-4e37d951e10b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder.
checkpoint-status |  |  | checkpoint | Check Screed (moisture test if required).
checkpoint-status |  |  | checkpoint | Apply primer (Enviro Shield/Enviro Shield or Prime WB by brush/roller
label | 10c5515c-006d-5687-aa7f-e887edf66193 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro 200P Ultra with a brush or roller.
label | 1e29dac7-ec62-5c4a-b9b3-dd4dabaf6631 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro 200P Ultra with a brush or roller. Achieve 0.8mm WFT and 1.0mm DFT.
label | 647d42ef-318e-59c7-bb90-a73db99f5bf8 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF