## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-BRUNT-Subgrade Preparation-Dam Backfill
ITP Description: |  | BRUNT-Subgrade Preparation-Dam Backfill
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2023-02-28
ITP created by: |  | Jason Lee
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Road Project Only
Inspection & Test Plan - Subgrade Preparation
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2023-02-28
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 204 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 173 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Non Dependent | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
3 | Preliminaries - Procedures & Documentation
3.1 | Non Dependent | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
4 | Pre-construction Activities
4.1 | Survey Set-Out | IFC Drawings | The Area of Excavation has been set out in accordance with the drawings. *IFC Drawings with work lots marked-up attachment required | Verify | Prior to Commencement of Excavation | IP | SE/Surveyor | This ITP
4.2 | Material Classified as Silt | Section 204.04 (b) - Table 204.041 | Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent. Type A Material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter. Superintendent satisfied with stabilisation Attach: TeamBinder Material Approval Ref No. | Document Review | Prior to Commencing | HP | Nominated Authority | Conqa HP Release
5 | Construction Activities
5.1 | Subgrade Material Properties Inspection | IFC Drawings Section 204.06 (c) Section 204.06 (e) | Section 204.06 (c) Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04 and Table 204.041 Section 204.06 (e) In situ material within 400mm of cut floor level to be consistent with IFC Drawings Assigned CBR not less than Type A material and shall have swell less than 2.5%. If parameters are met, rip and re-compact to a depth of 150mm. If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill. Attach: Laboratory testing Verification Enter: Type A fill Lot Number: | Verify - Document Review | Each Lot | HP | Nominated Authority | Conqa HP Release
5.2 | Acceptance of Rock Subgrade (where applicable) | Section 204.06 (f) | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review. | Site Inspection/Document Review | Prior Construction of the regulating layer | HP | Nominated Authority | Conqa HP Release
5.3 | Unsuitable Material | Section 204.07 (d) | Where unsuitable material is encountered, proposed in-situ treatment or extent of excavation must be submitted to the Superintendent for review. | Visual Inspection | Each Lot | HP | PE/Nominated Authority | Conqa HP Release
5.4 | Groundwater | Section 204.06 (h) | Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. | Visual Inspection | Each Lot | HP | SE/Nominated Authority | Conqa HP Release
5.5 | Fill Construction | IFC Drawings Section 204.10 (b) Section 204.11 (b) | No Fill to be commenced on prepared areas until area has been reviewed by the Superintendent. As per the notes in the IFC drawings, excavation is required until natural clay is exposed with a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement. No Fill placed against or within 3m of a structure until the foundation for fill has been reviewed by the Superintendent. | Site Inspection | Each Lot | HP | SE/Nominated Authority | Conqa HP Release
5.6 | Proof Roll | Section 173 | Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification | Visual inspection | Each lot | HP | SE/Nominated Authority | Conqa HP Release
5.7 | Compaction Testing | Table 204.131 IFC Drawings | As per IFC Drawings Notes: 7. SCALE A MAY BE ASSUMED FOR THE PURPOSES OF ALL MATERIAL TESTING EXCEPT WHERE APPROVED BY THE DESIGNER Attach: Compaction Test Result: | Document Review | Each lot | IP | PE/SE | Test Records Lot Register
5.9 | Post Compaction Material Property Testing | Table 204,041 Table 204.141 Section 204.14 a) or b) | Material Properties (Not Applicable for Scale C): CBR ≥ 8% and Swell ≤ 1% Max Permeability = N/A Grading: 75.0mm 100% 37.5mm 50-100% 4.75mm 25-65% 0.425mm 10-25% 0.075mm <20% Max. PI x%Passing 0.425mm = 1000 , PI = <25 Scale A: CBR & Swell Initial - 1 Lot Test to determine Assigned CBR and swell Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots Max Permeability Initial - 1 test per 2 lots Reduced - 1 test per 4 lots Grading: Initial - 1 test for each lot tested for compaction Reduced - 1 test for every second lot tested for compaction Max. PI x%Passing 0.425mm & PI Initial - 1 test per 2 lots Reduced - 1 test per 4 lots Scale B: 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability. Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed. Attach: Post compaction test results: | Review Document | Refer to Section 204 | IP | PE/SE | Sign ITP Attach Material Property Test Report
6 | Post-construction Activities
6.1 | Survey Conformance | VicRoads 204.03 (f,g,h) Section 173.05 | The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Level tolerances (Scale A): Range x = +5, -15mm Max S = 12 mm 80 measurements per lot Level tolerances (Scale B): Range x = +5, -25mm Max S = 15 mm 40 measurements per lot Level tolerances (Scale C): Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level. | Review Document | Each lot | SP | SE/Surveyor | Sign ITP Attach Survey Report
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /