## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-BRUNT-CIV-Type A Fill (Supply & Install)
ITP Description: |  | Type A Fill (Dam Backfill - Replacement Material)
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2023-02-28
ITP created by: |  | Jason Lee
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Road Project Only
Inspection & Test Plan - Type A Fill - (Supply and Install)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-02-28
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 173 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VicRoads Section 204 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
| Non Dependent | VicRoads Section 176 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Material Conformance | Section 204.04 (b) Table 204.041 IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848) | REPLACEMENT MATERIAL (Type A) TO MEET THE REQUIREMENTS IN TABLE Note 1 of IFC Drawing MRP-089-C-ACD-DRG-30-BFD-CBR-2848, AND OTHERWISE CONFORMING TO TYPE A FILL REQUIREMENTS IN ACCORDANCE WITH VICROADS STANDARD SPECIFICATION SECTION 204 and Table 204.041 Table Note 1: Assigned CBR ≥ 8% Swell ≤ 1% Grading: 75.0mm 100% 37.5mm 50-100% 4.75mm 25-65% 0.425mm 10-25% 0.075mm <20% Reference: Material approval in Teambinder | Document Review | Once, for each material type | HP | Nominated Authority | Conqa HP Release
3 | Preliminaries-Documentations
3.1 | Pre-Commencement of Fill Works | Section 204.10 (b) | Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority. No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority Reference: Subgrade Preparation Lot Number: | Visual Inspection | Prior to commencement of fill works | HP | Nominated Authority | Conqa HP Release
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set Out | IFC Drawings | Set out pegs in place and clearly mark out limits of works. ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP) | Visual Inspection | Each lot prior to commencement | HP* | PE | This ITP
4.2 | Flora and Fauna | Section 176.I1 IFC Drawings | Prior to removing any vegetation, an on site inspection with the Superintendent and other relevant authorities to confirm, identify and mark trees, vegetation to be removed. Any removal shall be consistent with the IFC drawings and any relevant permits. | Visual Inspection | Each lot prior to commencement | HP* | PE | This ITP
5 | Type A Fill Activities
5.1 | Placing of Fill | Section 204.10 (d) | Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm. | Visual Inspection | Each Lot | WP | SE/Site Supervisor | This ITP
5.2 | Fill at Structures | Section 204.11 (b) | No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality. | Site Inspection | Each Lot | HP* | SE/Site Supervisor | This ITP
5.2 | Test Roll | Section 173.03 Section 204.12 | Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion. Superintendent to be present during all test rolling Attach: Test/Proof Roll Checklist | Visual Inspection | Each Lot/Layer | HP | SE/Nominated Authority | Conqa HP Release
5.3 | Compaction Testing | Table 204.131 Section 204.14 (c) Table 204.142 | Testing as per 204.13. Ensure testing is tracked and reports available. Standard Compactive Effort For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six. For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three. Compaction and Moisture content Scale A: Characteristic Density Ratio 99%. Scale B: Characteristic Density Ratio 98%. Scale C: Mean Value of Density Ratio: 100% Lot size - the leser of one day's production or 4000sqm ATTACH: COMPACTION TEST RESULTS | Review Document | Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work, subject to Superintendent satisfaction | HP* | SE/Site Supervisor | This ITP
5.4 | Preparation of final surface | Section 204.15 Section 204.03 (g) | The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water. | Measure | Top layer | IP | SE/Site Supervisor | This ITP
5.5 | Post Compaction Material Property Testing | Table 204,041 Table 204.141 Section 204.14 (a) or b) | Material Properties (Not Applicable for Scale C): CBR ≥ 8% and Swell ≤ 1% Max Permeability = N/A Grading: 75.0mm 100% 4.75mm 25-65% 0.075mm <20% Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25 Scale A: CBR & Swell Initial - 1 Lot Test to determine Assigned CBR and swell Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots Max Permeability Initial - 1 test per 2 lots Reduced - 1 test per 4 lots Grading: Initial - 1 test for each lot tested for compaction Reduced - 1 test for every second lot tested for compaction Max. PI x%Passing 0.425mm & PI Initial - 1 test per 2 lots Reduced - 1 test per 4 lots Scale B: 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability. Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed. Attach: Post compaction test results: | Review Document | Refer to Section 204 | IP | SE/Site Supervisor | This ITP
6 | Post-construction Activities
6.1 | Survey Conformance - Asbuilt | VicRoads Section 204.03 (f), (g) and (h) Table 204.031 Section 173.05 | The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173. The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2. Level tolerances Scale A: Range x = +5, -15mm Max S = 12 mm 80 measurements per lot Level tolerances Scale B: Range x = +5, -25mm Max S = 15 mm 40 measurements per lot Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level. Attach: As-built conformance report/data | Document Review | Top of Type A | HP* | Surveyor SE/PE/SPE | This ITP
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /