## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-Brunt-Signage (Supply and Install)
ITP Description: |  | Brunt-Signage (Supply and Install)
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2023-02-28
ITP created by: |  | Jason Lee
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Road Project Only
Inspection & Test Plan - Installation of Signage
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-02-28
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 860 (Feb 2023) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 714 (Feb 2023) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VicRoads Section 703 (Aug 2021) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 | Non Dependent | AS 1742.2:2009 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Manufacture & Supply of Signages and Posts | Section 860 Section 860.06 Section 860.07 Table 860.071 Section 714.03 Section 714.06 IFC Drawings | Signs are to be manufactured in accordance with Section 860 and IFC Drawings Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071. Packaging and Storage of Sign to be in accordance with Specification 860.06. Signs and components shall be handled and transported so as to prevent damage. Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer. Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either: - Hot dipped galvanised; or - Pre-galvanised prior to forming Attach: TeamBinder Material Approval Ref No | Document Review | Prior to works start | HP | Nominated Authority | Conqa HP Release
3 | Preliminaries - Documentation
3.1 | Check for correct documentation | IFC Drawings | Ensure that all employees and sub contractors are: - Using the correct and complete set of drawings - All drawings are the latest version | Visual inspection | Prior to commencing any activity | HP* | SE/Site Supervisor | This ITP Signed-off
4 | Pre-construction / Pre-installation Activities
3.1 | Setting Out - Position of Posts and Signs | Section 714.06 IFC Drawings | Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Superintendent before the erection of posts | Verify | Prior to start | HP* | Surveyor SE/PE Nominated Authority | This ITP Signed-off
4 | Construction / Installation Activities
4.1 | Foundation | Section 714.06 ( c) Section 703 | All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below: Post sizes 32mm and 50mm nominal bore steel = 225mm diameter Post sizes 80mm to 150mm nominal bore steel = 300mm diameter Frangible hardwood posts 180mm x 100mm = 300mm diameter Concrete shall be 20MPa and complying with requirements in Section 703. Attach: Concrete Delivery Docket | Measure Visual | Per Lot | HP* | SE/PE Nominated Authority | This ITP Signed-off
4.2 | Post Installation in Sockets | Section 714.06 (d) Table 22 of AS 1742.2:2009 | For Post Size 32mm Socket size to be 50mm Nominal Bore Tube For Post Size 50mm Socket size to be 65mm Nominal Bore Tube The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface. The sign post must penetrate a minimum 450 mm into the socket. Depth of the socket should be as per Table 22 of AS 1742.2:2009. The sign post should be securely fixed into the socket by an approved vandal-proof method. | Measure Visual | Per Lot | IP | SE/PE | This ITP Signed-off
4.3 | Backfilling of Post Holes | Section 714.06 e | 32 and 50 mm Nominal Bore Steel Posts Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa. 180 mm x 100 mm Frangible Hardwood Timber Posts - frangible Hardwood Posts shall be erected in accordance with the drawings; - post-holes for frangible hardwood posts shall be filled with a mixture of gravel and cement (4% by weight) Attach: Delivery Dockets | Verify | Per Lot | IP | SE/PE | This ITP Signed-off
4.4 | Sign Fitting | Section 714.07 | Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows: -Signs up to 200mm in depth – one fitting per post - Signs 201 to 900mm in depth – two fittings per post - Signs 901 to 1200mm in depth – three fittings per post One extra fitting provided per post for each 400mm increment or part thereof above 1200mm. | Measure Visual | Per Lot | IP | SE/PE | This ITP Signed-off
4.5 | Mounting of Signs | Section 714.07 (d,e,i) IFC Drawings | Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground Signs shall be positioned in accordance with the following tolerances: (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign; (ii) +/-100 mm of the pegged sign location or specified location. When a sign is to be mounted on frangible posts on a cut batter having a slope steeper than or equal to 2:1, the mounting height at the shorter post may be reduced providing that: (i) the uphill corner of the sign is a minimum of 800 mm above the ground; (ii) the sign at the longer post is 2200 mm minimum above the ground. Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰) After erection of each sign, all stiffening bars are to be removed. | Measure Visual | Per Lot | IP | SE/PE | This ITP Signed-off
4.6 | Masking of Signs | Section 714.08 | Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign. Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard. | Measure Visual | Per Lot | IP | SE/PE | This ITP Signed-off
5 | Post-construction / Post-installation Activities
5.1 | As-built Survey | Section 714.05, IFC Drawings | Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714. Attach: Survey Conformance Data/Report | Document Review | Per Lot | IP | Surveyor SE/PE/SPE | This ITP Signed-off
5.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed-off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /