## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-BRUNT-Concrete Bus Bay
ITP Description: |  | BRUNT-Concrete Bus Bay
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2023-02-28
ITP created by: |  | Jason Lee
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Road Project Only
Inspection & Test Plan - Concrete Bus Bay
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-02-28
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 204 (Dec 2015) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 173 (Oct 2008) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VicRoads Section 306 (Feb 2023) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | VicRoads Section 610 (Feb 2020) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 | Non Dependent | VicRoads Section 611 (Nov 2018) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.6 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries-Materials
2.1 | Material Conformance - Subbase | Section 306.04 Section 815.04 IFC Drawings | Cementitious Treated material shall comply with the requirements of Section 815. CTCR mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each material type prior to start of works | HP | Nominated Authority | ConQA HP Release
2.2 | Concrete Mix | Section 610.07 Table 610.071 IFC Drawings | Contractor shall submit to Superintendent the concrete mix design for approval 4 weeks prior to placement of concrete. Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
2.3 | ACRS Certification (for Reinforcement) | Section 611.05 (a) IFC Drawings | Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days of award of contract | HP | Nominated Authority | ConQA Hold Point Release
2.4 | Curing Compound (where required) | Section 610.23 (d) IFC Drawings | Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
3 | Preliminaries-Documentations
3.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP Signed-off
3.2 | Curing Method | Work Activity Pack / Works Procedure | Contractor shall submit to the Superintendent for review full details of the proposed methods of curing, as part of the concrete mix design submission, not less than four weeks prior to placement of concrete. The Contractor shall not proceed with the placement of concrete until the curing method(s) has been reviewed and approved by the Superintendent. Enter: Teambinder Hold Point Ref No. [free text box] | Document Review | Once, for each product, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set-Out | IFC Drawings | Area has been set out in accordance with the IFC Drawings. ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP): | Verify | Prior to commencement of excavation | HP* | SE/Surveyor | This ITP Signed-off
5 | Construction / Installation Activities
5.1 | Inspection of Subgrade Material Subgrade Material Properties | Section 204.06 ( c) Section 204.06 ( e) IFC Drawings | Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04 In situ material within 400mm of cut floor level to be consistent with IFC Drawings Assigned CBR ≥ 2.5% If parameters are met, rip and re compact to a depth of 150mm. If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill. If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised. Attach: Laboratory testing Verification: Enter: Type A fill Lot Number: | Verify-Document Review | Each lot | HP | PE/Nominated Authority | ConQA Hold Point Release
5.2 | Material classified as Silt - Subgrade | Section 204.04 b) | Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority | Document Review | Prior to commencing | HP | SE/Nominated Authority | ConQA Hold Point Release
5.3 | Acceptance of Rock Subgrade (where applicable) Subgrade | Section 204.06 (f) | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review. | Site Inspection/ Document Review | Prior construction of the regulating layer | HP | SE/Nominated Authority | ConQA Hold Point Release
5.4 | Unsuitable Material - Subgrade | Section 204.07 (d) | Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review. | Visual inspection | Each lot | HP | SE/Nominated Authority | ConQA Hold Point Release
5.5 | Groundwater - Subgrade | Section 204.06 (h) | Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. | Visual inspection | Each lot | HP | SE/Nominated Authority | ConQA Hold Point Release
5.6 | Cut to Fill Zones - Subgrade | Section 204.06 (g) | All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material. | Site Inspection | Each lot | IP | SE/Site Supervisor | This ITP Signed-off
5.7 | Proof Roll - Subgrade | Section 173 | Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification. Attach: Proof Roll Inspection Checklist | Visual inspection | Each lot | HP | SE/Nominated Authority | ConQA Hold Point Release
5.8 | Compaction Testing - Subgrade | Section 204.13 Table 204.131 | All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level Scale A: Characteristic Density Ratio 99%. Scale B: Characteristic Density Ratio 98%. Scale C: Mean Value of Density Ratio: 100% Attach: Compaction Test Result | Document Review | Each lot | HP* | PE/SE | ConQA Hold Point Release
5.9 | Post Compaction Material Property Testing Subgrade | Table 204,041 Table 204.141 Section 204.14 a) or b) | Material Properties (Not Applicable for Scale C): CBR ≥ 3% and Swell ≤ 1.5% Max Permeability = 5X10-9 m/s Grading: 75.0mm 100% 4.75mm 40-80% 0.075mm 10-40% Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25 Scale A: CBR & Swell Initial - 1 Lot Test to determine Assigned CBR and swell Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots Max Permeability Initial - 1 test per 2 lots Reduced - 1 test per 4 lots Grading: Initial - 1 test for each lot tested for compaction Reduced - 1 test for every second lot tested for compaction Max. PI x%Passing 0.425mm & PI Initial - 1 test per 2 lots Reduced - 1 test per 4 lots Scale B: 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability. Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed. Attach: Post compaction test results / Attach Material Property Test Report | Review Document | Refer to Section 204 | IP | PE/SE | Sign ITP
5.1 | Test Roll - Subbase | Section 306.10 Table 306.091 | Shall be test rolled in accordance with Section 173 within maximum allowable working time for the relevant binder and time of year as specified in Table 306.091 Table 306.091 Type GP - 2 hrs (Oct to Apr), 3 hrs (May to Sep) Type GB - 3 hrs (Oct to Apr), 5 hrs (May to Sep) Slag/Lime Blend - 8 hrs (Oct to Apr), 12 hrs (May to Sep) | Testing | Each Lot/Layer | HP | Nominated Authority | ConQA Hold Point Release
5.11 | Compaction Testing - Subbase | Section 306.09 Table 306.091 | If the Contractor proposes to use an alternative cementitous binder to those included in Table 306.091, laboratory test results shall be produced to the Superintendent showing that the binder satisfies the required working time determined in accordance with the VicRoads Test Method. In addition, the cementitious treated material using the alternative binder shall meet specified strength requirements. Characteristic Value of Density Ratio Scale A - Not less than 96% Mean Density Ratio Scale B - Not Less than 96% Attach Compaction Test Report | Review Document | Scale A - 6 per lot Scale B - 3 per Lot | HP | SE/Site Supervisor Superintendent | ConQA Hold Point Release
5.12 | Reinforcement Placement - Base | IFC Drawings VicRoads SD 2071 Section 611.06 Section 611.09 Section 611.10 Section 611.11 Section 611.12 | The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the drawings. Projecting reinforcement is the correct length and location. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. Minimum cover as shown on the drawings for each face has been achieved (including tie wire locations). | Measure Visual | Each element | IP | Foreman SE/PE/SPE | This ITP Signed-off
5.13 | Pre-pour Inspection - Base | IFC Drawings Section Section 610.18 (a) (ii) & (iii) | Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority All foreign material has been completely removed from the forms. | Measure Visual | Each element | HP* | SE/Site Supervisor Superintendent | This ITP Signed-off
5.14 | Weather Conditions & Evaporation Limits - Base | Section 610.17 Section 610.17 (a) & (e) Table 610.171 | All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record. | Measure Visual | Each element | IP | Foreman SE/PE/SPE | This ITP Signed-off
5.15 | Concrete Testing - Sampling Frequency - Base | Section 610.16 (b) | Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork. Record: Required information on the Concrete Pour Record. Qty of samples taken | Testing | Each element | HP* | Concrete Tester Foreman SE/PE/SPE | This ITP Signed-off
5.16 | Concrete Testing - Slump - Base | Section 610.16 (c) | Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record. | Testing | Each sample of Standard or Superplasticised Concrete | IP | Concrete Tester/ SE | This ITP Signed-off
5.17 | Concrete Testing - Spread, Passability & Viscosity - Base | Section 610.13 (b) | Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record. | Testing | Each sample of Self-compacting Concrete | IP | Concrete Tester | This ITP Signed-off
5.18 | Concrete Testing - Compressive Strength Cylinders - Base | Site Sampling & Testing Procedure | Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record. | Testing | Each sample | IP | Concrete Tester/ SE | This ITP Signed-off
5.19 | Supply & Discharge Rates - Base | Section 610.13 (a) & (f) | Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record required information on the Concrete Pour Record. | Measure Visual | Each load | IP | Foreman SE/PE/SPE | This ITP Signed-off
5.20 | Placement & Compaction - Base | Section 610.18 (a) & (b) Section 610.18 (d) (i) | All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Concrete is not dropped freely from a height exceeding 2m. Concrete is not moved horizontally by use of vibrators. Adequate compaction is ensured Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments. Concrete layers are not more than 350mm Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence. Vibration continued at each point until air bubbles cease to emerge from the concrete. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets | Visual | Each load | IP | Foreman SE/PE/SPE | This ITP Signed-off
5.21 | Surface Finishes - Base | IFC Drawings Section 610.31 Section 610.20 | Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority. | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP Signed-off
5.22 | Curing - Base | Curing Methodology Section 610.23 Table 610.231 | Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS. | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP Signed-off
6 | Post Construction Activities
6.1 | Survey Conformance - Subgrade Prep | VicRoads Section 204.03f,g and h | The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Level tolerances (Scale A): Range x = +5, -15mm Max S = 12 mm 80 measurements per lot Level tolerances (Scale B): Range x = +5, -25mm Max S = 15 mm 40 measurements per lot Level tolerances (Scale C): Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level. Attach: Survey Conformance Report/Data | Review Document | Each lot | HP* | SE/Surveyor | This ITP Signed-off
6.2 | Survey Conformance - Subbase | VicRoads Section 306.03 | Level tolerances Scale A: Range x = +4, -8mm Max S = 8 mm 80 measurements per lot Level tolerances Scale B: Range x = +6, -12mm Max S = 13 mm 40 measurements per lot Level tolerances Scale C: No point on the subbase surface shall be more than 10 mm above or 25 mm below the specified level. Attach: Survey Conformance Report/Data | Document Review | Each lot | HP* | SE/Surveyor | This ITP Signed-off
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed-off
6.4 | Surface Inspection - Cracks (Concrete Base) | Section 610.24 | No cracks greater than 0.2mm (exposure classification B1) | Visual Measure | Each element | IP | SE/PE/SPE | This ITP Signed-off
6.5 | Surface Inspection - Surface Finish | IFC Drawings Section 610.31 (a) - (n) Section 610.32 | Comply with the IFC drawings and specifications. | Visual | Each element | IP | SE/PE/SPE | This ITP Signed-off
6.6 | Measurement of Concrete Cover | Section 610.34 | Concrete covermeter check one 3m² test area for every 25m² exterior surface area. Minimum 10 no. measurements recorded in each area. Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority. Attach: Covermeter Check Record | Measure | Each element | IP | SE/PE/SPE | This ITP Signed-off
6.7 | Compressive Strength & VPV Test Results | IFC Drawings Table 610.051 Table 610.061 Section 610.16 (g) | 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results | Document Review | Each cylinder | HP* | SE/PE/SPE | This ITP Signed-off
6.8 | As-built Survey | IFC Drawings Section 610.46 Table 610.462 | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report | Document Review | Each element | HP* | Surveyor SE/PE/SPE | This ITP Signed-off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /