## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-022-CIV-Brunt-Subgrade Preparation-Dam Backfill | [5 empty] | ITP-022-CIV-Brunt-Subgrade Preparation-Dam Backfill
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
note | Document Title: ITP-CIV-BRUNT-Subgrade Preparation-Dam Backfill
note | ITP Description: BRUNT-Subgrade Preparation-Dam Backfill
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 0
note | Revision Date: 28/02/2023
note | ITP created by: Jason Lee
note | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
note | Reference - VicRoads Section 204
checkpoint | 1.2 - Non Dependent
note | Reference - VicRoads Section 173
checkpoint | 1.3 - Non Dependent
note | Reference - IFC Drawings
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Non Dependent
note | Reference - N/A
note | Acceptance Criteria - N/A
note | Method - N/A
note | Frequency - N/A
note | Category - N/A
note | Responsibility - N/A
note | Verifying Documents - N/A
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Non Dependent
note | Reference - N/A
note | Acceptance Criteria - N/A
note | Method - N/A
note | Frequency - N/A
note | Category - N/A
note | Responsibility - N/A
note | Verifying Documents - N/A
section | 4. Pre-construction Activities
checkpoint | 4.1 - Survey Set-Out
note | Reference - IFC Drawings
note | Acceptance Criteria - The Area of Excavation has been set out in accordance with the drawings.
note | ○ IFC Drawings with work lots marked-up attachment required
note | Method - Verify
note | Frequency - Prior to Commencement of Excavation
note | Category - IP
note | Responsibility - SE/Surveyor
note | Verifying Documents - This ITP
checkpoint | 4.2 - Material Classified as Silt
note | Reference - Section 204.04 (b) - Table 204.041
note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
note | ○ Type A Material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
note | ○ Superintendent satisfied with stabilisation
note | ○ Attach: TeamBinder Material Approval Ref No.
note | Method - Document Review
note | Frequency - Prior to Commencing
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 5. Construction Activities
checkpoint | 5.1 - Subgrade Material Properties Inspection
note | Reference - IFC Drawings
note | ○ Section 204.06 (c)
note | ○ Section 204.06 (e)
note | Acceptance Criteria - Section 204.06 (c)
note | • Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04 and Table 204.041
note | ○ Section 204.06 (e)
note | • In situ material within 400mm of cut floor level to be consistent with IFC Drawings
note | • Assigned CBR not less than Type A material and shall have swell less than 2.5%.
note | • If parameters are met, rip and re-compact to a depth of 150mm.
note | • If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
note | ○ Attach: Laboratory testing Verification
textbox | Type A fill Lot Number:
note | Method - Verify - Document Review
note | Frequency - Each Lot
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Acceptance of Rock Subgrade (where applicable)
note | Reference - Section 204.06 (f)
note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
note | Method - Site Inspection/Document Review
note | Frequency - Prior Construction of the regulating layer
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Unsuitable Material
note | Reference - Section 204.07 (d)
note | Acceptance Criteria - Where unsuitable material is encountered, proposed in-situ treatment or extent of excavation must be submitted to the Superintendent for review.
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - HP
note | Responsibility - PE/Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Groundwater
note | Reference - Section 204.06 (h)
note | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Fill Construction
note | Reference - IFC Drawings
note | ○ Section 204.10 (b)
note | ○ Section 204.11 (b)
note | Acceptance Criteria - No Fill to be commenced on prepared areas until area has been reviewed by the Superintendent.
note | ○ As per the notes in the IFC drawings, excavation is required until natural clay is exposed with a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement.
note | ○ No Fill placed against or within 3m of a structure until the foundation for fill has been reviewed by the Superintendent.
note | Method - Site Inspection
note | Frequency - Each Lot
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Proof Roll
note | Reference - Section 173
note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Compaction Testing
note | Reference - Table 204.131 IFC Drawings
note | Acceptance Criteria - As per IFC Drawings Notes:
note | 7. SCALE A MAY BE ASSUMED FOR THE PURPOSES OF ALL MATERIAL TESTING EXCEPT WHERE APPROVED BY THE DESIGNER
note | ○ Attach: Compaction Test Result:
note | Method - Document Review
note | Frequency - Each lot
note | Category - IP
note | Responsibility - PE/SE
note | Verifying Documents - Test Records, Lot Register
checkpoint | 5.8 - Post Compaction Material Property Testing
note | Reference - Table 204,041
note | ○ Table 204.141
note | ○ Section 204.14 a) or b)
note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
note | • CBR ≥ 8% and Swell ≤ 1%
note | • Max Permeability = N/A
note | ○ Grading: 75.0mm 100%
note | • 37.5mm 50-100%
note | • 4.75mm 25-65%
note | • 0.425mm 10-25%
note | • 0.075mm <20%
note | • Max. PI x%Passing 0.425mm = 1000 , PI = <25
note | ○ Scale A:
note | • CBR & Swell
note | Initial - 1 Lot Test to determine Assigned CBR and swell
note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
note | • Max Permeability
note | Initial - 1 test per 2 lots
note | Reduced - 1 test per 4 lots
note | • Grading:
note | Initial - 1 test for each lot tested for compaction
note | Reduced - 1 test for every second lot tested for compaction
note | • Max. PI x%Passing 0.425mm & PI
note | Initial - 1 test per 2 lots
note | Reduced - 1 test per 4 lots
note | ○ Scale B:
note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
note | • Attach: Post compaction test results:
note | Method - Review Document
note | Frequency - Refer to Section 204
note | Category - IP
note | Responsibility - PE/SE
note | Verifying Documents - Sign ITP, Attach Material Property Test Report
section | 6. Post-construction Activities
checkpoint | 6.1 - Survey Conformance
note | Reference - VicRoads 204.03 (f,g,h) Section 173.05
note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
note | ○ Level tolerances (Scale A):
note | • Range x = +5, -15mm
note | • Max S = 12 mm
note | • 80 measurements per lot
note | ○ Level tolerances (Scale B):
note | • Range x = +5, -25mm
note | • Max S = 15 mm
note | • 40 measurements per lot
note | ○ Level tolerances (Scale C):
note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
note | Method - Review Document
note | Frequency - Each lot
note | Category - SP
note | Responsibility - SE/Surveyor
note | Verifying Documents - Sign ITP, Attach Survey Report
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP