## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-023-CIV-Brunt-Type A Fill-Dam Backfill | [5 empty] | ITP-023-CIV-Brunt-Type A Fill-Dam Backfill
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
note | Document Title: ITP-BRUNT-CIV-Type A Fill (Dam Backfill - Replacement Material)
note | ITP Description: Type A Fill (Dam Backfill - Replacement Material)
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 0
note | Revision Date: 28/02/2023
note | ITP created by: Jason Lee
note | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
note | Reference - IFC Drawings
checkpoint | 1.2 - Non Dependent
note | Reference - VicRoads Section 173
checkpoint | 1.3 - Non Dependent
note | Reference - VicRoads Section 204
checkpoint | 1.4 - Non Dependent
note | Reference - VicRoads Section 176
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Material Conformance
note | Reference - Section 204.04 (b) Table 204.041
note | ○ IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848)
note | Acceptance Criteria - REPLACEMENT MATERIAL (Type A) TO MEET THE REQUIREMENTS IN TABLE Note 1 of IFC Drawing MRP-089-C-ACD-DRG-30-BFD-CBR-2848, AND OTHERWISE CONFORMING TO TYPE A FILL REQUIREMENTS IN ACCORDANCE WITH VICROADS STANDARD SPECIFICATION SECTION 204 and Table 204.041
note | ○ Table Note 1:
note | • Assigned CBR ≥ 8%
note | • Swell ≤ 1%
note | ○ Grading:
note | • 75.0mm 100%
note | • 37.5mm 50-100%
note | • 4.75mm 25-65%
note | • 0.425mm 10-25%
note | • 0.075mm <20%
note | ○ Reference: Material approval in Teambinder
note | Method - Document Review
note | Frequency - Once, for each material type
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documentations
checkpoint | 3.1 - Pre-Commencement of Fill Works
note | Reference - Section 204.10 (b)
note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
note | ○ Reference: Subgrade Preparation Lot Number:
note | Method - Visual Inspection
note | Frequency - Prior to commencement of fill works
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set Out
note | Reference - IFC Drawings
note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
note | Method - Visual Inspection
note | Frequency - Each lot prior to commencement
note | Category - HP*
note | Responsibility - PE
note | Verifying Documents - This ITP
checkpoint | 4.2 - Flora and Fauna
note | Reference - Section 176.I1 IFC Drawings
note | Acceptance Criteria - Prior to removing any vegetation, an on site inspection with the Superintendent and other relevant authorities to confirm, identify and mark trees, vegetation to be removed. Any removal shall be consistent with the IFC drawings and any relevant permits.
note | Method - Visual Inspection
note | Frequency - Each lot prior to commencement
note | Category - HP*
note | Responsibility - PE
note | Verifying Documents - This ITP
section | 5. Type A Fill Activities
checkpoint | 5.1 - Placing of Fill
note | Reference - Section 204.10 (d)
note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - WP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - This ITP
checkpoint | 5.2 - Fill at Structures
note | Reference - Section 204.11 (b)
note | Acceptance Criteria - No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent
note | ○ In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
note | Method - Site Inspection
note | Frequency - Each Lot
note | Category - HP*
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - This ITP
checkpoint | 5.3 - Test Roll
note | Reference - Section 173.03, Section 204.12
note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
note | ○ Superintendent to be present during all test rolling
note | ○ Attach: Test/Proof Roll Checklist
note | Method - Visual Inspection
note | Frequency - Each Lot/Layer
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Compaction Testing
note | Reference - Table 204.131
note | ○ Section 204.14 (c)
note | ○ Table 204.142
note | Acceptance Criteria - Testing as per 204.13. Ensure testing is tracked and reports available.
note | ○ Standard Compactive Effort
note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
note | ○ Compaction and Moisture content
note | • Scale A: Characteristic Density Ratio 99%.
note | • Scale B: Characteristic Density Ratio 98%.
note | • Scale C: Mean Value of Density Ratio: 100%
note | ○ Lot size - the leser of one day's production or 4000sqm
note | ○ ATTACH: COMPACTION TEST RESULTS
note | Method - Review Document
note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work, subject to Superintendent satisfaction
note | Category - HP*
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - This ITP
checkpoint | 5.5 - Preparation of final surface
note | Reference - Section 204.15
note | ○ Section 204.03 (g)
note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
note | Method - Measure
note | Frequency - Top layer
note | Category - IP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - This ITP
checkpoint | 5.6 - Post Compaction Material Property Testing
note | Reference - Table 204,041
note | ○ Table 204.141
note | ○ Section 204.14 (a) or b)
note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
note | • CBR ≥ 8% and Swell ≤ 1%
note | • Max Permeability = N/A
note | • Grading: 75.0mm 100%
note | • 4.75mm 25-65%
note | • 0.075mm <20%
note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
note | ○ Scale A:
note | ○ CBR & Swell
note | • Initial - 1 Lot Test to determine Assigned CBR and swell
note | • Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
note | ○ Max Permeability
note | • Initial - 1 test per 2 lots
note | • Reduced - 1 test per 4 lots
note | ○ Grading:
note | • Initial - 1 test for each lot tested for compaction
note | • Reduced - 1 test for every second lot tested for compaction
note | • Max. PI x%Passing 0.425mm & PI
note | • Initial - 1 test per 2 lots
note | • Reduced - 1 test per 4 lots
note | ○ Scale B:
note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
note | ○ Attach: Post compaction test results:
note | Method - Review Document
note | Frequency - Refer to Section 204
note | Category - IP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - This ITP
section | 6. Post-construction Activities
checkpoint | 6.1 - Survey Conformance - Asbuilt
note | Reference - VicRoads Section 204.03 (f), (g) and (h)
note | ○ Table 204.031
note | ○ Section 173.05
note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
note | ○ Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173. The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
note | ○ Level tolerances Scale A:
note | • Range x = +5, -15mm
note | • Max S = 12 mm
note | • 80 measurements per lot
note | ○ Level tolerances Scale B:
note | • Range x = +5, -25mm
note | • Max S = 15 mm
note | • 40 measurements per lot
note | ○ Level tolerances Scale C:
note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
note | ○ Attach: As-built conformance report/data
note | Method - Document Review
note | Frequency - Top of Type A
note | Category - HP*
note | Responsibility - Surveyor, SE/PE/SPE
note | Verifying Documents - This ITP
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP