## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-025-CIV-Brunt-Kerb & Channel (Supply and Install) | [5 empty] | ITP-025-CIV-Brunt-Kerb & Channel (Supply and Install)
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
note | Document Title: ITP-CIV-Brunt-Kerb and Channel (Supply and Install)
note | ITP Description: Brunt-Kerb and Channel (Supply and Install)
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 0
note | Revision Date: 28/02/2023
note | ITP created by: Jason Lee
note | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
note | Reference - VicRoads Section 703 (August 2021)
note | VR SD2001
note | VR SD2102
note | AS 2876
note | AS1379
section | 2. Preliminary - Materials
checkpoint | 2.1 - Mix design
note | Reference - SD2001 AS1379
note | ○ Section 703.05, 703.06, 703.07
note | Acceptance Criteria - Approved VR mix design to be used.
note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
note | ○ Attach: TeamBinder Material Approval Ref No.
note | Method - Verify, Document Review
note | Frequency - Prior to commencing any activity
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Bedding Material
note | Reference - Section 703.21 IFC Drawings
note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
note | ○ Attach: TeamBinder Material Approval Ref No.
note | Method - Verify, Document Review
note | Frequency - Prior to commencing any activity
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Curing Compound
note | Reference - Section 703.10
note | Acceptance Criteria - Curing compound shall comply with AS3799
note | ○ Attach: TeamBinder Material Approval Ref No.
note | Method - Verify
note | Frequency - Prior to commencing any activity
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminary - Documentation
checkpoint | 3.1 - Check for correct documentation
note | Reference - IFC Drawings
note | Acceptance Criteria - Ensure that all employee and sub contractors are:
note | – Using the correct and complete set of drawings
note | – All drawings are the latest version
note | Method - Visual inspection
note | Frequency - Prior to commencing any activity
note | Category - HP*
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - ITP Signed
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Setting out
note | Reference - Section 703.17 IFC Drawings
note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
note | ○ The superintendent will review and confirm set out.
note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
note | Method - Verify
note | Frequency - Prior to start
note | Category - HP
note | Responsibility - Surveyor/Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Temporary drainage provisions
note | Reference - Section 703.18 CEMP
note | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
note | ○ Attach: relevant written approval from relevant stakeholder.
note | Method - Visual inspection, Document Review
note | Frequency - Prior to start (where required)
note | Category - HP*
note | Responsibility - SE/PE/Site Supervisor
note | Verifying Documents - ITP Signed
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Bedding
note | Reference - Section 703.21
note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - WP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - ITP Signed
checkpoint | 5.2 - Formwork
note | Reference - Section 703.12 AS3610
note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - WP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - ITP Signed
checkpoint | 5.3 - Pre Pour Check
note | Reference - Section 703.09
note | ○ Section 703.2
note | ○ Section 610.17 (a,b,c)
note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface.
note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
note | ○ Attach: Pre-pour Inspection Record
note | Method - Verify
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - ITP Signed
checkpoint | 5.4 - Concrete placement
note | Reference - Section 703.08
note | ○ Section 703.23
note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
note | ○ Attach: Concrete Pour Records
note | Method - Site inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - ITP Signed
checkpoint | 5.5 - Transitions
note | Reference - Section 703.24
note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
note | Method - Site inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - ITP Signed
checkpoint | 5.6 - Surface Finish
note | Reference - Section 703.25
note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
note | ○ Renderings shall be applied within 30 minutes of extrusion.
note | ○ Concrete to have a neat appearance and uniform colour.
note | ○ Class 3 finish required for external surfaces.
note | ○ Class 4 finish required for permanently hidden surfaces.
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - ITP Signed
checkpoint | 5.7 - Formwork Stripping
note | Reference - Section 703.12 AS3610
note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
note | – External faces 2 days
note | – Permanently hidden faces 1 day
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - ITP Signed
checkpoint | 5.8 - Tolerance
note | Reference - Section 703.15
note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
note | ○ Attach: Post-pour Inspection Records
note | Method - Verify
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE/Surveyor
note | Verifying Documents - ITP Signed
checkpoint | 5.9 - Curing
note | Reference - Section 703.10
note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - ITP Signed
checkpoint | 5.10 - Joints
note | Reference - Section 703.26
note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
note | Method - Verify
note | Frequency - Each joint
note | Category - IP
note | Responsibility - SE / Site Supervisor
note | Verifying Documents - ITP Signed
checkpoint | 5.11 - Protection of Concrete
note | Reference - Section 703.27
note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - ITP Signed
checkpoint | 5.12 - Bus Stop Kerb Height
note | Reference - DoT Handover Process
note | Acceptance Criteria - Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
note | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
note | Method - Visual Inspection
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - SE
note | Verifying Documents - ITP Signed
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Backfilling
note | Reference - Section 703.29
note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
note | Method - Verify
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - ITP Signed
checkpoint | 6.2 - Cracking of Concrete
note | Reference - Section 703.30
note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
note | ○ Attach: Pot-pour Inspection Record
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - ITP Signed
checkpoint | 6.3 - Survey Conformance
note | Reference - Section 703.15
note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
note | Method - Document Review
note | Frequency - Completion of each lot
note | Category - WP
note | Responsibility - Project Engineer/ Surveyor
note | Verifying Documents - As-built survey records
checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP