## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-029-CIV-Brunt-Concrete Bus Bay | [5 empty] | ITP-029-CIV-Brunt-Concrete Bus Bay
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
note | Document Title: ITP-CIV-BRUNT-Concrete Bus Bay
note | ITP Description: BRUNT-Concrete Bus Bay
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 0
note | Revision Date: 28/02/2023
note | ITP created by: Jason Lee
note | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
note | Reference - VicRoads Section 204 (Dec 2015)
checkpoint | 1.2 - Non Dependent
note | Reference - VicRoads Section 173 (Oct 2008)
checkpoint | 1.3 - Non Dependent
note | Reference - VicRoads Section 306 (Feb 2023)
checkpoint | 1.4 - Non Dependent
note | Reference - VicRoads Section 610 (Feb 2020)
checkpoint | 1.5 - Non Dependent
note | Reference - VicRoads Section 611 (Nov 2018)
checkpoint | 1.6 - Non Dependent
note | Reference - IFC Drawings
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Material Conformance - Subbase
note | Reference - Section 306.04
note | ○ Section 815.04
note | ○ IFC Drawings
note | Acceptance Criteria - Cementitious Treated material shall comply with the requirements of Section 815.
note | ○ CTCR mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Once, for each material type prior to start of works
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Concrete Mix
note | Reference - Section 610.07
note | ○ Table 610.071
note | ○ IFC Drawings
note | Acceptance Criteria - Contractor shall submit to Superintendent the concrete mix design for approval 4 weeks prior to placement of concrete.
note | ○ Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - ACRS Certification (for Reinforcement)
note | Reference - Section 611.05 (a) IFC Drawings
note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Once for each supplier, 14 days of award of contract
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Curing Compound (where required)
note | Reference - Section 610.23 (d) IFC Drawings
note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documentations
checkpoint | 3.1 - IFC Drawings
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
note | Method - Document Review
note | Frequency - Prior to starting Works and at regular intervals
note | Category - HP*
note | Responsibility - All
note | Verifying Documents - This ITP Signed-off
checkpoint | 3.2 - Curing Method
note | Reference - Work Activity Pack / Works Procedure
note | Acceptance Criteria - Contractor shall submit to the Superintendent for review full details of the proposed methods of curing, as part of the concrete mix design submission, not less than four weeks prior to placement of concrete.
note | ○ The Contractor shall not proceed with the placement of concrete until the curing method(s) has been reviewed and approved by the Superintendent.
textbox | Enter: Teambinder Hold Point Ref No.
note | Method - Document Review
note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-Out
note | Reference - IFC Drawings
note | Acceptance Criteria - Area has been set out in accordance with the IFC Drawings.
note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
note | Method - Verify
note | Frequency - Prior to commencement of excavation
note | Category - HP*
note | Responsibility - SE/Surveyor
note | Verifying Documents - This ITP Signed-off
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Inspection of Subgrade Material Subgrade Material Properties
note | Reference - Section 204.06 (c)
note | ○ Section 204.06 (e)
note | ○ IFC Drawings
note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
note | ○ Assigned CBR ≥ 2.5%
note | ○ If parameters are met, rip and re compact to a depth of 150mm.
note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
note | ○ Attach: Laboratory testing Verification:
textbox | Enter: Type A fill Lot Number:
note | Method - Verify-Document Review
note | Frequency - Each lot
note | Category - HP
note | Responsibility - PE/Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Material classified as Silt - Subgrade
note | Reference - Section 204.04 b)
note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
note | Method - Document Review
note | Frequency - Prior to commencing
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable) Subgrade
note | Reference - Section 204.06 (f)
note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
note | Method - Site Inspection/ Document Review
note | Frequency - Prior construction of the regulating layer
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Unsuitable Material - Subgrade
note | Reference - Section 204.07 (d)
note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Groundwater - Subgrade
note | Reference - Section 204.06 (h)
note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Cut to Fill Zones - Subgrade
note | Reference - Section 204.06 (g)
note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
note | Method - Site Inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.7 - Proof Roll - Subgrade
note | Reference - Section 173
note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification.
note | ○ Attach: Proof Roll Inspection Checklist
note | Method - Visual inspection
note | Frequency - Each lot
note | Category - HP
note | Responsibility - SE/Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Compaction Testing - Subgrade
note | Reference - Section 204.13 Table 204.131
note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
note | ○ Ripped and re-compacted material below Cut Floor Level
note | ○ Scale A: Characteristic Density Ratio 99%.
note | ○ Scale B: Characteristic Density Ratio 98%.
note | ○ Scale C: Mean Value of Density Ratio: 100%
note | ○ Attach: Compaction Test Result
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - PE/SE
note | Verifying Documents - ConQA Hold Point Release
checkpoint | 5.9 - Post Compaction Material Property Testing Subgrade
note | Reference - Table 204,041
note | ○ Table 204.141
note | ○ Section 204.14 a) or b)
note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
note | • CBR ≥ 3% and Swell ≤ 1.5%
note | • Max Permeability = 5X10-9 m/s
note | • Grading: 75.0mm 100%
note | • 4.75mm 40-80%
note | • 0.075mm 10-40%
note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
note | ○ Scale A:
note | • CBR & Swell
note | • Initial - 1 Lot Test to determine Assigned CBR and swell
note | • Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
note | • Max Permeability
note | • Initial - 1 test per 2 lots
note | • Reduced - 1 test per 4 lots
note | • Grading:
note | • Initial - 1 test for each lot tested for compaction
note | • Reduced - 1 test for every second lot tested for compaction
note | • Max. PI x%Passing 0.425mm & PI
note | • Initial - 1 test per 2 lots
note | • Reduced - 1 test per 4 lots
note | ○ Scale B:
note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
note | ○ Attach: Post compaction test results / Attach Material Property Test Report
note | Method - Review Document
note | Frequency - Refer to Section 204
note | Category - IP
note | Responsibility - PE/SE
note | Verifying Documents - Sign ITP
checkpoint | 5.10 - Test Roll - Subbase
note | Reference - Section 306.10
note | ○ Table 306.091
note | Acceptance Criteria - Shall be test rolled in accordance with Section 173 within maximum allowable working time for the relevant binder and time of year as specified in Table 306.091
note | ○ Table 306.091
note | • Type GP - 2 hrs (Oct to Apr), 3 hrs (May to Sep)
note | • Type GB - 3 hrs (Oct to Apr), 5 hrs (May to Sep)
note | • Slag/Lime Blend - 8 hrs (Oct to Apr), 12 hrs (May to Sep)
note | Method - Testing
note | Frequency - Each Lot/Layer
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.11 - Compaction Testing - Subbase
note | Reference - Section 306.09
note | ○ Table 306.091
note | Acceptance Criteria - If the Contractor proposes to use an alternative cementitous binder to those included in Table 306.091, laboratory test results shall be produced to the Superintendent showing that the binder satisfies the required working time determined in accordance with the VicRoads Test Method. In addition, the cementitious treated material using the alternative binder shall meet specified strength requirements.
note | ○ Characteristic Value of Density Ratio
note | • Scale A - Not less than 96%
note | ○ Mean Density Ratio
note | • Scale B - Not Less than 96%
note | ○ Attach Compaction Test Report
note | Method - Review Document
note | Frequency - Scale A - 6 per lot, Scale B - 3 per Lot
note | Category - HP
note | Responsibility - SE/Site Supervisor, Superintendent
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.12 - Reinforcement Placement - Base
note | Reference - IFC Drawings
note | ○ VicRoads SD 2071
note | ○ Section 611.06
note | ○ Section 611.09
note | ○ Section 611.10
note | ○ Section 611.11
note | ○ Section 611.12
note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the drawings.
note | ○ Projecting reinforcement is the correct length and location.
note | ○ The reinforcement surface condition is free from dirt, debris and damage.
note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
note | ○ Minimum cover as shown on the drawings for each face has been achieved (including tie wire locations).
note | Method - Measure, Visual
note | Frequency - Each element
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.13 - Pre-pour Inspection - Base
note | Reference - IFC Drawings
note | ○ Section 610.18 (a) (ii) & (iii)
note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
note | ○ All foreign material has been completely removed from the forms.
note | Method - Measure, Visual
note | Frequency - Each element
note | Category - HP*
note | Responsibility - SE/Site Supervisor, Superintendent
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.14 - Weather Conditions & Evaporation Limits - Base
note | Reference - Section 610.17
note | ○ Section 610.17 (a) & (e)
note | ○ Table 610.171
note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
note | ○ Record: Required information on the Concrete Pour Record.
note | Method - Measure, Visual
note | Frequency - Each element
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.15 - Concrete Testing - Sampling Frequency - Base
note | Reference - Section 610.16 (b)
note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
note | • 0m³ to 10m³ = 1 sample
note | • 10m³ to 25m³ = 2 samples
note | • 25m³ to 50m³ = 3 samples
note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
note | • For each additional 50m³ and additional sample shall be taken.
note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
note | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
note | ○ Record: Required information on the Concrete Pour Record. Qty of samples taken
note | Method - Testing
note | Frequency - Each element
note | Category - HP*
note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.16 - Concrete Testing - Slump - Base
note | Reference - Section 610.16 (c)
note | Acceptance Criteria - Slump testing tolerances =
note | • <60mm = ±10mm
note | • ≥60mm to ≤80mm = ±15mm
note | • >80mm to ≤110mm = ±20mm
note | • >110mm to ≤150mm = ±30mm
note | • >150mm = ±40mm
note | ○ Record: Required information on the Concrete Pour Record.
note | Method - Testing
note | Frequency - Each sample of Standard or Superplasticised Concrete
note | Category - IP
note | Responsibility - Concrete Tester/SE
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.17 - Concrete Testing - Spread, Passability & Viscosity - Base
note | Reference - Section 610.13 (b)
note | Acceptance Criteria - Spread range = 550mm to 750mm
note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
note | ○ Passability = ≤10mm (aggregate height differential)
note | ○ Record: Required information on the Concrete Pour Record.
note | Method - Testing
note | Frequency - Each sample of Self-compacting Concrete
note | Category - IP
note | Responsibility - Concrete Tester
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.18 - Concrete Testing - Compressive Strength Cylinders - Base
note | Reference - Site Sampling & Testing Procedure
note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
note | ○ Record: Required information on the Concrete Pour Record.
note | Method - Testing
note | Frequency - Each sample
note | Category - IP
note | Responsibility - Concrete Tester/SE
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.19 - Supply & Discharge Rates - Base
note | Reference - Section 610.13 (a) & (f)
note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
note | ○ No water is to be added once discharge commences.
note | ○ Maximum time between batching trucks is 25 minutes.
note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
note | ○ Record required information on the Concrete Pour Record.
note | Method - Measure, Visual
note | Frequency - Each load
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.20 - Placement & Compaction - Base
note | Reference - Section 610.18 (a) & (b)
note | ○ Section 610.18 (d) (i)
note | Acceptance Criteria - All concrete batches are traceable.
note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
note | ○ Concrete is not dropped freely from a height exceeding 2m.
note | ○ Concrete is not moved horizontally by use of vibrators.
note | ○ Adequate compaction is ensured
note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
note | ○ Concrete layers are not more than 350mm
note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
note | ○ Record: Required information on the Concrete Pour Record.
note | ○ Attach: Concrete Pour Record
note | ○ Attach: Concrete Dockets
note | Method - Visual
note | Frequency - Each load
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.21 - Surface Finishes - Base
note | Reference - IFC Drawings
note | ○ Section 610.31
note | ○ Section 610.20
note | Acceptance Criteria - Surface finish as per IFC drawings.
note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
note | Method - Visual
note | Frequency - Each element
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 5.22 - Curing - Base
note | Reference - Curing Methodology
note | ○ Section 610.23
note | ○ Table 610.231
note | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
note | Method - Visual
note | Frequency - Each element
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
section | 6. Post Construction Activities
checkpoint | 6.1 - Survey Conformance - Subgrade Prep
note | Reference - VicRoads Section 204.03f,g and h
note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
note | ○ Level tolerances (Scale A):
note | • Range x = +5, -15mm
note | • Max S = 12 mm
note | • 80 measurements per lot
note | ○ Level tolerances (Scale B):
note | • Range x = +5, -25mm
note | • Max S = 15 mm
note | • 40 measurements per lot
note | ○ Level tolerances (Scale C):
note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
note | ○ Attach: Survey Conformance Report/Data
note | Method - Review Document
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - SE/Surveyor
note | Verifying Documents - This ITP Signed-off
checkpoint | 6.2 - Survey Conformance - Subbase
note | Reference - VicRoads Section 306.03
note | Acceptance Criteria - Level tolerances Scale A:
note | • Range x = +4, -8mm
note | • Max S = 8 mm
note | • 80 measurements per lot
note | ○ Level tolerances Scale B:
note | • Range x = +6, -12mm
note | • Max S = 13 mm
note | • 40 measurements per lot
note | ○ Level tolerances Scale C:
note | • No point on the subbase surface shall be more than 10 mm above or 25 mm below the specified level.
note | ○ Attach: Survey Conformance Report/Data
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - SE/Surveyor
note | Verifying Documents - This ITP Signed-off
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 6.4 - Surface Inspection - Cracks (Concrete Base)
note | Reference - Section 610.24
note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
note | Method - Visual, Measure
note | Frequency - Each element
note | Category - IP
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 6.5 - Surface Inspection - Surface Finish
note | Reference - IFC Drawings
note | ○ Section 610.31 (a) - (n)
note | ○ Section 610.32
note | Acceptance Criteria - Comply with the IFC drawings and specifications.
note | Method - Visual
note | Frequency - Each element
note | Category - IP
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 6.6 - Measurement of Concrete Cover
note | Reference - Section 610.34
note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
note | ○ Minimum 10 no. measurements recorded in each area.
note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
note | ○ Attach: Covermeter Check Record
note | Method - Measure
note | Frequency - Each element
note | Category - IP
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 6.7 - Compressive Strength & VPV Test Results
note | Reference - IFC Drawings
note | ○ Table 610.051
note | ○ Table 610.061
note | ○ Section 610.16 (g)
note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061.
note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
note | Attach: Compressive Strength Test Results
note | Method - Document Review
note | Frequency - Each cylinder
note | Category - HP*
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | 6.8 - As-built Survey
note | Reference - IFC Drawings
note | ○ Section 610.46
note | ○ Table 610.462
note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
note | ○ Attach: Survey As-builts / Survey Report
note | Method - Document Review
note | Frequency - Each element
note | Category - HP*
note | Responsibility - Surveyor, SE/PE/SPE
note | Verifying Documents - This ITP Signed-off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP