## FRP
Structure – FRP Strengthening
notes
Pre-Start
Ensure necessary permits and approvals are obtained
Check for documentation for material certifications and test report
Check storage conditons for FRP components
confirm site ready to receive FRP (eg. Clean, dry, free of contaminants)
Confirm approved FRP installation procedures
Safety
Clear access
Workers PPE
Safe working platform; safety sign boards etc
Installation
Surface Preparation (bare concrete exposed- to repair >0.3mm width cracks)
Inspect adhesive mixing process
ensure overlaps (min. 200mm) and sealed joints.
Inspect installation of anchors and fasteners
confirm spacing and alignment.
Structural Eng inspection report received and close-out
Post Installation/ Curing
Confirm adequate drying time (48 to 72hrs)
Conduct thickness measurements to comply with design specs
Do visual inspection for defects/air pockets and irregularities
Documentation
Specialist Installer QA/ITP submission
Document any deviations from the installation plan

## Insitu
Structure – In Situ Concrete - others
Pre-start
Foundation sign-off/QA received
GL and datum provided
Clean work area
Review construction drawings and setout
Pre-pour
Service trade sign off/QA | tickbox
i. attached mark-up
Formwork signoff/QA
Reo sign off/QA
GN inspection
i. Drawings UptoDate, check for CAN's | tickbox
ii. Reinforcement details checked | tickbox
iii. Scabbling, Starters/ embedment depth, cover checked | tickbox
iv. Clean formwork, seals and ready for pour | tickbox
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Access/safety
Access for trucks/pump
Safe access to all areas of pour
Exposed reo capped
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Post Pour
Checks
i. Finish | Tickbox
ii. Levels | Tickbox
Pour QA received including concrete dockets