## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Structure - In Situ Concrete - others
section | Pre-start
checkpoint | Foundation sign-off/QA received
checkpoint | GL and datum provided
checkpoint | Clean work area
checkpoint | Review construction drawings and setout
section | Pre-pour
checkpoint | Service trade sign off/QA
bool | i. attached mark-up
checkpoint | Formwork signoff/QA
checkpoint | Reo sign off/QA
checkpoint | GN inspection
bool | i. Drawings UptoDate, check for CAN's
bool | ii. Reinforcement details checked
bool | iii. Scabbling, Starters/ embedment depth, cover checked
bool | iv. Clean formwork, seals and ready for pour
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | Access/safety
checkpoint | Access for trucks/pump
checkpoint | Safe access to all areas of pour
checkpoint | Exposed reo capped
section | Pour
checkpoint | Confirm mix
checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint | Weather recorded
section | Post Pour
checkpoint | Checks
bool | i. Finish
bool | ii. Levels
checkpoint | Pour QA received including concrete dockets
checklist | Structure - FRP Strengthening
section | Pre-Start
checkpoint | Ensure necessary permits and approvals are obtained
checkpoint | Check for documentation for material certifications and test report
checkpoint | Check storage conditons for FRP components
checkpoint | Confirm site ready to receive FRP (eg. Clean, dry, free of contaminants)
checkpoint | Confirm approved FRP installation procedures
section | Safety
checkpoint | Clear access
checkpoint | Workers PPE
checkpoint | Safe working platform; safety sign boards etc
section | Installation
checkpoint | Surface Preparation (bare concrete exposed- to repair >0.3mm width cracks)
checkpoint | Inspect adhesive mixing process
checkpoint | Ensure overlaps (min. 200mm) and sealed joints
checkpoint | Inspect installation of anchors and fasteners
checkpoint | Confirm spacing and alignment
checkpoint | Structural Eng inspection report received and close-out
section | Post Installation/Curing
checkpoint | Confirm adequate drying time (48 to 72hrs)
checkpoint | Conduct thickness measurements to comply with design specs
checkpoint | Do visual inspection for defects/air pockets and irregularities
section | Documentation
checkpoint | Specialist Installer QA/ITP submission
checkpoint | Document any deviations from the installation plan