## Checklist Templates
Id | Type | Name | Values | Prompting Name
9ba0620f-3600-43e0-ba33-6f340eb77671 | checklist | QA - 2 Sided Structural |  | 2 Sided Structural
a10dfc54-a85a-4fd8-8f12-b9dc5030dc95 | checkpoint | Frame prep
af6861d8-9c7b-4aaf-9ce4-3406cb410bb4 | checkpoint | Structural taping
15b3771d-277d-448b-b99f-0f8e57a9ab85 | checkpoint | Glass installed per structural submission
4ae5e6e0-7efd-5e63-91e6-53997539c447 | note | Pre-check edgework & any markings on glass
45ae458e-1140-48fe-9a7b-ad00cc8a2c9d | checkpoint | Beads installed
fd239154-f923-48a3-baa5-f1cd2b6e5969 | checkpoint | Ties installed
51c0a933-b454-46a3-81db-951f886ea188 | checkpoint | Structural silicone
6643abad-01d7-42bf-9549-c1185014bfe9 | checkpoint | Trade clean
4eeb0133-679f-4029-8f8f-3f41971c5594 | checkpoint | Ties removed
02b55767-ef07-4814-b9f8-e83764693490 | checklist | QA - Ballustrades |  | QA - Ballustrades
ebe581be-79e1-4de6-9a56-66fbeb1c6121 | checkpoint | Fixings drilled & chem-set
7f2af103-acf3-5808-bb32-1900c955c262 | note | timber: coach screwed with sika-fix
38895f8a-6270-42cb-abd7-0e0dd69ae148 | checkpoint | Hardware installed per PS1
11ce906b-65e1-56fe-a3b8-921d81dadb27 | note | Re-tension fixings & check hardware for damage
c1be2f10-556c-48f2-b5fa-0d102b23369c | checkpoint | Glass installed & plumbed per PS1
e4d778ed-3dc6-55d4-91f2-b8e51167d393 | note | Pre-check edgework & ensure gaps are even
dc8b873d-359c-4224-a23a-7b473826456b | checkpoint | Hand-rail / link-rail installed
6529ce9f-9b63-40ea-bad3-0e5a0692d122 | checkpoint | Cover Caps and end caps Installed
d86b850d-4d6b-4385-93d1-d0b80d3232ce | checkpoint | Trade clean
3444a99a-69b8-474e-862f-1a279dc00d1a | checklist | QA - Canopies |  | Canopies
1672347e-0010-4277-aade-76ca231058a9 | checkpoint | Install hardware per PS1
9b5d2520-7154-597f-ae90-075f1ea7e5fd | note | Ensure fittings & swivel heads bolted tight
e5cb80c7-75fe-4983-b794-c98b50d3e4b8 | checkpoint | Glass installed & aligned per PS1
b42c3e08-32d1-5644-9798-7a0e5f648494 | note | Check edge-work & unit marking
666c2a11-93b7-43ad-8bee-88b78acba2da | checkpoint | Silicone joints
cf66d7e5-9a90-44d5-94a4-4a5588c94e79 | checkpoint | Trade clean
23e5626d-4f50-4768-a3db-da41adb7e117 | checklist | QA - Captive Glazing |  | Captive Glazing
16d79d94-3903-4038-b569-681b1aa533c8 | checkpoint | Frame prep
cf6f8214-e641-5026-be55-ec28d6505a9e | note | Ensure setting blocks @ quarter points
bd66ad66-d603-4c52-beed-c84870eae882 | checkpoint | Glass installed correct way around
bd3c2621-1838-583f-9e02-d4614abab3e4 | note | Check edge-work & unit marking
53fa4fa2-e24d-45b7-8e0d-4b8fd9427bc0 | checkpoint | Beads installed
69a3e5c9-41c1-4024-a97d-8cff1942b8c5 | checkpoint | Wedge installed
be048a3e-435f-58f1-a25c-8dca34139c60 | note | Correct wedge per specification
a04e665a-9719-4048-a145-8df078e69d25 | checkpoint | Trade clean
792d3a74-0ba7-49a5-8590-fc1d7446d7f8 | checklist | QA - Captive Skylight |  | Captive Skylight
f5fe5b16-56ba-430c-9e5a-7eef1a13d0d8 | checkpoint | Frame prep
3ecdd06f-32a9-56bd-8351-16d33178236e | note | Ensure setting blocks @ quarter points
0550e3c8-7c90-4ddf-81c2-31ddc188b403 | checkpoint | Check feet are installed
82d23771-08d3-4ecc-b947-9d071dcb7233 | checkpoint | Glass installed
4622ef1d-7353-41f3-91f5-6967474f0cb3 | checkpoint | Beads installed
da0ddde5-06fa-483b-8bed-bb836013c95c | checkpoint | Correct wedge installed
9dc728d7-8d17-4594-8710-9dbce537a9b9 | checkpoint | Silicone joints
1ad1d5a9-a061-44d6-b8c3-c87da1436671 | checkpoint | Trade clean
19fa7750-dbe5-4ccf-8e58-2409fb730a48 | checklist | QA - Framed Fixed Glazing |  | QA - Framed Fixed Glazing
af9f978a-f269-4230-b2a3-4e9dad106745 | checkpoint | Channel for fixed panel installed correctly
629aa2da-fd80-5f23-8701-ff4b1b35d9cc | note | Check screws installed correctly
26c68614-a94a-571c-b6ec-75ed9ee112a3 | note | Check for damage
d8c42e92-5686-4f36-a8d1-9ff6fb8d540d | checkpoint | Backing wedge installed
4412073a-e2c7-433a-b4cc-cbe6fee68d3b | checkpoint | Glass installed correct way around
d8758292-682c-5ca2-8e95-4e588a94ca6d | note | Ensure setting blocks @ quarter points
51608391-5c6d-5f5b-89e9-8bcded6a54c6 | note | Check edge-work & unit marking
05a7a6ee-7f8f-4373-a3a1-50e2204a8e97 | checkpoint | Beads installed
56f1b9a0-b23e-48e0-9ad1-6ea9dc4dedbd | checkpoint | Wedge installed
a3c5f313-c0f0-5a02-a62d-c14953583ab7 | note | Correct wedge per specification
187d1a22-93ce-4908-a16f-2df19ba87878 | checkpoint | Silicone joints completed
bb56350f-5ca8-4d7c-a4a2-1f38ee3c5da6 | checkpoint | Trade clean
33f71324-f3d0-4986-8098-a7c07c701411 | checklist | QA - Frameless Auto Doors |  | Frameless Auto Doors
f63f9707-bde9-4307-85a4-45cbe1a76e90 | checkpoint | Hardware installed
54b77993-eee4-499b-bdfe-3daebfcf614d | checkpoint | Glass installed level & plumb
df484dd4-d049-44ca-b9b1-cc5c652179eb | checkpoint | Check gaps are even
5b523103-f950-4da9-9e87-e654bd9d3d5f | checkpoint | Trade clean
f083fb0b-6704-4252-afcd-9417f9ef629d | checklist | QA - Frameless Doors |  | Frameless Doors
ef308dcd-31df-433b-b9be-1831902bb7cc | checkpoint | Channel installed
fbcc1f25-70bc-540d-ad49-8fe8c7287b63 | note | Check alignment per plans & check for damage
a0307595-04c2-41f2-95ed-61113e60154b | checkpoint | Hardware installed
68dd3294-0126-59fd-b983-20e59987d909 | note | Check for marking
ca20ef54-1340-4273-9478-4bca62a142a8 | checkpoint | Check gaps are even
6308ba30-75e8-4564-aa66-3d0be45f0117 | checkpoint | Glass installed
a1ff8970-2b25-4deb-b32d-ecd570eb4218 | checkpoint | Silicone joints
4f547536-39b2-47e1-bb08-3e17f97a5118 | checkpoint | Trade clean
c727103b-4c3c-4c36-bbfd-82a8a5cc7e1d | checklist | QA - Frameless Manual Sliding Doors |  | QA - Frameless Manual Sliding Doors
c4c1c162-1ff6-4047-90f7-8445423af99c | checkpoint | Top Tracks installed correctly
911ba1a5-31d8-5e9a-b7a1-e2c8d72a447e | note | Check screws installed correctly
ddf98eb1-ad31-4196-9f73-376f5f7c93f1 | checkpoint | Bottom tracks installed correctly
8745cd73-25ba-5123-9c3e-a0b0d72003ab | note | Check plastic insert is installed
c8f42486-167f-4fc8-a2c8-daa1a1968593 | checkpoint | H Packers cut back and painted
d73ed5f4-9d82-41e5-870e-fb2f331cb2fb | checkpoint | Door rails installed correctly to the glass
53140f9d-3e2f-4ab1-ac44-fbad5c012295 | checkpoint | Covers, end caps and pick ups installed
b800f5e8-f925-4489-b1f4-073396e5437b | checkpoint | Handles installed
767b3931-80e7-4e13-aa22-17e1702bdc77 | checkpoint | Channel for fixed panel installed correctly
5001eb1c-c91c-53d3-85f8-10ebbe92868f | note | Check screws installed correctly
305af284-4cc2-595f-9c50-0689308cf628 | note | Check for damage
5737d599-4d50-45ad-84e7-3ed1c2916f46 | checkpoint | Glass installed correct way around
5a465e78-88b3-5710-b916-4ed93e4b68b4 | note | Ensure setting blocks @ quarter points
d28c7252-4e8a-5e41-9587-6a558061c353 | note | Check edge-work & unit marking
2e0dea59-78fa-43db-beb9-5e50bc6b4e5a | checkpoint | Correct wedge installed
7a329cc2-0d8b-5388-8398-60d93ac4d30f | note | Check tight fitment
30967a8a-ae60-4567-a32d-e06c1d44c2f1 | checkpoint | Silicone joints completed
4eb72556-4398-458c-8369-fc7e5a08a084 | checkpoint | Trade clean
a55bd02b-99f5-44bb-ab41-4f246e92e70c | checklist | QA - Internal Glazing |  | Internal Glazing
a28059c0-7c37-41cd-a759-b02ab08f3ed2 | checkpoint | Frame prep
58d8e2e6-25ab-519d-8000-091272880ee0 | note | Ensure setting blocks @ quarter points
57fd627a-6447-4e46-b14e-4fea3309a4ab | checkpoint | Glass installed
9603afcc-72ee-4743-9252-720ff8085e68 | checkpoint | Beads installed
c68e1c91-d0f1-49d4-8468-1aecc949b4ec | checkpoint | Correct wedge installed
cf9b77b2-4d2f-46b0-9d8d-ef9457128a73 | checkpoint | Silicone joints
245e6fcd-9622-4739-ae39-0bcc836623f9 | checkpoint | Trade clean
5c7f43c0-e70b-4e17-b219-4a40a4b0037e | checklist | QA - Mirror/Splashbacks |  | Mirror/Splashbacks
2161f328-1541-40a9-8c68-7af931d809af | checkpoint | Surface prep
1b437a9b-1767-44ad-9262-9c9647f8ef1d | checkpoint | Glass installed
846fe988-b244-42ef-9c3e-571416481031 | checkpoint | Trade clean
43ab5d0f-1054-4aad-b505-0f5552a97ea3 | checklist | QA - Showers |  | Showers
6beade9b-4400-44b4-9909-4bece929102d | checkpoint | Channel installed
45959ffb-c1c8-59da-9c61-4b4d8b647adf | note | Check alignment per plans & check for damage
7f85092a-b3a7-4a5d-806e-833e153293a4 | checkpoint | Hardware installed
66d30591-4d81-54e2-9aa6-138e7ce833a9 | note | Check for marking
6ccfd93c-8c01-43f8-999f-2ace185df305 | checkpoint | Glass installed
9b8e7677-4968-530c-9b92-6926c3259ea5 | note | Check quality, safety stamps & gaps are even
faf40a78-94d4-41e6-8680-ed3aaa8deb09 | checkpoint | Silicone joints
055092f6-f484-4176-95a2-4532ce058e0a | checkpoint | Trade clean
e1fe79cb-99dd-40ee-8ba4-1a752f2427b2 | checklist | QA - Spider Walls |  | Spider Walls
ff1ea9d5-9c58-4a02-8c13-4d388a979f50 | checkpoint | Install hardware per PS1
2cc3d4e5-e192-57b9-843e-99accbff44ff | note | Ensure fittings & swivel heads bolted tight
bffaed8d-3c8c-46fb-8c12-568da7f00443 | checkpoint | Glass installed & aligned per PS1
af078006-19a5-536b-8c01-ef68562ba257 | note | Check edge-work & unit marking
f25ac75f-c199-4cae-a58e-36b9c5dbd48c | checkpoint | Silicone joints
44400ef3-1aeb-4563-ba7d-69a161f8c32b | checkpoint | Trade clean