## Checklist Templates
Id | Type | Name | Values | Prompting Name
153ea7e4-ee87-420d-9f6d-628d085be60f | checklist | QA - 2 Sided Structural |  | QA - 2 Sided Structual
7e02a41c-254e-42bb-b43c-1a1e05e8248d | checkpoint | Frame prep
36be8560-0ed8-49b8-a625-65f86438d4cd | checkpoint | Structural taping
0f726cd8-299f-4533-838f-8f57305aee40 | checkpoint | Glass installed per structural submission
d661dac5-faa5-5293-9e5e-d371a97d0428 | note | Pre-check edgework & any markings on glass
c502c0c7-ab84-42f3-99c9-1492aac978c7 | checkpoint | Beads installed
f8559e66-29d3-42bb-a88c-03e83565febb | checkpoint | Ties installed
6b26993b-2525-4dd9-910f-3aa542227616 | checkpoint | Structural silicone
748b3e4c-3a2b-469e-abfd-aa555f20f825 | checkpoint | Trade clean
6d33fe3a-983d-4c59-85e7-7a2912c06f10 | checkpoint | Ties removed
4970c8f3-1b92-45ae-bf2c-fe2a558e2364 | checklist | QA - Ballustrades |  | QA - Ballustrades
d63fcf95-57e0-4785-b762-d085b3e23d49 | checkpoint | Fixings drilled & chem-set
72aecca6-5953-5cab-b50b-4ba7d537867c | note | timber: coach screwed with sika-fix
3e7d4566-0bab-4e70-9c20-3b8861cdbea7 | checkpoint | Hardware installed per PS1
58568015-892e-5125-a337-30681e403e0c | note | Re-tension fixings & check hardware for damage
75ac3372-bc69-496a-a4b5-f40093911b11 | checkpoint | Glass installed & plumbed per PS1
62ffcc9e-270c-55c6-b5ff-74c722484d37 | note | Pre-check edgework & ensure gaps are even
a666aec1-df6e-4141-817d-77b9540a675b | checkpoint | Hand-rail / link-rail installed
52bec8d0-270c-4fed-b159-b6e2c4363bf9 | checkpoint | Trade clean
b1c0e849-ae2f-4b6e-989b-e00ec8b13cc8 | checklist | QA - Canopies |  | QA - Canopies
df4c69a8-fd2d-4c1d-9d89-3fd4cadfbf45 | checkpoint | Install hardware per PS1
912bd00b-9856-54c5-b704-6ec22d915e03 | note | Ensure fittings & swivel heads bolted tight
bc22e7fd-d912-4e22-9fb2-f3ad875d08bf | checkpoint | Glass installed & aligned per PS1
7a282a82-9c07-56f0-94ba-e17a32908de3 | note | Check edge-work & unit marking
a5be3f05-b27b-4477-bded-56a7d0ded68d | checkpoint | Silicone joints
6816457e-277c-436b-94c4-fa1db6447983 | checkpoint | Trade clean
5da8045b-193a-408e-838d-3751ce3e3197 | checklist | QA - Captive Glazing |  | Captive Glazing
33a98ddd-7093-4684-b77f-fdd2fa7054f2 | checkpoint | Frame Prep
cc09c556-0ae8-5929-9853-3c2302e0c61e | note | Frame Clean Of Debris, And Setting Blocks At Quarter Points & Not Blocking Drain-Holes
49720836-219b-4f73-9884-83a1f029c6cc | checkpoint | Glass Installed
32231c76-982c-57d0-aad5-bf8cebc8dfa0 | note | Check Edge-Work, Unit Marking, LowE Orientation Correct
83f2885e-1b6a-4686-8a62-f8c07d44fcb0 | checkpoint | Beads Installed
14b6839c-9b36-4bf2-8a7e-751c0b9f5dcd | checkpoint | Wedge Installed
74b13482-c947-5864-9e2d-56e7c9e11459 | note | Correct Wedge Per Specification
623efced-3ff4-4147-ae6e-d87de215ee8e | checkpoint | Trade Clean
49790b2c-2159-5dc6-be19-c6eb07af76f4 | note | Window Trade-Clean And Room Tidied Of Glazing Debris
9897e092-b67a-48d8-8c3b-29170feb46aa | checklist | QA - Frameless Doors |  | Frameless Doors
d8f08a04-8368-4e27-bf16-6f48ec67ae34 | checkpoint | Channel installed
2a3c4984-2a8d-5d36-aa95-35363b96ba67 | note | Check alignment per plans & check for damage
4fb3e6c4-3d4c-4db6-b673-9cfe29f0a7c9 | checkpoint | Hardware installed
f3669dfe-d3b4-5fe7-b3d3-c551ee8113c0 | note | Check for marking
9beb0dfe-b0e4-437e-a7fa-bd7605f13277 | checkpoint | Check gaps are even
0a5ba40c-d492-4589-ac60-cb39f42e3a29 | checkpoint | Glass installed
f87a85bb-15f6-4b63-bed1-8696879edff5 | checkpoint | Silicone joints
e0c968e3-d732-4dc2-8f0d-4e577a9ac896 | checkpoint | Trade clean
e5227133-1f3d-4a90-81e9-8b539645160f | checklist | QA - Mirror/Splashbacks |  | QA - Mirror/Splashbacks
024ac361-d7fa-4a3c-a684-0ebdd9920b5d | checkpoint | Surface prep
69e2783d-8c03-43f3-8353-74f97805f53c | checkpoint | Glass installed
27707d3e-8305-4c75-a808-492abbbfc5d8 | checkpoint | Trade clean
eb05738d-1878-4039-b869-bb9dad804f9e | checklist | QA - Retrofit Double Glazing |  | Retrofit Double Glazing
b5455664-9613-46cd-9966-72352ee64171 | checkpoint | No obvious damage or blemishes to glass
8181ea37-bdcc-430a-8900-a8d29811f24f | checkpoint | All opening windows fitted and closing correctly
1b8f682e-628f-4bdc-b31e-11c4561ceb05 | checkpoint | Acceptable quality of finishing on new beads
1dfbb480-ff1f-4b77-9275-5a15c329cc35 | checkpoint | All window sills clean and clear of shavings
559dd969-4451-4317-8dda-a6027dba8401 | checkpoint | Doors are sliding and closing freely
180dd345-d8c8-42b3-80e6-aa2216b2c5e4 | checkpoint | I All work areas have been left clean and tidy
63493dc9-8737-41f6-b710-91b4a799728b | checkpoint | Any concerns have been discussed and addressed
8ef55a53-828f-498e-b599-e9643c475799 | checkpoint | All units requiring rework have been identified and will be ordered
f0a71235-cd28-4bd6-8682-608e6e8ef28a | checkpoint | Any additional work/hardware requested/completed
2e57cda9-54bb-409a-a1de-96e611da07d1 | checklist | QA - Showers |  | QA - Showers
6085744d-c529-4bca-89ef-bdd3235e6e4b | checkpoint | Channel installed
d3f9e121-2803-5c89-9dbf-af00189bdb5b | note | Check alignment per plans & check for damage
144abbe9-8bf1-4193-b6f7-2b3642d93a11 | checkpoint | Hardware installed
50be0dff-38c8-54c5-81ee-26f5d07c2575 | note | Check for marking
467bba6f-a634-4c44-ba82-a17907c071cd | checkpoint | Glass installed
a13d5d10-8ec1-5ddb-9c75-4b61d7bcec0d | note | Check quality, safety stamps & gaps are even
06518421-4cd9-4864-a046-52fb827fc784 | checkpoint | Silicone joints
3c8416a7-5a8d-45de-b6ad-a7ef2d8798ad | checkpoint | Trade clean
9c7efa52-a3f0-41ad-86a5-26af10768f65 | checklist | QA - Spider Walls |  | QA - Spider Walls
01a994f7-f569-46ea-b1a7-30c8558a37d8 | checkpoint | Install hardware per PS1
b83fef2f-59e1-54d7-a654-13fe458a643b | note | Ensure fittings & swivel heads bolted tight
aacff3af-6dec-46d4-a596-1b0b53481f60 | checkpoint | Glass installed & aligned per PS1
75af2eb1-b9d0-521a-92ba-713914b9a287 | note | Check edge-work & unit marking
886e232b-9565-4567-92b5-ababc5fd99af | checkpoint | Silicone joints
940b4675-8859-42b0-8fdb-0ad575ecd9ef | checkpoint | Trade clean