## Checklist Templates
Id | Type | Name | Values | Prompting Name
542e4b7f-af55-4eaa-804f-675307b78dab | checklist | 2 Coat Checklist |  | 2 Coat Checklist
90c7ab9e-a300-4c9b-875c-38c465b98e1c | section | 2 Coat
b991d643-8670-44b2-aac0-1b6d4c2f544c | checkpoint | Surface conditions suitable for installation - details in comments below
2e6319b5-3b36-49e1-affb-675c63874bbd | checkpoint | Moisture test complete - result in comments below
a1318a6e-0b11-5e88-8fa3-b044c7b69182 | note | Must be below 5% to pass
25cff9aa-341e-4905-988e-47064adb84e7 | checkpoint | Substrate inspected and accepted
969a5083-988f-5c74-a5fe-df74ef3e7900 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
a8c4e706-8e58-42da-8aa7-20c6da3674aa | checkpoint | Application of Primer as per specification
fbe21cc8-fd49-5975-b7c4-cbd2d9495dc8 | note | Cementious Coving completed (if required)
f3121801-f015-49ac-85b1-0c115826f849 | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
156515c5-6bb6-43e5-baff-3bc249586b16 | checkpoint | Application of membrane as per project specification - 1st Coat
870834a8-8279-5606-853b-c9b1005ba3ac | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
2bdcaa8f-501e-4c7a-baf8-6038232e1eea | checkpoint | Application of membrane as per project specification - 2nd Coat
aef23c5a-d6bc-55aa-b34f-e6350d20b695 | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
9fdec97e-329b-46d3-9505-b3cc991b036f | checkpoint | Additional products / elements installed - selected all that apply below
f2b8560b-742f-5b67-888b-bd021dcf3cb2 | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
eab1f670-b0b6-56dc-934d-b69d47ccf85b | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
47193555-450e-5d8d-a6c0-c0065310015d | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
2bf9a7fd-b802-4a2e-9f9d-f952fe42f681 | checkpoint | Final DFT Thickness of Membrane
aeb8710e-0a7f-4201-aa72-2933cbbf3268 | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
de73f275-84ff-49f8-a534-2554aa3d411f | checkpoint | Test 1 Flood Test Pass/Fail
d6a91d11-1d85-4dc1-9d38-72c846374b14 | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
8c08de73-0727-4cb5-aebd-8f930e99f7a6 | checklist | 3 Coat Checklist |  | 3 Coat Checklist
8b2fe9c6-fe16-4f44-8938-16552fca95a1 | section | 3 Coat
63f004a4-9870-415b-a6b6-4450b72fa16c | checkpoint | Surface conditions suitable for installation - details in comments below
e7517584-cb3d-47d9-a96a-bc4039ac0137 | checkpoint | Moisture test complete - result in comments below
31504a12-0364-57a3-8a1e-0dc58d647026 | note | Must be below 5% to pass
55ec54fc-3115-45fd-a716-8524bea9c74c | checkpoint | Substrate inspected and accepted
6815fc0a-7336-5e61-b1ac-5608fb1b5ad0 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
b13fc695-c956-438c-8db3-7f956a2ca176 | checkpoint | Application of Primer as per specification
761ef192-bb60-4d2a-bc5c-eab80155c3bb | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
3520704c-649e-47f7-826a-1b76e706c614 | checkpoint | Application of membrane as per project specification - 1st Coat
c2508ca5-78bf-5602-aab7-4b7bd4b93baf | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
b8344372-bada-424a-aff2-d886438d64ab | checkpoint | Application of reinforcement sheet (if pedestal pavers)
cf5ffb4a-8bc9-4c5b-8413-bae176b2db1d | checkpoint | Application of membrane as per project specification - 2nd Coat
23ae7af1-b7dd-5d39-ac96-d7287a34127b | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
b8b58158-8be6-448a-9bca-32074260afee | checkpoint | Application of membrane as per project specification - 3rd Coat
0ba4a9d3-9ccc-5dad-beff-f4540714eed2 | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
294593d7-dc19-4350-866c-115e95d29f82 | checkpoint | Additional products / elements installed - selected all that apply below
c23d98ca-8038-5335-ab8a-d015d4509e92 | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
9879e516-aaee-5f23-bd58-1b6046ed4507 | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
16f558bc-37be-5c9b-8cfd-8910a26af7e4 | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
eff7f464-b6a3-424a-b285-3cf960664cc9 | checkpoint | Final DFT Thickness of Membrane
d4937768-be9e-4317-a05e-8d7ff269834b | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
86c4c942-5551-43dc-a147-8d2768b56828 | checkpoint | Test 1 Flood Test
989ad2df-a070-4652-9e67-e8454d0a4417 | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
299618e9-d9cf-4677-baff-84cc206065fd | checklist | Balconies Checklist |  | Balconies Checklist
67ef0412-0845-437a-95b0-3705d29c070b | section | Balconies
50c9dcb4-e1f2-44d7-a865-62e616ca0afe | checkpoint | Surface conditions suitable for installation-details in comments below
cba4805e-95b2-416b-aef1-b4f7db79105d | checkpoint | Moisture test complete-result in comments below
31fe6c30-4c5d-51c4-bb2a-41530c8876ee | note | Must be below 5% to pass
856ae83d-0921-4123-8a14-eca8a7bf825a | checkpoint | Substrate inspected and accepted
bd807c58-d64d-56b4-aa4f-b664701bb87c | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
2a616883-68bf-4091-976a-0ebe23160760 | checkpoint | Application of Primer as per spec
61fad653-7e16-406b-8987-530f43c48c29 | checkpoint | Application of Caulking or Bandage (if required) completed
d9c58956-1e9f-4db8-abee-548a6bb0a205 | checkpoint | Application of membrane as per project spec-1st Coat
d1206547-987c-4a43-98f6-a7222aac56af | checkpoint | Application of reinforcement sheet (if pedestal pavers)
deb3b6d1-19db-4c55-88d9-bac2ab321905 | checkpoint | Application of membrane as per project spec-2nd Coat
4bed16c0-d925-459f-896f-1db072e5f11b | checkpoint | Application of membrane as per project spec-3rd Coat
f2d9d962-710e-4889-a4b5-a6e900bd1f29 | checkpoint | Final DFT Thickness of Membrane
25d73f01-6ac2-40e3-a7d3-4ddd3e2be5d3 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.
82f8f06c-6d65-4d65-be30-7ccb5ff16053 | checkpoint | Test 1 Flood Test Pass/Fail?
5199556d-b5db-449f-884e-9539b98d265a | checklist | Epoxy Rooms-Hychem Hy Flake Checklist |  | Epoxy Rooms-Hychem Hy Flake Checklist
5e9410db-7003-4c53-b652-8f6e8f901be4 | section | Epoxy Rooms-Hychem Hy Flake
d4387b5b-c500-406e-8d02-a8cfb4dfb922 | checkpoint | Substrate inspected and accepted
f9f20dae-eaa9-512c-a01d-6a7068001de3 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
9ebf03a3-4c3a-496a-9e7a-febeb654fa33 | checkpoint | Atmospheric conditions
35e0f9c7-2f28-5df5-b82f-7a2c3180c437 | note | Note ambient temp, Relative Humidity, Dew Point
64a1c9db-8f77-49a9-ac60-386a553bc807 | checkpoint | Product Batch Numbers
a7b8ebba-8e23-5f5a-a111-37a0555623ae | note | Note batch numbers for products used
485db6fe-5ad3-4d32-bf9c-0d2d15d7a8ea | checkpoint | Equipment used
eb1e2e9f-06b7-5920-b84b-1d299af4d709 | note | Note equipment used like rollers etc.
8f7e66c9-d65d-4b19-a0d1-1d0a3c2700c0 | checkpoint | Apply Clear coat and Flakes
1faaaaa4-6b7a-5b4b-b4bd-a4d7f4bab9e4 | note | Apply Clear epoxy coats and Real Stone Flakes
159d31dc-8064-417f-a88f-a56288d77df5 | checkpoint | Apply Topcoat with non slip grit
f0a5d228-7814-5bc2-9ccc-77eacbc874f9 | note | Apply Topcoat with non slip grit
04209a83-4672-452e-810f-66450358b261 | checklist | External Liquid Membrane Checklist |  | External Liquid Membrane Checklist
00c9afca-394e-4292-ad26-f6b30beb7a79 | section | External Liquid Membrane
e7e8fe93-381b-4467-b851-fc6e25e28931 | checkpoint | Surface conditions suitable for installation-details in comments below
86977fe8-e857-4432-9a8d-169bb9a94f1e | checkpoint | Moisture test complete-result in comments below
7cb986ad-3527-57b1-8b95-472d1ca3cec5 | note | Must be below 5% to pass
455439dd-2c3a-49c6-9514-280a333bdd8b | checkpoint | Substrate inspected and accepted
f4196e28-8dfd-5b97-b56a-d6f2e7b9fcf7 | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
8172b8af-57bf-4afd-9f6a-61126eac2b74 | checkpoint | Application of Primer (if required) as per specification
8a75bc2f-41fc-43f3-869e-49ca6331b70a | checkpoint | Application of Caulking and or Bandage (if required) completed
c7016d27-d624-47f4-910b-220a62ac5c5d | checkpoint | Application of membrane as per project specification-1st coat
71e4c01c-2549-4014-927e-679dce59c490 | checkpoint | Application of membrane as per project specification-2nd coat
7a64d3c2-60dd-49e0-a640-72be5f6deb9d | checkpoint | Application of Anti-slip UV stable top coat (if required)
2bc79a6d-3f52-469c-b8c1-3d20f6254afb | checkpoint | Final DFT Thickness of Membrane
61e715a4-b142-47e8-b476-a30588f2bf1a | checkpoint | Installation of Corlute Protection Board completed (if required)
d59db1f6-39da-4f48-8a65-c38e5db3d778 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
fbd2c9fd-6fd7-4b3d-a761-cc480291c371 | checkpoint | Test 1 Flood Test Pass/Fail
9770d212-b77e-4be2-8ab1-3a56438ce92e | checklist | Internal Wet Areas Checklist |  | Internal Wet Areas Checklist
22a0af56-961c-442b-a68e-1c91a252b8b8 | section | Internal Wet Areas
5d4dc749-2266-44c7-8b48-97bcd8b0c044 | checkpoint | Surface conditions suitable for installation-details in comments below
1b7fe15a-2de0-4770-9745-d38f24badff2 | checkpoint | Moisture test complete-result in comments below
412441ee-9dde-5ed5-b707-42a2676c1b96 | note | Must be below 5% to pass
0c5e04bc-1101-44b3-b32a-5d09e14cc3eb | checkpoint | Substrate inspected and accepted
518c06ff-da30-51f3-bcf3-7dbb7839fe43 | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
978821f1-b70d-4778-88b2-1ae73b5ab891 | checkpoint | Application of Primer as per specification
151dfbab-0351-4257-a108-ff67e675292e | checkpoint | Application of Caulking and or Bandage (if required)
a24d6110-09e1-4742-965b-d2bb7f224069 | checkpoint | Application of membrane as per project specification-1st coat
182024d4-1058-4091-979f-5bdc6bd0ae68 | checkpoint | Application of membrane as per project specification-2nd coat
e16581b9-23b3-4056-b402-c10b6eebbd2e | checkpoint | Final DFT Thickness of Membrane
4412baf4-4769-46e7-9cdb-d1dd1c0f35d5 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
aef13e38-b310-4ee5-b6d9-32ce6126ec7a | checkpoint | Test 1 Flood Test Pass/Fail
73ea7384-6196-4c82-ad5f-330ae3d4bea5 | checklist | Planters Checklist |  | Planters Checklist
07626e60-b11e-4e16-9e1e-69ca0b985385 | section | Planters
64c712d1-cfd6-43a9-8cb2-623237fce7f0 | checkpoint | Surface conditions suitable for installation-details in comments below
61058c7c-b4cb-449d-8226-dd2aadd8af05 | checkpoint | Moisture test complete-result in comments below
d2a23abf-b9de-503c-8193-2cac8774029f | note | Must be below 5% to pass
d4981979-4d31-4cdd-a796-6ac7b3383354 | checkpoint | Substrate inspected and accepted
0cf16084-4a3e-5b5d-8c99-5639711679de | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
cd0dcc41-5059-461a-9cc5-db34507c7ba6 | checkpoint | Application of Primer (if required) as per specification
a35a070b-f0f6-4256-836c-0763a4f6aeb1 | checkpoint | Application of Cementitious Coving (if required) completed
728338bd-d6fa-494d-826f-59e9f51bc93e | checkpoint | Application of Caulking and or Bandage (if required) completed
43e56735-ab37-4833-bdb0-426c507d8b4a | checkpoint | Application of Membrane as per project specification-1st coat
e3b44014-2430-4776-9b18-4a7a14444524 | checkpoint | Application of Membrane as per project specification-2nd coat
a81c2ccc-3966-45b2-a81a-2ef018d59763 | checkpoint | Final DFT Thickness of Membrane
1988b9c0-cf4a-4b60-84f2-3ae0dfc157aa | checkpoint | Installation of Corflute Protection Board Completed
e382843e-bc74-4a7f-9784-4b2fa1aabc31 | checkpoint | Installation of Drainage Cell Completed
7955ffd8-4eae-4343-addf-60dadf1e8261 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
004931f5-9311-4819-84a9-7289fd6d2fe0 | checkpoint | Test 1 Flood Test Pass/Fail
f207d83d-ca6d-4659-ab5a-3dd6055759a5 | checklist | PVC Sheet Membrane Checklist |  | PVC Sheet Membrane Checklist
135baf3b-af69-4a22-acc3-1dcba082701f | section | PVC Sheet Membrane
759c75ee-2de3-4da3-8451-4c74f7279940 | checkpoint | Surface conditions suitable for installation-details in comments below
a35dad83-8445-4476-87dd-7dbbde0a855e | checkpoint | Moisture test complete-result in comments below
116a6eef-53e1-5ca8-b322-3f04538bae5e | note | Must be below 5% to pass
5e00b3bb-c6c0-45b5-af1c-5a89c366bdfd | checkpoint | Substrate inspected and accepted
32956873-3ee0-5e7c-8bf6-5c19b7de0347 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
657c657f-1f41-49a9-ba36-36139915521d | checkpoint | Application of Geofabric to substrate
43aeeaa5-94fa-4fee-9510-6aa0dc1850c4 | checkpoint | Application of PVC Sheet Membrane
02eba2a3-da5d-4a86-94b5-92f9c401f0ba | checkpoint | PVC Sheet Membrane Detailing as required
9171ef23-36db-442c-8cb2-244ff5c701aa | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
01c00ebe-fb6a-498a-bff1-11634ea2bd25 | checkpoint | Test 1 Probe Test Pass/Fail
389ed8c8-799d-4570-bb11-4d3a739d7ae5 | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
d56c313f-d331-4095-bea7-f2ef4fd3e38a | checklist | PVC Tanks Checklist |  | PVC Tanks Checklist
0697f81b-62b0-4a41-9c9e-072bf42d792f | section | PVC Tanks
9df7b70c-e9e2-44a2-aca2-31b1b7b03a44 | checkpoint | Surface conditions suitable for installation - details in comments below
2fe11708-2ccf-41d4-aed0-2d7e0eebcb28 | checkpoint | Moisture test complete - result in comments below
c1ffa13c-0065-5616-9ebe-73aee0e9b7b7 | note | Must be below 5% to pass
cc6585c6-34be-4d87-9497-74957c73bb64 | checkpoint | Substrate inspected and accepted
2e0379bb-3b94-5a5b-9da4-f971f97957ba | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
84ac3c57-6c3a-4de0-b110-857a453ed40e | checkpoint | Application of Geofabric to substrate
eaac1706-4c2f-4d88-b83a-27db564e51c0 | checkpoint | Application of PVC Sheet Membrane
51db333a-a828-4b9e-8669-d3ecf93750fc | checkpoint | PVC Sheet Membrane detailing as required
65ee3af4-703f-44ea-812a-e203bcaf43d9 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
ad798a3e-507a-4e39-8857-b8513450802a | checkpoint | Test 1 Probe Test
cd1b9082-7d56-4b21-962d-577d46ac4e05 | checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
fb8fca5b-5805-43e2-957f-33cde4f115ab | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
9cd00f08-c384-4556-b7e8-a29335bc2282 | checklist | Screed Checklist |  | Screed Checklist
16194990-6e63-4ecb-9399-c514acea7b15 | section | Screed
64bf989f-55ad-449d-82f5-e659d208529d | checkpoint | Mixing of Topcem Pronto
557ceafc-d6c2-4947-8b1c-225965ebda47 | checkpoint | Application of Topcem Pronto
247657cb-6b6b-4d22-892e-a800f477624d | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
8a66fa4b-5e8b-4f22-9052-91bd79644bb0 | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
4b20b505-9a6e-400f-8a96-a4f3dd6b213f | checklist | Trafficable Liquid Membrane Checklist |  | Trafficable Liquid Membrane Checklist
7ae494ba-cd8c-431d-8345-a47d6000deec | section | Trafficable Liquid Membrane
714178a0-e472-40bf-88b2-fda475fac00a | checkpoint | Surface conditions suitable for installation-details in comments below
ac79c12a-3e44-4390-9a10-59ddac9d6698 | checkpoint | Moisture test complete-result in comments below
8f00077e-2615-555c-bfe4-13ac7442a6e6 | note | Must be below 5% to pass
6092240f-01a4-4376-95ae-3d7d69507766 | checkpoint | Substrate inspected and accepted
f18bb7b2-b069-591a-929e-a6089eefb660 | note | Substrate has fall, is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
87ff50e9-6e05-4bc8-a4f8-7ca2dcf62d4b | checkpoint | Application of Primer (if required) as per specification
a08190ec-0cc7-45a6-b5bf-2a22e2faec44 | checkpoint | Application of Cementitious Coving (if required) completed
f457608b-7422-45e0-aefc-7c0e17faffb1 | checkpoint | Application of Membrane as per project specification-1st coat
23239000-e988-438c-b8dc-9fb485ef6a59 | checkpoint | Application of Membrane as per project specification-2nd coat
96d3a5b5-40a7-43d9-8e3d-29fa200e46c7 | checkpoint | Final DFT Thickness of Membrane
451ec080-2cd8-4df1-8fb2-b6d296c7f374 | checkpoint | Installation of Corlute Protection Board Completed
b824a377-d2cf-4507-9119-c4271e15357b | checkpoint | Installation of Drainage Cell Completed
a7dd6cff-8c0c-4449-8114-182c17457d18 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
c7486513-28a0-4e93-9ce3-1257a8eabce0 | checkpoint | Flood Test Pass/Fail
74e42085-18c5-45a3-95d9-216bbf594580 | checklist | Waterstop-Penebar Checklist |  | Waterstop-Penebar Checklist
a9c900de-e09b-456e-8dc4-c994aaa0cf5e | section | Waterstop-Penebar
c0b6c7ad-fa2c-4875-aba2-5eb8f2269b44 | checkpoint | Surface conditions suitable for installation-details in comments below
b9b7280b-8cce-4411-8570-4b82014e8f84 | checkpoint | Substrate inspected and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
a956e819-2f90-41a3-8b45-8c9a8a8f4888 | checkpoint | Application of Penetron Penebar SW55
431a9298-3695-472f-81bb-8de0cf02a413 | checkpoint | Ensure all Butt Joints are completed as per TDS
6c1db31a-5ccb-4c30-a1ab-7d602eba8e80 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
b51c6eea-599e-4ec6-afd2-2d1307035989 | checkpoint | Test 1 Probe Test Pass/Fail
0a537492-f4f7-47d6-870b-98e09d5d25bc | checklist | Wet Areas Checklist |  | Wet Areas Checklist
68a813cd-2afb-445e-bfa1-690cc342322c | section | Wet Areas
cbeda2b9-6f02-493f-850d-6dfb1ded321c | checkpoint | Substrate inspected and accepted
bdd1e3a0-935a-5832-879c-b5dffbb63562 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
576a6d1d-047f-44a4-9804-40dba4a657b8 | checkpoint | Atmospheric conditions
8f8d0c04-a73a-5e57-b6f5-a0042983eda9 | note | Note ambient temp, Relative Humidity, Dew Point
c7e66847-e995-49ce-baf3-3038f8303464 | checkpoint | Product Batch Numbers
20afa8d8-8b3b-5bf2-83d2-48b5d31833c2 | note | Note batch numbers for products used
e0fec8e9-ccf5-4fdb-be4a-ca41e677c07b | checkpoint | Equipment used
751053ab-846e-52dd-b291-ac5ee8041ab2 | note | Note equipment used like rollers etc.
020d14dd-825f-4fa3-b452-67613b6967c2 | checkpoint | Apply Primer, Seal Joints
3f304cb4-ebbd-562b-9441-ac1365407cc1 | note | Apply Primer, Caulk and Tape Joints
07afcabf-435c-409e-bf70-f22c9b40fd95 | checkpoint | Apply Wet Area Membrane
8d3c1557-b69d-5e06-8fd7-1b79881dc4a5 | note | Apply Wet Area Membrane by brush, roller
3e04f000-c2e9-47ab-be8a-b1636b083658 | checklist | Windows and Doors Checklist |  | Windows and Doors Checklist
29198f64-5578-4f01-9511-0d772f30085c | section | Windows and Doors
2d7998dc-22de-4a23-a60e-44a2bdf676d7 | checkpoint | Surface conditions suitable for installation-details in comments below
45bb0adc-0621-4de6-9a92-69cb7dee9cc9 | checkpoint | Substrate has fall (if required) is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
5eff9ac4-5709-50ff-bf0a-628ca41cc5d0 | note | Must be below 5% to pass
fae11bf7-3615-4d60-8985-d1a5611b90cc | checkpoint | Application of Primer as per specification
f938357c-8ae5-412f-8b7c-2be87a507c89 | checkpoint | Application of Caulking and or Bandage (if required) completed
69c6e136-7b31-45f8-98a1-c6c34c020aea | checkpoint | Application of Membrane as per project specification -1st coat
b07eb9c3-32c3-4e5f-ba8c-c4e34ff41a21 | checkpoint | Application of Membrane as per project specification-2nd coat
59b2c107-3121-46f0-926e-b65a285cc377 | checkpoint | Final DFT Thickness of Membrane
66e0ea10-3532-4a79-864e-5576f77bbe40 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
19a2a9f7-d8cb-40b1-a85e-09348c46930d | checkpoint | Flood Test Pass/Fail