## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Combined Remaining Items - 105 - Rev A | itp |  |  |  |  | ITP - Combined Remaining Items - 105 - Rev A
section | 3.01 General
checkpoint | 3.01.01 - Precondition Surveys
label | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
label | Standard / Specification - PS 2.13
label | Verifying Document - Precondition Survey
label | Frequency - Prior to the Contractor taking possession of the Site.
label | Verification Activity: Activity - H
label | Verification Activity: By - PM
section | 4.34 Traffic Service Materials
checkpoint | Safe Lane Delineator Concrete
label | Acceptance / Conformance Criteria - Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days.
label | Standard / Specification - PS 23.7
label | Verifying Document - Datasheet / Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Guard Rail Concrete
label | Acceptance / Conformance Criteria - Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Datasheet / Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Proposed Guard Rails
label | Acceptance / Conformance Criteria - The Contractor shall submit details of proposed proprietary materials and systems.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Datasheets
label | Frequency - Prior to material order (4 weeks prior to installation)
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Guard Rail Maintenance Instructions
label | Acceptance / Conformance Criteria - The Contractor shall submit details of the manufacturers maintenance instructions for the type of barrier installed.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Maintenance Instructions
label | Frequency - Upon completion of the Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Coloured Surfacing
label | Acceptance / Conformance Criteria - The contractor shall provide evidence to the Engineer before preparation and marking of the surfacing, that the material conforms in its entirety to the requirements of NZTA P33.
label | Standard / Specification - PS 23.4
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.35 Sign Materials
checkpoint | Retro-reflective sheeting
label | Acceptance / Conformance Criteria - All retro-reflective sheeting must be approved for use in New Zealand and comply with the following requirements of NZTA P24 Specification for Permanent Traffic Signs and AS/NZS 1906.1: 1993 Retro-reflective Materials and Devices for Road Traffic Control Purposes, Part 1 Retroreflective Sheeting.
label | Standard / Specification - PS 23.2.6
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Anti-Graffiti Coating
label | Acceptance / Conformance Criteria - Graffiti protective coating shall be applied to all ground mounted sign and shall be approved for such use by the reflective sheeting manufacturer and shall maintain all guarantees for the sign.
label | Standard / Specification - PS 23.2.14
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Dew Effect Coating
label | Acceptance / Conformance Criteria - All overhead mounted signs, except for bridge name plates, shall be manufactured with an overlay that is designed to prevent dew droplets forming to overcome the phenomenon known as ‘dew effect’.
label | Standard / Specification - PS 23.2.15
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Sign Shop Drawings
label | Acceptance / Conformance Criteria - The supplier shall prepare shop drawings detailing the panel layout, positions of channel framing, and assembly systems prior to the manufacture of any sign. The shop drawings shall be submitted for review and comment at least ten working days prior to manufacture of the sign.
label | Standard / Specification - PS 23.2.6
label | Verifying Document - Shop Drawings
label | Frequency - At least ten working days prior to manufacture of the sign.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Timber Posts
label | Acceptance / Conformance Criteria - Timber posts shall not exceed 100mm x 100mm section size.
label | ○ They shall be Building Grade or Number 1 Framing grade timber as specified in NZS 3631, dried to 20-24% moisture content, and treated in accordance with the New Zealand Timber Preservation Council’s requirements as specified in NZS 3640 for Hazard Class H4.
label | ○ The timber finish may be gauged or dressed.
label | ○ The timber posts shall be primed and finished with white high gloss paint over the length above ground level.
label | Standard / Specification - PS 23.2.19
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Steel Posts
label | Acceptance / Conformance Criteria - Steel posts shall be of an approved frangible design.
label | ○ They shall be hot-dip galvanised and finished with white high gloss paint.
label | ○ The paint system shall be specified and applied in accordance with AS/NZS 2312.1. All poles shall be fitted with white PVC caps.
label | Standard / Specification - PS 23.2.20
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Aluminium Poles
label | Acceptance / Conformance Criteria - Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps.
label | Standard / Specification - PS 23.2.21
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Impact Resistant System Posts
label | Acceptance / Conformance Criteria - Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps.
label | Standard / Specification - PS 23.2.22
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Sign Fixings
label | Acceptance / Conformance Criteria - All signs shall be installed using approved sign support channel bracket fittings that do not penetrate the front face of the sign.
label | ○ No bolts, rivets or other fixings shall penetrate the front face of the sign.
label | Standard / Specification - PS 23.2.23
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Training
label | Acceptance / Conformance Criteria - The installer shall demonstrate prior to undertaking the works that its staff has attended, or are scheduled to attend, a recognised training course in the handling, installation, and maintenance of retro-reflective road signs.
label | Standard / Specification - PS 23.2.25
label | Verifying Document - Training Records
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.36 Long-life Road Markings Materials
checkpoint | Applicator Approval
label | Acceptance / Conformance Criteria - The applicator(s) used for the contract works must be certified to NZTA/NZRF T/12.
label | ○ No installation shall commence without the written approval of the Engineer accepting the certification and suitability of the applicator(s) proposed.
label | Standard / Specification - PS 23.5.2
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Long-life Road Markings Materials, Marking System and Format
label | Acceptance / Conformance Criteria - Only products approved to NZTA specifications are to be used.
label | ○ The Contractor must submit to the Engineer details of each of the products that will be used in the contract works.
label | ○ The submission must include:
label | Standard / Specification - PS 23.5.3
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Installation Limitations
label | Acceptance / Conformance Criteria - The Contractor shall supply the Engineer with the Supplier Specifications or Instructions on Installation for the long-life road marking system proposed to be used. No installation shall commence without the written approval of the Engineer accepting the suitability of the long-life road marking system proposed.
label | Standard / Specification - PS 23.5.4
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Glass beads
label | Acceptance / Conformance Criteria - The Contractor shall ensure that glass beads have appropriate adhesive coatings for the long-life road marking product being used.
label | ○ No installation shall commence without the written approval of the Engineer accepting the suitability of the glass beads proposed.
label | Standard / Specification - PS 23.5.5
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Raised Pavement Markers
label | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers.
label | Standard / Specification - PS 23.5.6
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Application Crew
label | Acceptance / Conformance Criteria - The Contractor is to notify the Engineer of any proposed changes to the crew. The Contractor shall provide a CV outlining their qualifications, skills and experience related to installation of long-life road marking systems.
label | ○ No installation shall commence without the written approval of the Engineer accepting the suitability of the nominated crew or any changes proposed.
label | Standard / Specification - PS 23.5.7
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.37 Pavement Marking Materials
checkpoint | High performance markings
label | Acceptance / Conformance Criteria - All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified. The Contractor shall nominate the brand, type and proposed application methods for materials to be used. This information shall be provided for approval prior to application.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Glass beads
label | Acceptance / Conformance Criteria - All glass beads added to the paint for reflectorised line application shall be in accordance with AS/NZS 2009 Glass Beads for Road-Marking Materials and the current NZTA Policy and Testing Regime for Heavy Metals (T17).
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Raised Pavement Markers
label | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Edge Marker Posts:
label | Acceptance / Conformance Criteria - Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.38 Fencing Materials
checkpoint | Post and Wire Fencing Materials
label | Acceptance / Conformance Criteria - All in ground timber posts shall be treated to H4 standard and all other timber shall be treated to H3 standard.
label | ○ All posts to be sunk to the required depth and supported to form a rigid boundary fence.
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Datasheet / Docket
label | Frequency - Prior to Installation
section | 4.39 Landscaping Material Supply
checkpoint | Plant Supply
label | Acceptance / Conformance Criteria - All plants shall be supplied true to the species and grades specified on the approved landscape plans and fill the specified planter bag.
label | ○ All street trees, unless specified otherwise, shall be of a minimum grade of 45 litres with a minimum 30mm calliper.
label | ○ All other stock shall be of minimum 2 litre grade for groundcover and 3 litre grades for shrubs.
label | Standard / Specification - PS 25.2.1
label | Verifying Document - Plant Details
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | General plant species and quality
label | Acceptance / Conformance Criteria - The Overseeing Organisation shall be provided with not less than five working days’ notice of dates upon which plants are to be delivered on site, so that arrangements can be made for quality inspection and confirmation of identification of plant material.
label | Standard / Specification - PS 25.2.1
label | Verifying Document - Notice
label | Frequency - 5 working day notice
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Street tree grades, species, and form
label | Acceptance / Conformance Criteria - All street trees, unless specified otherwise, shall be of a minimum grade of PB 95 and be first grade nursery specimens.
label | ○ No substitution of species or grade shall be made without the written approval of the Engineer.
label | Standard / Specification - PS 25.2.2
label | Verifying Document - Plant Details
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Chemical applications for weed and pest control
label | Acceptance / Conformance Criteria - All chemical application on planted areas shall be carried out by qualified, trained personnel and according to NZS 8409 Management of Agrichemicals, any relevant local Herbicide Policy and manufacturers’ requirements.
label | Standard / Specification - PS 25.5.2
label | Verifying Document - Qualifications and Datasheet
label | Frequency - Prior to Application
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Biodegradable plant guards
label | Acceptance / Conformance Criteria - All plant and animal pest control used for the landscaping works shall fully comply with Section D of NZTA P39.
label | Standard / Specification - PS 25.6
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Fertilisers
label | Acceptance / Conformance Criteria - Fertilisers shall be either an approved pelletised natural or organic fertiliser or an approved synthetic fertiliser.
label | Standard / Specification - PS 25.7.3.2
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Imported Topsoil
label | Acceptance / Conformance Criteria - Topsoil, both imported and existing on site, shall be a loam soil of good quality, free draining, free of weeds and contaminates, free of building materials and debris, screened, health, and contain no pans.
label | Standard / Specification - PS 25.8.1
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Biodegradable Weed Matting
label | Acceptance / Conformance Criteria - The biodegradable weed matting shall conform with NZTA P39 and be coconut fibre mat, Woolmat or similar approved.
label | Standard / Specification - PS 25.9.1
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Mulching fabric Testing
label | Acceptance / Conformance Criteria - A simple test to ascertain whether the mulching fabric is viable is to hold a sample to the sky.
label | ○ It should be mostly opaque. This density inhibits weed seeds trapped under the mulching fabric from sprouting, provides good moisture retention and assists with batter erosion control.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Test Results
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Mulch
label | Acceptance / Conformance Criteria - The mulch shall be supplied as scheduled, clean, and free of soil, sawdust and wood preservatives, and a sample shall be provided to the Engineer for approval prior to spread.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Engineers Approval
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Turf / Instant turf
label | Acceptance / Conformance Criteria - The turf shall be of good quality in line with industry standards.
label | Standard / Specification - PS 25.10.5
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 15.01 Streetlighting Quality Assurance plan
checkpoint | Streetlighting Quality Assurance plan
label | Acceptance / Conformance Criteria - Provide a Quality Assurance plan to propose, establish, maintain, monitor and document a quality assurance system covering all aspects of the procurement, fabrication, installation and completion of the works.
label | Standard / Specification - PS 22.4.6
label | Verifying Document - Streetlighting QA Plan
label | Frequency - Prior to Streetlighting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 16.01 Signs
checkpoint | Redundant Signs
label | Acceptance / Conformance Criteria - All redundant sign equipment shall be offered to the New Zealand Transport Agency to be uplifted for possible future use.
label | ○ All redundant equipment not required by New Zealand Transport Agency, shall be uplifted, removed completely off site, and disposed of in an appropriate manner.
label | Standard / Specification - PS 23.2.2
label | Verifying Document - Site Records
label | Frequency - Where Required
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Relocated Signs
label | Acceptance / Conformance Criteria - All relocated signs shall be Firmly installed in a vertical position and securely attached to posts where appropriate. Fixed to posts with appropriate fixing brackets.
label | ○ Signs shall not be fixed to posts by bolting through the sign unless specifically approved by the Engineer.
label | Standard / Specification - PS 23.2.3
label | Verifying Document - Site Records
label | Frequency - Each Sign
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Posts and poles
label | Acceptance / Conformance Criteria - The Contractor shall maintain construction records for each sign that clearly shows that all post, poles and foundation details comply with the requirements of this Specification.
label | ○ The design of foundations should, where required, consider the very close proximity of services and not subject these services to any dead or live loadings from the sign support structures.
label | Standard / Specification - PS 23.2.17, PS 23.2.18, PS 23.2.24
label | Verifying Document - Checksheet
label | Frequency - Each Sign
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Ground Mounted Signs
label | Acceptance / Conformance Criteria - All ground mounted signs shall be orientated such that they are turned about five degrees away from the driver’s line of sight or the normal to-the-road centreline as detailed in Clause 1.10 ‘Orientation’ of the Waka Kotahi NZ Transport Agency Manual of Pavement Markings and Signs Part 1.
label | Standard / Specification - PS 23.2.27
label | Verifying Document - Site Records
label | Frequency - Each Ground Mounted Sign
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
section | 16.02 Pavement Markings
checkpoint | Surplus Chip Removal
label | Acceptance / Conformance Criteria - Accumulations of surplus chip and other coarse material shall be removed prior to road marking.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Prior to Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | High Performance Marking
label | Acceptance / Conformance Criteria - All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Site Records
label | Frequency - Each Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Roadmarking Removal
label | Acceptance / Conformance Criteria - All road markings that are to be permanently removed must be either by water blasting or milling off in line with the NZRF line removal guide.
label | ○ The removal of all redundant pavement marking shall be such that The shape of the marking cannot be distinguished, The final surface texture is like the surrounding pavement; and No evidence of the paint remains.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Each Removed marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Raised Pavement Markers
label | Acceptance / Conformance Criteria - These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14.
label | ○ The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Each Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Edge Marker Posts:
label | Acceptance / Conformance Criteria - Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Each Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Coloured Surfacing
label | Acceptance / Conformance Criteria - Coloured surfacing shall be laid in accordance with the requirements of NZTA P33.
label | Standard / Specification - PS 23.3.2, PS 23.4
label | Verifying Document - Site Records
label | Frequency - Each Application
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
section | 16.03 Long-life Road Markings
checkpoint | Mark out the Contract Works with Engineer
label | Acceptance / Conformance Criteria - The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences.
label | ○ The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004.
label | ○ The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site.
label | Standard / Specification - PS 23.5.9
label | Verifying Document - Markout Records
label | Frequency - 5 Working Day notice prior to mark out
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Applicator, Marking System, Marking Format and Applicator Crew Trial
label | Acceptance / Conformance Criteria - The trial shall be completed using the applicator(s), marking system(s), marking format and crew approved for the contract works.
label | ○ The Contractor shall give the Engineer 5 Working Day notice of the date for the trial(s).
label | ○ Installation shall commence only if the Engineer is satisfied with the trial result(s).
label | ○ Verbal acceptance will be given to the Contractor immediately after the trial with written confirmation to follow.
label | Standard / Specification - PS 23.5.11
label | Verifying Document - Trail Results
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Inspection and Measuring During Installation
label | Acceptance / Conformance Criteria - The Contractor shall inspect the long-life road marking against dimensional and installation tolerances as installation progresses.
label | ○ The Contractor shall on a daily frequency complete a Daily Quality Assurance Form (Thermoplastic and CAP respectively).
label | ○ The form records the material data, environmental conditions, etc.
label | Standard / Specification - PS 23.5.13, PS 23.5.15
label | Verifying Document - Daily Quality Assurance Form
label | Frequency - During installation
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Inspection Post Installation
label | Acceptance / Conformance Criteria - Formal visual drive over inspections.
label | ○ The visual inspection shall include An initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor of the first 25 to 50km per type of roadmarking installed (approximately 5 to 7 days of installation).
label | ○ The inspection shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event.
label | ○ Subsequent visual inspections by the Engineer and the Contractor shall be jointly carried out of a sample of the contract works.
label | Standard / Specification - PS 23.5.16
label | Verifying Document - Report
label | Frequency - Minimum of 20% of the total contract works will be inspected per type of roadmarking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Monitoring Post Installation
label | Acceptance / Conformance Criteria - The Engineer and the Contractor shall agree on representative sites for ongoing monitoring.
label | ○ Monitoring sites shall be 2 per 100km of edge-line per roadmarking type.
label | ○ Three sets of monitoring shall be carried out First monitoring following installation of all contract works.
label | ○ The monitoring shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event.
label | ○ Second monitoring approximately six months after the first monitoring.
label | ○ The Engineer may waive the monitoring if they are satisfied with the performance of the markings based on the first monitoring.
label | ○ Third monitoring prior the issue of Final Completion Certificate.
label | Standard / Specification - PS 23.5.17
label | Verifying Document - Report
label | Frequency - 2 per 100km of edge-line per roadmarking type
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 16.04 Safety Barriers
checkpoint | Ground profile
label | Acceptance / Conformance Criteria - The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Site Records
label | Frequency - Prior to post installation
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Installation Notice
label | Acceptance / Conformance Criteria - The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Notice
label | Frequency - Prior to Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Guardrail Alignment Visual Inspection
label | Acceptance / Conformance Criteria - The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels.
label | ○ When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Site Records
label | Frequency - When erected but before posts are permanently fixed
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Guard Rail and End Post Installation Checksheets
label | Acceptance / Conformance Criteria - The Contractor shall submit a completed and signed installation check sheet for each terminal and guardrail section installed to the Engineer for acceptance
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Checksheets
label | Frequency - Upon completion of the Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Galvanising Repair
label | Acceptance / Conformance Criteria - After assembly, any areas of the galvanised coating that have been damaged or show signs of deterioration shall be wire brushed and washed to thoroughly clean down to fresh zinc or parent metal.
label | ○ They shall then be spot painted with two brush coats of un-thinned approved zinc rich paint the first coat being applied to a dry surface immediately after cleaning.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Site Records
label | Frequency - Where Required
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 16.05 Safe Lane Delineators
checkpoint | Safe Lane Delineator Installation
label | Acceptance / Conformance Criteria - The safe lane delineators are to be installed in accordance with the manufacturer’s specification unless otherwise directed in the Contract Drawings.
label | Standard / Specification - PS 23.7
label | Verifying Document - Site Records
label | Frequency - Post Installation
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Chemset Safe Lane Delineator
label | Acceptance / Conformance Criteria - Where detailed in the Contract Drawings the Contractor shall excavate a 300mm x 300mm diameter hole and ensure all loose debris is removed from the hole.
label | ○ The hole shall be back filled with 20MPa concrete and the safe lane delineator is to be chemset in place.
label | ○ The concrete shall be level with the existing surfacing around the hole and water shall drain away from the delineator.
label | Standard / Specification - PS 23.7
label | Verifying Document - Site Records
label | Frequency - Each Post
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 17.01 Services
checkpoint | Existing Services
label | Acceptance / Conformance Criteria - The Contractor shall locate or arrange for the relevant service authority to locate existing services prior to commencing work in any area.
label | ○ Where a clash of services is identified the Contractor shall summit a proposal for overcoming the problem to the Engineer.
label | ○ The Contractor shall give service authorities reasonable notice when excavating within close proximity to their services.
label | Standard / Specification - PS 24.1.1
label | Verifying Document - Comms
label | Frequency - Prior to commencing work
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Private Services
label | Acceptance / Conformance Criteria - Any private services such as domestic water and power supplies, rural mailboxes etc., damaged by the Contractor’s operations shall be repaired at the Contractor’s expense.
label | ○ The Contractor shall keep disruptions to individual landowners/occupiers to the minimum practicable.
label | ○ The Contractor shall consult with all affected landowners/occupiers to arrange for a mutually acceptable time for works that will interrupt availability of services and to identify any special requirements for continuity of supply.
label | ○ Where there is a requirement for continuity of supply the Contractor shall take all reasonable measures necessary to satisfy the affected party’s requirements.
label | ○ Where possible at least 10 Working Days’ notice should be given before shutdowns.
label | Standard / Specification - PS 24.1.2
label | Verifying Document - Comms
label | Frequency - 10 Working Days’ notice should be given before shutdowns.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Service Connections
label | Acceptance / Conformance Criteria - The Contractor shall liaise with the appropriate service provider to coordinate connection of the new service into the existing service.
label | Standard / Specification - PS 24.1.3
label | Verifying Document - Comms
label | Frequency - Prior to connections
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 17.02 Locate and Pothole Services
checkpoint | Service Location
label | Acceptance / Conformance Criteria - All locations where connection to an existing pipe is proposed, the Contractor shall pothole and expose the pipe and level the crown.
label | ○ If an issue is identified from potholing, the Contractor shall notify the Engineer.
label | Standard / Specification - PS 24.2
label | Verifying Document - Potholing Record
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | Service Clashes
label | Acceptance / Conformance Criteria - The Contractor shall notify the Engineer immediately of any service clashes identified and the Engineer will advise on how to proceed.
label | Standard / Specification - PS 24.2
label | Verifying Document - Notice
label | Frequency - Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Service Plans
label | Acceptance / Conformance Criteria - The Contractor shall be responsible for obtaining all service plans and identifying all existing services on site, including potholing where required to confirm the exact location and depth.
label | Standard / Specification - PS 24.2
label | Verifying Document - Service Plans
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | 18.01 General
checkpoint | Topsoil Placement Inspection
label | Acceptance / Conformance Criteria - The Engineer shall inspect the cut surfaces prior to the placement of topsoil and planting.
label | Standard / Specification - PS 15.10.10
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Topsoil Placement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Setting out Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Applying herbicide Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Applying herbicide.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Cultivation of planting areas Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Cultivation of planting areas.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Delivery of plants and trees Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Delivery of plants and trees.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Planting or seeding Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Planting or seeding.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Site visits during maintenance period Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Site visits during maintenance period.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 18.02 Weed, Pest, and Litter Control
checkpoint | Litter control
label | Acceptance / Conformance Criteria - The planting area shall be kept clear of all rubbish, including domestic and building materials.
label | Standard / Specification - PS 25.5.1
label | Verifying Document - Site Records
label | Frequency - Ongoing
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Spraying Operations
label | Acceptance / Conformance Criteria - All spraying operations shall be carried out in windless, dry conditions, when rain is not imminent for at least 12 hours and at times which minimise possible hazards or disruption to the public, animals or other beneficial fauna.
label | ○ Care shall be taken to prevent spray drifting onto non-target areas or plants and comply with notification requirements as required by the proposed Waikato Regional Plan.
label | Standard / Specification - PS 25.5.2
label | Verifying Document - Site Records
label | Frequency - Each Application
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Chemical weed control in planting areas
label | Acceptance / Conformance Criteria - Chemical weed control in planting areas shall be kept within the edge of the planting beds, within a maximum of 500mm of tree trunks, within 50mm of the edge of any undefined mulch surface, and within 50mm of any posts or the base of any landscape structures.
label | Standard / Specification - PS 25.5.2
label | Verifying Document - Site Records
label | Frequency - Each Application
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Biodegradable plant guards
label | Acceptance / Conformance Criteria - All plants to be fitted with biodegradable plant guards.
label | Standard / Specification - PS 25.6
label | Verifying Document - Site Records
label | Frequency - Each Plant
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 18.03 Planting
checkpoint | Planting Layout
label | Acceptance / Conformance Criteria - All plants shall be positioned in the locations and in the quantities shown on the drawings., Planting Schedule and Typical Cross Sections for inspection and authorisation by the Engineer prior to planting.
label | Standard / Specification - PS 25.7.1
label | Verifying Document - Site Records
label | Frequency - Prior to Planting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Specimen and street trees
label | Acceptance / Conformance Criteria - Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation.
label | Standard / Specification - PS 25.7.2.1
label | Verifying Document - Site Records
label | Frequency - Each Tree
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Irrigation and Fertilising
label | Acceptance / Conformance Criteria - During installation and establishment, the soil in all planting areas moisture shall be retained to ensure active plant growth throughout the growing season (September – May).
label | Standard / Specification - PS 25.7.2.3
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Fertilising
label | Acceptance / Conformance Criteria - Generally, some form of fertiliser shall be applied to planting depending on the soil type. For shrubs and trees, all fertiliser shall be well mixed with the backfilled soil.
label | ○ For bedding or groundcover all fertiliser shall be well mixed with the site topsoil prior to planting.
label | Standard / Specification - PS 25.7.3.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Plantings
label | Acceptance / Conformance Criteria - All specimen tree plantings shall have two-year slow release fertiliser tablets installed at the time of planting.
label | Standard / Specification - PS 25.7.3.3
label | Verifying Document - Site Records
label | Frequency - Each Tree
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Topsoiling (1)
label | Acceptance / Conformance Criteria - All topsoil and operations relating to topsoil for the project shall fully conform to Section F of NZTA P39.
label | Standard / Specification - PS 25.8.1
label | Verifying Document - Site Records
label | Frequency - prior to planting.
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Topsoiling (2)
label | Acceptance / Conformance Criteria - All new planting areas on existing topsoil shall be deep ripped to a minimum of 300mm prior to planting.
label | Standard / Specification - PS 25.8.1
label | Verifying Document - Site Records
label | Frequency - prior to planting.
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
section | 18.04 Biodegradable Weed Matting and Mulching
checkpoint | Biodegradable high density mulch matting
label | Acceptance / Conformance Criteria - The blanket shall be installed according to the Manufacturer’s directions and shall include stapling the blanket at a minimum of 1 metre centres and perimeter edges buried to 300mm depth buried soil.
label | Standard / Specification - PS 25.7.1
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Flat Site Mulch
label | Acceptance / Conformance Criteria - On sites flatter than a 1:2 grade (1.0m high by 3.0m metres long), bark or arb mulch shall be spread evenly to a depth of 80-100mm over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Steep Site Mulch
label | Acceptance / Conformance Criteria - On slopes steeper than 1:2 mulching for weed control shall consist of an Engineer approved matting with the following criteria:
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Very Steep Slopes Mulch
label | Acceptance / Conformance Criteria - On steep slopes (1 in 4) with erosion issues that are receiving planting, biodegradable netting with no geotextile or geonet content shall be used at the Engineer’s discretion.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 18.05 Grassing, Sowing and Turfing
checkpoint | Preparation for sowing or turfing
label | Acceptance / Conformance Criteria - Excessive compaction of subsoil in existing grassed areas shall be relieved to achieve satisfactory long-term growing conditions.
label | ○ All topsoil removed to permit contract works to be carried out shall be stockpiled for reuse. All new grass areas shall be built on soil prepared to industry best practice standards.
label | ○ Sloped areas shall be neatly contoured into adjoining grassed areas. Perennial weeds shall be controlled with industry best practice methods.
label | Standard / Specification - PS 25.10.1
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Fertilisers
label | Acceptance / Conformance Criteria - Fertilisers shall be lightly arrowed into the topsoil, 2-3 days prior to seed sowing, at the following rates at 200kg/ha.
label | ○ This shall be followed one month after sowing, with an application of: Di-ammonium Phosphate (DAP) 100 kg/ha.
label | Standard / Specification - PS 25.10.2
label | Verifying Document - Site Records
label | Frequency - 2-3 days prior to seed sowing and 1 month after sowing
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Grass sowing
label | Acceptance / Conformance Criteria - On large areas the seed shall be “check” sown in at least two directions and surface rolled with suitable flat roller.
label | ○ On small areas the grass seed shall be evenly applied and raked into the soil.
label | Standard / Specification - PS 25.10.3
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Establishment of sown areas
label | Acceptance / Conformance Criteria - Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state.
label | ○ Grassed areas shall be watered as required to achieve an efficient germination of the seed.
label | ○ Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces.
label | Standard / Specification - PS 25.10.4
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Grassed areas adjacent hardscape
label | Acceptance / Conformance Criteria - If base of grass level is 30mm lower or more than adjacent hardstand, grass will need to be removed min 1m back from path, soil put back in, levelled and re-consolidated to spec and grass res-own to correct level.
label | ○ If less than 30mm top dressing at 10mm each time, over time will be acceptable until the correct level is achieved.
label | Standard / Specification - PS 25.10.4
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Turf / Instant turf
label | Acceptance / Conformance Criteria - Turf shall be installed and maintained in accordance with supplier’s requirements.
label | Standard / Specification - PS 25.10.5
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Slope areas
label | Acceptance / Conformance Criteria - In all sites, except natural gully systems, where the slope gradient is steeper than 1:3 (one metre high by three metres long), it is preferable that the embankment is either scarified or grooved on an angle to a depth of 200mm, from the top of the bank to the base.
label | ○ This assists topsoil adhesion and prevents separation of the top 150mm topsoil from the base material due to gravity and/or glazed/planning of base material.
label | Standard / Specification - PS 25.10.6
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 18.06 Fencing
checkpoint | Seven Wire Fencing Order
label | Acceptance / Conformance Criteria - The Contractor is to liaise with the property owner to establish the preferred spacing and order of the seven wires.
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Comms
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Post and Wire Fencing Installation
label | Acceptance / Conformance Criteria - New seven wire standard boundary fence shall be erected with the following Offset tolerances 0.0m towards the centreline and 0.0m to 0.3m away from the centreline.
label | ○ The fence shall be vertical, and the grade shall generally follow the contour of the ground.
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Survey Records
label | Frequency - Each Fence
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
section | 19.01 Road Opening
checkpoint | Pre-Opening Safety Review
label | Acceptance / Conformance Criteria - Prior to opening the Works for use by the general travelling public, a pre-opening safety review will be undertaken by the Engineer and the Principal’s Road Safety Audit team, to approve the removal of any temporary works, speed limits and traffic management.
label | Standard / Specification - PS 7.5.1
label | Verifying Document - Report
label | Frequency - Prior to opening the Works for use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Post Construction Safety Audit
label | Acceptance / Conformance Criteria - Prior to the issue of Practical Completion, a post construction safety audit must be completed by the Engineer and the Principal’s Road Safety Audit team.
label | Standard / Specification - PS 7.5.2
label | Verifying Document - Report
label | Frequency - Prior to the issue of Practical Completion
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT