## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Concrete and Structures - 103 - Rev A | itp |  |  |  |  | ITP - Concrete and Structures - 103 - Rev A
section | 4.18 Kerb and Channel Materials
checkpoint | Water and Aggregate
label | Acceptance / Conformance Criteria - Water and aggregate for concrete shall comply with NZS 3121.
label | Standard / Specification - PS 17.2.1
label | Verifying Document - Details / Mix Design / datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Cement
label | Acceptance / Conformance Criteria - Cement shall comply with NZS 3122 Type GP.
label | Standard / Specification - PS 17.2.2
label | Verifying Document - Details / Mix Design / datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Concrete
label | Acceptance / Conformance Criteria - All concrete, except site concrete, shall be manufactured by an approved ready-mix plant unlesspecifically approved otherwise in writing by the Engineer.
label | Standard / Specification - PS 17.2.3
label | Verifying Document - Plant Details
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 20MPa Concrete
label | Acceptance / Conformance Criteria - Concrete for structures shall be grade 20 and have a minimum crushing strength of 20MPa at 28 days except where otherwise specified.
label | Standard / Specification - PS 17.2.3
label | Verifying Document - Mix Design
label | Frequency - before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Mortar
label | Acceptance / Conformance Criteria - Mortar shall consist of two parts of fine, sharp, well graded sand to one part of cement measured by dry loose volume and well mixed by hand (unless otherwise specified), or in a suitable mechanical mixer, with just sufficient water to make it slightly moist.
label | ○ It shall be mixed in small quantities as required. Any mortar not used within 30 minutes of mixing shall be discarded.
label | Standard / Specification - PS 17.2.4
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Reinforcing
label | Acceptance / Conformance Criteria - Reinforcing shall be Grade 300 bars unless otherwise shown.
label | ○ Grade 430 bars shall not be substituted for Grade 300 bars without the approval of the Engineer.
label | ○ Welded wire fabric shall comply with AS/NZS 4671.
label | Standard / Specification - PS 17.2.5
label | Verifying Document - Mill Certs
label | Frequency - Prior to Completion
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Kerb and Channel Concrete
label | Acceptance / Conformance Criteria - Kerb and channel shall be cast in-situ using 20MPa concrete placed by an approved extruding machine operated by skilled personnel.
label | ○ The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
label | Standard / Specification - PS 17.3.2
label | Verifying Document - Mix Design
label | Frequency - Before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Machine Laid Kerb Channel Concrete
label | Acceptance / Conformance Criteria - Kerb and/or channel may be cast in situ using 25MPa concrete placed by an approved machine operated by skilled personnel.
label | ○ The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
label | Standard / Specification - PS 17.3.4
label | Verifying Document - Mix Design
label | Frequency - Before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Island Infill Concrete
label | Acceptance / Conformance Criteria - The new concrete shall be 100mm in depth, coloured "Indian Summer" and constructed in accordance with NZS 3109.
label | ○ The concrete shall have a 28-day compressive strength of 17.5 MPa.
label | Standard / Specification - PS 17.3.6
label | Verifying Document - Mix Design
label | Frequency - Before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Kerb Profiles
label | Acceptance / Conformance Criteria - The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
label | Standard / Specification - PS 17.3.2
label | Verifying Document - Profile Details
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Shared Paths Concrete
label | Acceptance / Conformance Criteria - Shared path shall be constructed from 25MPa concrete and shall be 100mm thick.
label | ○ The concrete shall include 3% black oxide colouring.
label | Standard / Specification - PS 17.4
label | Verifying Document - Mix Design
label | Frequency - Before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Roundabout Concrete Apron Concrete
label | Acceptance / Conformance Criteria - The roundabout apron shall be constructed from 40MPa concrete
label | Standard / Specification - PS 17.4.2
label | Verifying Document - Mix Design
label | Frequency - Before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Driveway Access Concrete
label | Acceptance / Conformance Criteria - The access roads shall be constructed from 20MPa concrete
label | Standard / Specification - PS 17.4.3
label | Verifying Document - Mix Design
label | Frequency - Before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.19 Retaining Wall Materials
checkpoint | T-CES 101
label | Acceptance / Conformance Criteria - All concrete shall comply with T-CES 101 (NZ) and NZS 3109.
label | ○ Refer to Section 5 of T-CES 101 (NZ) for Concrete Acceptance Tests which shall comply with Clause 9 of NZS 3109.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
label | Frequency - Prior to Works
checkpoint | Retaining Wall Concrete
label | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa for both piles and the capping beam.
label | ○ The contractor shall submit the proposed concrete mix including slump to the Engineer before the commencement of works.
label | Standard / Specification - PS 18.2.5, PS 18.5.1
label | Verifying Document - Mix Design
label | Frequency - before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Hot-dip Galvanising
label | Acceptance / Conformance Criteria - Steel sections, and all associated fittings shall be hot dip galvanised, in accordance with AS/NZS 4680.
label | ○ All alterations to fittings shall be hot dip galvanised following fabrication.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Verifying Document - Datasheet
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Welding of Structural Steel works
label | Acceptance / Conformance Criteria - All welding of steelwork shall comply with T-CES 301.
label | ○ All welds shall be fully sealed.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Frequency - Prior to Works
checkpoint | Welding Procedures
label | Acceptance / Conformance Criteria - All welds shall be weld category GP in accordance with NZS 3404.
label | ○ All welding procedures shall be in accordance with AS/NZS 1554.
label | ○ The Contractor shall submit full details of the proposed welding procedures and electrodes, with drawings and schedules as required.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Verifying Document - Welding Procedures
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Welders Qualifications
label | Acceptance / Conformance Criteria - Only welders qualified to AS/NZS 1554, or equivalent standard shall be employed on the works.
label | ○ Proof of welder’s proficiency and qualification shall be made available to the Engineer on request.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Verifying Document - Qualification
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Steel Piles
label | Acceptance / Conformance Criteria - Steel piles shall be 310 UC137, mild steel Grade 300, complying with NZS 3404 and galvanised in accordance with AS/NZS 4680.
label | ○ Only new steel pile section to be used.
label | ○ All piles and production certificates shall be made available for inspection by the Engineer at any time.
label | Standard / Specification - PS 18.2.4, PS 18.2.1, PS 18.2.2
label | Verifying Document - Mill Certs
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Steel Reinforcement Compliance
label | Acceptance / Conformance Criteria - Conformin Steel Reinforcement Mill Certs conforming to AS/NZS 4671 shall be supplied.
label | Standard / Specification - AS/NZS4671 & NZS3109
label | Verifying Document - Detail Sheets and Mill Certificates
label | Frequency - Prior to ordering steel
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | Reinforcing Welding Qualifications
label | Acceptance / Conformance Criteria - Welders and Procedures are to be qualified to AS/NZS 1554.3, reviewed by TPI for conformance and submitted to the Engineer for Acceptance.
label | Standard / Specification - Drawings
label | Verifying Document - TPI Report
label | Frequency - Prior to Welding
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcing Welding
label | Acceptance / Conformance Criteria - All welded reinforcing shall be completed as per AS/NZS 1554.3 and be 100% Visually NDT inspected by an independent and approved Third Party Inspector (TPI).
label | Standard / Specification - Drawings
label | Verifying Document - TPI Report
label | Frequency - Prior to concrete pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Pile Concrete Mix Design / Tremmie Mix Design
label | Acceptance / Conformance Criteria - Mix design compiling with the requirements of the contract to be approved by the Engineer.
label | Standard / Specification - Drawings
label | Verifying Document - Approved Mix Design
label | Frequency - Submitted to and approved by the Engineer prior to concreting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Concrete Aggergate
label | Acceptance / Conformance Criteria - Aggregates for concrete shall be selected from a single source, which shall be used for all concrete that will form part of the permanent works.
label | ○ Nominal maximum coarse aggregate size shall be 15mm.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
label | Verifying Document - Mix Design
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Concrete Capping Concrete
label | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa.
label | Standard / Specification - PS 18.5.1
label | Verifying Document - Approved Mix Design
label | Frequency - Submitted to and approved by the Engineer prior to concreting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Capping Steelwork
label | Acceptance / Conformance Criteria - All grade 500E (MA) reinforcement shall comply with AS/NZS 4671 and be manufactured using micro alloy Process.
label | ○ Quench and tempered is not permitted.
label | Standard / Specification - PS 18.5.2, PS 18.1.2
label | Verifying Document - Detail Sheets and Mill Certificates
label | Frequency - Prior to ordering steel
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | PFC & UC Steelwork
label | Acceptance / Conformance Criteria - Sections shall be grade 300 unless noted otherwise.
label | ○ All PFC & UC's to be grade 350 unless indicated otherwise All structural steel welding to comply with AS/NZS 1554 Class G.P.
label | ○ All welds to be 6mm minimum continuous fillet welds, unless noted otherwise.
label | Standard / Specification - PS 18.5.2, PS 18.1.2
label | Verifying Document - Detail Sheets and Mill Certificates
label | Frequency - Prior to ordering steel
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.20 Fall Protection Materials
checkpoint | Fall Protection Fence Materials
label | Acceptance / Conformance Criteria - Safety fence design load shall be in accordance with NZS1170.1: Table 3.3 Type C3.
label | ○ All steelwork shall be hot-dip galvanised in accordance with AS/NZS 4680:2006.
label | Standard / Specification - PS 18.6.1, PS 19.25.1
label | Verifying Document - Datasheets and Mill Certs
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Fall Protection Fence Epoxy
label | Acceptance / Conformance Criteria - SikaDur UA Epoxy Repair Mortar or a similar approved mortar.
label | Standard / Specification - PS 18.6.1, PS 19.25.1
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Fall Protection Fence Base plates
label | Acceptance / Conformance Criteria - Mild steel baseplate with holes shall be Hot Rolled Grade 250 complying with AS/NZS3678:2016 (AS/NZS3678-350).
label | Standard / Specification - PS 18.6.1, PS 19.25.1
label | Verifying Document - Datasheets and Mill Certs
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.21 Underpass Materials
checkpoint | Concrete Plant
label | Acceptance / Conformance Criteria - All plants supplying concrete to the project shall hold and maintain a current quality Certificate of Audit in accordance with NZS 3104 throughout the duration of their supply of concrete for the contract.
label | ○ A copy of each plant’s current Certificate of Audit shall be submitted to the Engineer prior to their initial supply of concrete.
label | Standard / Specification - PS 19.7.1
label | Verifying Document - Audit Cert
label | Frequency - Prior to their initial supply of concrete
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Blinding Concrete
label | Acceptance / Conformance Criteria - Blinding concrete shall have a minimum 28 days compression strength of 10 MPa and comply with the requirements for Prescribed Mix concrete specified by NZS 3104.
label | Standard / Specification - PS 19.5.1, PS 19.7.10
label | Verifying Document - Approved Mix Design
label | Frequency - Submitted to and approved by the Engineer prior to concreting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Underpass Entrances Concrete
label | Acceptance / Conformance Criteria - The Underpass Entrances (insitu) concrete shall be a Normal 40MPA 19mm Mix.
label | Standard / Specification - PS 19.6.1, PS 19.7.9
label | Verifying Document - Approved Mix Design
label | Frequency - Submitted to and approved by the Engineer prior to concreting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Precast Mild steel fixings
label | Acceptance / Conformance Criteria - All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication.
label | Standard / Specification - PS 19.15.6
label | Verifying Document - Datasheet / Mill Certs
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Precast Stainless steel
label | Acceptance / Conformance Criteria - Stainless steel shall be type 316 unless otherwise specified.
label | Standard / Specification - PS 19.15.7
label | Verifying Document - Datasheet / Mill Certs
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Reinforcement cover spacer blocks
label | Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas.
label | Standard / Specification - PS 19.7.8
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.22 Underpass Materials
checkpoint | uPVC Pipe
label | Acceptance / Conformance Criteria - Pipes and fittings shall comply with the requirements of AS/NZS 1254:2010 for uPVC pipes
label | Standard / Specification - PS 19.27
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Anti-Graffiti Product
label | Acceptance / Conformance Criteria - Permanent (not sacrificial) anti-graffiti coatings shall be applied to the exposed faces of all concrete surfaces including wingwalls.
label | ○ The coatings shall have a design life of not less than 10 years.
label | ○ The Contractor shall submit the proposed extent of application for authorisation by the Engineer.
label | Standard / Specification - PS 19.24.1, PS 19.24.2
label | Verifying Document - Details of prequalified Product
label | Frequency - Prior to Application
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Anti-Graffiti Label
label | Acceptance / Conformance Criteria - At least two weeks prior to the applicable works, the Contractor shall submit details of the label to the Engineer for authorisation.
label | Standard / Specification - PS 19.24.4
label | Verifying Document - Label Details
label | Frequency - At least two weeks prior to the applicable works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Steelwork Fabrication Notice
label | Acceptance / Conformance Criteria - To allow for the provision of inspection and verification, the Contractor shall, in writing, notify the Engineer at least one weeks prior to commencement of the workshop fabrication work.
label | Standard / Specification - PS 19.26.6
label | Verifying Document - Notice
label | Frequency - At least one weeks prior to fabrication
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Steelwork Shop and Erection Drawings
label | Acceptance / Conformance Criteria - The Contract Drawings show the design intent. The Contractor shall submit shop and erection drawings to the Engineer for approval a minimum of 10 days prior to fabrication.
label | Standard / Specification - PS 19.26.7
label | Verifying Document - Drawings
label | Frequency - 10 days prior to fabrication
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Welding Plan
label | Acceptance / Conformance Criteria - The Welding Plans shall comply with AS/NZS 5131, Section 7.
label | Standard / Specification - PS 19.26.8
label | Verifying Document - Welding Plan
label | Frequency - Prior to Welding
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Welder Qualiications
label | Acceptance / Conformance Criteria - Welder Qualiications shall comply with AS/NZS 5131, Section 7.
label | Standard / Specification - PS 19.26.8
label | Verifying Document - Qualifications
label | Frequency - Prior to Welding
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Supply of Non-slip Coating
label | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150.
label | Standard / Specification - PS 19.23.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Joint Sealing and Waterproofing Sealant
label | Acceptance / Conformance Criteria - Joints are to be sealed using a fuel resistant, multi-component polysulphide sealant designed for horizontal and vertical joints in concrete and is joint sealant pourable or gunning grade as appropriate.
label | Standard / Specification - PS 19.22.1, PS 19.22.7
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Debonding tape / Backing Rod
label | Acceptance / Conformance Criteria - A polyethylene bond breaker tape, or a closed cell, polyethylene backing rod shall be used in movement joints unless joint sealant is natureally bond breaking.
label | Standard / Specification - PS 19.22.3
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Compressible filler board
label | Acceptance / Conformance Criteria - Details of the Compressible filler board proposed to be used shall submitted to the Engineer for acceptance at least 1 week prior to installation.
label | Standard / Specification - PS 19.22.6
label | Verifying Document - Datasheet
label | Frequency - prior to installation.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcement bars
label | Acceptance / Conformance Criteria - All Reinforcement bars shall be of New Zealand origin unless otherwise accepted, grade 500 ductility class E and shall be manufactured by the micro-alloy process.
label | ○ Quenched and tempered reinforcement shall not be permitted.
label | Standard / Specification - PS 19.16.12
label | Verifying Document - Mill Certs
label | Frequency - Each Item
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Reinforcing coating mass and thickness
label | Acceptance / Conformance Criteria - The coating mass and thickness shall be determined in accordance with Appendix G and shall comply with Table 1 and 2 of AS/NZS 4680.
label | ○ In case of disagreement, the test method selected shall be agreeable to both Contractor and Engineer.
label | Standard / Specification - PS 19.16.14
label | Verifying Document - Datasheet / Coating Cert
label | Frequency - Before incorporating these materials
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Reinforcement Welding Approval
label | Acceptance / Conformance Criteria - Steel reinforcement shall not be welded, except where specified on the Drawings or approved by the Engineer. In either case, welding of reinforcement shall comply with AS/NZS 1554.3.
label | Standard / Specification - PS 19.16.15
label | Verifying Document - Engineers Approval
label | Frequency - Before Welding
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Welding TPI Inspections
label | Acceptance / Conformance Criteria - The welding shall be inspected by the Contractor’s Third Part Inspector who shall meet the "Qualifications of Inspectors" requirements of AS/NZS 1554.3 Clause 10.2.
label | ○ Inspections of the welding shall be in accordance with AS/NZS 1554.3 with the following additional requirements: All welding shall undergo visual scanning. Welding shall be non-destructively tested to the extent and standards of acceptance of AS/NZS 1554.1 Appendix F, for SP welds.
label | ○ All welds shall be visually scanned by the steel fabricator. 30% of the welds shall undergo visual examination in accordance with Table 6.2.2 and 5% of the welds shall be subjected to radiography or ultrasonic testing in accordance with Table 6.2.1 of AS/NZS 1554.1.
label | Standard / Specification - PS 19.16.16
label | Verifying Document - TPI Report
label | Frequency - 100% Visual Scanning 30% Visual Examination 5% Radiography / Ultrasonic Tesing
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Bar Schedule
label | Acceptance / Conformance Criteria - The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars.
label | Standard / Specification - PS19.16.20
label | Verifying Document - Bar Schedule
label | Frequency - At least 14 days before the start of placing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcing Mill Certs
label | Acceptance / Conformance Criteria - Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of ay work incorporating these materials.
label | ○ Test certificates shall be traceable to the batch of material supplied to the work.
label | Standard / Specification - PS19.16.23
label | Verifying Document - Mill Certs
label | Frequency - At least one week before the programmed commencement of ay work incorporating these materials
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Corrosion Protection
label | Acceptance / Conformance Criteria - Unless otherwise shown on drawings, all steel members, bolts, nuts and washers, excluding any stainless-steel components shall be hot dip galvanized after fabrication in accordance with AS/NZS4680.
label | Standard / Specification - PS 19.17.1
label | Verifying Document - Datasheet
label | Frequency - Each Item
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 8.01 Kerb and Channel
checkpoint | Saw Cutting
label | Acceptance / Conformance Criteria - Existing surfaces shall be sawcut at the limits of excavation if they are not to be reconstructed following the construction of the concrete kerbs and channels etc.
label | ○ Existing kerbs to remain shall be sawcut to 50mm depth on all exposed faces.
label | Standard / Specification - Downer
label | Verifying Document - Photos
label | Frequency - Each Kerb
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Foundations
label | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | Standard / Specification - Downer
label | Verifying Document - Scala Report
label | Frequency - 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Fill Compaction Testing
label | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
label | Standard / Specification - Downer
label | Verifying Document - IANZ NDM Report
label | Frequency - 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Kerb String Line Inspection
label | Acceptance / Conformance Criteria - Prior to laying, string lines will be inspected by the Engineer.
label | Standard / Specification - PS 17.3.2
label | Verifying Document - Pre Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | Kerb
label | Acceptance / Conformance Criteria - Contraction joints (saw cut joints) in channels shall be formed at maximum 4m spacings, at right angles to the kerb line.
label | ○ The joint material shall be set flush with the surface and shall be a minimum of 25mm deep.
label | Standard / Specification - PS 17.3.2
label | Verifying Document - Post Pour
label | Frequency - Every 4m
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Kerb Finish
label | Acceptance / Conformance Criteria - Concrete surfaces, un-trafficked by vehicles or pedestrians exposed to view above ground level, shall be smooth and comply with Finish F4 in NZS 3114.
label | ○ Horizontal concrete surfaces, trafficked by vehicles or pedestrians, shall be wood floated to comply with Finish U2 in NZS 3114.
label | Standard / Specification - PS 17.3.2
label | Verifying Document - Post Pour
label | Frequency - Each pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Unreinforced Channel Contraction Joints
label | Acceptance / Conformance Criteria - Contraction joints in unreinforced channels shall be formed at 4-metre centres, at right-angles to the kerb line, by insertion of "Malthoid" D.P.C or equivalent strip.
label | ○ The joint material shall be set flush with the surface and shall be a minimum of 25mm deep.
label | ○ Contraction joints shall be coincident with joints in precast kerb blocks.
label | Standard / Specification - PS 17.3.3
label | Verifying Document - Post Pour
label | Frequency - Every 4m
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Channel Finish
label | Acceptance / Conformance Criteria - The top surface of channels shall be finished smooth and even with a steel trowel.
label | ○ Channels shallnot pond water at any point.
label | Standard / Specification - PS 17.3.3
label | Verifying Document - Post Pour
label | Frequency - Each pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Kerb and Channel Tolerances
label | Acceptance / Conformance Criteria - Tolerances for kerb and channel shall be ±5.0mm vertically and ±10mm horizontally.
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - 16.34.3
label | Verifying Document - Survey Records
label | Frequency - At the completion of the construction of kerb and channel
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | Kerb and Channel Completion Inspection
label | Acceptance / Conformance Criteria - Engineer to review completed works including kerb and channel position, level and grade, and transitions between kerb types and at catchpit and catchpit manhole aprons / back entry lintels.
label | Standard / Specification - PS 16.38, PS 17.3.2
label | Verifying Document - K&C QA
label | Frequency - Upon compltion of K&C
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
section | 8.02 Machine Laid Kerb and Channel
checkpoint | Foundations
label | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | Standard / Specification - Downer
label | Verifying Document - Scala Report
label | Frequency - 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Fill Compaction Testing
label | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
label | Standard / Specification - Downer
label | Verifying Document - IANZ NDM Report
label | Frequency - 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Machine Laid Kerb Channel - Concrete island infill
label | Acceptance / Conformance Criteria - The base of the infill area shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP40 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm.
label | ○ Where infill is to be placed directly onto pavement surfacing, a 25mm thick sand bedding layer is to be provided.
label | ○ The base layer shall be well wetted with water immediately prior to the placing of concrete.
label | Standard / Specification - PS 17.3.6
label | Verifying Document - Pre Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Machine Laid Kerb and Channel - Contraction joints
label | Acceptance / Conformance Criteria - Contraction joints shall be formed at 5-metre maximum centres and at right-angles to the kerb line, by saw cutting or other approved method.
label | ○ Where a footpath adjoins the kerb, Contraction joints shall be coincident with joints in the footpath.
label | Standard / Specification - PS 17.3.4
label | Verifying Document - Post Pour
label | Frequency - Every 5m
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Machine Laid Kerb Channel - Pin on kerb
label | Acceptance / Conformance Criteria - Kerb installed on top of pavement surfaces shall be pinned using reinforcing pins, drilled, and epoxied into the existing pavement at a maximum spacing as specified in the drawings.
label | ○ Additional pins are to be installed at discontinuities or tight radius within the proposed kerb alignment.
label | Standard / Specification - PS 17.3.5
label | Verifying Document - Post Pour
label | Frequency - As Required
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 8.03 Concrete Island Infill
checkpoint | Foundations
label | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | Standard / Specification - Downer
label | Verifying Document - Scala Report
label | Frequency - 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Concrete Island Infill Bedding
label | Acceptance / Conformance Criteria - The base of the infill area shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP40 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm.
label | Standard / Specification - PS 17.3.6
label | Verifying Document - Pre Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity -
label | Verification Activity: By -
checkpoint | Fill Compaction Testing
label | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
label | Standard / Specification - Downer
label | Verifying Document - IANZ NDM Report
label | Frequency - 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Concrete Island Infill Concrete Placement
label | Acceptance / Conformance Criteria - The new concrete shall be 100mm in depth, coloured "Indian Summer" and constructed in accordance with NZS 3109.
label | Standard / Specification - PS 17.3.6
label | Verifying Document - Pre Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Concrete Island Infill - Construction Joints
label | Acceptance / Conformance Criteria - The Contractor shall form construction joints every 4m by saw cutting or other approved method.
label | Standard / Specification - PS 17.3.6
label | Verifying Document - Post Pour
label | Frequency - Every 4m
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Concrete Island Infill Finishing
label | Acceptance / Conformance Criteria - The edges of the infill shall be neatly chamfered.
label | ○ Concrete shall be poured in one operation and without interruption between formed construction joints.
label | ○ The whole of the surface shall be screeded, and after the initial set, it shall be carefully broomed to achieve a NZS 3114 class U5 finish.
label | Standard / Specification - PS 17.3.6
label | Verifying Document - Post Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Concrete Island Infill Curing
label | Acceptance / Conformance Criteria - The finished work shall be kept continuously wet by approved means and shall be thoroughly protected from frost, from direct rays of the sun, and from drying winds, for at least seven days after pouring.
label | ○ The concrete shall be laid so no water ponding occurs on the surface after completion.
label | Standard / Specification - PS 17.3.6
label | Verifying Document - Post Pour
label | Frequency - At least seven days after pouring
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 8.04 Shared Paths, Roundabout Concrete Apron and Driveway Access Road
checkpoint | Foundations
label | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | Standard / Specification - Downer
label | Verifying Document - Scala Report
label | Frequency - 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Driveway Access Subgrade and Subbase
label | Acceptance / Conformance Criteria - As per Pavement Type D, the subgrade shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved NZTA M/4 (≥ 100MPa) granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm.
label | ○ The granular base layer shall be well wetted with water immediately prior to the placing of concrete.
label | Standard / Specification - PS 17.4.3
label | Verifying Document - Pre Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Shared Paths and Roundabout Concrete Apron Subgrade and Subbase Installation
label | Acceptance / Conformance Criteria - The subgrade shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP20 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 500mm.
label | Standard / Specification - PS 17.4
label | Verifying Document - Pre Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Fill Compaction Testing
label | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
label | Standard / Specification - Downer
label | Verifying Document - IANZ NDM Report
label | Frequency - 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Granular Base Prep
label | Acceptance / Conformance Criteria - The granular base layer shall be well wetted with water immediately prior to the placing of concrete.
label | Standard / Specification - PS 17.4
label | Verifying Document - Pre Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Shared Paths, Roundabout Concrete Apron and Driveway Access - Construction Joints
label | Acceptance / Conformance Criteria - The Contractor shall form construction joints every 4m by saw cutting or other approved method. Concrete shall be poured in one operation and without interruption between formed construction joints.
label | Standard / Specification - PS 17.4
label | Verifying Document - Pre Pour
label | Frequency - Every 4m
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Roundabout Concrete Apron - Reinforcing Placement
label | Acceptance / Conformance Criteria - D12 reinforcing bars spaced at 400mm centres radially and D12 reinforcing bars spaced 300mm centres centrally placed as per the drawings and shall be 200mm thick.
label | Standard / Specification - PS 17.4.2
label | Verifying Document - Pre Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Roundabout Concrete Apron - Expansion Joints
label | Acceptance / Conformance Criteria - Expansion joints shall be formed at maximum spacings of 21m.
label | Standard / Specification - PS 17.4.2
label | Verifying Document - Post Pour
label | Frequency - Every 21m
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Shared Paths, Roundabout Concrete Apron and Driveway Access - Finishing
label | Acceptance / Conformance Criteria - The edges of the paths shall be neatly chamfered.
label | ○ The whole of the surface shall be screeded and after the initial set it shall be carefully broomed transversely to present a non-skid surface.
label | ○ The surface shall comply with NZS 3114 class U5.
label | Standard / Specification - PS 17.4
label | Verifying Document - Post Pour
label | Frequency - Prior to Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Shared Paths, Roundabout Concrete Apron and Driveway Access - Curing
label | Acceptance / Conformance Criteria - The finished work shall be kept continuously wet by approved means and shall be thoroughly protected from frost, from direct rays of the sun, and from drying winds for at least seven days after pouring.
label | ○ The boxing supporting the vertical faces shall not be removed for at least 36 hours after the concrete is placed.
label | Standard / Specification - PS 17.4
label | Verifying Document - Post Pour
label | Frequency - At least seven days after pouring
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 9.01 Pile Construction
checkpoint | Contractor’s Methodology for Pile Construction
label | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for acceptance his methodology for the construction of the steel soldier piles at least two weeks prior to commencement of the works.
label | Standard / Specification - PS 18.3.1, PS 18.1.2
label | Verifying Document - Approved Methodology
label | Frequency - At least two weeks prior to commencement of the works.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Construction of Piles
label | Acceptance / Conformance Criteria - in T-CES 213
checkpoint | Setting Out
label | Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the position of the piles and anchors correctly to reflect the requirements of the specification and drawings.
label | Standard / Specification - PS 18.4.2
label | Verifying Document - Survey Records
label | Frequency - Each Pile
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Setout Approval
label | Acceptance / Conformance Criteria - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out.
label | ○ No other works shall be carried out until this has been checked and approved by the Engineer.
label | Standard / Specification - PS 18.4.2
label | Verifying Document - Engineers Approval
label | Frequency - Each Pile beofre excavation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Depth of Foundation
label | Acceptance / Conformance Criteria - The Engineer will advise the depth of founding for each cylinder based on the driller’s ground description log, examination of the material from the excavation and samples at no more than 0.5 m intervals.
label | Standard / Specification - PS 18.3.2
label | Verifying Document - Engineers Approval
label | Frequency - Each Pile Before Survey and Concrete
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Pilling Records
label | Acceptance / Conformance Criteria - The pile driller shall maintain a daily record of the progress of the piling with time recorded, and details of drilling equipment used, casing installed, groundwater levels and ground conditions recorded.
label | ○ The daily records from the driller shall be submitted no later than noon the following day.
label | Standard / Specification - PS 18.3.2
label | Verifying Document - Pilling Records
label | Frequency - Daily
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Pilling Timming
label | Acceptance / Conformance Criteria - During pile construction, none of the pile holes shall be kept open for more than 48 hours and no more than 4 piles under construction at one time.
label | Standard / Specification - PS 18.3.2
label | Verifying Document - Survey Records
label | Frequency - Each Pile
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Pile Excavation Survey
label | Acceptance / Conformance Criteria - On completion of excavation, the Contractor shall survey the final reduced level of founding for each cylinder, measured to the nearest 0.01 m, and submit the surveyed final reduced levels for approval to the Engineer, prior to placing reinforcement and concrete."
label | Standard / Specification - PS 18.3.2
label | Verifying Document - Survey Records
label | Frequency - Each Pile before concrete
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Construction Tolerances for Piles
label | Acceptance / Conformance Criteria - The allowable positional tolerances of the concrete piles shall be ± 50 mm.
label | ○ The completed pile shall be plumb to within 1% of vertical, as determined by the angle from the vertical.
label | Standard / Specification - PS 18.3.3
label | Verifying Document - Survey Records
label | Frequency - Each Pile
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | Remedial Painting
label | Acceptance / Conformance Criteria - Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Verifying Document - Site Records
label | Frequency - Each Occurance
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 9.02 Monitoring Points and Survey
checkpoint | Monitoring Surveys / Deformation Surveys
label | Acceptance / Conformance Criteria - Monitoring / Deformation Surveys shall be completed on all Structures as agreed with the engineer using installed monitoring pins or fix location on structures.
label | Standard / Specification - PS 18.7.1
label | Verifying Document - Survey Records
label | Frequency - As Required
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
section | 10.01 Concrete Pours
checkpoint | Construction Joint Locations
label | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Approval
label | Frequency - Prior to Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Dry Pack Mortar
label | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Pre pour
label | Frequency - Before Works
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Blinding Concrete Subgrade Inspection
label | Acceptance / Conformance Criteria - A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer.
label | Standard / Specification - PS 19.5.1
label | Verifying Document - Pre Pour Checksheet
label | Frequency - Prior to Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcement Pre Pour Inspection
label | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Pre pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Pre-Pour Inspection
label | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Signed Pre-Pour
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Delivery Dockets
label | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Slump Testing
label | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
label | Verifying Document - Pre Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Compression Testing Insutu Concrete
label | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative.
label | ○ The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily.
label | ○ A set of test specimens shall consist of at least six field specimens made from one sample of concrete.
label | ○ Three shall be tested at 28 days after casting.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2, PS 19.8.7
label | Verifying Document - IANZ Test Results
label | Frequency - One Set Daily consist of at least six field specimens
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Compression Testing Precast Concrete
label | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
label | ○ For repetitive small pours (e.g., precast concrete barrier pours) undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
label | Standard / Specification - PS 19.8.7, PS 19.8.8, PS 19.8.9, PS 19.8.10, PS 19.8.11
label | Verifying Document - Plant Test Results
label | Frequency - 1 set per 50m3 or part therefor of / First Five then every 5th
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 10.02 Post Pours
checkpoint | Post Pour Inspection
label | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Standard / Specification - PS 18.2, PS 19, PS 19.15
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Construction joints
label | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
label | Standard / Specification - PS 18.2, PS 19, PS 19.15
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Concrete Curing
label | Acceptance / Conformance Criteria - Concrete shall be cured for at least 7 days as per the drawings / specification.
label | Standard / Specification - PS 18.2, PS 19, PS 19.12
label | Verifying Document - Post Pour
label | Frequency - At least 7 days after pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Stripping
label | Acceptance / Conformance Criteria - No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete.
label | Standard / Specification - PS 18.2, PS 19
label | Verifying Document - Post Pour
label | Frequency - At least 3 days after pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Protection of Completed Works
label | Acceptance / Conformance Criteria - Protect the completed work from damage and from dropping other materials during the remainder of the construction period.
label | ○ Do not use the completed work as a building platform or for material storage.
label | Standard / Specification - PS 18.2, PS 19
label | Verifying Document - Post Pour
label | Frequency - During the remainder of the construction period
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Defective Concrete Finishes
label | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | Standard / Specification - PS 18.2, PS 19, PS 19.13
label | Verifying Document - NCR
label | Frequency - Prior to non Minor Repair
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
section | 11.01 Fall Protection Fence
checkpoint | Fall Protection Fence Installation
label | Acceptance / Conformance Criteria - Safety fence system shall be Webforge and shall be installed in accordance with Manufacturers Specification.
label | ○ Posts are to be positioned vertically in both the longitudinal and transverse directions. All rough or sharp edges or protrusions to be buffed smooth.
label | ○ All rails should be jointed within post sphere.
label | ○ Rails should be fixed to spheres at every post by welding.
label | Standard / Specification - PS 18.6.1
label | Verifying Document - Site Records
label | Frequency - Each Fence
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Remedial Painting
label | Acceptance / Conformance Criteria - Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Verifying Document - Site Records
label | Frequency - Each Occurance
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Fall Protection Fence Post Spacing
label | Acceptance / Conformance Criteria - Post spacing shall not be larger than 2m.
label | ○ Posts should not be placed closer than 200mm from the edge of the wall joints.
label | Standard / Specification - PS 18.6.1, PS 19.25.1
label | Verifying Document - Site Records
label | Frequency - Each Fence
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Fall Protection Fence Reinforcement scanning
label | Acceptance / Conformance Criteria - Reinforcement scanning shall be carried out at every post location.
label | ○ If clashes with reinforcement are identified, the following amendments shall be taken, posts at which the rail is not spliced shall be moved +/- 50mm along the handrail alignment.
label | Standard / Specification - PS 18.6.1, PS 19.25.1
label | Verifying Document - Site Records
label | Frequency - Each Hole
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Fall Protection Fence Drilling
label | Acceptance / Conformance Criteria - Holes for fixings shall be formed using a rotary hammer drill.
label | ○ It is not permissible to cut or core through reinforcement.
label | ○ Should reinforcing steel be struck, the hole shall be abandoned, cleaned out using compressed air and backfilled with SikaDur UA Epoxy Repair Mortar or a similar approved mortar.
label | Standard / Specification - PS 18.6.1, PS 19.25.1
label | Verifying Document - Site Records
label | Frequency - Each Hole
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 12.01 Undercut to Drying Site and Backfill with Compacted GAP65
checkpoint | Excavations
label | Acceptance / Conformance Criteria - All excavations/cuts shall be carried out in fully drained conditions with no free water on the working surface.
label | Standard / Specification - PS 19.4.1
label | Verifying Document - Site Records
label | Frequency - During Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Foundations
label | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | Standard / Specification - Downer
label | Verifying Document - Scala Report
label | Frequency - 10m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | GAP65
label | Acceptance / Conformance Criteria - The imported granular Material shall be GAP65 with the grading envelope given in Table 15-3 and have the following geotechnical parameters after placement and compaction Angle of internal friction = 35° and Cohesion = 0kPa
label | Standard / Specification - PS 19.4.5.3
label | Verifying Document - IANZ Test Reprots
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | GAP65 Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
label | Standard / Specification - PS 19.4.5.4
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | GAP65 Layer thickness.
label | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitored for Layer thickness. The GAP65 layers shall be constructed in accordance with NZTA B/2. The maximum lift thickness shall be 200mm.
label | Standard / Specification - PS 19.4.5.4
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Proof Rolling
label | Acceptance / Conformance Criteria - The GAP65 layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots.
label | ○ The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
label | Standard / Specification - PS 19.4.5.5
label | Verifying Document - Site Records
label | Frequency - Prior to Concreting
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
section | 12.02 Concreting
checkpoint | Insitu Concreting Methodology
label | Acceptance / Conformance Criteria - The Contractor shall submit the proposed handling and placing methods, sequence and timing of pours and location on construction joints for the Engineer's consent before concrete placing commences.
label | ○ Where a placing diagram, construction joint location diagram or equivalent is included in the drawings, the requirements thereof shall be followed unless changes are specifically agreed by the Engineer in writing.
label | Standard / Specification - PS 19.9.1
label | Verifying Document - Methodology
label | Frequency - Before concrete placing commences
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 12.03 Precast Concrete
checkpoint | Precast Methodology
label | Acceptance / Conformance Criteria - Details of the proposed method of casting, curing, storing, transportation, and erection shall be submitted to the Engineer before commencing manufacture of the mould and precast units.
label | ○ The Engineer shall be informed 24 hours prior to the casting of any unit, to allow the Engineer to attend the pre-casting plant to inspect before and during production of the units.
label | Standard / Specification - PS 19.15.1
label | Verifying Document - Methodology
label | Frequency - Before commencing manufacture of the mould and precast units.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Precast Shop Drawings
label | Acceptance / Conformance Criteria - The Contractor shall make available the shop drawings to the Engineer for review, at least 14 days prior to manufacture.
label | ○ Any variations between the Drawings and shop drawings shall be clearly identified and brought to the attention of the Engineer.
label | Standard / Specification - PS 19.15.16
label | Verifying Document - Shop Drawings
label | Frequency - At least 14 days prior to manufacture
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 12.04 Installation and Bolt Tightening
checkpoint | Structural steelwork fixed to the concrete surfaces Dry Packing
label | Acceptance / Conformance Criteria - All structural steelwork fixed to the concrete surfaces shall be bedded against the concrete surfaces using a layer of dry pack mortar, plastic bedding mortar or grout with a minimum compressive strength at 28 days of at least the specified compressive strength of the element being bedded against.
label | Standard / Specification - PS 19.18.1
label | Verifying Document - Pre Pour
label | Frequency - All structural steelwork fixed to the concrete surfaces
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Bolt, threaded rod, and stud connections
label | Acceptance / Conformance Criteria - All bolt, threaded rod, and stud connections shall be installed in accordance with AS/NZS 5131 Section 8.2.
label | ○ Tightening shall be to the snug tight condition as specified in Section 8.3 of AS/NZS 5131 after the mortar packing or grout has hardened.
label | ○ Where shown on the drawings, lock nuts shall be fitted, and snug tightened against the nut.
label | Standard / Specification - PS 19.18.2
label | Verifying Document - Site Records
label | Frequency - Each Bolt
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | 12.05 Underpass and Wingwall Backfill
checkpoint | Polythene Sheet above Underpass
label | Acceptance / Conformance Criteria - Two layers of polythene sheet shall be placed across the full width and length of all underpass precast concrete units.
label | ○ The polythene sheet shall have a nominal thickness of 0.25mm and comply with the requirements of the New Zealand Building Code.
label | ○ Polythene sheet shall be lapped by a minimum of 150mm at all joints.
label | Standard / Specification - PS 19.19.1
label | Verifying Document - Site Records
label | Frequency - Each Sheet
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Minimum cover over Underpass
label | Acceptance / Conformance Criteria - The minimum cover to the underpass within all traffic lanes is to be 600mm to the top of the pavement.
label | Standard / Specification - PS 19.19.1
label | Verifying Document - Survey Records
label | Frequency - During Backfilling
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | AP40 Backfill alongside Underpass
label | Acceptance / Conformance Criteria - Fill shall be spread in horizontal layers not exceeding 200mm loose depth.
label | ○ Backfill shall be compacted in accordance with TNZ B/2.
label | ○ The maximum lift thickness shall be 200mm.
label | ○ Backfill shall be carried out in unison on both sides of the box underpass such that the level of backfill on one side is not more than 500mm different from the other side, at all times. and testing shall be completed on each lift.
label | Standard / Specification - PS 19.19.2
label | Verifying Document - Site Records
label | Frequency - Each lift
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | AP40 Backfill Compaction Testing
label | Acceptance / Conformance Criteria - Clegg testing shall be carried out and recorded for each lift (200mm Maximum) to be carried out once per 10m length of the 300mm wide AP40 strip. A CIV value of 40 shall be achieved for each test.
label | Standard / Specification - PS 19.19.2
label | Verifying Document - Clegg Results
label | Frequency - Each lift to be carried out once per 10m length of the 300mm wide AP40 strip
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Polythene sheet at Culvert
label | Acceptance / Conformance Criteria - The polythene sheet between the precast culvert and the structural fill, or site concrete layer.
label | ○ The polyethene sheet shall be a single continuous sheet with no joins.
label | ○ The sheet is to be laid flat with folds or wrinkles prior to the placement of material on top.
label | Standard / Specification - PS 19.20.2
label | Verifying Document - Site Records
label | Frequency - Each Culvert Entrance
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 12.06 Joint Sealing and Waterproofing
checkpoint | Preperation
label | Acceptance / Conformance Criteria - The joints surfaces should be accurately formed and must be thoroughly dry, clean, and free from frost.
label | ○ Remove all laitance, curing compounds, form release agents, loose material, and any contaminating foreign matter from joint faces by grinding, grit blasting or wire brushing.
label | ○ The prepared sealing slot should be blown out with dry, oil-free compressed air.
label | ○ The sealant may be applied in joints up to a maximum of 30mm wide.
label | ○ All moving joints should be designed to an optimal width to depth ratio of 2:1, with a minimum joint size of 12mm sealant depth.
label | Standard / Specification - PS 19.22.2
label | Verifying Document - Site Records
label | Frequency - Each Joint
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Movement joints
label | Acceptance / Conformance Criteria - In movement joints, the sealant must not be allowed to bond to the back face of the joint.
label | Standard / Specification - PS 19.22.3
label | Verifying Document - Site Records
label | Frequency - Each Joint
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Concrete Age
label | Acceptance / Conformance Criteria - New concrete must be allowed to cure for a minimum of 28 days before sealant installation.
label | Standard / Specification - PS 19.22.4
label | Verifying Document - Site Records
label | Frequency - 28 days post pouring
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 12.07 Supply and Install of Non-slip Coating
checkpoint | Install of Non-slip Coating
label | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150 applied after the installation of the box culvert segments.
label | ○ The thickness of this is to be between 3 and 5mm.
label | ○ The application of the product must be done in accordance with the manufacturer’s specifications.
label | Standard / Specification - PS 19.23.2
label | Verifying Document - Site Records
label | Frequency - Each Underpass
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | 12.08 Anti-Graffiti Finish
checkpoint | Anti-Graffiti Application
label | Acceptance / Conformance Criteria - The anti-graffiti coatings shall be applied and maintained in accordance with the manufacturer's requirements.
label | Standard / Specification - PS 19.24.3
label | Verifying Document - Site Records
label | Frequency - Each Application
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Anti-Graffiti Label Application
label | Acceptance / Conformance Criteria - A self-adhesive label shall indicate all areas of anti-graffiti coatings on site.
label | Standard / Specification - PS 19.24.4
label | Verifying Document - Site Records
label | Frequency - Each Structure
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 12.09 Steelwork Fabrication and Installation
checkpoint | Welding
label | Acceptance / Conformance Criteria - Welding shall comply with AS/NZS 5131, Section 7.
label | Standard / Specification - PS 19.26.8
label | Verifying Document - Site Records
label | Frequency - Each Weld
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Holing
label | Acceptance / Conformance Criteria - Holing shall comply with AS/NZS 5131, Section 6.7.
label | Standard / Specification - PS 19.26.9
label | Verifying Document - Site Records
label | Frequency - Each Hole
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Installation
label | Acceptance / Conformance Criteria - Holing shall comply with AS/NZS 5131
label | Standard / Specification - PS 19.26
label | Verifying Document - Site Records
label | Frequency - Each Item
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 12.10 uPVC Pipe
checkpoint | Plastic Pipe Trench Backfill
label | Acceptance / Conformance Criteria - Except as shown otherwise on the drawings, or directed otherwise by the Engineer, support material shall be as per AS/NZS 2566.2.2002 "Buried flexible pipelines – installation" corresponding to the relevant pipe support type as detailed.
label | ○ All materials in bedding zones, side zones and haunching zones shall comply with the grading specification in the aforementioned AS/NZS 2566.2.2002.
label | Standard / Specification - PS 19.27.4