## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-024 Pit Works Completion - Rev.1 | itp |  |  |  |  | INF-HSEQ CC0375-ITP-024 Pit Works Completion - Rev.1
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 1.2 - Lot Traceability
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance criteria - Prepare a lot map for traceability of the work area
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Set out
label | Ref docs - Drawings
label | Acceptance criteria - Setout pits to the location and levels on the drawings. This shall be presented for inspection by the superintendent.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 1.4 - Pit Handover
label | Acceptance criteria - Each pit shall be visually inspected prior start of the completion works. Any defects recorded must be reported and rectified before receiving back the pit from HPP.
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Joint inspection with HPP rep
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Pit Completion Works
checkpoint | 2.1 - Pit Lid Installation
label | Ref docs - Drawings
label | Acceptance criteria - Pits Lids to be installed as per drawings and manufacturers specifications utilising certified lifting points.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.2 - Access Covers & Grates
label | Ref docs - Drawings
label | Acceptance criteria - Access covers, grates and frames to be installed as per the drawings AS 3996
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.3 - Step Irons
label | Ref docs - Drawings
label | Acceptance criteria - Pits deeper than 600 to be fitted with galvanised plastic-coated step irons as per AS1657
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.4 - Pit Jointing (if applicable)
label | Ref docs - Spec. 1354 Stormwater Drainage Structures [Cl 3.5]
label | Acceptance criteria - Internal joints between precast pits and riser units to be waterproofed as per Symal RFI-037 & manufacturer recommendations.
label | ○ External Joints between pits and abutting concrete pavement, kerb or structures to be a 10mm isolation joint.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.5 - Brass Marker Plates
label | Ref docs - Spec. 0002 General Electrical Installation [Cl 6.11] Drawings
label | Acceptance criteria - Brass marker plates to be installed at each pit showing cable/conduit routes, contact phone number, organisation & drawing number.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.6 - Cable Markers
label | Ref docs - Spec. 0002 General Electrical Installation [Cl 6.10]
label | Acceptance criteria - Install Concrete Cable markers on the surface of all underground cable joints, at every change in direction, and on straight runs at least every 30m.
label | ○ Markers to be a 400mm square and 100mm deep concrete block with a brass label attached. Label to identify conduit type and direction.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
section | 3.0 Conformance Check
checkpoint | 3.1 - Survey Report
label | Ref docs - Spec. 0161 Quality [Cl 3.13]
label | Acceptance criteria - An as-built survey of the drainage system been completed to ensure all structures are within construction tolerances.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - W
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Survey report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT