## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Drains |  |  |  |  | Yes | Drains | 20ab26d1-a3b3-43bd-adc7-afe7648643e9
checkpoint-status |  |  | checkpoint | Drains
checkpoint-status |  |  | checkpoint | Smoke Seal Penetrations
checkpoint-status |  |  | checkpoint | Acoustic Lagging
checkpoint-status |  |  | checkpoint | Testing (Water/Air)
checklist-flat |  |  | checklist | Commisioning |  |  |  |  | Yes | Commisioning | a98ae8f2-1b63-4eef-8c0d-df882f597d4f
checkpoint-status |  |  | checkpoint | Bulk Hot Water
checkpoint-status |  |  | checkpoint | Test Hot Water Temperature
checkpoint-status |  |  | checkpoint | Test Waste for leaks
checklist-flat |  |  | checklist | Fit Off |  |  |  |  | Yes | Fit Off | aea657fa-7980-414e-ae4b-afd61c309c58
checkpoint-status |  |  | checkpoint | Bathroom Shower Mixer
checkpoint-status |  |  | checkpoint | Bathroom Shower Rail/Rose
checkpoint-status |  |  | checkpoint | Bathroom Basin
checkpoint-status |  |  | checkpoint | Bathroom Basin Mixer
checkpoint-status |  |  | checkpoint | Bathroom Bottle Trap
checkpoint-status |  |  | checkpoint | Bathroom Toilet
checklist-flat |  |  | checklist | Corridor/Shafts |  |  |  |  | Yes | Corridor/Shafts | caae1443-824b-43ab-9c9a-bce03d85f42d
checkpoint-status |  |  | checkpoint | Hot Water
checkpoint-status |  |  | checkpoint | Hot Water Lagged
checkpoint-status |  |  | checkpoint | Cold Water
checkpoint-status |  |  | checkpoint | Test Hot Water
checkpoint-status |  |  | checkpoint | Test Cold Water
checkpoint-status |  |  | checkpoint | PRV'S installed
checkpoint-status |  |  | checkpoint | Fire Caulking to Apt
checklist-flat |  |  | checklist | Rough In |  |  |  |  | Yes | Rough In | eb644cf7-c403-4063-bf58-f2f537cf106a
checkpoint-status |  |  | checkpoint | High Level Rough In
checkpoint-status |  |  | checkpoint | Wall Set Out
checkpoint-status |  |  | checkpoint | Wall Rough In
checkpoint-status |  |  | checkpoint | Waste Rollovers & AAV'S
checkpoint-status |  |  | checkpoint | Test Water
checklist-flat |  |  | checklist | Plant and equipment |  |  |  |  | Yes | Plant and equipment | eb8de2a9-dbc0-4dca-8147-b3b92eda9434
checkpoint-status |  |  | checkpoint | Hot water system
checkpoint-status |  |  | checkpoint | Cold water pump
checkpoint-status |  |  | checkpoint | Cold water break tank
checkpoint-status |  |  | checkpoint | Rainwater pump
checkpoint-status |  |  | checkpoint | Rainwater tank / Diversion valve
checkpoint-status |  |  | checkpoint | Water meter assembly
checkpoint-status |  |  | checkpoint | GIT