## Master List Templates
Id | Type | Name | Values | Prompting Name
c31ab009-b12c-48be-b530-3179f6d5c8ed | checklist | ITP021 Conduit Installation |  | ITP021 Conduit Installation
f9da0fd8-e475-4507-b6df-1e8c03a1d7cf | section | Details
33bc2c15-5629-43e6-8901-1e0fac0bac78 | checkpoint-no-value | Conduit Details
97f5a68b-a2c1-55f4-a650-3933528ce60c | textbox | Conduit Run Type
04d81416-0b54-5816-875b-5db51bdd9352 | textbox | Description. Conduit route, size and Qty.
fba12d56-ec8b-5781-95db-b935f8c548b6 | textbox | Drawing Reference
3271b2b6-7da3-44af-b7c7-fd925e6fc5e3 | checkpoint | Check for existing services, correct location & permit approval
0337ef87-06a5-5363-85d8-89414319e2d8 | textbox | Details
26e054e1-a963-4b2d-a01a-2297ffa14be9 | checkpoint | Correct Depth / Cover
4e5f7d63-d15d-494e-a0c3-2e2499bb0358 | checkpoint | Tied and joins glued
b4bb149b-f1f7-4fa9-8fc4-27856f213e59 | checkpoint | Marker Tape Required
9d96e5cb-c1a6-4f8d-8ceb-b37d8404fd0d | checkpoint | Compaction
fbe43d98-5869-4be8-843b-8fb6a496880f | checkpoint | Draw Strings Installed
f130f197-56b4-4b53-95d3-501696a84829 | checkpoint | Pits installed as required
955522fd-1f9e-491e-9e03-9187279e7c57 | checkpoint | Sealed Ends
d1b7151a-2023-41eb-b5f9-3121feb2e912 | checkpoint | Area Clean & Safe
904f49b5-605f-40ab-b15c-f3a557a1eeb8 | checkpoint | Mark up on Drawings
0d51c61b-cfa6-435c-943b-922923fd40ca | checkpoint | Ready for wall sheeting
b6fe094c-991f-439f-b052-a11bb9b6d839 | checkpoint-no-value | Additional notes

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
1a799176-a361-4fc6-8d7a-2a0d4d9bdb61 | checklist | SNSW Maintenance - Additional Notes |  | SNSW Maintenance - Additional Notes
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
aec4cb23-80de-4042-8434-e45a976919ff | checkpoint-no-value | Please detail anything else you believe to be an issue/concern
083013e9-7c55-472c-b96f-20dc889a7bef | checklist | SNSW Maintenance - Building details |  | SNSW Maintenance - Building details
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
6a72155b-7b97-4ba6-a1b0-f0c2d3f01753 | checkpoint-no-value
0c986895-8f61-5b14-aaa2-18227c6c9fdd | date | Date:
bbb1a129-f06b-571a-8db3-fd90885e1a8d | dropdown | Service NSW Centre | Albury Service Centre, Armidale Service Centre, Auburn Service Centre, Ballina Service Centre, Bankstown Service Centre, Batemans Bay Service Centre, Bathurst Service Centre, Bega Service Centre, Blacktown Service Centre, Bondi Junction Service Centre, Botany Service Centre, Broken Hill Service Centre, Brookvale Service Centre, Burwood Service Centre, Casino Service Centre, Castle Hill Service Centre, Cessnock Service Centre, Chatswood Service Centre, Coffs Harbour Service Centre, Cooma Service Centre, Cootamundra Service Centre, Corrimal Service Centre, Cowra Service Centre, Deniliquin Service Centre, Dubbo Service Centre, Eastgardens Service Centre, Eden Service Centre, Edmondson Park Service Centre, Engadine Service Centre, Erina Service Centre, Finley Service Centre, Forbes Service Centre, Glen Innes Service Centre, Glenmore Park - New centre, Gosford Service Centre, Goulburn Service Centre, Grafton Service Centre, Griffith Service Centre, Gunnedah Service Centre, Haymarket Service Centre, Hay Service Centre, Hornsby Service Centre, Hurstville Service Centre, Inverell Service Centre, Kempsey Service Centre, Kiama Service Centre, Leeton Service Centre, Lightning Ridge Service Centre, Lismore Service Centre, Lithgow Service Centre, Liverpool Service Centre, Macarthur Service Centre, Maclean Service Centre, Macquarie Fields - DT & DTK Centre, Maitland Service Centre, Marrickville Service Centre, Merrylands Service Centre, Miranda Service Centre, Mittagong Service Centre, Moree Service Centre, Moruya Service Centre, Mount Druitt SNSW, Mudgee Service Centre, Murwillumbah Service Centre, Muswellbrook Service Centre, Nambucca Heads Service Centre, Narooma Service Centre, Narrabri Service Centre, Narrandera Service Centre, Nelson Bay Service Centre, Newcastle Contact Centre, Newcastle Service Centre, North Rocks Service Centre, North Sydney Service Centre, Nowra Service Centre, Nyngan Service Centre, Orange Service Centre, Parkes Service Centre, Parramatta Contact Centre, Parramatta Service Centre, Penrith Service Centre, Port Macquarie Service Centre, Queanbeyan Service Centre, Raymond Terrace Service Centre, Revesby Service Centre, Richmond Service Centre, Rockdale Service Centre, Roselands Service Centre, Ryde Service Centre, Silverwater Service Centre, Singleton Service Centre, Springwood Service Centre, St Marys Driver Test Centre, Tallawong Service Centre - New centre, Tamworth Service Centre, Taree Service Centre, Tenterfield Service Centre, Toronto Service Centre, Toukley Service Centre, Tuggerah Service Centre, Tumut Service Centre, Tuncurry Service Centre, Tweed Heads Service Centre, Ulladulla Service Centre, Wagga Wagga Service Centre, Walgett Service Centre, Wallsend Service Centre, Warners Bay Service Centre, Warrawong Service Centre, Warriwood Service Centre, Wauchope Service Centre, Wellington Service Centre, Wentworth Service Centre, West Wyalong Service Centre, Wetherill Park Service Centre, Wollongong Service Centre, Woy Woy Service Centre, Wynyard Service Centre Service Centre, Yass Service Centre, Young Service Centre Service Centre
932c751b-6b5d-518f-a759-4e79eeb1ecc0 | textbox | Name of Supervisor/Technician
71e91821-b97a-5ade-a494-ad156cbfdacf | textbox | Start Time (24 hour)
98c35063-0c1c-5a19-88fb-6b2ee96829c6 | textbox | Finish Time (24 hour)
b6d752fe-297e-469b-958f-fe9695d7a7ac | checklist | SNSW Maintenance - Comms Rack |  | SNSW Maintenance - Comms Rack
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0efb5852-fe39-4946-be24-e307073cb2ad | checkpoint-no-value | Where is the comms rack located
9e857b29-fe36-4d70-a942-875904a6010b | checkpoint-no-value | Are keys required to access the comms room
b1a88671-f7e2-47ef-9c35-4700ecd60cdb | checkpoint-no-value | Model of the comms rack
d23e214e-2bdd-47a5-a9e8-96065006c485 | checkpoint-no-value | Brand of comms cable
080278c2-5283-421c-992e-fc40e72e6a47 | checkpoint-no-value | Take photos of comms rack
7ec780e2-b177-4022-9d57-aa88a4d6f9b5 | checkpoint-no-value | Take close up photos of all equipment in the comms rack
3711e959-92e5-4429-a6cb-2d0479e737d1 | checkpoint | Add new checklist for additional comms racks
5fcfc3ef-ac3e-484b-b82f-a65a71eced86 | checklist | SNSW Maintenance - Comms Rack - Final check |  | SNSW Maintenance - Comms Rack - Final check
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0a8a32f1-a313-46d4-b632-2d9955cbbe5e | checkpoint | Have you taken pictures of comms rack
92a98b30-dfe1-490d-bb8d-22495b35d0b3 | checkpoint | Have you taken pictures of comms equipment
b6deebc8-bb3f-4733-aad7-74ecdc4069f4 | checkpoint | Have you detailed brand of comms cable
b7e7b25b-bad5-4371-91c4-e916f092c90e | checkpoint | Have you added checklists for additional Comms racks
bab58b83-cc57-434b-acb8-7c4f57e5d38a | checklist | SNSW Maintenance - Distribution Board |  | SNSW Maintenance - Distribution Board
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
efd832a3-feae-4752-8b66-55ae6405c07e | checkpoint-no-value | Name of distribution board?
85a1f1f3-05f4-4054-bb4d-31fd6b80bb98 | checkpoint-no-value | Where is the Distribuition board located? - Photo of location
eecd95e2-73e5-4d81-bda5-9a8478f36a93 | checkpoint-no-value | Is there a DB schedule in the board - take photo
94256916-0d5f-43e7-b913-94bb2bfcabeb | checkpoint-no-value | Does the DB schedule need to be updated? If yes, detail why.
f1c77355-8286-4b95-9f87-709d6e4e8ae1 | checkpoint-no-value | How do you access the DB room (e.g. what keys /access is required) - Photos of keys required for DB & Room.
ec2a1292-a0b0-4588-b6f0-aea10f95356e | checkpoint-no-value | Take photo of board with cover on
07e7a9c9-6f36-4c69-accf-a88ba43122df | checkpoint-no-value | Take photos of board with cover off
0d242b76-9c49-4d38-be95-87cd5e55b1c5 | checkpoint-no-value | Take photos of main switch
7ced2515-e4ac-4f57-bc9d-03905b6b95c7 | checkpoint-no-value | Where is the DB fed from / isolated from? - If possible take photos
e6e88b51-7124-4800-89a0-66fe838d2c7e | checkpoint-no-value | What is the size of breaker feeding the DB? - If possible take photos
aa1c7516-59fa-40ca-aae6-92185f4bf8e6 | checkpoint-no-value | What is the size of the cable feeding the DB? - If possible take photos
b6f85025-3895-4eaf-b75f-660acf69dcf0 | checkpoint-no-value | What capacity is the DB / How many spare ways? - Take photos
640f4293-6040-4213-915c-3ddcb71d1083 | checkpoint-no-value | Is there a UPS? - If yes list the model number and take photos
83e8766c-70f8-4c05-8a24-c7400783ef79 | checkpoint-no-value | Is there a backup generator? - If yes list the model number and take photos
07387250-df05-46e0-869d-949ee697b57a | checkpoint-no-value | Do you see any issues with the current DB? Provide as much detail as possible and support with pictures
192f470e-adc8-4569-b486-21aeb1278178 | checkpoint-no-value | Brand of RCBO's - Take photos
b615c8fa-0755-4675-b4af-73dbfa067fd6 | checkpoint | Add new checklist for additional DB's
7621228f-b145-4f79-bf1f-a9df1048b022 | checklist | SNSW Maintenance - Distribution Board - Final check |  | SNSW Maintenance - Distribution Board - Final check
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
765550ca-a87a-4e48-a9e6-5e92b5303cd6 | checkpoint | Have you added checklists for additional DB's
0c17724a-5fbe-49e7-b8bd-a3ff6cff7d80 | checkpoint | Photos taken of DB
7138bb85-7393-494c-8316-6de8d09e5453 | checkpoint | Photos taken of UPS
0d454626-0318-4802-b4d7-b5a72fc9b195 | checklist | SNSW Maintenance - Emergency Lighting |  | SNSW Maintenance - Emergency Lighting
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b011b396-ce7e-4b41-b6ca-9da680a282fd | checkpoint-no-value | What type/model/brand of emergency lights are installed? (e.g. monitored)
29363325-396c-4453-a1c5-9152af657052 | checkpoint-no-value | Is there an emergency test switch?
698b4a29-415c-4a74-be58-c14a5e141914 | checkpoint-no-value | How many emergency spitfires? Detail model number
4187156c-08bf-4a75-b028-b42c7f154eee | checkpoint-no-value | Take a photo of the spitfire model number
7ade4140-eb03-4bb2-a928-c29d7ee8b48b | checkpoint-no-value | How many emergency exits? Detail model number
596c28e6-7da2-4eff-820d-2f1bb7f48c91 | checkpoint-no-value | Take a photo of the emergency lights
15e002f6-748d-4336-86b9-4a626ce54320 | checkpoint | Is there an emergency log book on site?
7eb2e767-d3e4-409e-8bbc-7bc05ddb5913 | checkpoint | If no, have you left one behind
eef4cc3a-b906-4ead-bd0d-bf68a7659de0 | checkpoint | Have you completed the emergency test - take photo
4fd8de14-e10f-5ded-830a-2c74c2b4763f | button | Did the emergency lights pass the 90min test | Yes, No
1eb819ac-dab5-5a3f-9735-ec6f24d36fb7 | textbox | If no, how many lights failed
8bce2ef4-28cb-4a95-88f6-3084268276ff | checkpoint-no-value | Detail lights that failed with model numbers
31af131c-4920-46d6-a3b6-d9dffca98504 | checklist | SNSW Maintenance - Emergency Lighting - Final check |  | SNSW Maintenance - Emergency Lighting - Final check
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4eb82889-31fd-445e-b13a-ffd35dc27f24 | checkpoint | Emergency light 90min test completed
14b53df1-17df-429b-9156-6b4620d79b37 | checkpoint | Emergency log book filled out
d776719c-411a-4918-994e-8b0062fc8f12 | checkpoint | Emergencies counted
15bd3ec0-3493-46d9-a1f3-75b725d8055b | checkpoint | Detailed any failed emergencies
98647442-ea2b-4e66-bde3-df80d8a80b9b | checkpoint | Photos taken
73fd6da9-ff47-4577-a662-d4d7d41cfeb8 | checklist | SNSW Maintenance - General maintenance |  | SNSW Maintenance - General maintenance
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
cac56815-fe09-4339-8865-0136ac684117 | checkpoint-no-value | How many counter desks are in the centre?
1c1c5500-e1bf-40ea-ba7e-f25aaf309bf6 | checkpoint-no-value | Take photos above and under each counter desk
afbf030c-5966-45b6-a76e-a32cd772f161 | checkpoint-no-value | Take photos above and under each desk
c59e0c5e-55b0-4a0b-8d7f-a68be1e6708c | checkpoint-no-value | What make is the soft wiring
360f39ad-3bd3-4966-acb3-55625de45483 | checkpoint-no-value | Take photos of privacy zones
53219b64-0eed-4aef-a963-6d97e8799ac1 | checkpoint-no-value | Take photos of internal offices
1ff0420d-32fc-4bf5-a050-604924faa167 | checkpoint-no-value | Take photos of toilet ceilings
5cf52e6b-2e33-4dae-91fa-61120a454eb8 | checkpoint-no-value | Take photos of Self service areas
43a5f5f0-c0a3-464a-bde2-c211771bbc9b | checkpoint-no-value | Take photos of photo booth areas
d1bd5a8b-9a86-402b-acc2-edf11e91a092 | checkpoint-no-value | Brand of swtiching / power
5b58553b-8c91-4aff-ace6-3ff5c6904f82 | checkpoint-no-value | Detail any issues found during the inspection (e.g. faulty soft wiring
cf27946f-692d-4e13-bb20-b8fe7f557f80 | checklist | SNSW Maintenance - General maintenance - Final check |  | SNSW Maintenance - General maintenance - Final check
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
24d8f4fa-cf6b-442f-bad0-ce62323b2aa7 | checkpoint | Have photos of all desks been taken
70f38a1d-4ff7-4a85-bd36-2f3e21c974df | checkpoint | Have you noted the make of soft wiring
2a928dff-bc64-46cc-b2af-504f3ca8be44 | checkpoint | Have you taken photos of photo booths
60998dcf-fa3e-4322-a083-363e1ac8cb0f | checkpoint | Have you taken photos of toilet ceiling
a1387082-fdc7-401b-9149-56e70a5e9939 | checkpoint | Have you taken photos of self service area
4a7b405c-dceb-424a-8096-e20a39f3689d | checkpoint | Have you noted any issues/concerns highlighted in the maintenance investigation
5a11ce38-1fab-4e10-906d-2f9d38ea8674 | checklist | SNSW Maintenance - Lighting Audit |  | SNSW Maintenance - Lighting Audit
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8b2bc637-7e06-4c31-bb78-d09e373f0571 | checkpoint | Has an LED upgrade been completed?
24b6cdf2-b443-53bb-b2b3-16d2fe91be27 | textbox | Number of Panel Lights - Detail the size of the panels / model numbers
a9110c5c-ed9b-4e58-a31c-9ec13f0d8b3b | checkpoint-no-value | Take a photos of the panel light model numbers - take photos of model numbers of all sizes of panels
b0195532-aea2-4d71-83e0-385df411ef1c | checkpoint-no-value | Number of Downlight Lights - Detail the size of the downlights / model numbers
00f1b321-0324-401f-8f0c-80bcc2cebf64 | checkpoint-no-value | Take a photos of the downlight model numbers
23f7f0fa-b2d7-4f4b-be98-fa81a688711e | checkpoint-no-value | Number of Halo Lights - Detail the size of the Halo's and model numbers
8e9f4433-9d11-4dd1-8c61-0c4e15a38972 | checkpoint-no-value | Take a photos of the halo model numbers
d28335eb-c0f1-468d-a1bc-8decfa3cb284 | checkpoint-no-value | Number of additional lights - Detail size & type of lights
7c4e01f2-b52b-4c0b-8229-e08ed658d680 | checkpoint-no-value | Take photos of all additional lights
ec5a5f96-a72b-4452-b463-5ff0c7da9cb1 | checkpoint-no-value | Total Count of the number of lights in the centre
6ad8285a-e14c-433c-a4ac-f6c3ccb5fa58 | checkpoint-no-value | How are the lights controlled? - (e.g. Dali) - Take photos of controls
77b1c60e-d567-41d5-b9fe-346cd29552ba | checkpoint-no-value | Are there any faulty lights? If yes, detail where they are located, model, number of lights, why they are faulty (e.g discoloured, not eorking, water logged)
1406c2a3-7d07-4402-856f-bce63bff80ae | checkpoint-no-value | Take photos of faulty lights
ae4da1cc-2f02-41ee-9022-423bfa840367 | checkpoint-no-value | Take photos of all lights in the Self service area
93741351-9b11-4af8-a869-f7ab824da64f | checkpoint-no-value | Take photos of all lights in the Test Area
d243f362-a04e-4187-a5db-6137faf68a7b | checkpoint-no-value | Take photos of all lights in the FOH
a164288c-412b-4cde-ab0e-5c97d5788097 | checkpoint-no-value | Take photos of all lights in the BOH
b7d03ccc-c543-4dfc-8e46-10b45e82c0d5 | checkpoint-no-value | Take photos of all lights in the Customer Area
95ee18ff-9c7d-4011-8483-a1fadca9d38c | checkpoint-no-value | Take photos of all lights in the Counter area
9e9c3845-7116-4f19-9d76-694e4b2d466d | checkpoint-no-value | Take photos of all lights in the additional areas - Name of area and photos
39cec3d7-1561-4bf0-8be5-e622fb1f7644 | checklist | SNSW Maintenance - Lighting Audit - Final check |  | SNSW Maintenance - Lighting Audit - Final check
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ebd00e83-783b-48cb-a39a-4f32f9c3bbb1 | checkpoint | Photos of all lights
8a01eaef-c251-4936-842a-5226641f4e65 | checkpoint | Lighting count
80fc85f7-7040-4f87-b23c-d5662aedb94d | checkpoint | Pictures of the model numbers of the lights
e46ed1b5-077d-483b-beef-444e162d1009 | checklist | SNSW Maintenance - RCD Testing |  | SNSW Maintenance - RCD Testing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d2549399-b1df-4edf-9921-33c18300ab81 | checkpoint | Complete RCD testing
9d1c7880-a3ea-42f4-9df8-449a13cd5eff | checkpoint-no-value | Complete RCD Test sheet - take photo of completed sheet
f69a9437-b8fd-496f-8425-bc06022fd70e | checkpoint-no-value | Have any RDC's failed - please identify RCD
bd645ae6-ad5f-47a0-a863-054ffccf83eb | checklist | SNSW Maintenance - Site Information |  | SNSW Maintenance - Site Information
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7452670f-9340-4387-81e7-1d2eba0a9dd6 | checkpoint | Is there parking available on site? If yes, take photos
d64cbd56-6d15-4276-be73-ff765aa61f2a | checkpoint | Where do you access the building? Take photos
7eca418e-b9b5-4413-82c3-3316f0f6de86 | checkpoint | Is there rear access to the centre? If yes, take photos
49004711-4044-4004-bc13-70b6f8e2187f | checkpoint | What is the ceiling height? - Please note if there are mutliple ceiling heights and take photos
84566535-da97-4947-a9b0-96c74884c637 | checkpoint | What type of ceiling is there? Detail and take photos (T-Bar, Gyprock etc)
184d29da-ba2a-4635-857f-aa89d1cd3dd8 | checkpoint | Is there external lighting? If yes, take photos
99cbe66a-0182-4a2b-a060-afb184c258ba | checklist | SNSW Maintenance - Site information - Final check |  | SNSW Maintenance - Site information - Final check
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
de82fd9a-a22e-4ba2-8e54-4b176204cb9b | checkpoint | Front access
0173ad43-9aef-4df3-809f-81d969b7cf41 | checkpoint | Rear access
1fff86a8-ca42-4087-8cf3-523968d2edcc | checkpoint | Ceilings in each room
1604fae0-225b-4b9b-a55c-6fa0283dd7d1 | checkpoint | Car park access
f34ec38c-c16a-452d-9eb6-d197a20dc3ac | checklist | SNSW Maintenance - Test and Tag |  | SNSW Maintenance - Test and Tag
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
5e20b494-dc8b-4e86-b6c8-26e4995e6e17 | checkpoint-no-value | Instruction:
c0c85cc3-460a-593e-8c22-2b4e47050434 | note | Service New South Wales centres are only allowed to have a limited number of appliances in their kitchens. The ONLY appliances that are to be tagged are:
bf6308af-06ec-4071-a4d6-23ae349c5438 | checkpoint-no-value | Test and tag - Sandwich press - Take picture
23adad0c-b29f-42a9-9aff-983fa1c9f95e | checkpoint-no-value | Test and tag - Microwave - Take picture
587711ef-9d42-4511-9a36-88467eccc55c | checkpoint-no-value | Test and tag - Fridge - Take picture
73caa21c-e9bc-4794-886a-e9454af565df | checkpoint-no-value | Test and tag - Kettle - Take picture
e46ea6dc-dcca-4dc7-b112-8f5d903447bc | checkpoint-no-value | Test and tag - Dishwasher - Take picture
1622b19d-b11c-4dda-862c-1207dbf192e6 | checkpoint-no-value | Test and tag - Toaster - Take picture
1f0a2a95-3880-4253-bbfc-143e7e32bb71 | checkpoint-no-value | SILVERWATER ONLY - Test and Tag - Hand dryers - Take picture
14eef3d7-a094-455b-b1e5-4b5509d11735 | checkpoint-no-value | Note down but DO NOT TAG any other appliances situated in the kitchen that is not on the approved list (E.g. Air Fryer, coffee machine etc)
203fe9b7-9d12-4b20-a794-6a9b382a91b7 | checklist | SNSW Maintenance - Test and Tag - Final check |  | SNSW Maintenance - Test and Tag - Final check
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b22d23c3-d6d6-44de-9583-260758595f3a | checkpoint | All approved items are tagged
2b2fe68f-238e-43cf-97b6-ea6b7062ea1c | checkpoint | Have any non-approved items have been tagged
9c784609-b74b-40a3-bf6a-8fc07577c83b | checklist | SNSW Maintenance - Thermal Imagery |  | SNSW Maintenance - Thermal Imagery
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
910f7a0b-2d88-4f87-90fe-1b0dc35518a7 | checkpoint-no-value | Name of Distribution Board
cd4b82d2-ecb6-457a-a5cc-84558eda55ad | checkpoint-no-value | Take photo of the name of the DB board and service centre written on paper (this is so we can identify which DB)
c19d7e49-c61a-48c5-b3c9-eb85e5333ad1 | checkpoint-no-value | Take picture of the front of DB with cover on
57fd989c-31c5-4b26-8bfc-a13b23962647 | checkpoint-no-value | Take picture of DB with cover off
ecd9d83a-14df-41fa-929e-6aed15076795 | checkpoint-no-value | Take close up picture of main switch
b59ff7ca-1ca2-494a-89d8-0fd017cc170a | checkpoint-no-value | Take close up pictures of any potential concerns
5d1a0e13-310d-430d-8737-d43313cef12e | checkpoint | Add new checklist for additional boards
b13f75ea-2324-4be0-b081-871b3d4979cb | checklist | SNSW Maintenance - Thermal Imagery - Final check |  | SNSW Maintenance - Thermal Imagery - Final check
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
47f01145-925d-47b9-811f-1284360250c0 | checkpoint | Take picture of the front of DB with cover on
11c0c923-80e0-41b4-a52d-479f651c25ea | checkpoint | Take picture of DB with cover off
d26f8370-919e-4520-ac0c-7a602b5cc4db | checkpoint | Take close up picture of main switch
41dd1ac8-90e8-42e5-b1dd-935284be8a82 | checkpoint | Take close up pictures of any potential concerns
05050d80-5d99-4114-b28d-224617e9aa73 | checkpoint | Have you completed a thermal imagery checklist for all DB's