## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
a4571027-64d8-44e7-8232-ba6237870364 | checklist | Commission Backflow Prevention Device |  | Commission Backflow Prevention Device
41d8349e-17da-490c-bd60-5085e92726df | section | Details
6c1adb52-1205-4b11-a836-48763586fc5c | checkpoint | Commission Backflow Prevention Device checked off as below:
ae75a95f-3aca-51de-8970-0fcf76240341 | dropdown | Valve Type: | Reduced Pressure Zone Device,Double Check Valve,Single Check Valve
94ba99c7-914f-5b40-bf67-db8620f7ebbc | dropdown | Hazard Type: | High Hazard,Medium Hazard,Low Hazard
69d9f89f-25f4-552b-a998-a2511c47e847 | textbox | Serial Number:
27c2b195-d101-5e66-83d0-d396835c6ab6 | textbox | Location:
a1bf1108-efc7-52fe-9898-3d7e2fabff14 | dropdown | Size: | 15mm,20mm,25mm,32mm,40mm,50mm,65mm,80mm,100mm,150mm,225mm
ddec811a-72f1-4817-928a-0214de52d82a | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
48d7b975-4fc6-413d-970d-08074a7b1426 | checkpoint | Installation complies with current drawings & specifications
0afe72f5-93cc-475c-98e0-50c015814531 | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
ecdc372f-d6ee-4140-befe-4235550c1067 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
2efcdfd2-230f-4b0a-8cf2-d97b7593b0fe | checkpoint | Check valves are fully open
e9aeb928-6248-4a37-bfee-3f53bca01740 | checkpoint | Check inlet water pressure does not exceed manufacturer specification
9112e4cc-8e79-42c5-b546-4c5b18199dda | checkpoint | Check outlet water pressure is as per manufacturer specification
e84d3095-42fd-49e6-8dbc-b0b4ec2d20f1 | checkpoint | Check pressure relief discharges to drainage
4c195b83-54a4-4be6-884f-20be06f1dd9b | checkpoint | Provide the commissioning report & all plant documentation to this checkpoint
52659ca4-a88d-4c2a-8b93-377367ff782f | checkpoint | Confirm area has been left clean
8cdd81cb-f08d-4b57-82d5-95e0a1a2b250 | checkpoint | Ensure that commissioning photographs have been taken
0bf79273-1860-4e5d-b66b-1144bc65faa4 | checklist | Commission Thermostatic Mixing Valves |  | Commission Thermostatic Mixing Valves
7a949b70-1bab-4003-aef3-b4304bded14b | section | Details
3c7b2d22-337e-495c-a029-2b4b6c6f3179 | checkpoint | Commission Thermostatic Mixing Valves checked off as below:
2b7f370a-9d71-5b22-a933-3429734a08df | textbox | Location:
033fe711-761d-4d0c-84f2-88cd0c1bc3be | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
19db64f6-4981-4772-9567-f80653cff183 | checkpoint | Installation complies with current drawings & specifications
3569738b-9473-49e0-9c42-ffbc4cef1258 | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
8523ea5c-e5b6-4777-a690-3362c7a2afc7 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
c13380fb-ed90-48e7-a5e1-c42a21a0fcd8 | checkpoint | Check TMV has been installed in a lockable wall box
8f732cb5-c2b9-48ef-85c1-88cc6e80982f | checkpoint | Check TMV has been installed in the room it services and can be readily accessed from floor level
678f10a5-14a6-4f7b-9586-4b8446566ca0 | checkpoint | Check water temperature does not exceed 45°C for disabled persons
0d815316-2b28-47c6-b759-4f381e320c48 | checkpoint | Confirm area has been left clean
36bfb39c-930f-4119-a74f-3152c614fcb9 | checkpoint | Ensure photograph has been taken of thermometer in water flow at maximum temperature
694b1793-3a26-4b6b-b290-6ef09131c2c5 | checklist | Commission Water Tank |  | Commission Water Tank
bfcf8910-7a7a-4463-8c22-819413b9f766 | section | Details
5bdbc74f-5ec2-4428-b9f6-da64c2607763 | checkpoint | Commission Water Tank checked off as below:
18e7b654-8aac-5483-a12b-2428f300ecc8 | dropdown | Service Type: | Potable Water,Rain Water,Fire Service Water
7a15f85c-594c-5fda-a82a-dafc71788b5c | dropdown | Position: | Below Ground,Above Ground
0dd2d15a-648b-56a0-ab66-b86ec3d956ec | textbox | Location:
67fb6fbc-4b7c-5eb1-b5e3-2d6a22b62ffb | textbox | Capacity:
9139a132-c6bf-4ce5-87ec-18b326b68fb1 | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
37e9ab59-e5b1-4b01-b081-8c11e5b2f98b | checkpoint | Installation complies with current drawings & specifications
bf4f305c-1469-483c-a1aa-bc6539e92d94 | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
f2458964-6256-4954-bff8-267ad8228692 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
7f05bdc8-c2e7-4987-8011-3cd5f7317528 | checkpoint | Check all fixing/hold down points
ff745b68-65b3-4fc5-9fe2-05e1fa7fe949 | checkpoint | Check isolation valves are fully open & non-return valves flow direction
4874f66d-1e2c-4078-bd59-8fde0a3b065e | checkpoint | Check access covers & hatches
7ed2742c-fca9-4dad-80a8-f0ad40beb2e1 | checkpoint | Check access ladders & statutory signage
bf1385a0-af54-465e-86d5-2cc469cc4696 | checkpoint | Check pipe connections & venting
9c2f1d08-7f0a-4363-9f93-18d7b5aa99a3 | checkpoint | Check over-flow & connection to drain
6115ad63-0ebb-42b0-9d92-99e7150ca310 | checkpoint | Check float tree or water level sensor is not impeded by water inflow
dd71750a-227a-4db5-92a9-92a61a0d2eca | checkpoint | Check water fill physical air break
23a2c800-0389-4c06-a320-fcee12c4ddd6 | checkpoint | Check water level set points
e4ec71db-1ffe-4055-a614-a59a9d2cb1cf | checkpoint | Check back-up mains water supply
4910dc9e-a518-481e-8ad7-29a8a0818e1c | checkpoint | Check 'Bermad' tank fill valve
ae2e94d5-cf9b-4387-bc6b-602243ff9965 | checkpoint | Check low level fault
08a6cf7e-3e1f-4215-bae1-c0e6d5081723 | checkpoint | Check high level fault
514ae9e3-8408-4199-9b80-69c40ea2bbab | checkpoint | Check passive over-flow
e3615429-8a0b-4bfd-815d-75d9320e640e | checkpoint | Check control panel display
45def23c-fde0-4017-ba1c-7ccca23658b3 | checkpoint | Check programmed set points
5e907b0b-2c25-4d5c-ba51-41d7889394a2 | checkpoint | Check BMS connection
dee1d135-aa15-4c5b-aa14-fab80eb2d2d8 | checkpoint | Check statutory warning signage
d060636c-76b8-428d-9057-0b43d4bce15b | checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint
cd95eb7e-72b2-47a9-b175-bf7ffbf15aed | checkpoint | Confirm area has been left clean
40a72ea4-c380-4bb0-9643-49be80f50970 | checkpoint | Ensure that installation photographs have been taken
a6325a3f-071c-44c2-a2c5-87af2d4ba3b2 | checklist | Fit Off & Commissioning |  | Fit Off & Commissioning
fe49888c-91d1-4eab-bc27-4d72c93348d2 | section | Details
089ef696-12c2-4081-a410-19e62c14dc62 | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4 &/or AS/NZS 5601.1 (2022)
88bcad7a-e1f4-4e4a-943b-ae0256c6cbf1 | checkpoint | Installation complies with current drawings & specifications
4c77af62-ac79-4f09-92af-394d39a3b8ee | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
ae9d90e1-5d9c-419d-bbef-9411523b7d59 | checkpoint | Thoroughly check all pipework, fittings, connections, etc for damage or water leaks
13652841-d77a-40e0-813c-32fc401d0df4 | checkpoint | Check for any damage or missing components
6fc1769d-e503-444e-b1f4-452c037f5ab9 | checkpoint | Check level & alignment of all fixtures & tapware
e82a088d-f384-4f08-856b-4372f67971ed | checkpoint | Check all fixtures, tapware & components are securely fixed
d56841d1-fae7-4781-873d-bab12ed94cb9 | checkpoint | Check all mini-stops and valves are fully open
a2d85aa3-96b4-4454-a6f7-9243289db9d3 | checkpoint | Check all pressure reduction & non-return valves
e9294226-a512-4fa6-9465-bfa73cb2629a | checkpoint | Check all flexible connections are not twisted or kinked
ea916261-4ba8-4c4e-a137-dde9922b75d4 | checkpoint | Check for water for cross connections
492f6faf-883e-469a-9b54-4c857d95575d | checkpoint | Check fixture wastes & connections
f23d6a3e-f2ee-4f96-b5bd-d13ec8f2639a | checkpoint | Check dishwasher drain hose is looped hard-up under bench-top
55f30bad-8ff9-4b8f-8277-c8362ab3f461 | checkpoint | Check pipework & all traps are clear of debris
aa09d571-b920-4445-9be1-4be500670381 | checkpoint | Check AAV is installed hard-up under bench-top
05e2c5b0-4231-47c2-ad59-0a8c5fb535cf | checkpoint | Check future connection water valves are securely capped (fridge/washing machine stops)
4ed8d37e-fd66-4b58-9ea3-29fa1dfb6957 | checkpoint | Check hot water delivery temperature
5e2b9355-1297-45c6-bad3-490d4094d4fe | checkpoint | Check TV do not exceed 50°C
fec4e5d2-ce6b-4234-a7d8-c1b63d317a10 | checkpoint | Check TMV do not exceed 45°C
0c80897b-4e95-4cbd-8fd2-29bbc9e4b8ae | checkpoint | Check dishwasher function through short cycle
249753a6-f10e-4953-9b7c-b56839187b2e | checkpoint | Check gas valves & regulators
d026f83a-ef4b-4aab-bcc1-caef88099d72 | checkpoint | Check gas flame stop device
9c02c113-e468-4ee5-abb1-08eea997fa14 | checkpoint | Check all gas burner functions
3d706d85-2014-4fd0-ac1c-2b315a16e9c7 | checkpoint | Check emergency gas shut-off valve is fitted
6fa79a3b-bc96-49cd-9fbd-9de180c55a32 | checkpoint | Check balcony hose tap is securely fixed
416e2e79-7695-4b75-bbb1-67afafac6ad3 | checkpoint | Check balcony floor grate is clear
357038c5-52b4-4c1c-86f5-79b035005de3 | checkpoint | Check all downpipes & overflows are fitted correctly
c960fb99-8f0a-4135-a9f5-fc4a7675b3d7 | checkpoint | Check all vents are finished & weather proofed
bacc8b59-d8d6-471e-ba32-d19e9d34b859 | checkpoint | Check all fixtures & tapware function correctly
3f12af23-bb75-48a3-8206-9faa4697cfb6 | checkpoint | Check receipt of all Authority sign-off & acceptance documentation
5e619cd5-dffc-41f4-a07a-88e994dbe3b4 | checkpoint | Check receipt of all manufacturers warranty documentation & owners manuals
d377be08-f342-4c8f-8956-6357ae31e5c5 | checkpoint | Confirm area has been left clean
2975550d-0107-4082-aa2d-dd486049055e | checkpoint | Ensure that commissioning photographs have been taken
0e96ac66-c37a-4b6b-93cc-fa42960c764f | checklist | In Wall Rough-ins (Cold Water, Hot Water, Recycled Water, Gas, Waste, Vents, Fire Services) |  | In Wall Rough-ins (Cold Water, Hot Water, Recycled Water, Gas, Waste, Vents, Fire Services)
5817b7c3-72da-4823-aa55-f2580a34ee03 | section | Details
5c5a0b20-6b4f-40e2-8424-da4f67704d4c | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
23225db7-663d-4d3d-9b42-01dc54a051a6 | checkpoint | Installation complies with current drawings & specifications
346c781d-29e8-48f3-9bee-d88028b089cd | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
228c597c-b39a-4e19-b69f-b87fae2b54a0 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
b5acbf19-a003-4e99-bf8f-23ccf5d08c02 | checkpoint | Check crimp fittings & joints
aa05400f-e0bd-4809-af11-0136b5c56ea9 | checkpoint | Check for cross connections
bc29cf95-3f82-47c8-91ef-2c808bc28e58 | checkpoint | Check alignment & levels
2aea8f15-d636-4344-b2d5-4bb3388e9ced | checkpoint | Check materials & joining methods
cc2253c4-5225-4836-aead-c054e20fb955 | checkpoint | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation
c32f0853-fb80-40f6-bd7a-af3ab769a4fa | checkpoint | Check in-wall mixer bodies & lugged elbows
37d524b7-7979-4e84-97fc-c2cffb7a4822 | checkpoint | Check in-wall fixture mounting brackets & concealed cisterns
7fed8fb7-9822-4507-a43d-bf7ca36dc899 | checkpoint | Check fixture fit-off noggins
f9038371-1e51-4415-8c62-55dca7249798 | checkpoint | Check sharp edge pipe protection
6e2d5181-fb35-4f15-b002-40b575702999 | checkpoint | Ensure Recycled Water Inspections has been booked
3913516b-2314-4cbc-8f5c-22bbaf05f83a | checkpoint | Ensure that system is pressure tested
afd9c7ba-84c0-4dbf-8519-244d1d3c7782 | checkpoint | Area to be cleaned before worker departs
2042c7b3-e59a-42ce-b967-d4c0eba1a2fa | checkpoint | Ensure that installation photographs have been taken
4845d5fc-7c69-4c6c-8f3b-26d1dc1ae027 | checklist | Install & Commissioning of Rain Water Storage Tank & Pump |  | Install & Commissioning of Rain Water Storage Tank & Pump
0559a95b-4fa6-43e1-8010-aac10eca0c25 | section | Details
f091152a-a2e2-427f-aef3-12dc74d4d4de | checkpoint | Commission Rain Water Storage Tank & Pump checked off as below:
8d12046a-d001-5f96-be73-6e6eeac87cbd | textbox | Tank Capacity:
7b7294a4-b1d7-55b1-9b7a-d305cd827779 | textbox | Location/Lot Number:
2296a804-321f-4ef8-9bba-b3d0deaed61c | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
dbd23dbc-0e1f-47ab-aa63-a3b434ce0b4f | checkpoint | Installation complies with current drawings & specifications
4f3a4f82-08f8-4481-9b42-5ecf4a3515bb | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
4beb8449-9510-4fda-a39a-37449bde2366 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
ab959176-9fe0-43ba-ac28-49fabe68aa6e | checkpoint | Check all fixing/hold down points
1c1ae9af-bf88-4852-8f46-43e0ffe17d3f | checkpoint | Check isolation valves are fully open & non-return valves flow direction
1665089d-d50f-44ac-97fc-d067332cbca7 | checkpoint | Check pressure pump & filters for correct operation
f1108048-e9fc-4ddc-ad1a-86b028df425b | checkpoint | Check downpipe connections & tank venting
172b2088-202a-420c-b1a3-896a3ed2c2ad | checkpoint | Check mains water back-up supply
50fa68dd-4c29-44ec-b9c6-bd4695f1bec6 | checkpoint | Check tank over-flows to drain
3d063b42-9198-4763-9474-d3c4359f81f7 | checkpoint | Confirm area has been left clean
a4a74b5d-05a2-431d-b159-6e82fd6ee792 | checkpoint | Ensure that commissioning photographs have been taken
66ddd73b-630a-4da7-9ac9-c34ecec08b48 | checklist | Install Backflow Prevention Device |  | Install Backflow Prevention Device
8c43e9cb-2d3a-47ef-b3f5-de8cda811382 | section | Details
1a2e8dbe-de79-46f9-b828-23d5a7e537c4 | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
aae5c915-7454-4633-97a7-6276382973e6 | checkpoint | Installation complies with current drawings & specifications
9d25e6f0-ab24-4d6c-89a8-289f63b4d6b2 | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
dbb40c21-713c-41d7-9781-3d7c258afdf0 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
bf7e7a11-6dec-49fb-9f8d-7c82c21c7db3 | checkpoint | Check materials & joining methods
96db22bb-43d0-4726-9226-d85bc8914776 | checkpoint | Check alignments & levels
6be4c709-6e33-4279-846f-bcc6621fecf4 | checkpoint | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation
73b94c72-f2b4-4381-ac33-840013204dec | checkpoint | Check isolation valves, filters, connections, etc
8ca5a3c6-668c-41be-91e0-52076ede2473 | checkpoint | Check pressure relief discharges to drainage
91a82e66-2b54-4682-81de-72813762d7f1 | checkpoint | Confirm area has been left clean
4868d283-d86a-40dd-b9a3-d6e896490350 | checkpoint | Ensure that installation photographs have been taken
b4ba80c2-8c00-4a6b-93da-ffca0c135e57 | checklist | Install Cast-in Pipework |  | Install Cast-in Pipework
24ee110e-d6c2-46c5-8e44-90cfb3e49230 | section | Details
78da6300-6f25-41b0-8f91-58f9246404f4 | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
5a08f317-bbdc-4281-b716-da83d48768cf | checkpoint | Installation complies with current drawings & specifications
26e663a0-3d63-4647-bf1d-29880ef4233a | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
31cfb252-cea5-4b9f-8c14-fe04779e7fa9 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
a00981ce-926e-4073-80c6-e675b6c21381 | checkpoint | Check materials & joining methods
ca508a3f-7473-4b88-84ff-373a6efff5bf | checkpoint | Check alignments, levels, grades, etc
1376597d-6e11-4e5c-8a0f-3031c171a652 | checkpoint | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation
e6b651e6-40a0-4022-aa90-2caffea2c554 | checkpoint | Check surface & floor grated outlets
9d791a35-89c3-4a91-b47b-e4d8a2863164 | checkpoint | Check pipework & traps are clear of debris
6e4c6270-cd29-40a9-8314-18f62b2f8fb8 | checkpoint | Check pipe expansion lagging
44bf6658-a9fb-4777-a997-203a10c30bd3 | checkpoint | Check open ends are sealed
0caa3faa-7de7-4351-959f-7875571c20a9 | checkpoint | Check pre-slab CCTV recording
567994e5-e44a-4ef8-ab6c-ce7bcf9fe6e5 | checkpoint | Confirm area has been left clean
8bef72b7-4778-491c-a7ed-83cb066d47b1 | checkpoint | Ensure that installation photographs have been taken
f56d25c2-a8af-49d9-b166-7e3a5c96e046 | checklist | Install Fire Booster Assembly |  | Install Fire Booster Assembly
8a18b201-03e2-4ad0-9e6c-387765f224e1 | section | Details
9e06ba99-3dd4-4620-ac4f-0b3b8f88413d | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
94deb2c7-f7be-41ab-bdd8-e7a4c77b1273 | checkpoint | Installation complies with current drawings & specifications
fd4f5adf-c84b-4652-bc2f-466313eb2a36 | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
1347b55a-9329-4e4c-8ed2-688147928a7a | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
b6628998-bfdc-4174-9e2a-62a9f5790830 | checkpoint | Check materials & joining methods
0764d163-ab80-498d-bd78-2b210d195296 | checkpoint | Check alignments & levels
a30728ad-ce42-4e98-82d0-4a34ae87e566 | checkpoint | Check pipe brackets & supports are correctly positioned & bedded
b752e048-ee38-41a2-aaf2-26669a4181a2 | checkpoint | Check thrust blocks
3dacac65-5a6b-4be9-8c87-6a1383fe5226 | checkpoint | Check trench depth, bedding, service clearances, minimum cover, etc
9377492f-9806-4806-9ea0-827ea66b9031 | checkpoint | Check suction valve assembly
f0a030d4-28ef-441e-b854-54497d3dffe3 | checkpoint | Check booster valve assembly
2b96fce2-a092-4d5f-ace4-213dd8bc50a0 | checkpoint | Check hydrant hose assemblies
dbe88bc9-a6ba-41bc-9a51-a758b98deffe | checkpoint | Check monitored valves & connections
35b0d525-398e-42b3-9052-b79aae3d0604 | checkpoint | Check isolation valves, connections, etc
e96570f1-ff72-4427-bff5-59b4b8d2163e | checkpoint | Check gauge lines
58f8a1ed-37a8-4de5-a6bd-859b00110d13 | checkpoint | Check pipework is clear of debris
c7e16ee6-f554-46e1-97b6-37548e0ca7c0 | checkpoint | Check pipe trench marking tape
37d5b801-bc1b-4b33-aaf9-5b13a0757335 | checkpoint | Check trench backfill & compaction
bb1ca22d-5e94-4420-8f34-9986268142eb | checkpoint | Check pipe labelling
7ed10817-2428-4df0-a76f-61767cfd9907 | checkpoint | Confirm area has been left clean
1b629e1d-8a3c-4247-8efd-443f80fa873b | checkpoint | Ensure that installation photographs have been taken
9e26e2e8-792a-456a-9235-6b7c2467dd8d | checklist | Install Fire Service (Hose Reels) |  | Install Fire Service (Hose Reels)
ac12bad2-bfe4-42c3-a91a-aed2a2a244f8 | section | Details
1fba6b76-a9ac-4f9e-8fcc-e7414c8d8ff1 | checkpoint | Installation complies with latest revision of AS/NZS-1221
87faee28-cd3f-47db-a510-f661efc5c1d8 | checkpoint | Installation complies with current drawings & specifications
6a568e9f-8989-4a2f-ba1e-ddf8026f95e1 | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
d9be1bb6-385e-4117-a15b-44158c832d09 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
563fd2a7-a7ce-49e4-9648-acf038ef107e | checkpoint | Check hose reel is mounted securely
050f5e41-69fa-4ccb-9365-0ef0bdb652fc | checkpoint | Check hose reel spindle heights are 1500mm above FSL
41c03017-e1ff-4b55-9ae0-d8051ea7cddc | checkpoint | Check hose reel cabinets conform (if specified)
25a5c2ed-fc7b-4415-afb5-266391c064c2 | checkpoint | Check roll-groove couplings
ab351e21-4174-4044-8070-8cf96090dc5e | checkpoint | Check crimp fittings & joints
832920ab-fb9e-42c7-a01c-39404d06e941 | checkpoint | Check materials & joining methods
49c78878-b95e-4a42-97b0-63814d40671e | checkpoint | Check pipe specification markings are visible
a3392676-82f3-40c9-94a6-4bc10eb949e0 | checkpoint | Check alignments & levels
f7e6093c-7c5b-4520-a856-de21f5405846 | checkpoint | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation
3aaa1e7c-2f5f-436a-b5ec-c398bdf3bdc2 | checkpoint | Check isolation valves, connections,etc
b636424e-4e2b-47cf-8280-f2fe33bde3ad | checkpoint | Check pipe labelling
c14199a6-fe99-4999-87cb-28c268908c15 | checkpoint | Confirm area has been left clean
aa17c6df-cca3-47d0-bc90-a26dd3c01092 | checkpoint | Ensure that installation photographs have been taken
a2c9521e-ead2-4bf6-a7be-c48ce1110404 | checklist | Install Fire Service (Hydrants) |  | Install Fire Service (Hydrants)
ed10a574-8bbd-4044-a74e-4c80a2be543b | section | Details
5fd68586-3d13-46d4-8f6e-5dfd03ddc41f | checkpoint | Installation complies with latest revision of AS/NZS-1221
46cb9182-b63b-45c1-83f4-d413ed037671 | checkpoint | Installation complies with current drawings & specifications
ca5116b9-d79e-4009-817e-7bb9fac6d115 | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
15c2bdc8-7892-42fa-95bb-3913d8d67c35 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
8813dc1d-80eb-4ca5-800d-6594e183dfee | checkpoint | Check hydrant is mounted securely.
8f8e5acc-e48b-477c-ab32-17921cd531f3 | checkpoint | Check above ground hydrants height are between 750mm to 1200mm above FSL
f51c5367-7198-49de-badb-57abcd913fb1 | checkpoint | Check hydrant cabinets conform (if specified)
72fcdcef-b2ca-4508-8c48-8859e29d10c3 | checkpoint | Check in-ground hydrant heads & covers conform
8b8a4de9-f7e9-4a22-8f9d-9d8827d40be5 | checkpoint | Check roll-groove couplings
45ec6cbb-06ae-4436-a2c5-c3b037394929 | checkpoint | Check materials & joining methods
ca454dc7-6d5b-4bdd-b705-c3976f5fd2ea | checkpoint | Check pipe specification markings are visible
22343db7-efe2-4c9c-985f-f60b6f9005bc | checkpoint | Check alignments & levels
18a95f8e-fe95-45ab-96c8-de6f94afadaa | checkpoint | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation
ef7f100e-7098-4a3a-a5a0-e1fd4c6a498c | checkpoint | Check isolation valves, connections, valve covers, etc
195c4fb3-cc02-4256-8124-dab3f505bbeb | checkpoint | Check monitored valves & connections
11544341-24ba-477b-8d24-93ac5eb4a647 | checkpoint | Check pipe labelling
dfec1ca8-536b-49a4-a178-e8f8b74a91a0 | checkpoint | Confirm area has been left clean
ae9bc1be-e253-4843-b11e-7ae777300886 | checkpoint | Ensure that installation photographs have been taken
7c81be6a-511f-47da-9247-21c32aad5e15 | checklist | Install Fire Service (In-ground) |  | Install Fire Service (In-ground)
1bb91ba5-4381-4ba7-b3e7-c51105a1c5f7 | section | Details
a2982c84-818a-4d21-b4e0-3b5c73c4ee74 | checkpoint | Installation complies with latest revision of AS/NZS-1221
123787bb-cb19-4d97-9482-ce19f39b66d5 | checkpoint | Installation complies with current drawings & specifications
004bd146-e909-433e-b66f-ac53967acf05 | checkpoint | All pipes, fittings, materials & associated systems were used are in accordance to manufacturer instructions
b60260c3-5a83-459c-805c-dd26c947060e | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
b42e2fa8-164f-4b79-ac71-d7ac1a473918 | checkpoint | Check materials & joining/ installation methods are in accordance to manufacturer instructions
d817756e-caa8-4343-a054-f2aafba68506 | checkpoint | Check thrust blocks
33a025ae-9fca-446c-b7ce-18fc5ecfc9d0 | checkpoint | Check pipework is clear of debris
c48f8593-0d91-4b89-b37b-83386c5e257f | checkpoint | Check pipe trench marking tape
6e8f259c-0fe3-43d3-ac0c-162025a188e7 | checkpoint | Check trench backfill & compaction
38510d5e-c49e-419c-8021-ecc2c9cb122c | checkpoint | Ensure that system is pressure tested
446d55f5-8808-4d34-a77a-bac5d7450380 | checkpoint | Area to be cleaned before worker departs
d571c902-1fa4-40fc-97ab-7d0ae2aa68f6 | checkpoint | Ensure that installation photographs have been taken
f28cc37d-e2b2-4e77-aea6-27a9994199f1 | checklist | Install Gas Services (In-ground) |  | Install Gas Services (In-ground)
58efdbde-7cd9-4c67-9698-797e2349b023 | section | Details
b742978d-c802-41aa-b360-df9e0d36c123 | checkpoint | Installation complies with latest revision of AS/NZS 5601.1 (2022)
d0220a5b-3cd7-4d27-8389-1cca9f6cccb4 | checkpoint | Installation complies with current drawings & specifications
73be759c-cb71-4c73-a182-35af13ee85f1 | checkpoint | All pipes, fittings, materials & associated systems were used are in accordance to manufacturer instructions
82893de4-703c-4a92-8a76-13c9bb618ebc | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
cf648ab2-519a-4dc9-984a-028bc45a08eb | checkpoint | Check materials & joining methods are in accordance to manufacturer instructions
613133f4-6744-40e1-82ba-74c6d4ed48ea | checkpoint | Check pipework is clear of debris
1180a4a7-c9cd-43cc-a0d6-c396b0727c01 | checkpoint | Check pipe trench marking tape
e6f418ce-1993-4c47-a1af-3d241782fcb3 | checkpoint | Check trench backfill & compaction
db8fcbd7-f825-486a-b54d-fdd5684ac825 | checkpoint | Ensure that system is pressure tested
b18a4975-36fd-4146-9db3-5c5246447feb | checkpoint | Area to be cleaned before worker departs
2350a3ba-308f-4607-9393-340da5463ff8 | checkpoint | Ensure that installation photographs have been taken
2083422b-17ab-49a7-a8ee-d4393c25c17c | checklist | Install Recycled Water Services (In-ground) |  | Install Recycled Water Services (In-ground)
76cb2eec-e129-498b-9d48-df30eeb53919 | section | Details
a182efcf-8f3f-4421-bab3-e49442c2f4fe | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
4263fc87-00b6-4975-a152-6fd7288a2a72 | checkpoint | Installation complies with current drawings & specifications
5ceac0c3-d05f-4084-881b-2a419ab01e77 | checkpoint | All pipes, fittings, materials & associated systems were used are in accordance to manufacturer instructions
fd48d1c6-33ff-4b29-a122-261ab94bf803 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
687b00a6-f802-4821-9be5-867798127477 | checkpoint | Check materials & joining methods are in accordance to manufacturer instructions
a6f23db4-83af-46c8-95f0-fdffe2e8f947 | checkpoint | Check thrust blocks
3b67f111-5f9a-41e6-aa33-3f832be463d1 | checkpoint | Check pipework is clear of debris
bd52e113-0a6a-403e-b55a-d4d6aae0cb1d | checkpoint | Check pipe trench marking tape
fa6dcc5d-61aa-4bf9-bceb-98279331ffbc | checkpoint | Check trench backfill & compaction
50bd6bd2-3c33-43a2-a2d9-70df2e26d42b | checkpoint | Ensure that system is pressure tested
a548f201-110d-4e88-bd35-b1e6bb122592 | checkpoint | Area to be cleaned before worker departs
3f1efc77-48e4-4b96-9ac3-4543c0c38b95 | checkpoint | Ensure that installation photographs have been taken
636dd8ac-7197-48f8-a525-74139d841671 | checklist | Install Sewer Drainage (In-ground) |  | Install Sewer Drainage (In-ground)
88dfa57a-03a2-4fb9-8883-003254f58cfc | section | Details
05b43eea-c295-44d9-ad9f-af7a525826ad | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
ac9b9fb9-0377-4ea1-9877-877e737e79bc | checkpoint | Installation complies with current drawings & specifications
70ffbb1c-05c3-461e-98d2-e3f47a4df785 | checkpoint | All pipes, fittings, materials & associated systems were used are in accordance to manufacturer instructions
563d2e40-5ea9-44ec-b9b0-39bb6ad749eb | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
67c19ac4-5296-4c53-be71-845086d43eb8 | checkpoint | Check materials & joining/ installation methods are in accordance to manufacturer instructions
78c5953e-5afa-4b2d-8d6e-e4c69c9c4947 | checkpoint | Check alignments, levels, grades, etc
37cdffba-db04-4850-b3cb-8e46fc0f21f3 | checkpoint | Check pipework & traps are clear of debris
c427aa51-7231-47ad-a64e-95e187cb9618 | checkpoint | Check trench backfill & compaction
255ba248-debb-4dcc-aeb8-758f73946292 | checkpoint | Check pre-slab CCTV recording
ff7c0cd9-15a0-4220-8980-fb39404069fb | checkpoint | Ensure that system is pressure tested
66d6d4ca-908b-44d5-9271-e8b1b475c8e3 | checkpoint | Area to be cleaned before worker departs
882cd459-fd4a-48d0-b0ee-8dd2dd3b6ec1 | checkpoint | Ensure that installation photographs have been taken
294036f5-6cc4-4c5f-bbb0-80d2b5e9f729 | checklist | Install Storm Water Drainage (In-ground) |  | Install Storm Water Drainage (In-ground)
244c6ac5-553e-4494-81e5-7edbc9ab86a8 | section | Details
3f87a243-ccb9-40de-aa65-921560f9c8c3 | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
dabbd3b7-c1a1-403c-85be-3bf4e7fb1628 | checkpoint | Installation complies with current drawings & specifications
02857a45-a952-4ffe-b503-fcb9aa8364c5 | checkpoint | All pipes, fittings, materials & associated systems were used are in accordance to manufacturer instructions
c05cb60d-b3bb-4465-aad3-9a65ecb00c2d | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
a263974a-1e67-440d-a137-44549f5f8642 | checkpoint | Check materials & joining methods are in accordance to manufacturer instructions
eaa6a461-bae7-4ea1-8630-caa1bcac6b8a | checkpoint | Check alignments, levels, grades, etc
3a20a7a4-5bb7-4394-82f7-13436a1a3b2f | checkpoint | Check pipework & traps are clear of debris
2499f97e-4119-4dfe-b916-b84fc474e23b | checkpoint | Check trench backfill & compaction
419e2213-427e-4cc6-bb8a-554bade26fcd | checkpoint | Check pre-slab CCTV recording
bbcede51-673e-4e37-943e-09630ea18120 | checkpoint | Ensure that system is pressure tested
03ac2ce4-04b8-4773-bd53-4eafb9b03a6a | checkpoint | Area to be cleaned before worker departs
6672e251-547c-4895-9c03-8e754610a1a9 | checkpoint | Ensure that installation photographs have been taken
e02450a8-f1f5-4d4d-86c7-a2303c25ac5a | checklist | Install Trade Waste Drainage (In-ground) |  | Install Trade Waste Drainage (In-ground)
7a91aec7-191b-4fd3-99ca-cbffc940aa3b | section | Details
3f8799c4-4e9a-4dd9-b889-088324046217 | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
0d4383ac-e3b6-46db-963f-affc0872e2bd | checkpoint | Installation complies with current drawings & specifications
44a8f95e-6673-418e-a7b6-320ca321c98b | checkpoint | All pipes, fittings, materials & associated systems were used are in accordance to manufacturer instructions
4c9037e7-d43b-461b-9f17-d622f9b95f12 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
42532bcf-0372-4328-a821-57c0013273da | checkpoint | Check materials & joining methods are in accordance to manufacturer instructions
b33597b0-a255-4424-bb2b-06f1e30a349e | checkpoint | Check alignments, levels, grades, etc
0a7504b0-437d-42be-a188-3031a51e6184 | checkpoint | Check pipework & traps are clear of debris
4cab3319-47a3-417d-b21a-bbff6fcff46c | checkpoint | Check trench backfill & compaction
a96b9abb-e763-45e1-bd4f-58e3a239de64 | checkpoint | Check pre-slab CCTV recording
1abcc974-1ac2-46b2-ad20-6d920d16f458 | checkpoint | Ensure that system is pressure tested
4032f371-78ec-4238-9626-5168de382753 | checkpoint | Area to be cleaned before worker departs
c49e2256-1826-4206-b801-f802aa9bc73e | checkpoint | Ensure that installation photographs have been taken and the system pressure tested
95311a86-aa76-4e53-b9d3-00d61ea368e7 | checklist | Install Water Services (In-ground) |  | Install Water Services (In-ground)
5b71910c-af02-41a3-8d5e-8c589031744f | section | Details
73668c6a-5734-4fb3-ac7f-4492c1a6bda9 | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
dfc1159f-a947-4d14-a201-9e574bcfddd7 | checkpoint | Installation complies with current drawings & specifications
0c2eb439-b602-4ed3-953b-2a5e88675a82 | checkpoint | All pipes, fittings, materials & associated systems were used are in accordance to manufacturer instructions
ec122041-f4ee-4a6b-8265-c2a006a76920 | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
e1c298f2-77eb-440e-ae46-70339713c495 | checkpoint | Check materials & joining methods are in accordance to manufacturer instructions
9173c22f-f0e0-4ad0-910d-8fc08449f542 | checkpoint | Check alignments & levels
e02795e9-b966-4f43-982a-96a5b3be9bad | checkpoint | Check thrust blocks
b59c3372-de54-4cd4-94b0-3ce2273ff435 | checkpoint | Check pipework is clear of debris
039d557a-00f4-4d65-9411-f23a9294e2b8 | checkpoint | Check trench backfill & compaction
68a68137-84e1-441a-8be1-a0b1f725c6b2 | checkpoint | Ensure that system is pressure tested
3f98b0fb-8f52-445e-aa0c-fc5f8d04953c | checkpoint | Area to be cleaned before worker departs
2f7fffbf-8c94-4665-8c09-54adf8c842f1 | checkpoint | Ensure that installation photographs have been taken
d2b2c48f-a3e2-4937-9119-90d5008cdd29 | checklist | Installation & Commissioning of Pump Stations (Sewer Pump Stations, Storm Water Pump Stations, Trade Wate Pump Stations) |  | Installation & Commissioning of Pump Stations (Sewer Pump Stations, Storm Water Pump Stations, Trade Wate Pump Stations)
960a4ebf-ae14-44e7-be7d-2af4756d5805 | section | Details
8ddad086-d0c7-4156-b502-c901038991e6 | checkpoint | Commission Drainage Pump Station (In-Ground) checked off as below:
5690b201-4628-5dcc-ac48-d4c925910f33 | dropdown | Type: | Sewer Drainage,Stormwater Drainage,Trade Waste Drainage
c00a2ffb-ae36-5495-9425-79d662526696 | textbox | Location:
ab1ffcba-cbea-4c7b-a6ef-7eb6d6c52b63 | checkpoint | Installation complies with latest revision of AS/NZS-3500 (2021) Parts 1 - 4
11e3472e-8583-4038-afa0-d0ee20a562aa | checkpoint | Installation complies with current drawings & specifications
48961c9e-a9b9-44d9-a6b7-38ec4313aafb | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
c41407f2-5473-4d9b-a430-828f25ca99dd | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
fa5368b7-8630-45b4-94ac-2d63ac858946 | checkpoint | Check access covers & hatches
6bc7a209-c094-4af2-bded-ef07ec335df4 | checkpoint | Check access ladders & statutory signage
e92d7891-bd80-48ce-a18d-c8fa4492f435 | checkpoint | Check pipe connections & venting
2e59a659-8ef9-4539-9d65-d80ef8d9a78c | checkpoint | Check all pipework, fittings, valves & connections
2c54cedb-6d34-48c2-9b73-2fc9a2c3850f | checkpoint | Check lifting rails & chains
e764c00f-60d2-47ab-8433-5bccc4577c35 | checkpoint | Check float tree or water level sensor is not impeded by water inflow
076ca417-0afe-4633-a8b1-dc3c84c3fd46 | checkpoint | Check water level set points
ceee8644-0e50-4a2c-b3d3-dcfa0442f2ce | checkpoint | Check pump motor rotation
8b25ceb7-254f-4f41-b1f1-6643eb5f89fc | checkpoint | Check dry pump fault
ca2557f3-5d39-45d7-b238-252c50dba89b | checkpoint | Check low water level fault
a0e38576-74fd-499e-8221-4f0539be4cb7 | checkpoint | Check high water level fault
b768b8e1-971e-4b70-9141-11bc485a734f | checkpoint | Check auto pump roll-over
01818a69-2828-4ddb-834b-b4a232cc18b4 | checkpoint | Check delivery flow rates
8426bbac-6380-4eda-8aa5-bffda4e76467 | checkpoint | Check control panel display
45484251-7242-4602-aebe-a571f5f41415 | checkpoint | Check programmed set points
929995d6-854a-4ddb-8bcc-e870d1c7e647 | checkpoint | Check fault warning alarms
72913b3c-ff5e-4aed-b9f8-4b805519c693 | checkpoint | Check BMS connection
35e167e3-e4f5-4800-b68f-273b8d5253c1 | checkpoint | Check statutory warning signage
32aaf9e1-108b-44b2-9105-0b8a33b83315 | checkpoint | Check suppliers commissioning report & all plant documentation
c966df70-05b6-4556-badd-c48c9a1e3bf5 | checkpoint | Confirm area has been left clean
d387626a-9014-44b4-96c9-dd9a3116eb50 | checkpoint | Ensure that commissioning photographs have been taken
4a1d9599-d1b9-481c-8982-52050dd66f70 | checklist | Rough In - Above Ground High Level (Sewer, Storm Water, Vents, Stacks) |  | Rough In - Above Ground High Level (Sewer, Storm Water, Vents, Stacks)
471e8bc9-e304-48b9-985d-dd84711d181f | section | Details
e6df6830-c1d2-4f66-b693-6bacd270fc7a | checkpoint | Installation complies with latest revision of Australian Standards
ebc09cb3-e599-4dd1-a400-cb067bdf20f4 | checkpoint | Installation complies with current drawings & specifications
0b1ec213-d5af-4718-9976-c6a98ab8e76f | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
92fd0459-6c7c-4f1a-9955-8bca81cbb9f9 | checkpoint | Setout & alignment as per drawing
54a67b55-bf0f-4bf4-9db4-62690fe346df | checkpoint | Support & fixings checked (acoustic / seismic / water hammer/ silicone)
42af57c7-24f9-4988-bf59-5c20f834817a | checkpoint | Pipework installation checked against standards (as per AS 3500.1)
1eae2173-71cc-4cd2-bc50-a57a80623b0d | checkpoint | Pipe risers water sealed per floor & capped off to prevent damage
10da3867-c5c8-4bf6-81e7-fc6e964ac76f | checkpoint | Check all, pipework, fittings, connections, etc for damage or leaks
cbb9d33f-c8bd-4d8e-98fb-fb8179123676 | checkpoint | Check materials & joining methods
3df9c446-b741-4cea-ab31-3f5865e6faef | checkpoint | Check alignments, levels, grades, etc
0822b401-2165-4dfb-a311-89208566e6a7 | checkpoint | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation
962e516d-cd40-4f45-b50d-59cc2048a3cf | checkpoint | Check expansion joints and anchor points
30ac8757-a80d-4418-a49e-e2c3448dbc72 | checkpoint | Check inspection openings
e3f7d239-73b1-4a68-baa5-1ab334c267cc | checkpoint | Check pipework is clear of debris
6ea5a2c7-1996-4e84-86a0-ad7d4087fc0d | checkpoint | Check open ends are sealed
fc869d18-c0de-4994-91fe-000dca774452 | checkpoint | Check acoustic insulation
d4550815-869a-42a6-83ae-040d2a201040 | checkpoint | Check pipe labelling
106b70e8-f12f-45b7-9c46-fd2538553c58 | checkpoint | Check floor/wall penetration fire proofing
ce7ac2d3-6808-4e8c-82c4-55010bfb00a7 | checkpoint | Check vents are run to atmosphere and are complete
532853bb-ae7b-4afe-aff5-c48a4a01e0ec | checkpoint | Ensure that installation photographs have been taken
774557a0-5beb-4d3d-b53c-e08a71347c6a | checkpoint | Pressure test
10c1d215-7c54-4ba4-9f22-cf6fb96efb33 | checkpoint | Identification of services
2255f460-d341-4119-9d2f-dd0397540dea | checkpoint | Check floor/wall penetration fire proofing
29c8952f-cfb9-4d25-b958-cccdcf572788 | checkpoint | Ensure that installation photographs have been taken
acf6b583-877a-468a-8e67-9242c7703c05 | checkpoint | Final sign off - Pass when happy to proceed (Any issues please comment & Add photos below)
6a6b258d-d93b-4373-8712-82707b8577a7 | checkpoint | Area to be cleaned before worker departs
7ae182f6-c9a5-44be-9f74-975b048c97ee | checkpoint | Ensure that installation photographs have been taken
7218af6a-61f9-4caa-8781-0a6e08841d31 | checklist | Rough In - Above Ground High Level Mains & Riser Installations (Hot Water, Cold Water, Recycled Water, Gas, Pump Services, Fire Services) |  | Rough In - Above Ground High Level Mains & Riser Installations (Hot Water, Cold Water, Recycled Water, Gas, Pump Services, Fire Services)
20397971-ca3e-43a1-8bee-87251186ea04 | section | Details
c53fa429-e274-47c0-8d24-eda812f50039 | checkpoint | Installation complies with latest revision of Australian Standards
5d4bbe49-d3f0-43e4-aee7-fe03aea459a1 | checkpoint | Installation complies with current drawings & specifications
3abf11c2-faf7-4387-85dc-877b73186eaf | checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
cc8d5520-2726-491d-b0ab-3b2495f1c003 | checkpoint | Setout & alignment as per drawing
41208eaf-f02c-4936-9d00-59d0a1050036 | checkpoint | Welding / pressfit / push fit / witness marks (as per AS 3500.1)
e34aaea5-79f5-4edd-ab08-f9c30dc48095 | checkpoint | Support & fixings checked (acoustic / seismic / water hammer/ silicone)
1564ec2e-bd9a-4e8f-9a5d-a7dc916a0804 | checkpoint | Pipework installation checked against standards (as per AS 3500.1)
774e7aef-1500-4985-a5ac-439c2950a049 | checkpoint | Check no cross connection
2d9d3505-0956-4b20-a4e2-20ca1a98cde8 | checkpoint | Pipe risers water sealed per floor & capped off to prevent damage
568657ec-cc80-4dba-a5dd-ba0bf69b794c | checkpoint | Pressure test water lines to (1500kpa)
9167246c-111b-491e-8a3c-1e4429f60c1c | checkpoint | Identification of services
149e2c70-ae64-4fa7-88a6-b7ac1524a1f9 | checkpoint | Check floor/wall penetration fire proofing
886ce0b4-4934-400f-8b64-bff7e416c130 | checkpoint | Ensure that installation photographs have been taken
0332550a-fddf-43b5-af23-5cc017ef9153 | checkpoint | Final sign off - Pass when happy to proceed (Any issues please comment & Add photos below)
de75f0a3-4457-4d34-a149-3be55c1c4715 | checkpoint | Area to be cleaned before worker departs
b13a4fd6-09ed-446e-8c4e-cc03f836dc39 | checkpoint | Ensure that installation photographs have been taken