## Master List Templates
Id | Type | Name | Values | Prompting Name
9c103913-36c2-5493-8ace-29092587dda3 | checklist | 2 Coat Checklist |  | 2 Coat Checklist
cd26fbc3-0c15-5ba7-8609-ddd37cffbedf | checkpoint | Surface conditions suitable for installation - details in comments below
2d87a46c-fe73-5831-8ebd-2db36f0ce21f | checkpoint | Moisture test complete - result in comments below
a07d57b2-7685-5648-8681-ca7baee3806a | note | Must be below 5% to pass
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
b33c4759-6640-5525-b30c-1e2521eec59c | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
2ce61c51-24ac-5114-b14b-f3167931548b | checkpoint | Application of Primer as per specification
cb05ac53-543c-5d0a-80e4-1c17ce23fc77 | note | Cementious Coving completed (if required)
c49d71db-cde7-512c-a1c3-efa963080f70 | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
e26ba506-d1e6-5a24-b722-8e3571dcfe02 | checkpoint | Application of membrane as per project specification - 1st Coat
1790702f-6330-5da8-be24-1303f3d0bdc1 | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
e9ae5d5e-c2df-5ac8-8c77-d32c11e0c026 | checkpoint | Application of membrane as per project specification - 2nd Coat
ab23ca0f-6ce8-50e7-8fe8-869f3f519ad4 | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
1fab7897-7640-51c3-8989-efa29904a478 | checkpoint | Additional products / elements installed - selected all that apply below
d76dd1e3-acf3-5bd7-a0c2-4f232420eb3a | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
ddb3ca37-8ba6-56ea-8972-f8365b10eb4a | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
f1d036e7-9ddc-57f6-a8d3-7ae4abbbc9ea | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
dbe23432-9e56-5eee-bd32-8d8c70795df4 | checkpoint | Final DFT Thickness of Membrane
55ae20f1-aa3b-5ceb-a3a5-6fdb4fb4a7a5 | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
00ca73e2-903a-5a2a-a7de-00a41c628f0d | checkpoint | Test 1 Flood Test Pass/Fail
ceb76426-273c-5130-8982-67333b2c5973 | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
31006cc9-661d-501a-b71f-d6a3fd14487a | checklist | 3 Coat Checklist |  | 3 Coat Checklist
cd26fbc3-0c15-5ba7-8609-ddd37cffbedf | checkpoint | Surface conditions suitable for installation - details in comments below
2d87a46c-fe73-5831-8ebd-2db36f0ce21f | checkpoint | Moisture test complete - result in comments below
392389f4-d4a2-58b0-bf8e-8702a99c6545 | note | Must be below 5% to pass
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
f2044125-9210-55f9-b38f-fb493eec4680 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
2ce61c51-24ac-5114-b14b-f3167931548b | checkpoint | Application of Primer as per specification
c49d71db-cde7-512c-a1c3-efa963080f70 | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
e26ba506-d1e6-5a24-b722-8e3571dcfe02 | checkpoint | Application of membrane as per project specification - 1st Coat
a92f976e-ff46-51be-ab87-64c085015c25 | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
b07d69b9-eb94-5cd4-ac45-6f0a29cdbccb | checkpoint | Application of reinforcement sheet (if pedestal pavers)
e9ae5d5e-c2df-5ac8-8c77-d32c11e0c026 | checkpoint | Application of membrane as per project specification - 2nd Coat
ca6a66ba-a293-5c57-b1a9-620d752fff57 | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
695c0ea3-5b5c-5fec-8a4b-695148dd3dd2 | checkpoint | Application of membrane as per project specification - 3rd Coat
f01b18cf-ad89-5c6a-97c8-88997d84be7f | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
1fab7897-7640-51c3-8989-efa29904a478 | checkpoint | Additional products / elements installed - selected all that apply below
162eeea3-b995-562b-9376-5c5b951feed0 | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
43caec97-3337-5f02-89f4-01d837f335b4 | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
1999adf3-8f6f-5329-a96b-7647441d8280 | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
dbe23432-9e56-5eee-bd32-8d8c70795df4 | checkpoint | Final DFT Thickness of Membrane
55ae20f1-aa3b-5ceb-a3a5-6fdb4fb4a7a5 | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
c94306f9-a402-5d05-b6d8-5019fe3100d8 | checkpoint | Test 1 Flood Test
ceb76426-273c-5130-8982-67333b2c5973 | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
ee458561-cdd0-5c57-9bc6-f77d3074b08a | checklist | Balconies Checklist |  | Balconies Checklist
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
68d5b242-29d2-598c-9490-45ffab9676e5 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
1253a59b-b2fd-5400-84c9-e9bf238db677 | checkpoint | Moisture Test Result (if required)
74997fb6-7846-5033-b443-1bb033a9c87b | note | Provide moisture test results if concrete placement<28 days
02d192e3-a45a-5f08-a271-c34afc723dc0 | checkpoint | Application of Primer as per spec
71b84abe-2525-54e6-a97b-fa7b78fe5647 | checkpoint | Application of Caulking or Bandage (if required) completed
b6b52302-8620-5300-aaac-73836f942caf | checkpoint | Application of membrane as per project spec-1st Coat
d1c61ce1-1cd0-531a-810c-53e43a871ba7 | checkpoint | Application of reinforcement sheet
70a732df-6101-52e2-84cc-b135b889b0d0 | checkpoint | Application of membrane as per project spec-2nd Coat
5b6ab0c2-8562-52c2-be29-cc5235e2b024 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.
2d18c6d1-ef0d-5d5b-9428-1336ec04909d | checklist | External Liquid Membrane Checklist |  | External Liquid Membrane Checklist
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
2712f8df-2d78-5866-8ed5-f6917bab3604 | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
457f3ab0-279f-51da-801d-cc3a50735df1 | checkpoint | Application of Primer (if required) as per specification
4bb928f0-d927-5027-9654-71ccd7e3d572 | checkpoint | Application of Caulking and or Bandage (if required) completed
f668bcbe-18b2-58f6-8d04-c8caee1e1cc7 | checkpoint | Application of membrane as per project specification-1st coat
6c9c242f-82a1-56f6-91c7-3e4d6e91b721 | checkpoint | Application of membrane as per project specification-2nd coat
e67dd1bc-5ae9-561c-b3c7-11a449cb6185 | checkpoint | Application of top coat (if required)
dbe23432-9e56-5eee-bd32-8d8c70795df4 | checkpoint | Final DFT Thickness of Membrane
6d2a0357-0222-5d52-993c-d1ce5cac3aba | checkpoint | Installation of Corlute Protection Board completed (if required)
b5efa035-6e14-5719-b1f0-2dd32b5cd9d1 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
3fd8aba7-b353-5720-8140-fc8cde6e2cfa | checklist | Internal Wet Areas Checklist |  | Internal Wet Areas Checklist
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
31a69271-8eb0-5857-86ce-27ddf1925f6e | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
f61e9903-8421-567a-a914-924a12124ffa | checkpoint | Atmospheric conditions
cd87a532-519d-5933-9a76-c9da1349c91c | note | Note ambient temp, Relative Humidity, Dew Point
d9857118-bff6-5f07-9bee-513074a9aa0a | checkpoint | Product Batch Numbers
6abbe554-83ed-57ed-9ef2-102708d9c8a0 | note | Note batch numbers for products used
4d0bc7f2-c48c-5256-88f2-2058d829395f | checkpoint | Equipment used
4488fe5c-6a88-5be2-b2cb-5308fd0608b0 | note | Note equipment used like rollers etc.
16ba4f63-0a63-581d-99c6-b76eb82da22e | checkpoint | Application of Bond Breaker completed
f668bcbe-18b2-58f6-8d04-c8caee1e1cc7 | checkpoint | Application of membrane as per project specification-1st coat
d1c61ce1-1cd0-531a-810c-53e43a871ba7 | checkpoint | Application of reinforcement sheet
6c9c242f-82a1-56f6-91c7-3e4d6e91b721 | checkpoint | Application of membrane as per project specification-2nd coat
dbe23432-9e56-5eee-bd32-8d8c70795df4 | checkpoint | Final DFT Thickness of Membrane
b5efa035-6e14-5719-b1f0-2dd32b5cd9d1 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
00ca73e2-903a-5a2a-a7de-00a41c628f0d | checkpoint | Test 1 Flood Test Pass/Fail
bb96a8e7-439d-58e5-b736-05539c8f8f3c | checklist | Liquid Membrane-1 |  | Liquid Membrane-1
2bcf7098-237e-52ba-9f38-ed7ce7e1a8d0 | checkpoint | Surface conditions suitable for installation-details in comments below
c83498fc-fddb-537d-ba5c-dae70f32fa64 | checkpoint | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
f61e9903-8421-567a-a914-924a12124ffa | checkpoint | Atmospheric conditions
35143a08-4139-5eed-a5a9-4413d61892fc | note | Note ambient temp, Relative Humidity, Dew Point | label
2ce61c51-24ac-5114-b14b-f3167931548b | checkpoint | Application of Primer as per specification
4bb928f0-d927-5027-9654-71ccd7e3d572 | checkpoint | Application of Caulking and or Bandage (if required) completed
e02701cd-c69c-5d0a-adc1-c36d5c25f514 | checkpoint | Application of Membrane as per project specification
b5efa035-6e14-5719-b1f0-2dd32b5cd9d1 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
b3143390-3922-5327-b733-6164affbb600 | checklist | Liquid Membranes Checklist-2 |  | Liquid Membranes Checklist-2
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
8453aba1-29fb-56f9-adb9-ac5c4afe0ce4 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
f61e9903-8421-567a-a914-924a12124ffa | checkpoint | Atmospheric conditions
bfe200fe-b280-5b46-adbd-38a9ab907bbc | note | Note ambient temp, Relative Humidity, Dew Point
d9857118-bff6-5f07-9bee-513074a9aa0a | checkpoint | Product Batch Numbers
50581ce2-0d09-5fdc-9720-e836721fbb1a | note | Note batch numbers for products used
4d0bc7f2-c48c-5256-88f2-2058d829395f | checkpoint | Equipment used
c8a0acaf-be99-5d4c-99dc-ff2cc4a3d26b | note | Note equipment used like rollers etc.
2ce61c51-24ac-5114-b14b-f3167931548b | checkpoint | Application of Primer as per specification
16ba4f63-0a63-581d-99c6-b76eb82da22e | checkpoint | Application of Bond Breaker completed
e02701cd-c69c-5d0a-adc1-c36d5c25f514 | checkpoint | Application of Membrane as per project specification
b5efa035-6e14-5719-b1f0-2dd32b5cd9d1 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
d4d881fc-4f37-5fc5-a225-8e1e5a2e8546 | checklist | Planters Checklist |  | Planters Checklist
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
60e00cdb-e7b8-56e1-90f8-c00c844ed224 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
457f3ab0-279f-51da-801d-cc3a50735df1 | checkpoint | Application of Primer (if required) as per specification
16ba4f63-0a63-581d-99c6-b76eb82da22e | checkpoint | Application of Bond Breaker completed
890b1b97-2bf9-5ece-8435-c6852f0da1be | checkpoint | Application of Membrane as per project specification-1st coat
6100c9b5-ce80-5115-b948-3720ac4c326e | checkpoint | Application of Membrane as per project specification-2nd coat
2157322a-327b-5a84-95fa-36ff1b01d3e9 | checkpoint | Installation of Corflute Protection Board Completed
70b8bb33-cd40-574d-ae5a-ac202b8b9a76 | checkpoint | Installation of Drainage Cell Completed
b5efa035-6e14-5719-b1f0-2dd32b5cd9d1 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
76b01e29-ce89-55e1-baba-e1b64983851c | checklist | Polyglass Spider P Checklist |  | Polyglass Spider P Checklist
01b26445-a057-5895-ae95-2d74cbd4629f | checkpoint | Substrate inspected, cleaned if required and accepted
152edbd9-eb7e-5177-b857-69915d9d126c | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
f61e9903-8421-567a-a914-924a12124ffa | checkpoint | Atmospheric conditions
88e06604-2206-5439-bf7e-eb35692918a6 | note | Note ambient temp, Relative Humidity, Dew Point
d9857118-bff6-5f07-9bee-513074a9aa0a | checkpoint | Product Batch Numbers
fa484a5b-090e-5340-a96f-bb156af91c93 | note | Note batch numbers for products used
4d0bc7f2-c48c-5256-88f2-2058d829395f | checkpoint | Equipment used
02ef1a8b-cfbd-5c94-9af7-0b5483d9f835 | note | Note equipment used like rollers etc.
49e9f78f-96fc-52d5-8479-b9b572d454de | checkpoint | Apply Primer to substrate
946e0b32-e579-5966-8deb-3571cd4c9480 | note | Primer coat to be applied uniformly across surface
d394190a-e5fd-5623-9434-42e0ea852a0a | checkpoint | Apply Polyglass Spider P Membrane
0cd8f7ca-b09d-5a07-8adb-910e73560a62 | note | Check that all laps are correct and use heavy duty roller on the seams
d9dfb6d5-7abd-56c3-9302-2d5b3425c4bc | checklist | Polyurea Spray Checklist |  | Polyurea Spray Checklist
01b26445-a057-5895-ae95-2d74cbd4629f | checkpoint | Substrate inspected, cleaned if required and accepted
040c0595-a35f-50c5-8221-6afd01ee341d | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
f61e9903-8421-567a-a914-924a12124ffa | checkpoint | Atmospheric conditions
7b444143-e71b-55ac-bd9c-926c8dff84fb | note | Note ambient temp, Relative Humidity, Dew Point
d9857118-bff6-5f07-9bee-513074a9aa0a | checkpoint | Product Batch Numbers
d9694661-59f9-50c2-af66-fc974464bdae | note | Note batch numbers for products used
4d0bc7f2-c48c-5256-88f2-2058d829395f | checkpoint | Equipment used
f7ee3f48-3bc9-5d12-a2a2-11c98b814c4e | note | Note equipment used like rollers etc.
53082c5a-4ab1-551c-ba26-c86cbfd303bb | checkpoint | Fixing/Repairing
19969450-aa9b-525b-8b05-4eed3f0f8ff5 | note | All voids/cracks to be sealed
ab8817e0-a0d6-56a7-b663-8ea3eb4397c7 | checkpoint | Priming & Sanding
c1cb9d78-87a1-59ee-8683-c81e440b785d | note | Primer coat to be applied and Sand to be spread across surface
52eb842b-011b-5b62-bdc3-00d036f1783e | checkpoint | Polyurea Spray
fc56f9cb-ca41-5855-ba2c-152191308759 | note | Polyurea spray coat to be applied uniformly across surface
21c2c044-a424-52e4-a106-3af2c0697fca | checklist | PVC Sheet Membrane |  | PVC Sheet Membrane
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
2bcf7098-237e-52ba-9f38-ed7ce7e1a8d0 | checkpoint | Surface conditions suitable for installation-details in comments below
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
52fb6463-ae08-5715-b707-41294dfe748d | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
e65954d1-181f-557a-8f35-b1fc05394d9e | checkpoint | Application of Geofabric to substrate
9de214f5-f3bc-5b94-975f-0ed2f93b859f | checkpoint | Application of PVC Sheet Membrane
70cf4fc6-afc1-558c-af29-910fdafd7ff9 | checkpoint | PVC Sheet Membrane Detailing as required
b5efa035-6e14-5719-b1f0-2dd32b5cd9d1 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
0fb89f1f-32a8-55eb-ac5a-fd945bc58480 | checkpoint | Test 1 Probe Test Pass/Fail
fc38e1e9-7f83-5b2a-afea-222710bf0783 | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
b9238b84-82f8-5072-8f08-df756914f83b | checklist | PVC Tanks Checklist |  | PVC Tanks Checklist
cd26fbc3-0c15-5ba7-8609-ddd37cffbedf | checkpoint | Surface conditions suitable for installation - details in comments below
2d87a46c-fe73-5831-8ebd-2db36f0ce21f | checkpoint | Moisture test complete - result in comments below
7712e9cd-5dab-58bb-93d1-bc2bf0a51eb7 | note | Must be below 5% to pass
f61e9903-8421-567a-a914-924a12124ffa | checkpoint | Atmospheric conditions
fe2b043f-8b97-5805-a7ec-9c2cb1d16fee | note | Note ambient temp, Relative Humidity, Dew Point
d9857118-bff6-5f07-9bee-513074a9aa0a | checkpoint | Product Batch Numbers
8bfe7591-bf97-503b-9f0d-b788f10435d6 | note | Note batch numbers for products used
4d0bc7f2-c48c-5256-88f2-2058d829395f | checkpoint | Equipment used
56fffd16-46ee-5aae-9938-1dade21f52e1 | note | Note equipment used like rollers etc.
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
8e822223-0baa-5b94-807c-86439eaa9b79 | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
e65954d1-181f-557a-8f35-b1fc05394d9e | checkpoint | Application of Geofabric to substrate
9de214f5-f3bc-5b94-975f-0ed2f93b859f | checkpoint | Application of PVC Sheet Membrane
c01f8ea2-4291-5c36-92da-c013c23b1fef | checkpoint | PVC Sheet Membrane detailing as required
f582b1e5-a148-5356-9bf7-0df4f03f1656 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
c78e3a36-76ff-5f52-a717-53781c802be9 | checkpoint | Test 1 Probe Test
03a42af0-c434-5896-8a47-100380c0a7a2 | checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
ceb76426-273c-5130-8982-67333b2c5973 | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
8cf1a393-0596-5832-b7a1-6df2dbe76be2 | checklist | Rectification Works Checklist |  | Rectification Works Checklist
51317976-a688-595d-82aa-0f143b5ef9e8 | checkpoint | Damage identification
690ef59b-d3a1-5fab-ad89-878d06ddf0d0 | checkpoint | Repair and Test
89235161-5074-59cb-b61b-f4892e548f3b | checkpoint | Area sign off complete
c0257015-84d0-50f3-bbed-06e960f7eed3 | checklist | Screed Checklist |  | Screed Checklist
169e8968-ef7e-5866-b14d-528019011200 | checkpoint | Mixing of Topcem Pronto
fc8f1d58-f20c-5127-99b0-611b4d416648 | checkpoint | Application of Topcem Pronto
55ae20f1-aa3b-5ceb-a3a5-6fdb4fb4a7a5 | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
ceb76426-273c-5130-8982-67333b2c5973 | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
3c559ffe-48ef-5e47-ba09-ddeb52e8b0cc | checklist | Sika Midwater Basement |  | Sika Midwater Basement
20ae6e8d-5bc6-5ab3-a496-485822fdf9ed | checkpoint | Membrane installation
3c1ed189-a7b5-5376-8cdd-16ee9110e553 | note | Sikaplan system installed as per project specific details supplied by Sika
f6e07443-28f6-542b-8089-96d37151d14f | checkpoint | System installed as per all relevant product data sheets
4187ac78-2978-5f68-a8d3-a53b612b34bc | note | Auxilary system installation
c7d8bbac-7e27-58c8-a508-24d8c251c16e | checkpoint | Auxiliary systems installed, noting rear guards, Fuko hose, compartment injection portals and waterstops installed as per approved details
8620e628-e8b7-5dc7-8f55-1f691b3f77af | note | Additional Photo evidence
0f350129-9530-5b71-bbae-3e2749519065 | checklist | Sika Midwater Doors, Balcony and Wet Areas |  | Sika Midwater Doors, Balcony and Wet Areas
36984233-018b-5034-86b5-1e4d03cade42 | checkpoint | Sarnafil installation
86d9fe71-eb2c-5948-9af1-6ac742ccb282 | note | Sarnafil system installed as per project specific details supplied by Sika
da87c48e-5286-5afc-a1f1-c12a35023103 | checkpoint | Installation as per data sheets
9f67d178-0c8a-5603-9f56-48a1c8cb7317 | note | System installed as per all relevant product data sheets
2b861131-7b9e-51e9-95bf-a57d2d62e13a | checkpoint | Photos
6aaba619-bed7-542f-adf2-164932d659d5 | note | Additional Photo evidence
ba34946f-659c-5937-912e-aa107bf01797 | checklist | Sika Sarnafil PVC Sheet Membrane Checklist |  | Sika Sarnafil PVC Sheet Membrane Checklist
2bcf7098-237e-52ba-9f38-ed7ce7e1a8d0 | checkpoint | Surface conditions suitable for installation-details in comments below
03fab0be-1f2d-5ee9-ae7e-a5d0b23a26ad | checkpoint | Moisture test complete-result in comments below
576b05c1-8274-5f6d-9368-14884291db04 | note | Must be below 5% to pass
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
3541b282-46f9-5a85-a099-2a1a2e7b789a | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
f09c52b1-17a7-546a-8bee-e66bb351f229 | checkpoint | Application of Sarnacol Adhesive to substrate
3178f190-e7a6-5605-b9ab-8b72597d2e17 | checkpoint | Application of Felt PVC Sheet Membrane
9bf128f3-2813-5c73-85b9-b145e5839012 | checkpoint | Application of Non-Felt PVC Sheet Membrane
70cf4fc6-afc1-558c-af29-910fdafd7ff9 | checkpoint | PVC Sheet Membrane Detailing as required
1d0a8e8d-e450-566e-ac13-8b4d9995e493 | checkpoint | Sarnabar Termination
b5efa035-6e14-5719-b1f0-2dd32b5cd9d1 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
0fb89f1f-32a8-55eb-ac5a-fd945bc58480 | checkpoint | Test 1 Probe Test Pass/Fail
fc38e1e9-7f83-5b2a-afea-222710bf0783 | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
065af263-5279-5edc-95ab-06cfeed5bbc5 | checklist | Trafficable Liquid Membrane |  | Trafficable Liquid Membrane
bd23fda8-b65f-5bef-8033-a5150b4ef1da | checkpoint | Substrate inspected and accepted
c5285207-3dc5-5567-aa09-7ef78bcff952 | note | Substrate has fall, is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
457f3ab0-279f-51da-801d-cc3a50735df1 | checkpoint | Application of Primer (if required) as per specification
890b1b97-2bf9-5ece-8435-c6852f0da1be | checkpoint | Application of Membrane as per project specification-1st coat
6100c9b5-ce80-5115-b948-3720ac4c326e | checkpoint | Application of Membrane as per project specification-2nd coat
940843e3-f112-5ba2-9305-c04410251d49 | checkpoint | Application of Top Coat
dbe23432-9e56-5eee-bd32-8d8c70795df4 | checkpoint | Final DFT Thickness of Membrane
4a260061-9edf-5eff-8152-852c9b468f92 | checkpoint | Installation of Corlute Protection Board Completed
b5efa035-6e14-5719-b1f0-2dd32b5cd9d1 | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
43301f44-61ef-52b0-a705-b4900a02bd59 | checklist | Waterstop-Penebar |  | Waterstop-Penebar
2bcf7098-237e-52ba-9f38-ed7ce7e1a8d0 | checkpoint | Surface conditions suitable for installation-details in comments below
287ff56f-5298-537c-b13e-1b6055407230 | checkpoint | Substrate inspected and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
059cf78f-aa32-5870-8748-6ac8a6f01c6d | checkpoint | Application of Penetron Penebar SW55 Primer
f81c16da-12f4-50eb-8203-d598c1e605e5 | checkpoint | Application of Penetron Penebar SW55 Waterstop