## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
7639e772-e021-4c52-b9dd-0f30241d221d | checklist | Tahunanui Back Beach Remediation ITP | itp | Tahunanui Back Beach Remediation ITP
208f0a9a-3d0f-49a8-a00f-116cbdc378e1 | section | 1.1 - Pre Construction
e38b5bf9-4e46-4c43-a715-dbf42720d3a0 | checkpoint | 1.2 - Vegetation Clearance
028d4e4f-45b4-5c90-bd36-6e310fd5ea13 | note | Inspection Point: Quality Control Activity - Removal of trees, and other plants within the area of works
8f2697ed-6343-5401-bb8a-8846ce1065b6 | note | Acceptance Criteria - Trees and plants removed in the area of works
2aea01f8-1941-5e1e-ac35-fef26b8dc586 | note | Verifying Document - Visual
6dfd048f-f0d7-548f-96bd-f1c5496e4a24 | note | Frequency - Pre Construction
0dc83f80-eff2-5e6f-b077-1a8d773dbbdc | note | Inspection Type (Visual, other) - Operation, Hold point
736e37c4-ae33-5f49-a513-e5d9f2fa97c4 | note | Inspection: Key - SUB
f73bc474-ee89-52f8-9b78-57e157e5b002 | note | Inspection: By (Role Key) - Nelmac
90e2e9e8-cd36-4c0d-b485-f1d5ebf03b18 | signoff | AUTHORITY HOLDPOINT
7399525a-7e2a-4786-9569-99ef1cd9ef7c | checkpoint | 1.3 - Traffic Management
ebfc79ac-a145-568d-b066-d8c91adc308e | note | Inspection Point: Quality Control Activity - Implementation of Traffic Management
0a1accde-9bdd-5b8e-af1e-994af4057ce6 | note | Acceptance Criteria - Traffic Management set up in accordance with approved TMP
adaecb45-b1a1-5b65-a24c-f7020d696303 | note | Verifying Document - Visual
509039e3-ec04-53fd-a1db-f6e816f9adc5 | note | Frequency - Constant monitoring
47f10b6a-a748-5383-af63-e92d1e3aed94 | note | Inspection Type (Visual, other) - Visual verification, Hold point
b0df7ce5-e6c2-5e61-9ffb-09f4c70eac1a | note | Inspection: Key - STMS
e2d54987-b2a4-552d-aef0-de572ccdc9f8 | note | Inspection: By (Role Key) - Downer
49a2fcb0-4723-4b38-9aad-89189b4e03a1 | signoff | AUTHORITY HOLDPOINT
75a5cd0c-4cc9-446d-b886-b3d12572f49c | checkpoint | 1.4 - Survey and Set out
99a920ab-43f0-5148-aa65-d8b20eb95687 | note | Inspection Point: Quality Control Activity - Pre construction survey and site set out
cb8cbda0-5123-5ad5-8c81-dfabe8641a95 | note | Acceptance Criteria - Set out follows provided coordinates
1fcf33a6-bbb5-590b-a986-41d5cd78417b | note | Verifying Document - Visual
d4b52095-6ff8-509d-84f6-e1081dc457cd | note | Frequency - Pre Construction
fa1cb9cd-8d96-5598-9b34-c00c195946d5 | note | Inspection Type (Visual, other) - Inspection, Hold point
5d1a3963-ab7f-5320-a664-9f5db0240dbe | note | Inspection: Key - SV, ENG
15e8fbb1-48ad-5c50-9f81-edbc13baf5d1 | note | Inspection: By (Role Key) - Downer, T+T
31996dcc-4ec9-42c2-a855-7ca079ab299c | signoff | AUTHORITY HOLDPOINT
8fe7bd23-77cf-4daa-b6f3-315c291c7b0d | section | 2 - Zone A Excavation
e93a5fb1-2316-4a99-be0c-909e31321812 | checkpoint | 2.1 - Final Excavation Level
3c572cb0-dc4a-5321-9122-23223915008f | note | Inspection Point: Quality Control Activity - XRF Contamination Testing
09678491-5682-58e5-9fce-a76b72a5db68 | note | Acceptance Criteria - Excavation free of contaminants
776cf50b-f76f-5a7c-987b-b43b80b299ed | note | Verifying Document - Engineer approval
f29589b7-39a8-5d78-8211-4736f24bf0dd | note | Frequency - Every 25m of the completed excavation
5a219ab6-3d45-537e-a886-5742dee3bd82 | note | Inspection Type (Visual, other) - Inspection, Hold point
96bda13c-591f-5b2d-be89-493f7fb8964c | note | Inspection: Key - ENG
50161dc1-0fe2-55f7-911c-2f591b68a64a | note | Inspection: By (Role Key) - T+T
bc293a83-0582-4f98-a665-499df393a127 | signoff | AUTHORITY HOLDPOINT
91157fba-5847-4b64-9488-821b6450ab7d | section | 3 - Zone B Excavation
3a3dceb0-0697-45b0-a0de-6af0b66ef059 | checkpoint | 3.1 - Final Excavation Level
ed66ddbc-c137-5453-9f87-0ccfa0848ee6 | note | Inspection Point: Quality Control Activity - XRF Contamination Testing
acd1da93-2347-5eb1-baa2-5eb5e7edea4b | note | Acceptance Criteria - Excavation free of contaminants
625f6b32-2962-5482-970f-f6e64310ce15 | note | Verifying Document - Engineer approval
299eddce-6253-5c9c-9b89-63727018743c | note | Frequency - Every 25m of the completed excavation
c3e06fa8-a9ae-5ca5-b15e-d7dc784ff96a | note | Inspection Type (Visual, other) - Inspection, Hold point
73c6c543-fae4-5a73-bd7f-9cd7185d2e2a | note | Inspection: Key - ENG
5c47964c-c921-5891-83d6-1067ae513403 | note | Inspection: By (Role Key) - T+T
71560cc9-77dd-47d8-b139-6c10f2c25da6 | signoff | AUTHORITY HOLDPOINT
3bacb13c-967e-421d-b794-efd09cbb2b8c | section | 4 - Carpark Construction
ed31ed6b-237c-40a6-ba8e-56eea3fef46a | checkpoint | 4.1 - AP40 Compaction
6504575c-520b-5f76-bc67-42302fa6c822 | note | Inspection Point: Quality Control Activity - NDM Testing
de3817ee-b1c2-5f90-840b-dc02e612ecb9 | note | Acceptance Criteria - Mean Value ≥98%, Min Value ≥95%
35ae209d-bf46-50fe-ab2a-ac90bd94303a | note | Verifying Document - Lab Report
f2fe3943-9baf-5610-aec0-d207f1882dc3 | note | Frequency - 1 lot ( 5 tests)
eb8edf82-eae9-5c09-af8e-ec750f36ef79 | note | Inspection Type (Visual, other) - Testing
47f0a7c8-f0cf-5fc4-8fc9-1447f5f24007 | note | Inspection: Key - SUB
67ef08c6-39f6-5c34-9f1a-fe636fd4775a | note | Inspection: By (Role Key) - Civil Engineering Labs
620f1ff0-8be4-4ef4-8544-f79fb21b0ffb | checkpoint | 4.2 - AP40 Compaction
fcd28fd4-874b-5283-b570-4d923df82037 | note | Inspection Point: Quality Control Activity - Beam Testing
efbe11ba-18e2-5609-bcaf-b875ed4413bc | note | Acceptance Criteria - Maximum Deflection 2.0mm
991341cb-c40e-5625-88d2-1c509da4ee0b | note | Verifying Document - Lab Report
3e336ada-93de-5388-a204-d304481f133d | note | Frequency - Every wheel track at 20m intervals
5439bc19-3772-58c6-8569-2731db9525d4 | note | Inspection Type (Visual, other) - Testing
b53d35fa-62bd-5aa5-830f-7618325b7e9a | note | Inspection: Key - SUB
b0e0e160-1290-56e6-ac4e-fc1792c2f909 | note | Inspection: By (Role Key) - Civil Engineering Labs