## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Approved Design Report |  | Approved Design Report | e0639135-48eb-4c56-999f-3e1a72be6ef2
| checkpoint | Approved Design Report
| checklist | Approved JMF |  | Approved JMF | 8ac71f70-40b1-42f7-82bd-850237aaf41a
| checkpoint | Approved JMF
| checklist | ITP - Granular Rehab |  | ITP - Granular Rehab | db966afa-080b-41c3-be49-2a8b7e9f1033
| section | 1.0 AP 40 M4 – Raw Aggregate Testing
| checkpoint | Sand equivalent, or
ce69a728-c599-5cec-b99c-64a7b1b0d060 | note | T
ad716045-053e-5607-a59c-4421336ae6c2 | note | Reference or Specification: Design
62cef0cc-f12a-5059-b24d-8d629fafb218 | note | Method/Test required: ≥35 Unit of measure?
b4109b10-eb05-59a2-8c2f-d23f7a804dcb | note | How Often? 1 sample per 500m3
951e56ec-963a-5dba-be4b-fcf3307dcc31 | note | Records Required: Test Report
45bae04d-3828-566f-b03a-98c2bcc02409 | note | Responsibility: Project Manager
| checkpoint | Clay Index (passing 0.075 mm), or
a6289f85-c843-52b9-bddb-b49fa9139848 | note | T
d0f9af63-f86d-51a8-ae7f-491062bb4f73 | note | Reference or Specification: Design
0838be70-19b8-53d0-a65a-a03257f0f969 | note | Method/Test required: <=3 Unit of measure?
bd72d7dc-6e4b-5948-a384-f1b58a8719d2 | note | How Often? 1 sample per 500m3
6919e779-47e1-564f-9357-0d2e693e2839 | note | Records Required: Test Report
4c1d77b6-c5a7-59dc-b831-6a7234ebecef | note | Responsibility: Project Manager
| checkpoint | Plasticity Index
ee378919-17b5-5907-bd14-6331b4227c3c | note | T
0e4b0798-7946-57ec-a40a-07c11fd42fa0 | note | Reference or Specification: Design
02d708c6-b257-51cc-98a5-a89e54c653b3 | note | Method/Test required: <=3 Unit of measure?
3a7f36df-de52-5e65-bb74-f4cc1dd046db | note | How Often? 1 sample per 500m3
8bb65a34-ac61-5b29-abe7-af358b583e25 | note | Records Required: Test Report
b1cf7f7b-66fd-59f8-a4b5-9bfe36182dae | note | Responsibility: Project Manager
| section | 2.0 Site set up
| checkpoint | Particle size distribution
60d29f41-860c-502b-a48d-49aeb4d4fc20 | note | T
f8b36724-246e-56ec-a73c-16ba3cba9b44 | note | Reference or Specification: Design
b3e81397-38ee-53e6-8a38-d4175e667cef | note | Method/Test required:
c970ae93-50ae-5878-bff2-86049064582f | note | • 100% passing 63mm
dc323022-448c-5f71-9859-e8e51adb54f8 | note | • 40% ≥ 65%passing 19mm
352712d9-523c-53cf-b808-8904fd2ea8da | note | • ≤ 10% passing 0.425mm425µm
cb5c14b2-5bcd-565d-b558-728689d9fb6f | note | How Often? 1 sample per 250m3
69d68354-e340-5dc4-8c00-dbc8b412a35e | note | Records Required: Test Report
0dd8316e-c580-5151-89cb-1d30e9fff193 | note | Responsibility: Project Manager
| checkpoint | Solid Density
d7185f64-a55d-5c04-b793-2b4e40fde087 | note | T
3a8f5a73-d4c7-5694-b2b5-3e8ea77d3448 | note | Reference or Specification: NZTA B/2 7.5
378c1a7c-c036-5c2c-b529-a1a8261c8a11 | note | Method/Test required:
9175eb7d-0c3e-5a26-ba7f-8945efc234e8 | note | • Unit of measure?
3f9dd623-a633-5791-b021-42c424f093e5 | note | • Tolerance?
57cf72a0-66d4-51fd-929c-331419749e66 | note | How Often? 1 test
ef1f43e0-22d2-542c-b4be-7adf6e2c3c53 | note | Records Required: Test Report
57e63228-0779-5341-a83a-7edcd5604e1b | note | Responsibility: Project Manager
| checkpoint | Determination of MDD & OWC
17562201-f80b-5bd8-82aa-09694982dceb | note | T
2a4d9850-0317-596b-bfd9-ea118792df47 | note | Reference or Specification: NZTA B/2 7.5
d60cb53a-2967-5a73-9cc1-f732aa49e8ed | note | Method/Test required:
9a547c82-e655-5987-b7b4-cc37713de689 | note | • Unit of measure?
95a19683-33fb-5b56-b8a5-44debb6f4820 | note | • Tolerance?
ef183e83-0621-558c-a069-0fd6b32dd76a | note | How Often? 1 test
26c35729-54fb-5210-bdd5-83444589010f | note | Records Required: Test Report
e124a433-48c3-50b5-b0c3-b7d68bb4a69d | note | Responsibility: Project Manager
| section | 2.0 Site set up
| checkpoint | Stakeholder notifications undertaken
23215615-9bd1-553c-9321-e6b3d1f38b51 | note | H
44c46434-666f-5d13-983c-45d3cb127056 | note | Reference or Specification: CSCMP
40274952-286a-5fbd-a6d2-bde64240a8fa | note | Method/Test required: Stakeholder notification emails and letter drops
c6cc75d9-6eaf-5a01-8246-19c2fdf8da51 | note | How Often? Each site
aee599c1-e71d-5e52-902e-16908271ee8a | note | Records Required: Evidence of notifications
50fcc313-354d-5463-814f-82afa08c3a66 | note | Responsibility: Network Manager
| checkpoint | Mark-out of services and Permits in place
95c80e26-4009-56c5-9422-42c4339390c8 | note | H
d2cf0e53-cc07-5921-b621-8947a177f323 | note | Reference or Specification: HSMP
ebb45c53-01bf-571c-9810-cc5dae536d38 | note | Method/Test required: Physical mark-out of all services and signed permits
03bea957-76f4-5d08-b659-1c4f3c5f44c0 | note | How Often? Each site
72cf1c1c-1246-5044-addc-6abffcbf3f2d | note | Records Required: Signed permit
6a1d3921-303e-5871-8239-105dc0931b56 | note | Responsibility: Project Manager
| checkpoint | Job start, identify risks and mitigations, communicate to team
078fb512-e0a4-5a40-8bf8-01beed709d09 | note | H
e17a0c58-4344-5750-b30c-ddcee3990944 | note | Reference or Specification: HSMP
ae4e10c0-ba2c-5211-981d-47066b6d7599 | note | Method/Test required: Record all hazards on JSEA and brief team
eecd5f5f-a6ba-5d5b-9011-417ad0058d31 | note | How Often? Each morning
82b7fe10-8f0c-5a68-917b-0ca1b4bed124 | note | Records Required: Job start form
e9594c5a-7dd4-5236-85e3-18880d60b001 | note | Responsibility: Supervisor
| checkpoint | Set up traffic management to plan
e14b900d-731d-5697-abd5-39fba73c353f | note | T
f44e9224-6a6e-5101-bf06-705d22f9a575 | note | Reference or Specification: TMP
c2df49d6-878b-5098-8f94-6d0a145428f2 | note | Method/Test required: Perform Site audit post-set up
618450f6-5404-55ad-9969-b5e98cabe419 | note | How Often? Each site
d0e9bd02-78fb-5901-a8e9-eac51607e42c | note | Records Required: Daily Diary
1967e463-9a78-5782-8b4b-65429604cc3b | note | Responsibility: STMS
| checkpoint | Assess environmental requirements of site and install sediment and erosion control measures if required
400370eb-b6a5-5e98-ae40-08fa0136c907 | note | I
486031be-e296-56eb-8bff-841b728acda8 | note | Reference or Specification: ESMP
df70acd6-4ce3-59f2-86c4-bdb2ab8bac3c | note | Method/Test required: Identify areas at risk and install control measures
6838c9de-7e5a-5f3c-bf5b-a6169c11b89b | note | How Often? Each site
5cab5010-72ad-54ce-9530-02b235006622 | note | Records Required: Daily diary
b785ea96-80bb-5c59-b09c-7206f39bb704 | note | Responsibility: Supervisor
| section | 3.0 Basecourse Inlay
| checkpoint | Cement Spread Rate
42117727-5208-58c5-94d0-7ba990fb56a0 | note | H
bff4a659-22bd-5cb3-a502-8d85e0a60878 | note | Reference or Specification: NZTA B/5
bc5f6032-9112-579c-a1b9-b51a8bd0ae27 | note | Method/Test required:
0e17e85a-b73c-53f1-b3df-8909a0f15e62 | note | • ±0.5kg/m2
76e2a5e0-3298-5917-ab80-0a6c3b517973 | note | • Weigh mat: Every 400m²
3eab6b5b-9284-5416-a65a-71869807ed3b | note | • Average usage test: Within ±2.5% of the specified rate
7456e484-9709-5cbb-ad55-a88ab42cb8f2 | note | How Often? Upon emptying the spreader and bulk tanker
9fc3768b-8cfb-58a8-b23c-e6b97b1f1cb1 | note | Records Required: Cement Sheet
8b67d880-7be5-5275-9f0f-dc33379cf72f | note | Responsibility: Stabilizing Supervisor
| checkpoint | Hoe and stabilise to design depth
b08607db-732a-5664-9609-cbf86eeacbae | note | I
06041f66-fb75-5185-84fa-c46772163bd8 | note | Reference or Specification: NZTA B/5
7632f830-b456-5aa1-867b-828adfe1234a | note | Method/Test required: -0mm / +20mm
baae4376-2de3-5739-b88e-b5b810e7b626 | note | How Often? Per run
7258cad2-a043-539c-8be8-3222fc3e129b | note | Records Required: Cement Sheet
78679d38-a130-51a7-987a-b6e4e3d9b2e7 | note | Responsibility: Stabilizing Supervisor
| checkpoint | Overlap longitudinal joints
13c3ab62-82a4-509b-8734-70e1d12c3006 | note | I
5f791713-8334-58a7-9294-bdc15a6c4809 | note | Reference or Specification: NZTA B/5
628ff46a-b7e6-50b3-a082-873e22776a5f | note | Method/Test required: Record hoe-depth setting
5752032c-3f65-5c19-8da5-b01000d6173d | note | How Often? Per run
a93531cf-cef8-5108-8cd0-e40708183f35 | note | Records Required: Stringline Sheet
6bc7634d-22cb-58f5-a965-7ce15bde1662 | note | Responsibility: Stabilizing Supervisor
| checkpoint | Plateau density test
3ca24cc3-87ae-50b6-98b7-dc4997c7d8e2 | note | T
081f23ad-45f7-5f91-9a1a-3f6fae111002 | note | Reference or Specification: NZTA B/5
1e26e019-24c5-5b74-8f6c-2454edcf5f8d | note | Method/Test required: 200mm overlap
f7e20c71-ce9b-5ec6-81ae-be8fed027788 | note | How Often? 20m centres each side
8a704a06-cafa-55eb-a340-35a348ed542a | note | Records Required: Plateau Density Sheet
01257f69-3e4a-5a18-a6f7-e64f1aeb9c8a | note | Responsibility: Quality Engineer
| checkpoint | Confirm layer thickness
268e0654-1918-5cb7-8736-14f8cb2f2c75 | note | T
52344fc3-1783-5be9-8944-8ca97d448c2d | note | Reference or Specification: NZTA B/5
eb8fa5fc-32a8-57aa-9824-72b021d5b789 | note | Method/Test required: Nuclear Densometer
25d9bef4-5b03-5b75-b87a-75923e884ea8 | note | How Often? 20m alternating wheel tracks
d687525f-b21c-5bde-b19a-fae9cf4b9cab | note | Records Required: Plateau Density Sheet
e2c46515-5972-58b4-a5b7-47372587c5bf | note | Responsibility: Quality Engineer
| checkpoint | Compaction as per sample test results
0d85bd6c-10d2-500b-adf1-dafd103cd386 | note | H
ee1b2554-601e-52cf-9962-a87fd5faae83 | note | Reference or Specification: NZTA B/5
ff324ec8-3077-5bf6-a3d0-36b8a4ebd1f3 | note | Method/Test required:
c1158d7d-d552-5a67-896f-ebd1376f23a5 | note | • Mean ≥95%
4fc4ac05-0853-5deb-8915-2341c6851742 | note | • Minimum ≥92%
f732b3a2-a83b-5e18-a2bd-3ad4d97e0ea5 | note | How Often? Every 20m alternating wheel tracks
4c9d227b-c887-5e63-8b77-aabbf38d2927 | note | Records Required: NDM Sheet
02eb0d4a-e4fa-5ea2-b504-61e87245e4de | note | Responsibility: IANZ Accredited Lab
| checkpoint | Impact hammer test
0461cd19-d306-53e5-89c5-c32d1aefb0e1 | note | H
7f39a19c-3ea8-5812-b98f-76fa1634e4de | note | Reference or Specification: Spec?
2df1a697-901c-561f-bfa8-7d659c8893cd | note | Method/Test required: ≥70 CIV
bcbd3ef6-417c-52cf-a4da-4152bd35ebe8 | note | How Often? Every 20m alternating wheel tracks
f37c0916-1534-5779-bf52-5ef56897a5a2 | note | Records Required: Clegg Sheet
5f40e634-c746-5e8c-ad85-b87eb289264e | note | Responsibility: IANZ Accredited Lab
| checkpoint | Confirm surface levels
51934aa2-5659-5604-8dd4-1e86e68e62df | note | T
6e23f4c3-a613-5b71-9262-c3b2d39d0101 | note | Reference or Specification: NZTA B/2 5.1
04d3fbe0-b0e8-5193-83e7-595235bda13c | note | Method/Test required: -5mm / +15mm
ecba9a9c-1eb1-5742-922e-5b1f0be51dbf | note | How Often? Every 20m, full width
9c7c1827-fd43-534f-a429-be2a5f8ca55a | note | Records Required: Stringline Sheet/As-Builts
1b76c7e1-c608-569e-a26c-c1a00c934ae1 | note | Responsibility: Project Manager
| checkpoint | Surface Finish
d3588765-1aeb-5935-839b-1a09c15802a4 | note | T
12822f3e-c52a-5717-bdf1-e8b8a7d5e2c3 | note | Reference or Specification: NZTA B/2 5.1
c59676e4-1726-5303-8e91-87045bf942fc | note | Method/Test required: -5mm / +15mm
ba769c71-81eb-50ba-a332-1398113054db | note | How Often? Every 20m, full width
edb5af76-9cd4-54bd-aec4-af0b7edd4cdf | note | Records Required: Stringline Sheet/As-Builts
e86ce6fe-e0dd-5f4f-a276-3a3fa15e27af | note | Responsibility: Project Manager
| checkpoint | Confirm surface levels
3f61ab98-e188-57e4-906b-9b6163516d10 | note | H
7583a3d3-1d80-5311-a165-2057dbbf5906 | note | Reference or Specification: NZTA B/2
bddd53b5-1dc5-5f0f-8dfc-1e68be8740ca | note | Method/Test required: On-Site Inspection
05164b95-b3f3-57ba-8e05-c1e976a4c0b2 | note | How Often? Per site
100be1c6-d322-5991-ba0d-2e6f5cfd189d | note | Records Required: Inspection between BECA/Higgins Staff
cd911ee0-e8e8-5cef-838f-26f375ddc6c8 | note | Responsibility: Renewals Manager
| checkpoint | Surface Finish
3c99e71b-8b41-5303-b86a-3c0774901386 | note | H
bb45cc1e-08c1-54df-b448-2fdb48c83600 | note | Reference or Specification: NZTA B/2
0b78398c-bff0-54bb-ba41-7f6a84ed1365 | note | Method/Test required: On-Site Inspection
787a82f4-31b9-535f-8444-a84c12e57128 | note | How Often? Per site
ff8de13c-611c-52e4-8c96-e610b37e8865 | note | Records Required: Inspection between BECA/Higgins Staff
c4261e22-e3c1-542e-a470-91ceb7d77a53 | note | Responsibility: Renewals Manager
| section | 5.0 Aggregate Testing – Sealing Chip
| checkpoint | Crushing Strength
a852e6d6-92de-5d93-927b-24296af73fb2 | note | T
1a67d1eb-d5e3-511d-a42b-aef096625f5a | note | Reference or Specification: NZTA M/6 3.2
a3e5672c-429a-5a6c-8a02-82c4202cad12 | note | Method/Test required: <10% fines passing 2.36mm under 230 KN load
2391c29b-21c6-55d2-abcf-51df95924414 | note | How Often? 1 Test
4fc6571e-92c0-5d3a-afe1-09eb4496d7ad | note | Records Required: Test Report
1f84c44d-ab0e-5b39-8a4c-b2d817cab78f | note | Responsibility: IANZ accredited laboratory
| checkpoint | Weathering Quality
8c292de0-11d5-511e-805e-cf1c804ca0cf | note | T
087f13a1-3bb3-57fe-8728-1158d8bccc08 | note | Reference or Specification: NZTA M/6 3.3
27da9846-1198-5f67-8e33-1dfe6c663f6d | note | Method/Test required: AA or BA
5b1cd088-984d-53f3-8d60-9c713179019b | note | How Often? 1 Test
b0482dae-5050-53bb-8d84-dd52f786ec1a | note | Records Required: Test Report
09a3f2e5-f547-5aa4-a384-7dbb2efea7f4 | note | Responsibility: IANZ accredited laboratory
| checkpoint | Polished Stone Value
a67a9e25-0f56-54a7-bd34-861020da906d | note | T
da45191a-8eed-5778-97fe-d3470b80a631 | note | Reference or Specification: NZTA M/6 3.5
86293b8e-ba4f-5c05-8e69-d9e375b99928 | note | Method/Test required: PSV Required = 52 min
20f592ec-11f9-5d10-bd60-2ade23589d29 | note | How Often? 1 Test
10a97dd4-886d-5e6c-8993-2330e54b1790 | note | Records Required: Test Report
b039c768-bb3c-5c18-8e57-3df53280449a | note | Responsibility: Accredited PSV Testing Agency
| checkpoint | Cleanliness
06b739cc-f4bf-5806-b553-468bb5354550 | note | T
27e74b13-c0f1-5841-8582-af4d9012d60b | note | Reference or Specification: NZTA M/6 4.1.1
8cff71d3-60f5-5356-aa50-f28abbf45208 | note | Method/Test required:
355b3bde-d99a-512a-b005-cc1f5d101642 | note | • Grade 5 – 89 min
0d81f4cb-b18c-5c99-8279-3f4d7ef85051 | note | • Grade 3 – 87 min
758669ac-f922-5da5-b263-c85182f048c3 | note | • Grade 4 – 85 min
8680abf9-e9ec-593d-a5c0-9d560bd60a60 | note | How Often? 1 Test
067bb561-a99f-5dae-a455-0598076f3438 | note | Records Required: Test Report
4a2c7123-b1dc-57ab-9452-ba53457f3708 | note | Responsibility: IANZ accredited laboratory
| checkpoint | Grading
56f750ab-bd4b-58bd-8437-26d3c9a1b7b5 | note | T
1a295f33-9f9b-50c4-9735-f06def6e01b5 | note | Reference or Specification: NZTA M/6 4.2.1
b7e4e3de-8c6d-5237-b9ef-1ad3beb98347 | note | Method/Test required: See NZTA M/6 4.2.1
b375432a-1c97-51f2-98f0-c1467f7bffc7 | note | How Often? 1 Test
612b1b2c-1b98-561c-913d-c9cdbadb1dec | note | Records Required: Test Report
353d8af3-05df-5ae1-8dc3-7b5355fad575 | note | Responsibility: IANZ accredited laboratory
| section | 6.0 Chipseal Control
| checkpoint | Confirm viscosity of bitumen
896b6d4a-c855-5e8d-b6f3-f3e1631f9760 | note | T
1eb45214-4706-5708-9f82-3c65fe2a67da | note | Reference or Specification: NZTA M/1 Table 1
d85aa5d4-4f90-5bc9-83c6-34c99e8d4d0d | note | Method/Test required: Viscosity PaS at 60°C
adcf85fc-9fac-516a-8e77-33f135d3218a | note | How Often? 1 Test
165b1375-06bf-5ceb-8122-6bf1f109cc78 | note | Records Required: Construction
1dd9a24f-9240-5a73-9b63-121c211638d4 | note | Responsibility: IANZ accredited laboratory
| checkpoint | Confirm penetration grade of bitumen
d8ca1c4b-cdb5-5a92-beaf-77b72d3dcecb | note | T
4ff06caa-2afd-59de-8b9f-0e2f40db9c47 | note | Reference or Specification: NZTA M/1 Table 1
a6045246-3959-5d47-86c1-5ec3838e8e3e | note | Method/Test required: Penetration at 25°C,100g, five seconds
0612141c-6529-5174-baf0-53bd7f01e77e | note | How Often? 1 Test
511580f3-d9e0-5d6f-878d-863a4938e4c0 | note | Records Required: Construction
ffb0367f-bd6c-545e-a253-e4e670a456c5 | note | Responsibility: IANZ accredited laboratory
| checkpoint | Spray bitumen, then place chip *and roll – refer design for chipseal Grade
636f4ca1-dcf0-55f3-a3e3-4205a6c0f076 | note | I
d2e76f2f-fdf4-52b6-ae4e-2dbeb1a8e2af | note | Reference or Specification: NZTA M/1 Table 1
7b247478-5d85-5eb6-b57c-d1552f6391eb | note | Method/Test required: Visual Check
915ca07f-6b2d-5f7f-9485-85574c4819a7 | note | How Often? On-Site
6c88f6fa-f3e3-5be4-8153-44172cfd4a03 | note | Records Required: Visual check
321289db-d346-5960-ad4c-8eb827ad0e68 | note | Responsibility: Supervisor
| checkpoint | Check for excessive "windows"
8f462d93-91c6-5a15-aadc-f1099d85794f | note | I
efa58039-37f4-536e-8ad9-d216abb153fb | note | Reference or Specification: NZTA M/1 Table 1
dde88c9f-4384-5b52-80eb-a5e43fa2d774 | note | Method/Test required: Visual Check
143ffa11-15c0-5b49-a49a-fbec80cefc10 | note | How Often? On-Site
f8e8a7b4-2d76-5203-a641-fc92ac20b6a9 | note | Records Required: Visual check
e51f9c18-c7cd-55a0-929f-aa56f2cbf177 | note | Responsibility: Supervisor
| section | 7.0 Site Close-out
| checkpoint | Field Quality Review
9393e35b-95d5-505a-b765-3b1387fb02b4 | note | I
474a86e2-8d5f-5ce2-b90b-1cdddc5a344b | note | Reference or Specification: QMP
14d1d9b1-6c9e-55c3-ba49-f6bcdb00676a | note | Method/Test required: Verification of Work Standards
46f702d1-4cfd-5fdd-9e18-efcdef1c200a | note | How Often? 10% of sites
7a94ece2-317f-5cbe-9104-6234286e20e0 | note | Records Required: Record in Audit Field of RAMM Contractor
9e1cdbab-4f2d-5896-a962-4cd6fd93812c | note | Responsibility: Supervisor
| checkpoint | Collect RAMM Data
843a7b8c-0ff1-59ca-bae1-405f585d07c5 | note | I
c4a1e74b-e6df-5699-b369-a154cfb072a0 | note | Reference or Specification: SHDOM / Data Quality Plan
8684986b-d193-5125-b9bf-d1ecff0d3ba7 | note | Method/Test required: L1 Accredited Personnel
29b75f49-55e5-565e-8f44-f677abeefa87 | note | How Often? All Jobs
c04d590f-6209-5bc5-98e1-353b1fb99b96 | note | Records Required: SHDOM Specs
1c89e1e4-7723-5f71-9405-c072c13d2208 | note | Responsibility: Foreman / Supervisor
| checkpoint | Verify RAMM Data
9b13ab29-7ccc-522c-9a7f-6d3ed37cb255 | note | I
4698340b-39d7-5c55-8d85-47c535fb998a | note | Reference or Specification: SHDOM / Data Quality Plan
662959b9-6420-5989-a4ac-8519f7d202af | note | Method/Test required: Level 2 Accredited Personnel
ec1acc2e-4074-559c-a4c9-a5e430cc33c4 | note | How Often? All Jobs
3c9a8adb-563a-5df0-8542-a9d9b660ca5b | note | Records Required: SHDOM Specs
c011a5c1-ced8-5f0e-8ec7-3d3a9875ba13 | note | Responsibility: Renewals Manager
| checklist | ITP - Pavement Rehab - Rotorua Airport | itp | ITP - Pavement Rehab - Rotorua Airport | aab63402-6fcf-4d73-be9d-45a0bbd5322b
| section | 1. Procurement
| checkpoint | Geometric Design
d52ea8f1-e6d3-56df-85f5-b981005a48b5 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
b424cb6e-91ae-5300-9c7c-0c660aefded0 | note | Acceptance Criteria - Principal Approval
5f4208d1-dcba-5eeb-8098-0392728fe765 | note | Method - Contractor and Principal peer review
92500e36-978c-53e9-a7d9-f25ac9eaa13a | note | Frequency - per design revision
1d160083-1187-59ab-80f6-a2107e915524 | note | Responsible Person - Contract / Rehab Manager
4d16a977-2ca6-5c4d-8793-74a8d4b35de7 | note | Conduct - C or PE
02021c34-bf67-5b19-abf0-b959f4cba471 | note | Produce Record - C
e3078580-01e2-5951-b915-ad5612e75148 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Pavement Treatment Design
ef3ffbfe-5848-5a14-8409-22439a3c7ffb | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
2f5d9cb1-f925-5a4e-83d7-042b0931a6d1 | note | Acceptance Criteria - Principal Approval
2130ed04-ef14-5c27-b175-ceddda721730 | note | Method - Contractor and Principal peer review
2f8d2f02-520a-5ed1-b40d-0e0e8c617fd2 | note | Frequency - per design
17cb4ba3-9c57-5279-8da8-aa97e717806c | note | Responsible Person - Contract / Rehab Manager
19b6ffcd-1f1e-569d-8ab3-180589afb639 | note | Verifying Document - Approvals Register - Pavement Rehabilitation Design Report
69e0f9df-3eb9-58ea-84af-7c64e83ed00a | note | Conduct - C or PE
397818c5-ac90-5deb-9ec8-daec756be48a | note | Produce Record - C
19383a60-ba12-5a7b-b402-d6ed70c8790e | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Material Geo Fabric: on the Sub grade (Digout Floor) - Geofabric for drainage improvement on Sub Grade
95dc4e81-df9e-5eda-890f-15f8c60754df | note | Controlling Documents - TNZ F1 Specification
79c96f56-1823-560d-9157-99245823e2d6 | note | Acceptance Criteria - Pincipal Approval Picture for Docket over Roll
365af4b3-dda8-534e-90b8-40f53f29b739 | note | Frequency - once per material change
3a1d846b-86b6-5587-b53f-7f9ac465bf47 | note | Responsible Person - Sub Contractor
01f13788-46cc-50b5-a3ba-2606d222ed9e | note | Verifying Document - Picture for Docket over Roll
3c97ead5-edb5-5bfe-908e-03a26f9c7ba2 | note | Conduct - SC
f69fe8e2-1717-56e0-936a-09c8d9de1e82 | note | Witness - PE
af12df98-82ca-5473-8b28-cc9c048bbacc | note | Produce Record - PE
8c0ccc5a-4ed3-5031-80c6-ed5b5c41c2ea | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre‐treatment Material (for Type 1, 2‐SB & 3‐SB Only ) - Aggregate Sampling
12dc8976-8c3f-594d-b27f-367bc3096191 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
96c143db-3ec3-5724-987b-50e202602db5 | note | Verifying Document - Sampling Worksheet
85892f53-bf66-5d78-94b3-949187e4ba15 | note | Conduct - SP
9e3321cd-b911-5497-abdc-8a4f49ed2dd5 | note | Witness - PE
5ece94e1-7779-513d-aa0d-d39bd139a106 | note | Produce Record - SP
47ca5d34-dba0-5b04-9ae9-c552922c6704 | note | Approval - E
| checkpoint | Materials: GAP 65 Pre‐treatment Material (for Type 1, 2‐SB & 3‐SB Only ) - Source Property Test
f6ac1dfc-72ee-5972-8d4b-2f175161aaad | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
91b4d386-1442-5e83-9e13-5ae2f529a70f | note | Acceptance Criteria - Soaked CBR ≥ 30%
2bdd1229-fff0-5ae2-8f3d-c872236a2fad | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
2ec53d5e-56b2-5bec-9477-7081143282a7 | note | Responsible Person - Project Engineer
23dac26b-06ad-5be0-884c-d20143427bd7 | note | Verifying Document - Test Report
86394d24-29b6-5faa-9003-08b044fedb1b | note | Conduct - SP
e6622ea9-95db-57e0-acdf-c49c22b10fac | note | Witness - PE
911f3485-6d6f-516e-b5bb-a59ae218e68a | note | Produce Record - SP
74db47ea-bb5b-566e-8a6c-c3304965dbaa | note | Approval - E
809db7d0-ec1f-51c7-bea0-d0828ad9e01f | note | Witness Point - Y
| checkpoint | Materials: GAP 65 Pre‐treatment Material (for Type 1, 2‐SB & 3‐SB Only ) - Production Property Test
0e01ea6f-0c9f-53ed-a2e8-c7777703289c | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
31e2a618-4b99-595b-9063-5126540d9f3a | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
ca6cb1ca-4e53-5ba0-a656-baac3e9c9708 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
d9158386-8d6b-5f88-8e2d-e9216bb0811e | note | Responsible Person - Project Engineer
de38e15b-3cef-5955-ac36-296b3b0f04e3 | note | Verifying Document - Test Report
704fb77d-ad89-546a-a692-fa709731c383 | note | Conduct - SP
9450cc1f-1eea-5d2a-b350-261946cc4b29 | note | Witness - PE
7f64ae53-c2d4-5b6e-9085-15e9adc685f3 | note | Produce Record - SP
69e31412-a514-5fad-8b91-1aeb0149eeb5 | note | Approval - E
ca463406-96ba-5788-9551-d0b19ea5e98c | note | Witness Point - Y
| checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
504aa969-7015-5bfc-8007-13383d2c7fa6 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
417206be-2bdb-5574-a16e-98083788b360 | note | Verifying Document - Sampling Worksheet
5f386605-2f20-5643-bf41-0d1841497969 | note | Conduct - SP
f692d5cd-b2eb-5676-bc3b-b90049cf4116 | note | Witness - PE
c1d23306-3ae3-55a7-82a8-f855eccbfa6d | note | Produce Record - SP
a5537e9f-43ab-536a-9d6a-5bfd3c949b24 | note | Approval - E
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
3e34ec05-da57-5776-892b-c3e3451d4cb1 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
3f9c6c0f-9b8b-5492-9948-b22b26f137a1 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
5d8e86d4-089f-5ce3-9cc3-dfb05824e83d | note | Method - Crushing Resistance Test (NZS 4407:1991, Test 3.10)
e1cc9595-1ebd-5c28-acc5-b66f665876f1 | note | Frequency - One test for every 10,000m³ of source material
9ea097ca-0fa4-5277-8619-131f8e85c974 | note | Responsible Person - Quality Controller/ Project Engineer
b87c4703-8cfd-5f7c-ad03-2e7535f7a379 | note | Verifying Document - Test Report
9b644272-41c4-5d33-a469-5f0ca161f318 | note | Conduct - SP
5af12822-b0c8-5544-a8c5-31400ee57db7 | note | Witness - PE
5a78e80f-d4b0-52f6-b9ca-c18d4af3d6a9 | note | Produce Record - SP
1f664957-e3c2-5f71-8b64-bd89f32a4a37 | note | Approval - E
5a873a45-eb2d-5600-9736-896df90372ca | note | Witness Point - Y
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
a51bf79f-24a2-536c-a77b-561a01a5b768 | note | Controlling Documents - Weathering Quality Index (3.3.2) ‐ TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
191123df-5a6c-5363-9d1f-18e09f35a409 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
bc6a8187-c6f8-59df-be2c-aec505c71c01 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
0efb347b-a0c8-57f9-b8a1-16d165999029 | note | Frequency - One test for every 10,000m³ of source material
da4e276b-0d58-5106-bb58-60b38aff9397 | note | Responsible Person - Quality Controller/ Project Engineer
45ed76c2-d5c1-5015-ade3-25954da8015f | note | Verifying Document - Test Report
b10f3081-4508-5d02-965e-fb7ef24c49d6 | note | Conduct - SP
62cf2b7c-9098-5796-b873-98d22c0d790d | note | Witness - PE
954cc043-6ce9-5842-afbb-511bf80b9330 | note | Produce Record - SP
1e0bff98-362a-5ee3-9ab2-8c38639f052b | note | Approval - E
a4e591cc-4c38-50f0-922d-f8e0a6c9db60 | note | Witness Point - Y
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
5af4b239-f71e-5b67-9a9f-4f9fa43c7cd5 | note | Controlling Documents - California Bearing Ratio (3.3.3) ‐ TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
f381ae2e-7d8a-5420-b61f-feedd4d827e3 | note | Acceptance Criteria - Soaked CBR ≥ 80%
afa95071-9bad-5d46-8e23-4dceecbe33f3 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
527f575c-94f8-5cdc-adc7-39309c69ca91 | note | Frequency - One test for every 10,000m³ of source material
43549322-c2a0-55d0-8914-16dfac7ebae3 | note | Responsible Person - Quality Controller/ Project Engineer
4f4a8dc0-ef76-5a71-a312-94c724d2a9d8 | note | Verifying Document - Test Report
429aaaa2-96ce-5d0a-9c75-04e8cdf2d3bb | note | Conduct - SP
c28c541b-e836-5005-9fad-07228097be5e | note | Witness - PE
b8aa2fa6-5f4c-598d-b387-a11655baaf02 | note | Produce Record - SP
c14b3bfc-98bf-5f89-b76c-6b96c229652d | note | Approval - E
1be19602-92ab-54f2-9151-189b65aae5b2 | note | Witness Point - Y
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
52825615-a41b-587f-9cd6-2c69b9b819ec | note | Controlling Documents - Sand Equivalent (4.2.1.1) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) ‐ TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
ce32c77f-d38b-5ada-b24b-d3681d3a1371 | note | Acceptance Criteria - Sand Equivalent ≥39; or Clay Index ≤3; or Plasticity Index ≤5
41455787-a407-572a-83a5-75f6541e2aeb | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
12559e60-55f9-5a6a-9ede-73171eaf5f61 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
0bb2835c-b820-55e2-a50f-6d0307a774f3 | note | Responsible Person - Quality Controller/ Project Engineer
fa9c4944-2a4f-5acb-b542-b035758b02f0 | note | Verifying Document - Test Report
7e9f52cf-c98d-5fbd-8c4c-8af556072b57 | note | Conduct - SP
d2ebc4ff-0f8a-5ef4-a5f6-a66cbf8ae890 | note | Witness - PE
f1b8e35b-53e2-57ff-b9b8-8639f1e7c4d4 | note | Produce Record - SP
03767998-5ab8-58d6-b379-ce52ca599533 | note | Approval - E
02ececab-5f7e-53f0-bdc8-c0bfc88a968d | note | Witness Point - Y
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
60a5c869-c4f0-54a5-ba0c-6d19d99bec8a | note | Controlling Documents - Broken Face Content (4.2.2) ‐ TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
19464737-e81e-50d0-a028-95aa4448178d | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
eb795dcd-2fd1-571f-8b3a-d99499f1abbd | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
dab3781e-fb4d-5edb-826e-d2fc3b27187e | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
5dc69104-e899-582e-b22e-845deca92365 | note | Responsible Person - Quality Controller/ Project Engineer
670f5a57-f754-54d6-a1b0-f008d98ae0b8 | note | Verifying Document - Test Report
b37d5fcf-56eb-59d0-9787-93c4831b820b | note | Conduct - SP
e5e049b6-0d53-5517-8d1f-da98482e1d0a | note | Witness - PE
9c181025-959a-5018-8b21-8c3ce0de0dd7 | note | Produce Record - SP
72500129-edcb-5cbb-a78b-2b1edd2b1fd7 | note | Approval - E
810a49e3-d175-58f4-a921-8501e8709f67 | note | Witness Point - Y
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
43d269ac-f878-5047-8f13-7a42c2299e1d | note | Controlling Documents - Particle Size Distribution (4.2.3) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
df97edca-ba25-5884-8fd0-627d769c1502 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
52681018-0bff-5a32-9975-2fb56f8d2382 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
46b676dd-5a8c-513c-a050-ac19a0843d2c | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
595142c6-6af3-5081-95dc-7d33c5ce6179 | note | Responsible Person - Quality Controller/ Project Engineer
ac606c46-2754-50d4-8523-f9f422185f05 | note | Verifying Document - Test Report
2b6c25b1-3edb-504c-afcf-5a0abeb84e1a | note | Conduct - SP
7fed94e9-762c-56d7-b759-3751e8b5f60a | note | Witness - PE
09c7d4aa-66e2-5e7d-9557-4f4b294d9922 | note | Produce Record - SP
dd7be2cb-ce38-516a-8001-43d7dad778fe | note | Approval - E
d49a2d36-ee7c-5b8c-91b3-fb29079cf0cc | note | Witness Point - Y
| checkpoint | Materials: Cement - Stabilising Agent Selection
dfd79fa6-b0cc-5c4c-98b2-8ae6c9b0f014 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
5882756d-916b-535b-8666-15e280a23100 | note | Acceptance Criteria - GP
1966af14-535a-55ed-9d6f-eea2adb488c5 | note | Method - Visual inspection of supplier docket
4dd8b67e-39da-5bdc-8101-4a01aefe09ec | note | Frequency - per truck load
c62bdd5e-735a-54e0-b0a5-8e306ee41731 | note | Responsible Person - Quality Controller/ Project Engineer
3eddbcde-e180-5e2d-8ab6-d56640c1159b | note | Verifying Document - Supplier Docket Supplier Cert
e9c86b66-0647-5cfb-b1dd-82a5694e03c8 | note | Conduct - Sp
a6ed9eac-b2c4-5131-bf07-1dfba0742eab | note | Witness - E
58ee1291-273e-5bee-be10-8fcc5e2066bd | note | Produce Record - Sp / PE
020f786a-bfbc-5efa-a305-ce4e09d4d813 | note | Approval - E
fe3cd971-080f-59bf-8acb-feb191702edb | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: Water - Water draw for stabilising
e266b12a-3cc7-5844-ab61-435c7c12fb07 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
31db09e3-e1f0-5e3b-9092-ed9a5a996a24 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
e524c5f4-0f90-53c2-8458-c389b894c64d | note | Method - Visual inspection of hydrant use form
f5f6d9e2-3e4e-590c-b897-1b6d3dae9b47 | note | Frequency - per truck load
b02b5b8f-3866-5493-827e-c4e5c846cf5f | note | Responsible Person - Sub Contractor
455ded47-7b1e-5434-aa64-2c71249c0d63 | note | Verifying Document - Hydrant use form
bf43d093-a265-5276-a053-f61d4aa3518a | note | Conduct - SC
4255c36f-b634-5b01-ad8b-8e142825e481 | note | Witness - PE
48b3c99d-e05d-5db4-904f-ec90b92101c5 | note | Produce Record - PE
e6e72883-c005-56e8-b3d8-605556b74a85 | note | Approval - C
9e8896c3-36bc-5e25-9f6c-ada7aab3cb9a | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Sub Soil Drain Materal - Sub Soil Drain Pipe
ab1c07e1-5d9f-5c0c-a9ec-3b001114231c | note | Controlling Documents - Sub Soil Drainage Contruction F/2 Specification
3d8b165d-af04-5940-a396-43a89a04e997 | note | Acceptance Criteria - Principal Approval High Density Corrugated Punched Pipe of Iplex Nexus Flo/Marley Brand Class 500 Blue Strip, SN 4 ‐ 110 Dia
227f92d0-9205-5cae-91fc-3907a13f86aa | note | Method - Visual inspection and Certificate from Supplier
ab5f5f4f-6aa1-548f-9630-f06ef74c486f | note | Frequency - once per material type
1dced832-a091-5bdf-8ee4-84f28edb1175 | note | Responsible Person - Sub Contractor
55c309b3-f0bf-574f-9aca-fd23ca60ca95 | note | Verifying Document - Docket Picture
0014e31f-ffae-5e65-bec5-d3e1bf487b79 | note | Conduct - SC
992441d8-9095-5707-82fd-56456ed85371 | note | Witness - PE
e72cdd28-e04b-5027-a1df-f49cb9c3d0d7 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Sub Soil Drain Materal - Drainage geo fabric
216881a0-9c5a-51b7-aefb-a1346f9e126f | note | Controlling Documents - Certificate from the supplier/Docket
b01c364e-12e5-514d-b83c-5b8a46bc37a1 | note | Acceptance Criteria - Principal Approval Bidim A14 Class Min
798fbb24-5fee-569d-9b2d-6b574a417b4b | note | Method - Docket photograph
e07e4959-0223-5419-8e67-6e0a2e526897 | note | Frequency - one per mateial approval
f59c5ed1-293c-5327-9ee4-db78c4706db8 | note | Responsible Person - Sub Contrctor
6a372acd-0c66-5a54-ba49-d3f88a6f89f2 | note | Verifying Document - Docket Picture
9ede5b67-da18-5e0d-889e-0b94ba68a35d | note | Conduct - SC
53f0e76e-e6aa-50ae-9b1a-d76b948515f8 | note | Witness - PE
b504a3ea-e570-588d-8a08-d847a2c9ddd2 | note | Approval - E
| signoff | HOLD POINT
| section | 2. Pre-Implementation
| checkpoint | Work Pack complete and held on site
b426f419-544f-5ea3-9a83-d2ea7ba4cdc0 | note | Controlling Documents - ..\Work Pack
774df748-b370-580c-afa9-d14a1bb93590 | note | Conduct - SC
2f75a2b3-b383-5982-9b82-beb854c762af | note | Produce Record - SC
c8e1f109-482e-50ee-8502-40477f4cb5f4 | note | Approval - PE
88543ee3-5506-58c7-8fe0-a1e7a62df36f | note | Witness Point - Y
| checkpoint | Communication Plan implemented
cdf953d7-57e5-5ead-ba94-97972c6fe0b2 | note | Controlling Documents - ..\4.5 CSCMP
810f71d2-8c04-5ea8-9705-136839c5cec3 | note | Conduct - SC
0bb49c87-df6d-51df-bfe1-db67d772dbd1 | note | Produce Record - SC
9a1579a8-128b-5eda-94d3-1afaf6286d3d | note | Approval - PE
6da7e2f5-a19b-5ecc-b6ad-c8b01e3e58eb | note | Witness Point - Y
| checkpoint | Are any consents /approvals required, including for taking water.
12b29c6e-e52f-5533-8a52-756d4d75e782 | note | Controlling Documents - Hydrant Use form
2c0a081f-8ced-5bf7-ab2f-453f53b88927 | note | Acceptance Criteria - Forms available for applicable days
467ecf3e-ff48-571c-9702-2e8af236a78c | note | Method - Visual inspection and recording
dcb5c995-fde7-571b-a839-eb849c4494b7 | note | Frequency - Daily as required
9080896d-859a-555c-811c-4fb3016282c0 | note | Responsible Person - Sub Contractor
0c82d272-2979-5d7c-a2f9-c312385a3107 | note | Verifying Document - Hydrant Use Form
67985a07-7dfa-5dc0-97fe-84bdca2d7639 | note | Conduct - SC
3d61f1c1-ddec-56d0-b9f9-3c8bf32b2761 | note | Produce Record - SC
42d210de-2c7d-50a9-be1f-6ab4d1b2c788 | note | Witness Point - Y
| checkpoint | Quality Control forms on site
4e93cd42-0788-573a-a8b0-abb3f46b013f | note | Controlling Documents - RQP, ITP, Scala Penetrometer Test Records, Material test sheets etc.
d3068790-75ad-5b2c-94ad-e293df790ba9 | note | Acceptance Criteria - Visual Confirmation
dc95bb10-4a6c-52ee-afe7-e7ff4667f722 | note | Frequency - Daily as required
9f5959cd-2799-583c-ba12-49bfb13740da | note | Responsible Person - Supervisor
f2ca348f-e67a-5db7-86d8-129d74e4c278 | note | Witness - C
| checkpoint | Person(s) on site with authority to stop work if quality of final outcome is compromised for any reason
51d1cd78-0456-59fb-a6b6-b3eb5eb3617b | note | Controlling Documents - QMP
af90d7cc-2568-5e06-a254-d98b665e6fa0 | note | Acceptance Criteria - At least one nominated staff member on site at all times
93afabad-01a8-5b3f-8a65-6be81fa6d027 | note | Responsible Person - Site Supervisor, Quality Controller, Engineer
c66e5c0a-5fc4-5197-9c55-6df5d03b343e | note | Verifying Document - Pre-start sheets, timesheets
acd8fd81-a0b7-5cae-b39a-7eac97c544ab | note | Conduct - C or PE
80110d9f-a2cb-509b-b2b0-832890203630 | note | Produce Record - PE
| checkpoint | On site Prestart Meeting
abc022b8-5fd1-5018-8c7a-958282d4f6b6 | note | Controlling Documents - Site design information - Earthworks plan - design drawings.
5d3236f9-47f7-5da5-b6ae-e2ed19069e8d | note | Acceptance Criteria - Visual confirmation and walk over - confirm associated works -verify extent of works - verify digouts or additonal items
29f5e50a-8958-5fe5-8ebb-436fe89f1bab | note | Method - Visual inspection and recording- variation approval process
00d65eed-963e-5154-bc03-6591d9bd92ad | note | Frequency - Prior to any phyusical work engagement
f0c0114c-316f-5bad-aa62-3402ae7b1994 | note | Responsible Person - Supervisor
3c25f519-bde0-55a6-8080-9d6eaf56c188 | note | Verifying Document - Pre Strart Attendance sheet
17d48c63-a64c-5067-8eb9-3c719d8cb17b | note | Conduct - SC
9fc866b0-3e94-5ecf-8e42-9b22d031b7e7 | note | Produce Record - PE
287e3e19-e578-5013-a54c-02bced364902 | note | Approval - E
9e5c1091-dea3-5533-855a-faf522d1073c | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Highlight the extent for different pavement types
ad437dfe-67cd-509c-bea7-f5262c6c277a | note | Controlling Documents - Reference from Project Drawing Sheet C 01, 02 & 03
9f4bce1c-e766-5c1b-97e8-314cb5dbdf56 | note | Method - Survey/Mobile Roads, Marks with Dazzle
d265834f-d919-5d55-876e-45990c6c9041 | note | Frequency - Chainages for every different pavement sections
48946090-9ae8-5da4-a68b-dca34661ee89 | note | Responsible Person - Sub Contractor/ Supervisor
33e497eb-bec2-56c6-8714-0d631a4b6954 | note | Verifying Document - Project Drawings
b780d198-4f0f-5e0e-962c-6502801bc962 | note | Conduct - SC
| checkpoint | Records Management (i.e. it is known what documented records are to be kept)
d0eb190c-fdae-5e05-b405-9f8534a158fb | note | Controlling Documents - ITP and QMP state what quality documentation is required
e0af5e00-5707-50e0-93a7-951cdd801fd6 | note | Acceptance Criteria - Filled in and Signed ITP
e2a53bb3-52f8-5d22-80f4-3c0d21fcf00e | note | Method - Visual inspection, recording and approval
c8e6143d-656b-5082-989e-facddca265db | note | Frequency - As per hold points in collaboration with the programme
78662f71-893a-5ef9-8ee5-fa6077b4b1d1 | note | Responsible Person - Quality Controller
a2384139-a309-5915-a0bf-dde2f89b420e | note | Verifying Document - ITP
4c22348b-55af-591a-a666-05a7027fb2e1 | note | Conduct - C
24efd5a8-0ee7-5aa6-978f-dacb45d888e6 | note | Produce Record - C
7c7dfa65-e4fd-53ed-a63b-67b7726f27c0 | note | Approval - E
d9dece21-cc54-5cb4-a4d2-b2e3d3ec3ad2 | note | Witness Point - Y
| signoff | HOLD POINT
| section | 2. Temporary Works (including Traffic Management, Environmental and Health and Safety Controls)
| checkpoint | Traffic Management Approved / Implemented (copy in Job Pack on-site)
8b34b0b1-66d3-51ff-8185-a542d891d224 | note | Controlling Documents - Site Specific TMP, COPTTM, Higgins TTM SOP, SCR Form
9ce1707d-3f1b-504e-bd8b-638481bd0dd1 | note | Acceptance Criteria - Passing SCR audits
af5327c5-891e-5cb1-8ade-f7f869f2cb2c | note | Method - Visual inpsection and recording
9d029537-503e-52b7-8371-ad7c91099f1e | note | Responsible Person - STMS
082dc0c3-e472-5de7-b045-d0bd2a4746c4 | note | Verifying Document - Site Specific TMP, SCR
0c513ebb-9ead-5641-8cd9-5e1399a1a98f | note | Conduct - C
74bfbbf9-d9dc-5a35-a19e-811052861b0d | note | Witness - C
7260dcb4-1c14-5047-9978-9e1ae1e2cdb5 | note | Produce Record - C
6adcc575-db83-5868-a369-fb473cd280de | note | Approval - C
59af7c82-3e72-5dff-abeb-b6f600a3f9ea | note | Witness Point - Y
| checkpoint | Environmental controls in place (Seal of Existing Catchpits or storm water line)
9fcc7746-8119-559d-b4f1-d44b7137a8f9 | note | Controlling Documents - HSE Audit, JSEA
18d55dc7-1079-5f81-9734-cd75ffd2f284 | note | Responsible Person - Site Supervisor
4f26f434-df9c-5e76-8736-827e36a807eb | note | Verifying Document - HSE Audit, JSEA
04bae34d-0156-5eda-9a55-c97f6a02a6a7 | note | Conduct - C
c3b98b4f-b860-5d1e-961a-fe08ff4c7f9a | note | Witness - C
e8b90322-3287-5fe3-b3ed-ad2f03fc958c | note | Produce Record - C
472b1378-d831-5989-807d-f53db2b3df6c | note | Approval - C
f90e22cd-8145-56c1-bddd-4f30d016427f | note | Witness Point - Y
| checkpoint | Health and Safety controls in place (e.g. Isolate work area)
b6d39078-01a8-5fe7-8983-86638757f5df | note | Controlling Documents - HSE Audit, JSEA
01319c4a-3ade-5a99-86ab-339b06f0b009 | note | Responsible Person - Site Supervisor
65ccfed8-1bfb-5108-96e7-4dcc34f312b3 | note | Verifying Document - HSE Audit, JSEA
39e9710c-fda0-5a53-bd45-d80485405f2d | note | Conduct - C
a88837bc-7b19-529b-88e1-a05029836f85 | note | Witness - C
82717222-a1c2-5151-9c1c-112a259859e9 | note | Produce Record - C
4dc02925-6c32-5375-ae25-0428520d1ad8 | note | Approval - C
6585e9af-9cfa-5052-a2af-589c1627aa56 | note | Witness Point - Y
| checkpoint | Standard Operating Procedures / JSEAs available on site
ed3d1d35-1791-5f11-89b8-84b06f89ed7e | note | Controlling Documents - HSE Audit
7f519da2-5474-5e10-8461-f3c175144455 | note | Responsible Person - Site Supervisor
053ef3dc-529e-510a-b346-94c5e6fd25f7 | note | Verifying Document - HSE Audit
187ed742-0c63-5e59-a5e6-da4e91a48fc5 | note | Conduct - C
9a86d6ae-6365-582d-9323-eec76fecc859 | note | Witness - C
157cbf97-74dc-5cda-a756-9ac15e4464ee | note | Produce Record - C
89056246-3742-581b-b1e3-6fe1cd9a60ba | note | Approval - C
d94fd84f-a581-5889-a63c-35770f0a6364 | note | Witness Point - Y
| checkpoint | Any service covers or utilities identified and protected to Service Authorities expectations
32bf204f-a009-5ddf-a075-c74ded1422c6 | note | Controlling Documents - PTW Process, B4UDIG
4e649217-71ef-5348-a12f-c86780e22779 | note | Acceptance Criteria - Work always undertaken under live PTW
4ebaa47d-848f-548b-b6f7-70f4eeb24d54 | note | Method - Visual inpsection and recording
b87f7add-5402-564a-b1c0-355ca9c89d93 | note | Frequency - Weekly
68152069-1090-5aed-b120-fe727c53e565 | note | Responsible Person - Permit Issuer
84dba820-99fd-5599-a704-64ca2542da07 | note | Verifying Document - PTW
de9c406c-2ed7-5875-a62c-615ff84b0b3e | note | Conduct - SC
f32e76b9-2db8-5f0a-971b-189a90f21991 | note | Witness - PE
840d63fe-97a2-52a8-87a5-f9ab8281701f | note | Produce Record - SC
320c95db-54c7-555c-8064-06098d7efa62 | note | Approval - PE
4630f997-875c-5175-b005-ee4cb2692ce8 | note | Witness Point - Y
| section | 3. Construction - Pre-treatment Digouts (for Type 1, 2 SB & 3 SB)
| checkpoint | Open Digout Depth as per the Attachment 1
f4403930-8f60-55e1-a421-5b1ae3d17bef | note | Controlling Documents - Pavement Rehabilitation Design Report 2019/20 030-0147-6900-7190 Rotorua Airport
2b2add23-9b77-52ba-bb32-57b9f63568dc | note | Method - Install Geogrid 30/30, (Class C) Geoteextile on Floor
1291de78-8e64-55c2-b20f-1515cc9848cf | note | Responsible Person - Sub Contractor
7a8bf15e-e7a0-5ca7-b895-3c833df07791 | note | Verifying Document - Photo Graphs with chaniange highlighted
0ffb3240-c363-5747-bcf6-7ee7e386b890 | note | Conduct - SC
6eb57cef-54d7-5ca4-83d1-9ea2bee9d468 | note | Witness - PE
a9d545e7-ee4b-5df3-8f70-cd7d5d1e5d42 | note | Produce Record - PE
400404df-f8d7-5561-a7c6-abc4f7ba826d | note | Witness Point - Y
| checkpoint | Excavation floor drainage
d2777ca6-37a5-51c5-bf08-9af97757b2dd | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
eea7796f-9ed1-5ff3-9e16-7ccdf05e9e1b | note | Acceptance Criteria - 4-8% toward edge of seal
03ef8801-93ca-5d05-a5a5-eb5d7a3cafcb | note | Method - Digital level
9ecbcd8a-4036-5c40-a43a-c52d88fe90ea | note | Frequency - As required
82b07b8a-542c-513a-aeee-014d386c0f8c | note | Responsible Person - Quality Controller/ Supervisor
fe93dc68-a950-598b-967d-86449f62a790 | note | Verifying Document - Dig out QA form
0de3f8f6-783f-5c28-b417-d6cf4df94b18 | note | Conduct - PE
cd21f309-86e6-5ce8-bb1b-25c80cfc1e9a | note | Witness - C
5af000db-027f-533a-bb49-02aeb35cead3 | note | Produce Record - PE
a7e91b4a-1927-5dd4-9f72-e5f4bd622b5f | note | Approval - C
| checkpoint | Sub Grade material hardness (In case of undercut req. on Soft Patch)
7882ad06-9f1f-5a54-980f-4732ffb06df4 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
23304c07-f5f6-5d4b-8001-2de975b4457e | note | Acceptance Criteria - ≥45 Clegg
f0941b29-d004-5d69-8c0d-70b982b990d6 | note | Method - Cleg Hammer
3d1fe524-90e0-5283-bdcf-eb9bb00b3845 | note | Frequency - 2 per patch
2588c5e2-696f-5e7f-a5b9-bda3f150592d | note | Responsible Person - Quality Controller/ Supervisor
4ed24c5f-da8e-543e-9df6-79be92c4e06f | note | Verifying Document - Cleg hammer form
560f663f-adc3-5aaf-bf97-354f45be743f | note | Conduct - PE
c7d47069-e00d-539f-8b49-d8d6f844524f | note | Witness - C
01dfae07-ca58-5a9a-be09-273e8c891c45 | note | Produce Record - PE
07b2ba21-0428-5d98-b162-f3d254207dc9 | note | Approval - C
| section | 4. Construction - Sub Soil Drainage
| checkpoint | Subsoil depth and discharge point into SW system around As per the Cross section Attached with this ITP
c26b9482-8af4-5701-b2f2-3666e5a7956c | note | Controlling Documents - Location as duirected by the principal engineer and methodology as per F/2 Specification
62af701c-1f56-5cad-8d44-2d28ea6c2e9c | note | Acceptance Criteria - Slope to be confirmed on the site with visual inspection / Laser Level on Site, Blue Strip facing upward
e38a00ed-33ab-56e1-9ed8-da6ddb3f65c5 | note | Method - Visual inspection to confrim Sub soil draiange installed to the correct depth with pipe surrounded by BIDIM A14
c3cd3e1b-a5c0-5ade-837a-1dd693f37389 | note | Frequency - As required
b8e11e2d-3cb3-58b6-aafe-3e6cc2f041b9 | note | Responsible Person - Sub Contractor
2bffbb81-e944-5e75-91bc-1b855167d8a4 | note | Verifying Document - Photo Graphs with Depth and position of blue strip
0d2f46fc-03cb-51c3-ad06-18041ac383d7 | note | Conduct - SC
9c5452e2-88ff-5258-ad5f-89735adfd7c4 | note | Witness - PE
b4fe417c-e79e-5866-a89e-71a83434a457 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Bedding/ Surrounding material 20/40 drainage 5 round pebbles
13b2bdc4-3b76-59c4-ab22-f9620b9478cf | note | Controlling Documents - Quarry Docket
fbf5f742-23a3-5d78-8843-69af040ec46d | note | Acceptance Criteria - Round Shape as per Drainage Specification F2. Depth under pipe & each layer should be min 75 MM
da1ac61f-6030-5d7d-81ec-59491aa56b81 | note | Method - Visual inspection
276a258d-bb06-5310-bce7-ae6730e093c1 | note | Frequency - As required
2ce20c03-bd56-5893-bfb8-7ad025168a06 | note | Responsible Person - Sub Contractor
08400ef1-55c8-522b-bc8f-fd8543e48a6e | note | Verifying Document - Photographs
b3d3590d-f730-542b-b8c0-a83bf876d002 | note | Conduct - PE
bcd84428-1f60-56d5-b1c8-390935d52241 | note | Witness - C
8aa79ff0-6e3a-522b-9f47-3808c9da2a56 | note | Approval - E
| signoff | HOLD POINT
| section | 5. Construction - Granular make up and In-situ Modification (GAP 65 5% cement - 250 mm depth for Sub Base @ Pavement Type 1,2 SB & 3 SB) and (TNZ M/4 AP 40 2 % Cement 200 mm depth for Base Couse throughout)
| checkpoint | Plant and Machinery Seletion
1010d9a4-cf0c-5735-ae31-5d2862270666 | note | Controlling Documents - Plant and Equipment (6.0.0) - TNZ B/5: 2008
20b28ac3-be54-553e-81a4-90cded915eca | note | Acceptance Criteria - Cement Spreading Truck, Direct Injection Stabilising Mill, Vibratory Single Drum Roller, Pad Footed Roller and PTR
d146a126-5058-5f6b-9e1f-55385e578a59 | note | Method - Visual Inspection
8b77c217-4b40-58bd-bd6b-79e076901881 | note | Frequency - Pre-establishment
41fc929e-b732-54d0-8622-371917e3dd71 | note | Responsible Person - Sub Contractor
0e9375ff-c86a-5654-962e-957623ffd159 | note | Verifying Document - Daily Site Record
c6b013b7-d521-53fb-8ee3-344759270425 | note | Conduct - SC
995aa98f-3ffb-547d-bb58-28cb04ddac82 | note | Produce Record - PE
e0123153-4815-5939-ae7a-4a06553928e6 | note | Approval - E
1937ac22-50a7-52b0-a5ee-25f8897c3eaf | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Weather including temperature
47f82877-d80e-5e33-b782-f2ae7c1b9007 | note | Controlling Documents - Weather Limitations (7.1.1) - TNZ B/5: 2008
2efb7fea-7e3c-5959-a0b7-87c453c64a91 | note | Acceptance Criteria - Ambient air temp ≥5˚ C, Wind speed ≤25km/h, Rainfall ≤0mm
f77ab8b9-f90d-5496-a219-8016a6484e61 | note | Method - Visual Inspection, Met Service/Windy
de4799b3-6e07-5bca-ae5c-c8b0971f75c7 | note | Frequency - Throughout process
50e8df2d-30fc-5922-9caf-50eef2be9f71 | note | Responsible Person - Sub Contractor
255bbac3-bf4f-50c7-b1b1-2b708896af93 | note | Verifying Document - Daily Site Record, Metservice
9a314a8d-6ec7-58c2-aa0f-7618c0ec8210 | note | Conduct - SC
c106a2d7-2ad3-5d53-a8d4-cd84d7434fba | note | Produce Record - PE
acde073a-6f29-570a-acd1-7f65af7e22e5 | note | Approval - E
3bb1ba62-8db9-50d0-9bd4-642205d16834 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Spreading of Cement
66db12c7-d770-5170-8a2c-fed559bbf45a | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
a428b012-da8a-5fec-8c19-7c0d5043c94c | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
ce5fb10e-bf40-51ea-9f96-ca5d8129ced0 | note | Method - Mat test (1m² canvas) and Average Usage Test
adccb7bf-20d5-55a3-a8b2-5682d35ce2c9 | note | Frequency - per 400m² and upon emptying the spreader
bfe882e4-b634-5372-b1e4-d665a8bc88ed | note | Responsible Person - Sub Contractor
062c11a9-0459-5dfd-b1f8-f3b15b95cb95 | note | Verifying Document - Mat Test Form and truck dockets
c1aeef6c-5bd0-5027-a887-7b5d8de9a25e | note | Conduct - SC
1f3b7fbf-e36d-595f-879d-d0688e046cd5 | note | Produce Record - PE
fe4c42d4-58e2-5594-a3fd-6e843af547d3 | note | Approval - E
b6d3799d-c5c4-582c-9ee0-0621516c4fcf | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Addition of Water
f67c5aca-e417-51cd-8b0e-8986917092d1 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
91159a84-4c01-56f8-bef7-2c9ec16cec51 | note | Acceptance Criteria - 90-100% OWC
641e8764-f002-500a-a005-6e519fc9c90e | note | Method - Nuclear Densometer Testing prior to Stabilisation
516f9b49-94aa-5758-9914-2a392cfa4a80 | note | Frequency - ≥1 per 1000m² lot
b58d3fe0-ebaf-5016-9fc6-03b341fe0262 | note | Responsible Person - Sub Contractor
02f6f3f2-4ada-5ff0-82ed-f21a8f8ffbb8 | note | Verifying Document - NDM Record
4bcf3d36-dbc2-5eba-ba31-1bbf6bb487ef | note | Conduct - SC
52df9588-e2a3-5b6a-8971-c240ca9ef274 | note | Produce Record - PE
8cb26c5c-052a-5eca-b28e-863ad5b8cc18 | note | Approval - C
13b41892-61d8-5c1f-84eb-93a269d07cf5 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Cut Depth
02c5640b-f05b-5d62-b996-ebba0b36daa8 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
0b76882a-a1b3-5045-9609-d9053aba96ef | note | Acceptance Criteria - -5mm and +15mm of design stab depth
c02ba2d2-00ab-5eae-84e6-5fe64ad3a37b | note | Method - Physical Measure and Visual Record
83500f79-4124-54ee-8f8a-5d273f894b91 | note | Frequency - ≥1 per 200m of cut length
8a3b001c-6a5a-5a07-8239-93cf8aca458b | note | Responsible Person - Sub Contractor
fdf4c0d6-e320-5386-adf9-b43a25c99193 | note | Verifying Document - Photographs and Daily Site Record
59121143-9c21-517d-8b02-d103c4a0b1ec | note | Conduct - SC
1d73adcf-ad32-593d-ab23-3b8bcad96487 | note | Produce Record - PE
54dff258-2eb3-505d-80c9-2706176e157c | note | Approval - C
21c41029-9e22-5337-93d5-d6935ef06970 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Tie in points
8f5d87a8-1eb4-5f6a-9119-fa10e361016a | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, NZ3910 Variations TNZ State Highway Geometric Design Manual
9601f2b5-0b38-5314-b755-1d0e4e3a4525 | note | Acceptance Criteria - Principal Approval
6d212c5b-594b-51a2-a650-47a4d4c1223f | note | Method - Physical Measure and Visual Record
8997015d-e470-5a36-94cc-43382652b3f2 | note | Frequency - Pre-physical work commencement
95fcd444-8644-516e-8e1d-3aeee79ee48e | note | Responsible Person - Sub Contractor
92253dac-714a-5b5a-8d21-4bd4d1e6c4f9 | note | Verifying Document - Design alteration variation ACCEPTANCE
cf7a5fd8-2afc-5043-ac77-7dbbf2225132 | note | Conduct - SC
989bf0a1-ea37-510b-896e-18094c8aab66 | note | Produce Record - PE
3940e52e-a4e5-5f7e-ab39-4646ade99c74 | note | Approval - E
55275d84-6172-5420-b8a1-fbe57201a3dd | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Longitudinal Joints
0de93937-145f-5c22-97ca-62f13bc5374c | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
a31ffd80-f476-52c5-806a-99e7e66b4774 | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
e529f473-8545-5691-9cb7-74843d97ac0f | note | Method - Visual Record
900e34b5-d0c6-582b-b3f3-80942dda8a03 | note | Frequency - per sucessive cut
d6c5ec7c-0760-5635-bcd3-f687eb64fff9 | note | Responsible Person - Sub Contractor
1f468e29-428e-540c-a32a-38069942400d | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
a44d313b-3e6c-5815-89c4-62f392759d13 | note | Conduct - SC
6f6aa5a1-0e61-58f3-b100-880c78fd27dd | note | Produce Record - PE
b9f84d5b-4427-532c-819c-644d6f5bcae1 | note | Approval - C
b0b9edff-7c7e-5a6f-90ad-540f5e97e0dc | note | Witness Point - Y
| checkpoint | Continuity of Layer
f1bdc028-a203-54c7-b880-b095f87a98fb | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
0878aedd-7974-5f7c-a934-3baa4f371f69 | note | Acceptance Criteria - Longitudinal overlap 1m
a3ed5699-5241-509d-bce3-f6bb14d9243d | note | Method - Visual Record
ccd6b76b-cfe5-5f73-968c-0e7a1276111f | note | Frequency - per sucessive cut
e9bba4d4-2b37-59b5-be90-d312a94f3bbe | note | Responsible Person - Sub Contractor
6f47fd5e-c4aa-52a6-8fae-e79808bf2922 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
424a4b0b-cc77-5434-8cdc-c5c92815c417 | note | Conduct - SC
0e822d84-1d3d-5b61-a8a3-d4078c71754b | note | Produce Record - PE
cd83896e-f9a1-58fb-a562-9e9284d873bd | note | Approval - C
e7b1643a-cba5-541c-abbe-c956eb3b2946 | note | Witness Point - Y
| checkpoint | Stabilised Material Particle Size Dsictribution (On Base Course only)
cf525949-1dc9-5efe-a186-d39817eb63e3 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
2d569efa-fc24-535a-97d5-b5b28da95e0b | note | Acceptance Criteria - NZTA B/^ Section 7.5.8
128aad39-5047-50e5-b464-5ef8ddfefded | note | Method - Wet Sieve
7c3d9372-8e69-5d79-8229-8244ccae2a58 | note | Frequency - 3 Per Lot
4a8edc1e-893a-5060-bb73-b20420432dd4 | note | Responsible Person - Lab Technician
c56129f0-461e-5fea-9d30-6280e47af8aa | note | Verifying Document - Test Report
aa4c5dc8-a69c-5738-afaa-fbf7db8ba620 | note | Conduct - LT
1e0be1f3-a42e-54f9-b725-55b10a7e2158 | note | Produce Record - PE or C
6a328127-36fa-56ac-b231-600dba60a4ae | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Strength Test Conducted -ITS (On Base Course only)
3370d664-298b-5f33-be2e-804abd9547bd | note | Controlling Documents - TNZ B2 /NZTA Best Practice Guide/ NZTA T 19 Notes
cf5b7893-a89b-5e86-a989-4d8d1f6005f1 | note | Acceptance Criteria - NZTA T19 Table 1 for Cement Modified Base course with results min 300 KPA for ITS
08d03905-0723-5f6c-8d03-3a9ee3aaaa9a | note | Method - Lab Testing on Sample collected after hoeing
67c0b264-d00d-5f50-adaf-1d882ca06647 | note | Frequency - 1 per lot
e43f5f95-150b-5efb-a58a-413c726277d9 | note | Responsible Person - Lab Technician
b46414f9-c53c-58e4-aeac-a16452b5847c | note | Verifying Document - Test Report
34a8e16a-5bd2-59c7-af0e-803be2e36bdb | note | Conduct - LT
2b8dbaa5-926f-5d07-9c36-ecd9289c0ea1 | note | Produce Record - PE/C
740a0a68-3ee8-558b-9845-5961a03853d8 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Establish Compaction Target
95b97d3e-c5e9-5ff3-82b0-d2f19cc82264 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
c57e12c8-6147-5a26-846b-f58c1f095d7f | note | Acceptance Criteria - Formal Agreement
1de6fb70-4d7c-5380-99b7-2e61d1bb024a | note | Method - Plateau Density Testing
27c3c1ae-d9b6-5d4a-97f5-7a5907a2a770 | note | Frequency - 1 time, or additional tests when material changes visually (Recommend a minimum of 1-2 tests per section)
af8a8535-1bcc-5d12-8218-ab8b4f3d2d52 | note | Responsible Person - Sub Contractor
b298cdfe-f3d9-53f2-b862-0ba9507a8222 | note | Verifying Document - NDM Record
f967a4b2-f06f-5b78-844c-11062e80bcbc | note | Conduct - LT/SC
ced53daf-975d-5102-aad0-699b2287e0a9 | note | Produce Record - PE or C
61b96489-fcd6-51d5-aed5-501aa2b05583 | note | Approval - C
35908eaf-610e-5eb7-826a-2dbf5dfad075 | note | Witness Point - Y
| checkpoint | Compaction Acceptance
9d8c71d4-2ebb-58a2-ad25-6d4b544d94ed | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 -TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
77cf19ab-078a-59ca-b3d4-9734211384b5 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
b2803f99-ac08-5abe-81ec-13b1edfc0f5e | note | Method - Nuclear Densometer Testing in Direct Transmission mode
6024bd2b-40f2-5de4-ab2a-50c7a2627e82 | note | Frequency - ≥ 5 tests per 1000m² lot
d90c07a0-200a-589e-880f-079a884ec5ba | note | Responsible Person - Sub Contractor
4f79a8fd-61e6-58f2-929d-eb32d755d066 | note | Verifying Document - NDM Record
74f9e1db-3581-59e8-9c6e-c6a34b6d2a2c | note | Conduct - PE or C
cc896c6b-0c18-59fc-a354-a67bacd2277d | note | Produce Record - PE or C
19b82950-ac17-52cf-9a7b-fcd76c2cd3e2 | note | Approval - C
14208b8d-d2e4-5bd4-8f02-4b8762b3109d | note | Witness Point - Y
| checkpoint | Control Testing
b832212d-3c45-5045-bc20-c9d19157af57 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
e7971f75-98ea-5170-801c-620a0f856ae6 | note | Acceptance Criteria - Nil
6bf8d613-5751-5d17-9dc5-13a610e10c09 | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
0fe3a27d-af33-5245-9698-c943a0095aad | note | Frequency - when agreed
bc935e21-b47c-50c9-a87f-7ad23b12c539 | note | Responsible Person - Sub Contractor
3d8af08a-d75d-56cf-8581-ac903adfbd48 | note | Verifying Document - Test Report
2fb41726-9d20-52ae-b784-617f71541760 | note | Conduct - PE or C
04bf4605-6965-5a59-ad16-0647750c1c34 | note | Produce Record - PE or C
46e6d861-2841-5a3d-9f36-944615ba9d2e | note | Approval - E
| checkpoint | Surface Roughness
17c8bc7c-cd5d-536b-8096-3c3c17dbeec0 | note | Controlling Documents - TNZ TM 7003 v1 2. Roughness Requirement
37b38508-c3cf-50ec-b41a-7420f40c3b68 | note | Acceptance Criteria - a. No 20 m reading in any lane shall exceed 70 NAASRA count/KM
08fb761b-acfa-5d60-932e-a0e61077a39f | note | Method - Measured in the Wheel paths of all lane surfaced under the contract in both directions
7175e51f-b083-5f5c-a491-9a4d4cc13575 | note | Frequency - On Completion Surface
36e0bf38-d33d-5087-8dc2-f8280cb6bedb | note | Responsible Person - Sub Contractor/ Lab Technician
506a0753-45c4-55a1-ab5c-3275fc0e475c | note | Verifying Document - Test Report
73e7fb11-3d96-5c70-b40f-94fe55dfb48a | note | Conduct - LT
76f710e5-5ab8-5eaf-b75d-63c0a16b743a | note | Produce Record - PE
f80e3e2a-28eb-53a2-b08f-65f711c61f50 | note | Approval - E
0ecfabc0-7482-5bf4-bc66-47c41ebc4d06 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Surface Shape
dff8c17d-900a-5030-9d58-552c90b25c21 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008 ;
882d5032-f860-555c-b039-d5dc549d8470 | note | Acceptance Criteria - Between -5mm and +15mm
150e858a-22fc-54dc-937b-8f07c648ac39 | note | Method - String lines or Survey Asbuilt
0e33b615-402c-5782-8802-c19d46b983b4 | note | Frequency - during construction and prior to seal
3859ae2d-6831-53c3-81b9-923b0403114e | note | Responsible Person - Sub Contractor
34762045-95d2-51df-8003-fe89a8b99928 | note | Verifying Document - String Sheet/Survey Asbuilts
f32d4b36-5101-5127-955c-2044610cf926 | note | Conduct - PE
265d3661-c56b-586a-92e2-41ca737f6501 | note | Produce Record - PE
24608447-868f-5186-ae7c-fc7043329995 | note | Approval - E
e19f8ca1-f3ca-5a6b-873a-4e449dea8da7 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Cross Fall
dd2e4923-8450-50bf-aaff-b070a32d6f78 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
6092006e-7873-59f8-b7d9-2a391f43a734 | note | Acceptance Criteria - 0.5% ≤ X ≤ ‐0.5%
827f883c-85c4-5dcd-8752-e8e210f5cb13 | note | Method - 3m straight edge or Survey Asbuilt
b2b8b3d1-5ac5-5080-9145-7f792e30a940 | note | Frequency - during construction and prior to seal
6ddf4ff2-de00-52df-b614-a35f8231b480 | note | Responsible Person - Sub Contractor
ece5e50a-54b7-5e8d-89fe-332380311b33 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
0b96d4af-e41e-56cf-9ef4-b3528a91cc62 | note | Conduct - PE
5dcefa11-6842-5cac-b105-3fa5822ca99e | note | Witness - C
9c50c46c-464c-582e-a9ae-6267b782b24b | note | Produce Record - PE
dfbc544b-08a7-5e2e-a113-33e956c859cc | note | Approval - E
bbf7922b-353b-5781-8525-2b800e4f7eb2 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Surface Finish
978dfb4c-2cad-5dd9-abe3-f62e7b3a53aa | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
8fb8ef54-4d3d-53f3-8164-4612a90d9379 | note | Acceptance Criteria - Tightly bound matrix post sweep
154a63a2-c0fd-58b5-b8ee-7441d780841d | note | Method - Visual inspection
c57b37e6-63e0-5f60-8cd7-5d0438862d6d | note | Frequency - prior to seal
f4affa67-24c0-5f0c-8c71-774f67948263 | note | Responsible Person - Sub Contractor
19bb312b-6485-5e1f-af11-4691f833130f | note | Verifying Document - Pre-seal inspection sheet
854333a0-2333-5546-b829-f3341c2ab947 | note | Conduct - C
8a11dcea-8f3a-5d08-a2c2-0824142606ab | note | Witness - C and E
33de88fe-96a1-5e98-974c-4f3c4214620f | note | Produce Record - C or PE
a589a1e1-cc1b-5e0e-8911-ecd7a6bca8e9 | note | Approval - E
8b4b049b-7ef5-5db4-861b-1d3d1a48dfd5 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Pre-sealing Requirements
37918730-473c-5903-82aa-68a0c56884f4 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
74b01fd8-73e1-5519-83f7-c8c9c93e24b0 | note | Acceptance Criteria - ≤80%, however 65% is ideal
c7d66e75-610b-5c0c-bc83-5aac8766ad91 | note | Method - Nuclear Densometer Testing
97c1a03b-487f-58d5-9c23-018aa9e30b65 | note | Frequency - if required, ≥5 tests per 1000m² lot
62be5d2a-7bc6-525e-b69a-026d9b097244 | note | Responsible Person - Sub Contractor
8e580e0d-6e77-511f-a6a9-ba063301211f | note | Verifying Document - NDM Record
c4db129e-5dc1-5fe5-ad1c-a73ed5505abf | note | Conduct - C
72b118e0-ecf9-5fcc-8ae8-2fa82d48e280 | note | Witness - E
59860957-7f40-5a0a-8791-61b91d71a706 | note | Produce Record - PE
74792bbe-e584-5b3e-98fc-c949e54eacbd | note | Approval - E
c7ae8d03-7434-548b-b8fe-896835e3aa3e | note | Witness Point - Y
| signoff | HOLD POINT
| section | 5. Construction - Granular make up and In-situ Modification (GAP 65 5% cement - 250 mm depth for Sub Base @ Pavement Type 1,2 SB & 3 SB) and (TNZ M/4 AP 40 2 % Cement 200 mm depth for Base Couse throughout)
| checkpoint | Binder - Penetration Grade
fc580ddf-b5b8-54b6-a1a4-073a0cc6f637 | note | Controlling Documents - TNZ M/1
8169b5bf-e55c-5d0b-83b7-ba75fe0f315f | note | Acceptance Criteria - Table 1
517c3ac2-d3d6-516c-b40c-ffb4db997200 | note | Method - Property Test
65bc4b69-bdfd-5018-8c64-2de884f07003 | note | Frequency - Annual
ef85f9a5-5945-518f-8724-2b166e40a98b | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
7c43407d-850e-5d57-b031-9f91391e4992 | note | Verifying Document - IANZ Report's
a8199a77-437c-5402-8def-6c080ed94b52 | note | Conduct - C
6db8813b-172b-50e0-a0d5-9ae574b3290b | note | Produce Record - C
f854fe21-e7fe-5fc0-8f7c-402468bfbc62 | note | Approval - N
bb684113-6212-5193-82ff-c173786193bf | note | Witness Point - Y
| checkpoint | Binder - Polymer Modified Emulsion
441ffdf6-ee4b-5cde-8a0a-e53cb20acd9c | note | Controlling Documents - Higgins Internal Specification
4d000bb6-0e9c-5e57-b580-b1d12bc8e184 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
2642bf1f-8313-5c3c-92f2-c318209af30d | note | Method - Property Test
94a1929e-1f99-5c6a-9af1-c53c8e33e208 | note | Frequency - 1/100,000 litres supplied
c8895826-fdc6-57ec-9c83-2d19bcdfa89e | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
b69fcc42-4ba3-54d1-b923-1257cb45f5c0 | note | Verifying Document - IANZ Report's
f81b7cb5-43b0-5f84-8f4d-030b72e6426f | note | Conduct - C
977676a7-c02c-50ce-a623-26d0d443656c | note | Produce Record - C
722fc4e3-80ec-5799-8702-cb0fbc20494e | note | Approval - N
c961b72d-9f74-5314-bf0f-09948a8289a0 | note | Witness Point - Y
| checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
f5075590-e997-55e9-8d26-4a3432297880 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
eaaeaa7e-7519-5c50-adf9-aa38a1644501 | note | Acceptance Criteria - <10% fines under 230kN minimum
5a08da65-b107-5c11-be9e-0f315aa40fb0 | note | Method - Sample Test - Crushing Resistance
22c62f5e-0b83-5a7c-bc7c-7507289b3df8 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
358ec4e5-8853-5a9f-9145-821123338c6a | note | Responsible Person - Surfacing Project Manager
d06e0763-4320-5f3d-a31f-96ec9a578dee | note | Verifying Document - IANZ Report's
2e43def2-c3f1-538c-b6ba-bae73e334ecc | note | Conduct - C
0d32cd50-b1ac-520b-b25f-6624c7ecfdb9 | note | Produce Record - C
710d9a21-fc60-5dec-8596-a97009ef0c7b | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
028d9fc1-e83e-54ce-a5c4-34943f7e6b2b | note | Controlling Documents - TNZ M6, RNZ 9805:2009
76af8ded-9b45-5f73-8d6a-b770c994b776 | note | Acceptance Criteria - AA or BA
74b34597-a2af-501f-be31-4e660d3fcc01 | note | Method - Weathering Quality Index
38a53cbf-dd02-5a65-8816-e5df3b2cde7c | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
acaa7553-2710-50fd-a943-ff097bc9b465 | note | Responsible Person - Surfacing Project Manager
ebeecf04-7f5a-5cd7-b004-271ed6a0dba0 | note | Verifying Document - IANZ Report's
366bbf95-2619-5d0b-981d-241bdd909b9b | note | Conduct - C
45f3b12f-3730-5b79-b15c-846d7af752fe | note | Produce Record - C
255f9c5e-a8b0-5a19-836d-52093bd48c57 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Skid Resistance
6d6cb55d-6186-5c99-8ef6-a63b5d817c8c | note | Controlling Documents - NZTA T/10
f8108f3e-a78e-5197-ac20-1a4d3e054500 | note | Acceptance Criteria - Meet Skid performance Requirement
9c98a175-4396-5eb3-b529-a0805ff24d56 | note | Method - Aggregate Perfomance Method
9f424d60-1e8c-5ae1-89c9-b737a7529671 | note | Frequency - Each Site
b6e07ca6-a1fa-5b09-9ef7-7e130b674b24 | note | Responsible Person - Surfacing Project Manager
87ed868e-e6c6-57b3-9ca6-93301adeb725 | note | Verifying Document - IANZ Report's
f4c0b8b8-24fd-587e-ab2e-9bc6ed8209fc | note | Conduct - C
6758bca2-eaf5-5bdc-bda9-3fa80ad04d1c | note | Produce Record - C
36644526-1dfc-540f-a07b-300d0ac578cc | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
fcbc7878-a07a-5a7f-b8ab-e2397ecb9d03 | note | Controlling Documents - NZTA P/17, M/6
eacfa732-91dd-5116-bb05-0f4c0037ecae | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
590527eb-f335-5c00-b57c-b901f2cf8fe0 | note | Method - Sample Test - Cleaness Value
5d638269-fefb-52b6-bc6a-894e7b60352e | note | Frequency - Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 3 Samples
06f61f3c-5681-56aa-82d4-1e0a6d92a4bc | note | Responsible Person - Surfacing Project Manager
f16e71c0-7ff5-5a47-a407-77c6be92d1aa | note | Verifying Document - IANZ Report's
00af4bad-4bd7-5e54-bdc4-2a22f3e347cb | note | Conduct - C
34541851-56dc-5c94-9fe1-34c3b1df740b | note | Produce Record - C
44de6fd7-88fd-50b2-8df9-cb46e2e03cd0 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
d2c82d87-3809-5827-bc9e-61505d2bd9f7 | note | Controlling Documents - NZTA P/17, M/6
2792ec4e-8ae4-5dc9-954b-457c2c1f9b17 | note | Acceptance Criteria - As per Table 2 and 3 NZTA M/6
1c2ae3ed-4313-5c57-abb0-a9ee433de7b7 | note | Method - Sample Test - Particle Size/Shape
274acf88-4818-5dcb-891e-ca2528357d7e | note | Frequency - Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 3 Samples
c057ab18-f03d-553a-a110-fc1a7f031989 | note | Responsible Person - Surfacing Project Manager
2b332500-9f51-5bb3-b0dd-f557b056c1fa | note | Verifying Document - IANZ Report's
960d76d6-34f7-522d-8a2b-afbd9a781ad9 | note | Conduct - C
10eef7dd-5a99-58b7-805c-963c252aa757 | note | Produce Record - C
47afb49a-a163-5e4d-be3c-339e61c837c9 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
299c1825-4fa7-5da7-ae8e-f4a4af9ed0ba | note | Controlling Documents - NZTA P/17, M/6
0fe3ed51-2cde-5ea7-8cf5-6b3db60fbd85 | note | Acceptance Criteria - 98%
535301e1-cb69-5a6e-9977-6abe0f4c0c85 | note | Method - Sample Test - Broken Faces
529c7eaa-80d9-56a0-96c2-5db69e6c06a1 | note | Frequency - Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 3 Samples
f04c9f86-eb2c-5c93-9652-b2f63d7a16da | note | Responsible Person - Surfacing Project Manager
f40f613b-a587-551b-98bc-9c0dd85e2b56 | note | Verifying Document - IANZ Report's
64b70d29-52a1-5db7-b099-83de5639f5a4 | note | Conduct - C
27dce6c3-8274-52aa-91f6-1b8f8ab20e77 | note | Produce Record - C
cb10e3ef-077b-5e57-9ef7-e59e2640175a | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Chipseal Designs
30495540-743f-50aa-8b35-47a65561770c | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
f0d80120-b208-58d5-a22d-9441a0a3611a | note | Acceptance Criteria - Client Approval
c60822dd-7893-5d27-9c13-1cce323b159e | note | Method - Review
608cb25c-2e87-5585-b26e-4e500644b8a4 | note | Frequency - Annual
7830fd29-447d-5135-b6b4-dcbcbc94e1b5 | note | Responsible Person - Surfacing Project Manager
17ba89c3-c267-52f7-a435-08eb5406bbff | note | Verifying Document - EBOP NOC Design Report Acceptance
c8c2f6c5-ce1f-565f-a70d-261b8fa9eb7e | note | Conduct - C
516ad084-7e30-5edc-b9f3-f66954628938 | note | Produce Record - C
41f09276-762f-52ce-a8d3-89f8938d7f58 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Finalise Sprayrate
6b981f82-bdf9-5409-90f7-fc8b1892b8ef | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
9b8142d6-0a0a-58bf-8324-2e44f24ecdbe | note | Acceptance Criteria - N/A
6e72c650-ebd1-52a8-88db-1a0c4c1ba302 | note | Method - Review
e332b7a9-2773-5d4f-974f-1bda301d0f74 | note | Frequency - Each Site
e3322120-5fe7-5bd8-85af-3614861bf221 | note | Responsible Person - Surfacing Supervisor
d004ea0e-5724-5e80-8573-bb57b11b23d2 | note | Verifying Document - Site/Spray Instruction
9cea0206-33d3-5a99-875d-066551ea28db | note | Conduct - C
d17c5878-fcb0-59cb-9080-11ce60afe01b | note | Produce Record - C
beec2c4e-065d-5220-a372-129023c99e72 | note | Approval - N
13127987-03c0-5ea0-95ee-7e3437a54103 | note | Witness Point - Y
| checkpoint | Check weather
7b97e366-3937-533a-bdd1-c36cbcbafc0a | note | Controlling Documents - N/A
f7b482b7-a70d-52c9-af8b-d5eba525c87c | note | Acceptance Criteria - surface. Base Temp ≥ 10ºC and rising. No rain forecast
2a0cf3a6-8ac0-5a95-bf6b-015a02d4a511 | note | Method - Weather Forecast
807512ae-146a-5e15-b9a8-2f8e4a98b9bf | note | Frequency - Prior to establishment each day
43084c15-7fb6-5443-b40b-5d4453fbc6bb | note | Responsible Person - Surfacing Project Manager
66bc5421-9765-5ea0-9740-7d005cec6a41 | note | Verifying Document - Daily Report, Chip Sealing Quality and Site Record
faf28405-a2ac-58a1-8011-7617325e14cc | note | Conduct - PE
f155f579-9801-5d3b-8e60-2e1203c0ea3b | note | Produce Record - PE
fdd149e7-c77f-536c-b460-dee944fd52c1 | note | Approval - C
3cf96bf4-7e1e-5450-aebd-1b1e68b67ed6 | note | Witness Point - Y
| checkpoint | Ensure limits of site are marked
cc3a8003-ac9c-562a-b1d5-61dea258ce60 | note | Controlling Documents - EBOP NOC Design Report
932165d5-9164-5cd7-8b26-551f8126883c | note | Acceptance Criteria - Visual Inspection
083c209d-acf0-54f7-b867-e1670c6df749 | note | Method - Visual
d340dd7f-c2e3-5b36-b422-ec261db8af5e | note | Frequency - Prior to start sealing each site
26b572d0-0ba9-5ed9-898e-d030827bc157 | note | Responsible Person - Surfacing Supervisor
44bc5417-073c-5711-8b96-e06d0671dbf4 | note | Verifying Document - Chip Sealing Quality and Site Record
241eb93c-e8f9-58c8-98bc-01c0e6f19f6d | note | Conduct - C
b777bf93-4c6a-5859-bed1-4084f3723616 | note | Produce Record - C
e22a76a4-3a11-567e-b46f-b8a1272b2baf | note | Approval - C
54eaca36-db6e-5d02-9acf-1e4928ae184c | note | Witness Point - Y
| checkpoint | Establish TTM
02f197b0-756a-5bf3-8f74-29ddeb41a6d5 | note | Controlling Documents - TMP
f76618b0-cbb5-59b5-83cd-da278f04d6de | note | Acceptance Criteria - Comply with TMP
d57bb692-78ed-5356-b3a7-7005634de3b1 | note | Method - Visual
44b037d2-a160-50a4-9d53-bd2141724ef9 | note | Frequency - Each Site
1298c576-2049-5f30-9c5c-34eb870cf656 | note | Responsible Person - Surfacing Supervisor / STMS
f1696bbd-a27f-5a37-a097-456df1756570 | note | Verifying Document - Daily Diary / STMS Record
6a067512-cb28-5cea-b721-1d69c9fcb20e | note | Conduct - C
8e1df8db-feab-5e59-b34e-05e56c5e6e24 | note | Produce Record - C
70030fea-87f1-517b-97dd-defd4369742b | note | Approval - C
63f0d9c9-813f-5ba4-826b-1d14445a3d9b | note | Witness Point - Y
| checkpoint | Sweep surface clean of deleterious material
5244db2c-d3c5-58a6-b687-337a19815365 | note | Controlling Documents - P/17
c199dbfc-d78d-57c8-8fb8-6eeddd48e100 | note | Acceptance Criteria - Visual Inspection
9c4da598-1129-5c1f-97ac-7d5d7c0e70dd | note | Method - Visual
dd8fb2e2-fc6d-58c1-bad9-3f2992dd6202 | note | Frequency - Each site, prior to start of sealing
9e3a365e-fb05-5c75-8987-a24edb8fc34c | note | Responsible Person - Surfacing Supervisor
4ff1aa8c-afa8-5f6f-8dce-93e220feb9de | note | Verifying Document - Chip Sealing Quality and Site Record
7273c2f9-8c8c-50a0-b0d6-6d8a2d2b468d | note | Conduct - C
871772f3-c29c-5338-9619-40faa9bd4394 | note | Produce Record - C
cb86d890-4ba2-587c-a9ca-419962184492 | note | Approval - C
0ad0416f-87dd-5d7f-a340-ac7a68e40114 | note | Witness Point - Y
| checkpoint | Record ATP's on site
1e9b798a-51e6-507b-b833-1c7bd71ba238 | note | Controlling Documents - N/A
fb759672-0378-5fb6-b712-f2b32eefb28e | note | Acceptance Criteria - Visual Inspection
0cb00418-1515-5207-b843-eef12708ad76 | note | Method - Visual
96d4b861-db5f-579f-8ffb-1f2f2552eba3 | note | Frequency - Each site, prior to start of sealing
9449f572-dc9c-58e3-9b72-a0f1de71fb93 | note | Responsible Person - Surfacing Supervisor
defd7e1d-58f6-57f9-a79c-aadab435e919 | note | Verifying Document - Chip Sealing Quality and Site Record
28e63e53-8d18-5274-8172-5b9830dd23a6 | note | Conduct - C
2b469ff7-c29f-5ffa-b636-344ea57d80c6 | note | Produce Record - C
607df728-d408-5e6c-8a07-9dc4bee735e5 | note | Approval - C
fe35ea50-bb3c-5e9e-8c4d-94fbd321850b | note | Witness Point - Y
| checkpoint | Confirm correct treatment(s) and chip
f8995286-eed6-5f7a-a073-32d4f0d194be | note | Controlling Documents - EBOP NOC Design Report
faf6b1c5-700f-599b-bb8d-319115089cc9 | note | Acceptance Criteria - Details/chip correct
95901d23-b363-5346-b207-b9b64714a826 | note | Method - Visual
93901fdf-b0da-5394-88d9-ac980f9b7306 | note | Frequency - Each Site
9c8c8fb4-07f0-5714-aaef-416a1295e8ec | note | Responsible Person - Surfacing Supervisor
c204ad7e-010e-57e9-8f53-68f86a813355 | note | Verifying Document - Chip Sealing Quality and Site Record
719066e7-696f-5927-bcb1-0220a7118db0 | note | Conduct - C
cf0894f6-1b11-55c5-a7ab-5fc6f54d9e82 | note | Produce Record - C
047e2dbd-bfa6-56ce-8091-7c872e49a3c6 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Cutback Bitumen Blend
7413d956-7567-5ccb-b2c5-a044e5c13e59 | note | Controlling Documents - RNZ 9803_0513
e630c080-d03f-53fa-ba20-e0aa235f23a4 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
44f33218-9e80-52a9-8e3b-c0dc779f6f22 | note | Method - Sample and test
a374ac1d-c5b5-5acd-9267-affeaa146914 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
b5894854-3f2a-503c-afc3-dcc9caa29c7a | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
9e98e65d-a78d-5ec3-84c9-e11587c6c86c | note | Verifying Document - IANZ Report's
68e1e3f3-11af-53ed-a497-a4d95bf6ccee | note | Conduct - C
61b1de34-6aaf-57d9-b7dc-5a0461840d67 | note | Produce Record - C
04eb7463-1459-5c32-b5bf-d6248e86efd5 | note | Approval - C
79a749f7-6a13-5ebc-95bc-14dd87e132fd | note | Witness Point - Y
| checkpoint | Bitumen Application Rate
aa9ca048-88a2-5b96-8a16-7a2eef20f05a | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
e8f59421-cc86-5cba-8d7c-260e34dd732d | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
5a645df4-a51a-51bf-bd58-36c1044a425b | note | Method - Test, Review
8f43d859-e9c4-5db5-aadc-9e7afbe4e244 | note | Frequency - Per Sprayer, Per Site
362922c1-9e5d-55f5-a43b-b0507db2502c | note | Responsible Person - Surfacing Supervisor/ Supervisor
c706b4b2-5045-54ca-bedd-601493b73f4a | note | Verifying Document - E/2 Certificate. Spray Sheets
5e3987b8-74b5-5ebd-9a88-f48ff5d9a1b2 | note | Conduct - C
69b1a6b0-33de-5c09-aa4b-6717e2fd0972 | note | Produce Record - C
a9bc87a2-53b6-552b-812f-e8a2a105e41b | note | Approval - C
de71487d-a4b0-5258-b91b-04c3ce8b7e77 | note | Witness Point - Y
| checkpoint | Chip Application Rates
8641b2ad-e2f8-53b9-94a3-a506ace23b1c | note | Controlling Documents - Chipsealing in NewZealand
2ec925b5-ae75-5af2-9862-c4b3d4222d8f | note | Acceptance Criteria - As per Chipping Guide
7f3a0211-c293-58d7-ae4e-eb0e580be01b | note | Method - Visual
ce0d0fe9-adb9-5a20-9b0a-202408560d91 | note | Frequency - Each Site
ec02f709-69f3-5785-9600-0b92fa9f71bf | note | Responsible Person - Surfacing Supervisor/ Supervisor
78cd1c1a-ac3f-523c-9a55-20da7f1324d2 | note | Verifying Document - check sheet. Chip Sealing Quality and
be8e3cfe-4a28-52d6-afda-54a595945e02 | note | Conduct - C
93c66ae5-d434-58ed-8937-8db41482cdb2 | note | Produce Record - C
286a884c-d013-5700-b2fd-9d7a493e62d8 | note | Approval - C
da82bb94-5488-5d46-8eed-233900cf6478 | note | Witness Point - Y
| checkpoint | Rolling
eeeec7ef-b32c-5c54-a50a-5c111064a535 | note | Controlling Documents - Chipsealing in NewZealand
fe0eeba7-cdbe-55fa-9bb0-82917eeeef42 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
57ddea62-6aab-5639-814a-a55274a481fc | note | Method - Visual
947cf51f-aca3-53f4-88a3-520e4f63247f | note | Frequency - Each Site
524421c1-6f95-5cf3-83ac-14924d572c2e | note | Responsible Person - Surfacing Supervisor/ Supervisor
93c40b03-8989-51b4-9d7e-0e2be52cd4a2 | note | Verifying Document - Chip Sealing Quality and Site Record
5324f01a-08c8-5e80-89e7-ff6500c0c630 | note | Conduct - C
32595d50-a3b1-5ad4-b866-2702143db73e | note | Produce Record - C
30c2a3db-e8d1-5fb3-9392-ef0dfacd1b31 | note | Approval - C
23610912-7a03-5ddc-8a41-52555c68123d | note | Witness Point - Y
| checkpoint | Cleanup
24774ae3-b5e2-5824-b2c8-4ec342a7f1c1 | note | Controlling Documents - Chipsealing in NewZealand
7f77cc3f-0d57-58e9-9184-dfac120c3bd8 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
ee5f0a2c-3733-5c0a-98ab-d5e7e2728583 | note | Method - Visual
b15d3bd6-3a53-589e-9aa9-1cd98fc105a6 | note | Frequency - Each Site
43844ad5-9d92-5037-9268-26afe2fae5bf | note | Responsible Person - Surfacing Supervisor/ Supervisor
a477e05c-1c5e-567f-b37a-6ebd31daf1da | note | Verifying Document - Chip Sealing Quality and Site Record
04e37441-3665-5490-a1a0-70213a8b6534 | note | Conduct - C
933104d5-b108-5c8d-9197-cad9dab9557b | note | Produce Record - C
f73bccc0-87c9-51e1-b538-7797637403b7 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Post Sweeping
64346def-8b7c-5c61-8c66-c5ddde88ce3b | note | Controlling Documents - Chipsealing in NewZealand
8c47fb8b-c6b2-5a3b-b46b-e7886d08a85f | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
bcc82bb6-4fc9-5d9b-9029-7735324a0536 | note | Method - Visual
319b1de4-3b0b-5e60-aeda-7534935dd2d8 | note | Frequency - Each Site
6bdf9709-3c97-5621-855d-493b53c492b8 | note | Responsible Person - Surfacing Supervisor/ Supervisor
b835cf97-45c5-51e9-8f04-5a5a8125b3ca | note | Verifying Document - Site Record
ad76f6a5-e05d-5ed8-bb27-83de0f2b89a8 | note | Conduct - C
05a971a4-0974-5e38-8ac9-36f68b53f7ca | note | Produce Record - C
8eb55bfb-96f4-5b41-bd0f-be6cf0064122 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Linemarking and RRPM Reinstated
43081c15-968c-5f06-9b44-a47d201ebf3e | note | Controlling Documents - MOTSAM
2cd5fead-0f81-534d-b0a4-1c0f848ddfde | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
4f0100e1-be01-5761-a0cf-1bec65af6686 | note | Method - Visual
8db40386-0c1a-518e-ac17-48c35aa62c54 | note | Frequency - Each Site
ee2e1c31-c657-51b2-96aa-0e9b878ab025 | note | Responsible Person - Surfacing Supervisor/ Supervisor
5995f5aa-3c6f-5cc9-b10e-637f66e4eede | note | Verifying Document - Site Record
82fe5970-8215-513b-a17c-f8e47b3e7670 | note | Conduct - C
ab8d1f3a-7934-59d3-b3c0-a9ac24c97a2b | note | Produce Record - C
2e8b6d7f-ede5-51c3-9ec4-e1cd2530cd69 | note | Approval - C
effcf118-b291-5b25-a565-988028031f85 | note | Witness Point - Y
| checkpoint | Removal of TTM
953b979d-aac4-5a1e-b012-23f723b11a42 | note | Controlling Documents - TMP
43250a03-be6e-514b-a930-3f6f2ae80ea4 | note | Acceptance Criteria - Comply with TMP
dc79f748-34c3-5e5b-bcce-b1f5f66ac594 | note | Method - Record
58acf35c-acf5-586f-a854-58e8cac4cdaf | note | Frequency - Each Site
32cf5176-687a-550b-a9f3-68e46e08a96a | note | Responsible Person - STMS/ Supervisor
b8f177dc-08b1-5b4f-8426-2d154d114ff4 | note | Verifying Document - STMS Record / Daily Report
5e6ad3a2-cbde-50b1-9c7a-ecab4bdac335 | note | Conduct - C
13a287ad-e832-5406-ba5a-1665baa85f8e | note | Produce Record - C
f17c383d-8f7b-5e4b-af09-b64d3e004329 | note | Approval - C
2967c25c-6a0c-5d97-8805-b20c6bc726af | note | Witness Point - Y
| checkpoint | Resurfacing Construction Completion report
1808cc91-6987-536b-9be1-a891abd2674a | note | Controlling Documents - NOC; MS 6.1.3
270165cd-5e76-577f-a584-83d123ae2e0a | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
29479111-9fab-50d2-bb3d-4c928e61c588 | note | Method - Record
716ed7ee-4d11-5ce2-aa76-1eb8930d7044 | note | Frequency - Each Site
566f511e-aa55-5264-a325-b0aea4899150 | note | Responsible Person - Resurfacing Construction Completion report
e0ba5188-934b-58dd-a378-c6fd24a8876e | note | Verifying Document - Daily Report / STMS Record
d29dcd59-6d2b-510f-84c8-98966ebcf103 | note | Conduct - C
cca30f42-a180-5527-9a36-453cddb1279b | note | Produce Record - C
e7796f3a-883f-53c4-9d03-8eebe2d96110 | note | Approval - C
7aff37b0-c7b4-517e-bf35-310c9fcbf5b3 | note | Witness Point - Y
| checkpoint | Chipseal Post-Verification Testing and Report
503eaa16-c190-5aa0-8227-10e15bfb7244 | note | Controlling Documents - NOC; MS 6.1.3
e5dbfdaf-689c-5fd5-b309-efdf534ab873 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
96edaf00-6f16-5954-9423-d649b31e9b35 | note | Method - Record
54ac5a23-8a1f-59bc-a140-5f495f862563 | note | Frequency - Each Site
3cb26fa2-b353-530f-a854-06a0b9f1e054 | note | Responsible Person - Surfacing Manager
1e2c286b-ac4f-5357-9285-0540f6b83656 | note | Verifying Document - Chipseal Post- Verification Testing and Report
ea87d7a8-b282-5f3c-a1bb-7e12663fd935 | note | Conduct - C
457f07e6-eece-5756-ad07-7af2ef027ec3 | note | Produce Record - C
fe110b64-3f63-587f-a32f-7fab2ca070b0 | note | Approval - C
| signoff | HOLD POINT
| section | 7. Close Out
| checkpoint | Post Construction Walkover
b01d7d18-4f73-5b6f-8eb1-ac587c494dd4 | note | Acceptance Criteria - Formal Agreement
cfb71279-35f3-5b16-bc6d-64394e6dedc5 | note | Method - Visual Inspection
943c12f7-2770-54cf-8dad-4035224b3a5a | note | Frequency - Post seal sweep
076e7810-6d04-5cf2-902f-180ddee0a544 | note | Responsible Person - Quality Controller, Supervisor and Engineer
ca9c5d44-1470-5259-a2b2-a260e2b5e585 | note | Verifying Document - Meeting Minutes
f3dedd7f-6610-591d-b4dd-fb744d419741 | note | Conduct - C
d5d78733-4cb5-5249-ae75-64b2629cc586 | note | Produce Record - C, PE and E
27a8e6e6-0fa6-536a-90ca-da0e26407fcb | note | Witness - C
d847173a-7102-5d4f-9ae0-265fcdac8ee3 | note | Approval - E
ec6bd07a-8279-5f46-a7f3-20e62023402e | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Pavement Rehabilitation Construction Completion Report
9f6260b7-0321-5002-aa7e-4c55814bc085 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
380b925c-60ea-5f66-919a-7fc9c96a8604 | note | Acceptance Criteria - Engineer Approval
15de9c71-563d-51de-8efd-199e585ea71a | note | Method - Visual Inspection
4f0ea467-54c7-55c2-a069-1cda14478a27 | note | Frequency - ≤2 months of 1st Coat Seal
b429f7c5-982b-54da-9db4-32494bdbf67e | note | Responsible Person - Contract Manager/ Quality Control
679b2b2a-d498-58ba-8ec5-e302b9b57f20 | note | Verifying Document - Signed Report
71dc7aec-d0f0-5c8f-95eb-b2e1a528764c | note | Conduct - C
836be43e-045f-5b5c-bfa4-aa618cf20340 | note | Produce Record - C, PE and E
ce71a803-de49-5580-89eb-f3fe1c5f64f1 | note | Witness - C
bb89b2ac-5c42-5d60-915f-70c8cceb88c3 | note | Approval - E
90ec7ac1-c635-5198-9670-c51a902aa325 | note | Witness Point - Y
| signoff | HOLD POINT
| checklist | ITP - Pavement Rehab - Ruato Bluff | itp | ITP - Pavement Rehab - Ruato Bluff | 38e27d50-d8b0-4205-9a1c-7ac0537690f1
| section | 1. Procurement
| checkpoint | Geometric Design
5931c8d8-39ad-5321-8470-b9abd1fcc4b2 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
1d369f5d-5497-5aa8-bef5-a8768cb47c59 | note | Acceptance Criteria - Principal Approval
502652a9-a209-51a5-8720-ea4a5f79f5ca | note | Method - Contractor and Principal peer review
211bf0d8-b4bb-55c9-8a2f-d150b4d8a294 | note | Frequency - per design revision
be6cc71a-bf5e-50a4-bf14-2b9adf97f020 | note | Responsible Person - Contract / Rehab Manager
51182a48-ec22-5e45-af98-72df06ada793 | note | Conduct - C or S
7abc69b4-53f1-577d-9fd1-baf37fbd1b7d | note | Produce Record - C
cf8cb95c-41a5-59c0-987e-14a1ae7efa85 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Pavement Treatment Design
060344e9-3b80-5545-b097-e451bc6c9a0b | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
d7854f16-099b-5fd7-9d12-7b6f008f2931 | note | Acceptance Criteria - Principal Approval
6f863b86-21cf-595f-abd6-52ced08e84e8 | note | Method - Contractor and Principal peer review
f436fd96-5e21-50e5-ac4a-adcafe4ef6fe | note | Frequency - per design
cc135d18-ab23-53d3-b2bb-f4139cc3c049 | note | Responsible Person - Contract / Rehab Manager
5253ed33-cace-5268-8dfc-fe84a55855ac | note | Verifying Document - Approvals Register - Pavement Rehabilitation Design Report
d799399a-1e80-5599-981b-26f33a402854 | note | Conduct - C or S
1f5b8a4b-fe53-5f32-9b3f-2ba365876434 | note | Produce Record - C
6f474105-2d79-5529-ae7f-af031566f410 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre‐treatment Material - Aggregate Sampling
5c003654-f050-5c1c-8855-9888b9236bdb | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
b37943c1-dd41-5f7c-a9c6-a4195a509744 | note | Verifying Document - Sampling Worksheet
950ac6f1-c2d8-5c92-9281-c2420dc2c8c6 | note | Conduct - C or S
d1ab30c4-e086-56e2-98bf-1636f9926909 | note | Approval - S
| checkpoint | Materials: GAP 65 Pre‐treatment Material - Source Property Test
ac19775b-b15e-5f7a-8cee-6c4913f939f3 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
b830c79a-3b13-55dd-8901-a1c32ff7b2ff | note | Acceptance Criteria - Soaked CBR ≥ 40
997ed26c-1334-509f-b069-ff0797b9def8 | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
6ecd5b8c-1861-59d7-b5cd-aa81ed504dcd | note | Responsible Person - Supervisor
6dafc18b-3ca8-539a-a99e-3218d970525a | note | Verifying Document - Test Report
a40681f1-5464-5d82-9c54-e121f4a6320d | note | Conduct - Sp or C or S
7670102a-bd7e-50db-84d0-d5ba1d8d7ad8 | note | Produce Record - Sp or S
435d3996-e167-58f5-8998-5b4476e7c0f6 | note | Approval - E
14e53181-da1a-5722-87a6-9bd4fb2759fa | note | Witness Point - Y
| checkpoint | Materials: GAP 65 Pre‐treatment Material - Production Property Test
e9a29740-9b8e-53d4-a847-15b8f273c80f | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
28993a25-47e9-599b-903f-0328d84f1200 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
1f55a7a3-06a8-53fd-a71b-6ca54bd9e2d9 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
a988e7c1-a165-5884-98dc-e7525abec1ce | note | Responsible Person - Supervisor
7ec5f0e6-6d24-5a04-8af8-af7e65518e8c | note | Verifying Document - Test Report
8e169746-41f8-5c28-96e1-3c38b15c8489 | note | Conduct - Sp or C or S
949010ed-5bfe-5094-9d58-64a757078ec7 | note | Produce Record - Sp or S
2b6cfdab-ab6f-51d7-838b-7dd5e66b4008 | note | Approval - E
f8b8e6a7-554c-5a57-a746-d5c3e872b369 | note | Witness Point - Y
| checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
3c3ded8b-0db7-5ac1-8ddb-fc8ca42e09eb | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
80edf9f1-8569-54ba-bd1b-c8cd0d68b907 | note | Verifying Document - Sampling Worksheet
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
af0705cf-3ae2-5ac8-9997-8351d10f29fc | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
c0768c87-f76a-54bc-9f99-b44ef5939898 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
2ea91f16-e43b-5e7a-8252-1b45731abfe1 | note | Method - Crushing Resistance Test (NZS 4407:1991, Test 3.10)
e80a0d19-a2d9-5e7b-a5f6-de92f7d74131 | note | Frequency - One test for every 10,000m³ of source material
819e0a2f-fe1b-56d2-b06c-fde709c02567 | note | Responsible Person - Quality Controller/Supervisor
c9485558-2b39-533f-b8a1-56ca5f57f0de | note | Verifying Document - Test Report
5e77b99d-693d-556d-8b99-db5ef17f762c | note | Conduct - Sp or C or S
0854bbd3-90fc-58b8-a922-d7e4c3826b7a | note | Produce Record - Sp or S
d582dbeb-2aa5-5bf4-a232-cf9a2c718df8 | note | Approval - E
1ffd37fa-9bbc-5f0b-8f96-0913d8aaeedc | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
48a65004-385a-53db-8bdd-cac64e9e61f6 | note | Controlling Documents - Weathering Quality Index (3.3.2) ‐ TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
14a14a9d-d857-5b59-a001-014aefc5a516 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
bd52226f-d6b7-5497-805e-af21ed4055f6 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
7862611e-b20b-5468-a357-34afdee2d5bd | note | Frequency - One test for every 10,000m³ of source material
6e33952a-74f9-590d-951c-b77ae4a08f22 | note | Responsible Person - Quality Controller/ Supervisor
23fb5924-7007-5b93-9cd4-8864f3ffccf0 | note | Verifying Document - Test Report
8b18d143-c6d3-566d-b35d-96e9fac1b27f | note | Conduct - Sp or C or S
c9e1fc35-8a31-5578-9481-ae879bc3a29a | note | Produce Record - Sp or S
6249c4d3-03db-5295-980a-9d631e55a217 | note | Approval - E
b8f74d96-d107-584a-9929-641ea55825e5 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
c03f7e67-5b8f-56fd-957e-70582773f219 | note | Controlling Documents - California Bearing Ratio (3.3.3) ‐ TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
99390c0f-f5cd-5054-87b1-12e7112f92e4 | note | Acceptance Criteria - Soaked CBR ≥ 80%
05a41e04-2920-54b4-b0c5-d399c0fd6f67 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
efb9c593-bcaf-5274-9ca0-e15849253386 | note | Frequency - One test for every 10,000m³ of source material
e7f55147-5a49-500c-a095-821d25cbfde8 | note | Responsible Person - Quality Controller/ Supervisor
4230ac9f-ea59-5158-96a1-d34eeb9a8e4b | note | Verifying Document - Test Report
7bb33d4d-c4f8-5c11-9273-086d91036183 | note | Conduct - Sp or C or S
53a91643-c440-532a-ba94-cfbeb6e68f5b | note | Produce Record - Sp or S
5bd9dfd6-8ba9-539a-9f9f-732a71833b07 | note | Approval - E
eb8ae1d6-3b34-5ffa-800f-806d756ddce4 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
c5eec582-84d4-599f-94fc-d1c463652ad4 | note | Controlling Documents - Sand Equivalent (4.2.1.1) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) ‐ TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
5a287c75-cdb0-5e0a-8c3e-8f9b8ece3661 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
65b320b5-b2bf-536e-93ce-33a04f4e9f0e | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
8272bc3e-08c9-57f9-beba-329b6364006c | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
261489b2-5ede-51e7-9524-735cb3a8d7d2 | note | Responsible Person - Quality Controller/ Supervisor
7062c2e7-7b2b-5309-bd33-e41d6e575470 | note | Verifying Document - Test Report
9a5f8387-0eee-51c7-aa20-9e8650b48fef | note | Conduct - Sp or C or S
2d39d0f3-a678-5135-a58b-ade12cced0b7 | note | Produce Record - Sp or S
b27532c4-d9b5-578c-b6fe-b4ee44a59882 | note | Approval - E
1e718ab6-0683-5acd-9019-2cb991963856 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
6c40e5fc-c3b1-5bb5-bf91-280fafb4fa09 | note | Controlling Documents - Broken Face Content (4.2.2) ‐ TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
d4010d69-ff1e-5cb1-9503-99f10462877f | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
ab3dbf64-82dc-5550-9fca-3b87b0e7e840 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
014019e4-514b-57f8-8401-f88d81b1eb0f | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
01870b55-5655-5d9c-9bec-11d2ea1bd7db | note | Responsible Person - Quality Controller/ Supervisor
013c86da-44a7-587e-88f9-5c65e7e0559e | note | Verifying Document - Test Report
05f110e9-52c8-5a98-95b0-83aca8186930 | note | Conduct - Sp or C or SSp or C or S
5f317b08-e06a-5a89-b2a1-ba68997c5ae9 | note | Produce Record - Sp or S
06818f99-f4b2-5d95-8f56-d512ef256deb | note | Approval - E
3d6c7ec2-46dd-59d6-bc3e-536086448ddc | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
db0a68f1-9c9d-5334-a5d8-dc3e5734475d | note | Controlling Documents - Particle Size Distribution (4.2.3) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
0bcdc681-286b-5aa4-9078-8070def19314 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
26d19dec-955b-5dcb-bb24-abdd5c51642c | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
a1f2424a-8dc8-546f-87ca-32813a3f69a7 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
16f76314-9cda-502a-883e-a53ed3c79e25 | note | Responsible Person - Quality Controller/ Supervisor
64310eff-7068-58fd-9170-bee65e0ed54d | note | Verifying Document - Test Report
50b5391f-6b08-52bb-8f9c-d8ef3b0497c4 | note | Conduct - Sp or C or S
07ea1367-f20a-57ac-aedc-3fc0f36befca | note | Produce Record - Sp or S
94581f16-352d-53a9-930c-3245b1c37004 | note | Approval - E
17dd1d9d-7798-551c-bf51-cab2babbfec5 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: Cement - Stabilising Agent Selection
17466144-908c-569f-b9a9-77e08aeebec6 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
9c8d1ea1-b025-5333-9acb-60c00a341993 | note | Acceptance Criteria - GP
caccdc45-e11e-5752-9932-692fb8a0ba09 | note | Method - Visual inspection of supplier docket
71561d1b-50bb-58de-b5e2-03b16cbaccb9 | note | Frequency - per truck load
d0761cee-903f-578b-911e-8383e37bbe8f | note | Responsible Person - Quality Controller/ Supervisor
710db147-1aa7-5a61-8f7f-0398b7ff3434 | note | Verifying Document - Supplier Docket Supplier Cert
5d78b737-38b9-563b-ac6e-3847bb848dd5 | note | Conduct - Sp or S
f80a25fd-d9b8-5c9a-b16c-2c5990974dbd | note | Produce Record - Sp or S
b5328563-da18-5c10-93cc-d51793a3f58f | note | Approval - C
214cac16-5082-5378-8844-6d07d0a272dd | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: Water - Water draw for stabilising
8a929071-da8c-53cc-ac49-61a807ee6b0a | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
54b0b9f0-29ef-5036-9116-dd89b4455b94 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
d5f512cb-1503-55cb-aa70-7a8ce2abd15b | note | Method - Visual inspection of hydrant use form
5de3d105-0df8-501d-9316-216cfd5814b1 | note | Frequency - per truck load
57b9b276-4158-5893-9804-3855d6d2c15a | note | Responsible Person - Quality Controller/ Supervisor
57a6fe29-2826-51be-972b-d368d208ab09 | note | Verifying Document - Hydrant use form
ad792e52-4d81-5c45-8aa2-c1cb89593d70 | note | Conduct - Sp or S
bf483d12-96d1-5436-88bf-a858c17db716 | note | Produce Record - Sp or S
936b911c-65fa-5179-89fb-43820c2a4385 | note | Approval - C
c6c87792-f891-564d-9122-74bcf786f57a | note | Witness Point - Y
| signoff | HOLD POINT
| section | 2. Pre-Implementation
| checkpoint | Work Pack complete and held on site
433ef703-a88a-5ee1-a434-655cd20cf811 | note | Controlling Documents - ..\Work Pack
d2d10130-6ad2-59d6-8c92-6badf89001ad | note | Conduct - C
54fd123b-c286-5387-9e2d-061932d3fb8d | note | Produce Record - C
a50709e7-85b0-50e9-bd03-59697aa97d72 | note | Approval - C
e61dd719-9320-5e3b-b9bb-61341ba7e080 | note | Witness Point - Y
| checkpoint | Communication Plan implemented
3ee150c8-dced-5ecb-b243-b118a093be96 | note | Controlling Documents - ..\4.5 CSCMP
59ecfcd3-77bf-5c38-b4ee-f4089db6a0a8 | note | Conduct - C
084cae29-1324-5094-a554-e1ef42339771 | note | Produce Record - C
0e7bb2aa-b9ec-5cee-98db-a49854f8fa6b | note | Approval - C
26f11b51-99c2-5479-83d9-2656d22dec4c | note | Witness Point - Y
| checkpoint | Are any consents /approvals required, including for taking water.
57af684b-deb1-53a7-a448-cd9b8168f184 | note | Controlling Documents - Hydrant Use form
5014cb52-af61-574d-a886-c0914361efa2 | note | Acceptance Criteria - Forms available for applicable days
d3588bdd-78d1-50ce-84fe-a703ec7dc72a | note | Method - Visual inspection and recording
601f5c02-2424-56e5-8835-b4e317c3e2e0 | note | Frequency - Daily as required
f50c7536-23eb-5706-9570-51f92661d6f6 | note | Responsible Person - Supervisor
8bcabbf0-34a3-5d66-8bbc-625d2b8506a2 | note | Verifying Document - Hydrant Use Form
1398c1ba-c712-5eb6-b616-4afb5076f8d0 | note | Conduct - S
a6dd163c-19d7-5f41-ba4f-77eb0c0d7fbb | note | Produce Record - S
890a9ec5-0ce3-5bb8-acd3-04343ff026ff | note | Witness Point - Y
| checkpoint | Quality Control forms on site
4f2079c8-8776-5723-aafb-1c8fa573645a | note | Controlling Documents - RQP, ITP, Scala Penetrometer Test Records, Material test sheets etc.
ebb71c64-cb53-5ef3-9ad1-febde074f243 | note | Acceptance Criteria - Visual Confirmation
088f4389-c660-5402-a857-2a0921973863 | note | Frequency - Daily as required
9a10261c-0f34-5a4c-85c9-fae9d076e402 | note | Responsible Person - Supervisor
b54a2cc4-5188-5239-8a99-101a826a90c8 | note | Witness - C
| checkpoint | Person(s) on site with authority to stop work if quality of final outcome is compromised for any reason
d886b158-c8d5-5492-9745-1d74dea26ff2 | note | Controlling Documents - QMP
de6105dc-2954-5506-a96b-d7661bf3c9e1 | note | Acceptance Criteria - At least one nominated staff member on site at all times
ade42503-e1cc-58b7-a4d7-4d786a72e702 | note | Responsible Person - Site Supervisor, Quality Controller, Engineer
63e4e125-d5e4-574d-a7b7-9667957fcdaf | note | Verifying Document - Pre-start sheets, timesheets
8875f70f-91bb-51e2-beeb-6b5df83fb063 | note | Conduct - C or S
c40744a6-cf1a-5e53-a2fc-cc0d18fe6170 | note | Produce Record - S
| checkpoint | On site Prestart Meeting
d0705246-be35-54b3-9f8b-6e93ac45cd5f | note | Controlling Documents - Site design information - Earthworks plan - design drawings.
7f20b6af-d16a-5edb-b4d5-9b381a6b9c0d | note | Acceptance Criteria - Visual confirmation and walk over - confirm associated works -verify extent of works - verify digouts or additonal items
5c1e4e39-4f9a-5e93-b062-d97ece1a36d1 | note | Method - Visual inspection and recording- variation approval process
73c125e5-0bac-5e1b-a4e0-2db8fbe215a5 | note | Frequency - Prior to any phyusical work engagement
2b6cea83-6cf9-5b8b-ab95-2bb2b4fb607f | note | Responsible Person - Supervisor
595e6a46-eeb4-5302-8c7b-8e30effcd0d9 | note | Verifying Document - Design alteration variation ACCEPTANCE
fc0276f4-8e30-586a-bf3a-6937d55f8214 | note | Conduct - S
8b4533af-9503-517d-a915-c3a7a50d9da2 | note | Produce Record - S
46adfe64-7a09-5a95-9b02-43052b1b8f0c | note | Approval - E
ddc3c5bc-cd53-5ce8-a2ad-7fad79a8de2a | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Records Management (i.e. it is known what documented records are to be kept)
e91920eb-711e-5dd2-b3d7-a5598d4d31db | note | Controlling Documents - ITP and QMP state what quality documentation is required
083fe4f4-3014-5b55-bed1-d368d139f023 | note | Acceptance Criteria - Filled in and Signed ITP
448637d7-11a2-58a5-bddf-f5a967eec792 | note | Method - Visual inspection, recording and approval
b9a588d9-d75f-5b8a-af4d-42b1dcdf4f31 | note | Frequency - As per hold points in collaboration with the programme
c4ba2351-de40-5a70-9a1f-ddbf2616aa0c | note | Responsible Person - Quality Controller
3faebb75-3872-547c-9e75-5277cd1bd29a | note | Verifying Document - ITP
c5c20425-5b32-5c01-9203-42ebee32ba2d | note | Conduct - C
bb55806e-5e44-528c-b8a3-d3e0a11c70e1 | note | Produce Record - C
49300072-d802-51f7-99c8-0b5e7c8b3cfb | note | Approval - E
56916333-57f5-54fc-b8a8-e547201c59f5 | note | Witness Point - Y
| signoff | HOLD POINT
| section | 2. Temporary Works (including Traffic Management, Environmental and Health and Safety Controls)
| checkpoint | Traffic Management Approved / Implemented (copy in Job Pack on-site)
eb35e671-8b11-5e9d-8dfd-4d486af457c1 | note | Controlling Documents - Site Specific TMP, COPTTM, Higgins TTM SOP, SCR Form
56f75984-880a-5b55-a119-7596ad4d844e | note | Acceptance Criteria - Passing SCR audits
4cc007a6-e9d8-5131-b634-e23cb032dbf7 | note | Method - Visual inpsection and recording
0f788581-7d2c-50d6-a454-8c5b57d783b7 | note | Responsible Person - STMS
be0089e2-948c-5fce-a13f-43a54db6f078 | note | Verifying Document - Site Specific TMP, SCR
a0e8a4c1-07d3-5e63-ad45-523bc47b4fb1 | note | Conduct - C
440e8248-6ebf-5962-b6a7-42b04e76b6de | note | Witness - C
3d42934f-65c6-5bbc-9e97-5e15c41bcdde | note | Produce Record - C
40839fde-fc2f-5848-aea1-ccdfca57a472 | note | Approval - C
f2cdda9a-d1e9-559a-aede-59a94383bee1 | note | Witness Point - Y
| checkpoint | Environmental controls in place (Seal of Existing Catchpits or storm water line)
470f9ab0-46e1-58a1-9645-2a58900241d1 | note | Controlling Documents - HSE Audit, JSEA
4ed0da58-f87d-5bf4-a0ed-d1a5bbc4183c | note | Responsible Person - Site Supervisor
75c8a222-b03c-511d-bbb9-2640669633f7 | note | Verifying Document - HSE Audit, JSEA
785af8c0-b86c-534d-8da9-3863cb369c97 | note | Conduct - C
3c6acc55-c286-54fb-bc16-f798fc485be8 | note | Witness - C
ab52adc2-5569-5be6-af00-92182900044a | note | Produce Record - C
10b3496a-c2f8-5ca4-9aa0-d3d4d832f27d | note | Approval - C
a7ac2b47-9646-56a1-aeaf-477dfaf566a6 | note | Witness Point - Y
| checkpoint | Health and Safety controls in place (e.g. Isolate work area)
1c069cea-99e0-52c5-90bc-f36b84aac12b | note | Controlling Documents - HSE Audit, JSEA
f8fed9d7-239d-5310-8b45-2045af2fe9ee | note | Responsible Person - Site Supervisor
868b88f3-0de0-54ee-83a9-bae349547b5a | note | Verifying Document - HSE Audit, JSEA
94e7ad1d-d189-565b-b3e5-181bdf6f7de4 | note | Conduct - C
eaf57735-06f5-5f1e-9e60-3d55fcad29e8 | note | Witness - C
d86ddfa1-f595-58a1-b116-cb42d839fad6 | note | Produce Record - C
4d6ed3e9-247e-55e8-bbcf-8cb703bb1073 | note | Approval - C
e4736441-ecf9-56a0-a756-c52251e4404e | note | Witness Point - Y
| checkpoint | Standard Operating Procedures / JSEAs available on site
28475ca3-9f24-5dd3-acb5-1f460c3c1bdb | note | Controlling Documents - HSE Audit
8123d24a-3bb1-56eb-aa9c-d317fa35cd0b | note | Responsible Person - Site Supervisor
a6cddcf9-db27-5289-ad40-9944e6e6f54b | note | Verifying Document - HSE Audit
295154a2-353d-5784-9ebc-80a60c1e7d09 | note | Conduct - C
f3b91831-9788-5922-8eb2-4d7365794990 | note | Witness - C
8bf2d092-b038-58c8-9f12-fb348464e60e | note | Produce Record - C
b39c5c60-c1d8-5452-a4c9-d64370597dcc | note | Approval - C
3040f65d-b0d3-5c2c-814c-941dfc2e84b5 | note | Witness Point - Y
| checkpoint | Any service covers or utilities identified and protected to Service Authorities expectations
659da524-e535-5806-95c8-7321e21a51a4 | note | Controlling Documents - PTW Process, B4UDIG
4ae5072f-0a9f-5171-a765-f2cda7de344e | note | Acceptance Criteria - Work always undertaken under live PTW
cd42de66-1844-5a03-9d1b-0b79551d7e66 | note | Method - Visual inpsection and recording
441dae83-4eb8-5b0c-aafb-684e77629814 | note | Frequency - Weekly
5c90a894-d42e-5f5d-bf5c-ed5541a06075 | note | Responsible Person - Permit Issuer
94b35b72-7dcb-50ff-88b0-3760c99d9376 | note | Verifying Document - PTW
ed99c398-6db1-5137-b03c-ead17d0decb8 | note | Conduct - C
67afc585-2f07-56a4-840e-df8811f7ca85 | note | Witness - C
4c1ae85b-9ab4-5706-b5d7-9ee6eae86d7e | note | Produce Record - C
8cc6baac-90d8-5336-85ed-ee4955708629 | note | Approval - C
2670c272-9a79-58f6-8aa5-3a48d502e71e | note | Witness Point - Y
| section | 3. Stripping Existing Pavement and 250mm Pavement Layer ; Test Pits for Confirming SG @ RP 10.822m
| checkpoint | Saw Cut Exiting Pavment @ RP 10494 (Start) & RP 11033 (END)
6307cfae-fa1b-53c1-88d7-b3c0668af951 | note | Controlling Documents - SH30 - RS158 / RP 10494- 11033 - RUATO ROCK BLUFF DRAWINGS Sheet C01 & C05
d4b20e64-464d-5a00-bf89-418ac0baf268 | note | Acceptance Criteria - Visual Confirmation
8e798910-d76c-5d0a-bd71-05d1ee859200 | note | Method - Saw Cutter
025b3b03-928a-5ac6-8675-f21fef2b4091 | note | Frequency - Start and End of Site
4cedec4f-882a-54e8-be41-391c68588381 | note | Responsible Person - Quality Engineer/Supervisor
fb8cf89f-9440-5b95-a701-8c8b7ee1828d | note | Verifying Document - Photographs
64674a36-257c-506a-8e04-28a31878c783 | note | Conduct - C
944dd1f1-9b6a-5666-9e63-73d5bb5ffaa3 | note | Witness - C
0b24b5a9-e939-566d-9c40-3e6b336ccb94 | note | Produce Record - C
845647cb-e95b-5f7e-a65e-ae705afc791a | note | Approval - C
c70eb02f-59bc-512f-9fec-4811076a6846 | note | Witness Point - Y
| checkpoint | To confirm the requirement of Pre- treatment Repair
ae80d601-3a5c-5967-aeaa-69161fa6cb57 | note | Controlling Documents - SH30 RUATO ROCK BLUFF - Design Report
011bd4e9-1cb4-5ded-aa1c-368882b12ce2 | note | Acceptance Criteria - Verifiy scala result against treatment type
7a0ab6af-a2f2-5d56-8932-455e398f2a17 | note | Method - Scala Penetrometer on Excavation Floor
6c0901c6-17e5-55e3-a07d-ebe965a67788 | note | Frequency - As required
e5fcd9d0-96ca-5faa-a75f-4273f1a888ad | note | Responsible Person - Quality Controller/ Supervisor
4af47182-23b3-5fc7-bff4-539849240773 | note | Verifying Document - Scala sheet test result
0f274f72-6bcb-5fea-82a9-710bb256349c | note | Conduct - C
8b1364fa-1195-50ae-bd0b-f04cb2e2c2f3 | note | Witness - C
dcac9bef-e472-578e-9a4e-a03a4aa25801 | note | Produce Record - C
5257df2f-1b8f-5119-a456-53ee8d3ea97b | note | Approval - E
0c39590c-e239-5ebb-aedf-9721efc5aa9b | note | Witness Point - Y
| signoff | HOLD POINT
| section | 4. Construction - Granular make up and In-situ Modification
| checkpoint | Plant and Machinery Seletion
18a309a8-447e-5e6d-ae7e-15872920a67d | note | Controlling Documents - Plant and Equipment (6.0.0) - TNZ B/5: 2008
6eaac196-d118-527f-ae15-63318e6bcd0e | note | Acceptance Criteria - Cement Spreading Truck, Direct Injection Stabilising Mill, Vibratory Single Drum Roller and either; 1 Smooth Double Drum and 1 PTR or 1 Combination Roller
61f3d77a-65fb-5d27-8e41-741e1a8c7514 | note | Method - Visual Inspection
abf6b5f3-3159-5599-8581-a78a0449db04 | note | Frequency - Pre-establishment
a7edbc9c-706c-5536-b175-9746599425e7 | note | Responsible Person - Supervisor
c6baf211-1e0a-5754-9421-1d6a3f07e1b3 | note | Verifying Document - Daily Site Record
7fa4572b-770c-593e-a6b0-835532e4dbf4 | note | Conduct - S
336cc9c8-004e-5b4b-bb94-78538b168470 | note | Produce Record - S
250ae6c3-6060-571b-9b53-0a4de96dea46 | note | Approval - E
b3f76d12-7770-59a9-9070-114e7dd9810c | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Weather including temperature
6e094444-ac89-5d12-a916-feac82decce2 | note | Controlling Documents - Weather Limitations (7.1.1) - TNZ B/5: 2008
49ddb045-0a99-5955-a40a-9ee4241aeb25 | note | Acceptance Criteria - Ambient air temp ≥5˚ C, Wind speed ≤25km/h, Rainfall ≤0mm
7f71694f-bccf-5f71-b7ce-a02cc1f34638 | note | Method - Visual Inspection, Met Service/Windy
3a3690df-30f6-5fa7-b6ff-af5d87af794b | note | Frequency - Throughout process
c0a055a6-779c-546d-be13-de217a0692ae | note | Responsible Person - Supervisor
d56618d4-8a72-50ad-b624-b5198186eca6 | note | Verifying Document - Daily Site Record, Metservice
d6878e8d-4362-57db-9404-1e701f2cb72b | note | Conduct - S
d71eed88-3088-56f5-8784-a36739f9d009 | note | Produce Record - S
b0ca6de1-63ca-5bce-af08-f5aab7f9cf79 | note | Approval - E
053a1c24-76af-5edc-923b-339af380d8ee | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Spreading of Cement
1ac71664-9818-5cd0-bbe3-580e3a7ef28c | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
274c698e-9841-5dea-9dd8-7e9c85c8c847 | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
2a4b8672-169d-500a-b266-efbd2b10e2cf | note | Method - Mat test (1m² canvas) and Average Usage Test
e3584e96-3768-5a4e-ab31-867bc94e8f5f | note | Frequency - per 400m² and upon emptying the spreader
86e5e4c0-5267-5f36-87ba-3840dc633666 | note | Responsible Person - Supervisor
f1dfad9d-33fd-5712-8144-0fdbb8ee6574 | note | Verifying Document - Mat Test Form and truck dockets
4a0b4dd2-2c3b-5985-a0d5-13a5ed9ac6de | note | Conduct - S or Sp
8ddfc432-2879-5c54-94f9-2597fd72e8d3 | note | Produce Record - S
9520fe51-c03f-5f60-bdec-33a0bac7d3ea | note | Approval - E
cccc4654-8381-5d69-aa0f-62d4b6b1b691 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Addition of Water
22e8a9dd-0329-5013-84d4-c0db73d5eb62 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
2ea71e1a-c06a-5a7b-9690-966e95e64b4a | note | Acceptance Criteria - 90-100% OWC
8e0955b2-02e8-548a-83f1-ace6e897ba2e | note | Method - Nuclear Densometer Testing prior to Stabilisation
94ee1bb1-4ee4-56e0-bdc8-57bad67b8ca2 | note | Frequency - ≥1 per 1000m² lot
dfc08634-5161-570a-82d1-1272eb63b61b | note | Responsible Person - Supervisor
800262ff-cf70-586f-9fd8-d7dcef814680 | note | Verifying Document - NDM Record
d8ce3f05-d9fa-547f-87e6-fd276741f9a9 | note | Conduct - S
7952aa25-a2a7-5e83-b853-3780ea51d6b6 | note | Produce Record - S
3e996fd4-8d95-5e9f-8d14-01a75fba88e2 | note | Approval - C
5f48a221-8c7a-5921-a048-e9ecc3d7eb34 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Cut Depth
047e49f7-c7b9-5ca8-8d21-674a1955d74d | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
7d2177b4-6f6e-5ccc-9661-ff781ca9ca21 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
6fadd367-5b49-59cb-b7f5-08dd14b78108 | note | Method - Physical Measure and Visual Record
549b3819-2b3e-5887-860b-55529e5fe13c | note | Frequency - ≥1 per 200m of cut length
fcb48f46-5f12-5965-b02e-c248860dda56 | note | Responsible Person - Supervisor
51fb9500-e98a-5b2d-8ec3-42b3ceba4475 | note | Verifying Document - Photographs and Daily Site Record
22d3a7b0-2870-5b47-9b39-0b8b74737d9e | note | Conduct - S
af0dea48-4ef6-5acd-9d5f-5f29bd9e5d12 | note | Produce Record - S
489afb20-5ee1-508b-a4d7-9ff7e37598dd | note | Approval - C
ab188afe-bec4-5a77-a4a5-637de5de277a | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Tie in points: Existing Vehicle entrance points , Existing Dish Channel, Existing Valve @RP 10640 including start and end points
df43b1f0-0258-536c-baf0-5e7724a93fe2 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, NZ3910 Variations TNZ State Highway Geometric Design Manual
324514d5-5637-57cd-af98-419b85949444 | note | Acceptance Criteria - Principal Approval
686fb7b5-c2ad-5903-b543-98b4bac7c398 | note | Method - Physical Measure and Visual Record
26fb2e6a-475b-5fc8-9bc0-cf12bff7a95e | note | Frequency - Pre-physical work commencement
f86619fd-104f-5838-b0ed-55890e9c2d84 | note | Responsible Person - Supervisor
6f06e584-16fb-5027-81c1-bf229473e97c | note | Verifying Document - Design alteration variation ACCPETANCE
65fb4f66-5b70-546d-9828-e3c34ca7cfbb | note | Conduct - S
f699dd49-917b-5dbe-aa85-ad20cfeed895 | note | Produce Record - S
2bf5669a-7a82-5f5c-ab90-65a78d242306 | note | Approval - E
4237d659-962b-575c-8f1a-41dae5c77c59 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Longitudinal Joints
0e853691-d143-5781-9ce0-bedd70702ca7 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
7e995cdf-f1bd-5558-804f-aab209af6d59 | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
2968a6c0-9d87-519f-87a2-5abe49e8dd82 | note | Method - Visual Record
3504dc17-8cce-5548-afbc-d6d746597a1e | note | Frequency - per sucessive cut
0405da19-bff4-53e3-b197-01a0da3990aa | note | Responsible Person - Supervisor
7cf40d36-753f-5ced-b82b-2b3dbac67544 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
9bef485d-f2db-5444-a683-0f9e38933f02 | note | Conduct - S
66fadea8-55d5-5d94-acf6-1687547477d3 | note | Produce Record - S
142a38a6-7412-5c6c-bb6e-76969d298955 | note | Approval - C
1d52ecfc-900e-5a65-879d-779107ff25a4 | note | Witness Point - Y
| checkpoint | Continuity of Layer
7a2a38aa-bbc5-5a22-9a0c-52e899154804 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
45f45688-0375-5c92-a3e2-749df71da3ca | note | Acceptance Criteria - Longitudinal overlap 1m
ac5a5ed4-2bff-51c0-98c4-84810e1795e3 | note | Method - Visual Record
1a6291f5-1391-5d42-9e81-3ff6d009f247 | note | Frequency - per sucessive cut
7b202053-095f-51c5-b0a1-e2217d9c4441 | note | Responsible Person - Supervisor
06300b00-2b5b-5050-ae5e-6d35778e6e76 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
4f5eb800-d882-5acd-89dd-4b4057d4e9f9 | note | Conduct - S
f2116d46-04cf-5a12-8109-ee8daf3ecc8e | note | Produce Record - S
04c4f188-342b-562b-abc5-f9c43cf87905 | note | Approval - C
45760863-84ff-5049-bb54-bca4c4260594 | note | Witness Point - Y
| checkpoint | Stabilised Material Particle Size
122b647b-9c95-5759-9c30-f7887268a5f4 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
f9b16b84-7eed-520c-9e7c-a84db32f1aa3 | note | Acceptance Criteria - No excessive breakdown of stabilised material
239ea0db-b499-55d9-8a77-cbd216845435 | note | Method - Visual Record
14fdbdf1-4439-52f9-be2e-d68153b17c1d | note | Frequency - within 20m per sucessive cut
bb96180b-6cb4-5b08-95de-6f7a1af42469 | note | Responsible Person - Supervisor
43514cc8-f49d-5bbf-80be-37d6e5153886 | note | Verifying Document - Photographs
80e102a2-b3aa-5b5a-b5e8-9c20472f744e | note | Conduct - S or C
120d2781-9647-50bc-a49a-3b5f4fd78285 | note | Produce Record - S or C
1d7162d3-6c70-5361-b980-654c26b281af | note | Approval - C
0db37f2b-26a8-58a4-bb61-c2e0485ef554 | note | Witness Point - Y
| checkpoint | Establish Compaction Target
33a89d13-edad-5d94-ba04-cc35804cb629 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
2897b1ad-f9ed-5fb3-885c-e6f60169d51f | note | Acceptance Criteria - Formal Agreement
3c00b640-384c-514b-9cf5-2ab662b6267e | note | Method - Plateau Density Testing
dbd6b646-751b-5410-ad06-7ee560198e5a | note | Frequency - 1 time, or additional tests when material changes visually (Recommend a minimum of 1-2 tests per section)
d20e34e7-8530-5c72-bc39-06e742cd374a | note | Responsible Person - Supervisor
4c506e7a-3eb7-5747-82af-70b7abbb2c12 | note | Verifying Document - NDM Record
e5bd852c-1e85-5f82-96e0-3cd227c6058c | note | Conduct - S or C
bac55604-0264-5eac-aaba-2dab8d7feba9 | note | Produce Record - S or C
700b4ac2-6a0e-58c9-8f33-bcf5ebd164f4 | note | Approval - C
d4499ba4-3291-577b-ae92-3db1b99c2388 | note | Witness Point - Y
| checkpoint | Compaction Acceptance
edee07d9-234f-5e4b-8499-bbbbff85613c | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
7778d914-c988-51cb-a979-f145e0e1602b | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
c635113f-973f-5e59-a6ac-0dfa17edec15 | note | Method - Nuclear Densometer Testing
67329f65-f797-5e7c-b066-7c2851820d8f | note | Frequency - ≥ 5 tests per 1000m² lot
f5d967dc-6986-546c-a4a8-588cb6361e1c | note | Responsible Person - Supervisor
325f990b-bd4e-52f5-9733-28bf16da8299 | note | Verifying Document - NDM Record
dbb3da7d-b788-588d-86ad-6a2d28923b82 | note | Conduct - S or C
ac3ea8ad-d2b1-58a4-9eac-d57e7479d30a | note | Produce Record - S or C
10f14f25-3f5d-5c82-965e-16b4d08330bd | note | Approval - C
c14bee11-21bb-5aab-acd6-c25183291c5d | note | Witness Point - Y
| checkpoint | Control Testing
ef76cdcc-c545-537d-bd65-8bfac94567f3 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
dcf4b871-d981-5945-bc25-04814a8fb227 | note | Acceptance Criteria - Nil
39ab3f9e-d536-57f0-a1c4-05d1a66a3052 | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
680e340d-9418-5361-a994-b1caae5542b9 | note | Frequency - when agreed
44f4d9ce-a443-5279-9eed-3fe17e451e22 | note | Responsible Person - Supervisor
783732f7-fd35-5dc5-a962-e04d27576498 | note | Verifying Document - Test Report
04272b70-a0d4-5507-8622-c8d12e7df761 | note | Conduct - S or C
4c7cf593-aa4a-5b5b-8a71-bd86075c3af7 | note | Produce Record - S or C
ba26d116-a8da-5114-8578-879daf47fe5f | note | Approval - E
| checkpoint | Surface Smoothness
afcba4e8-00d2-5203-9d48-1772148ce7db | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
498931a3-2dad-50b9-aace-fc6f945cc1df | note | Acceptance Criteria - ± 10mm deviation
d1d035fd-3725-5d19-ba2c-957569c492d7 | note | Method - 3m Straight Edge
5399f21c-ff43-505c-8999-9834630fdc38 | note | Frequency - during construction and prior to seal
8adc9376-5be8-55a8-9c03-225c422107be | note | Responsible Person - Supervisor
4c570461-d5a4-59d5-9df0-b5257017ffd4 | note | Verifying Document - Photographs
3d4a8082-2737-5f9f-a7eb-e1dc2a8b5d88 | note | Conduct - S
70745057-8088-501a-b0f7-443c11db0053 | note | Produce Record - S
72f9f0e5-4d5d-57a9-bd4e-316ca4aa9058 | note | Approval - E
2cccf9ca-d11c-5e73-b84b-728a33f473c3 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Surface Shape
ac834940-62b7-5ee4-937b-af46a9c1dd5f | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008 ; Superelevation RP 10500 - 10800 = 10 % & 10900 - 10970 = 6%
5f24b9ad-9d00-530b-82d2-5c8129016c61 | note | Acceptance Criteria - Between -5mm and +15mm
9ca4e208-0dc1-579f-ae22-4988e58af4bf | note | Method - String lines or Survey Asbuilt
157eb5c6-90b6-51bc-a509-48fa815b7f34 | note | Frequency - during construction and prior to seal
457690c6-dbf6-50cf-a156-a16b7e19470d | note | Responsible Person - Supervisor
2b39869c-538e-5174-90c2-9d188c9a89fd | note | Verifying Document - String Sheet/Survey Asbuilts
1b2b0b99-d8da-5b04-843d-37fb66bc317d | note | Conduct - S
8a883e52-0fc2-513c-8b49-4e8c2dc944ec | note | Produce Record - S
3493c422-f3d7-53ec-8013-f6f9464643a9 | note | Approval - E
462e4435-e6ef-54dc-8b2f-99249758aebf | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Cross Fall
63c50964-4169-5ac0-bd67-b611167bec13 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
6d14cb01-f140-537a-be79-6da632cd4d26 | note | Acceptance Criteria - 0.5% ≤ X ≤ ‐0.5%
e6882734-f3e2-5278-af58-1a0ca24238d8 | note | Method - 3m straight edge or Survey Asbuilt
d4850656-769e-591c-adc0-7d3d5914ff5f | note | Frequency - during construction and prior to seal
c6c12907-f19f-530f-afd9-53177a45d08a | note | Responsible Person - Supervisor
89ca0803-3529-5505-8fdd-3d73db52d237 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
8e4b4573-0029-5ca8-bb11-f0b8d80e8e2a | note | Conduct - S
9d9ee40c-cf0f-56ee-b6ca-bb7b05934759 | note | Witness - C
925962b6-455b-5aef-ab16-bd792e4b0b1b | note | Produce Record - S
3ad992e7-1429-5e13-ae70-abbc26b77811 | note | Approval - E
1ca33a71-816e-565b-af9b-cc825765a6d1 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Surface Finish
4d7d44b9-cd23-54cf-ac2b-83234414c00b | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
d8bac6e2-c0f9-599c-867b-bed34a5b62a7 | note | Acceptance Criteria - Tightly bound matrix post sweep
95d21031-a2e5-5042-89bf-01c04d5ce9a6 | note | Method - Visual inpsection
0322e229-a3c7-5212-b634-e0794eaac6b2 | note | Frequency - prior to seal
c53754a0-8ed4-5496-80f1-55bfa396734b | note | Responsible Person - Supervisor
180fb1f7-3fb2-5767-9c04-5cb30cdffdb7 | note | Verifying Document - Pre-seal inspection sheet
a6d3a0f9-45c2-5485-badf-b5499afa6c89 | note | Conduct - C
7ae2d835-f1a1-5b68-85f9-581c39e73390 | note | Witness - C and E
81be719b-8630-5bb2-bf89-69db386586d4 | note | Produce Record - C or S
0fd728ff-870b-519d-8a5e-59c158b7776c | note | Approval - E
8427975b-ae33-5472-83c1-ca8f7666f64a | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Pre-sealing Requirements
781cfe29-de5e-56bc-a762-e8eb91a33127 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
fbbc40b9-fe76-56bb-b140-4b47d0ab80ab | note | Acceptance Criteria - ≤80%, however 65% is ideal
90eea2f0-8fdb-53b5-9fe0-dc85f643bb99 | note | Method - Nuclear Densometer Testing
a6e2dfc9-04e0-519c-be81-45fc09341b9a | note | Frequency - if required, ≥5 tests per 1000m² lot
1d14363e-8157-51d8-a5ab-27ee41adefad | note | Responsible Person - Quality Controller
95576893-4c29-596c-9d52-ff3ef6402e2e | note | Verifying Document - NDM Record
39bb9184-e827-58bc-8956-38799cd30e05 | note | Conduct - C
56b1c6f4-e46c-5aef-b8fe-bae619cbce71 | note | Witness - E
5aa4784a-367a-545c-9474-153de8aaf8ff | note | Produce Record - S
bbca507c-0b1c-55eb-b781-7687c2e0895d | note | Approval - E
f37c2fad-fc2a-5d46-a78c-55ac307b2679 | note | Witness Point - Y
| signoff | HOLD POINT
| section | 5. Chip Sealing 2/4 - 2 Coat Chipseal with Catonic Emulsion or 180/200 Binder
| checkpoint | Binder - Penetration Grade
ffc82700-78c7-51ac-82e5-951327f6c3c0 | note | Controlling Documents - TNZ M/1
10d03c05-3c46-5b55-867b-8fb610a14365 | note | Acceptance Criteria - Table 1
abf09842-3ed7-5e14-b1ef-6f952004d20f | note | Method - Property Test
56c106d7-bb88-5af8-a437-5607fb92642a | note | Frequency - Annual
c784e711-73b7-50eb-93ba-680952bd5bd6 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
1c04ba97-bf49-56b4-a5b7-08a192b9da6d | note | Verifying Document - IANZ Report's
bdf93233-d3a5-5525-ba0b-c9af1e9bcc88 | note | Conduct - C
c266dcf5-ba1a-53b1-a825-677d35606e9d | note | Produce Record - C
96023534-8153-5c0f-ae32-5139f70a3921 | note | Approval - N
6948e94f-fa4a-5420-ad58-3d835d187aaa | note | Witness Point - Y
| checkpoint | Binder - Polymer Modified Emulsion
6f794177-c90a-5044-8b6a-52a14451d0a8 | note | Controlling Documents - Higgins Internal Specification
fdb18e95-4e9b-57fc-b0b8-3973d8997a83 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
7f6fc134-e828-51b4-8fb0-70ec703f6e30 | note | Method - Property Test
044858e4-9a30-5120-ab3c-2059405d0bbd | note | Frequency - 1/100,000 litres supplied
ba169fbc-39f0-5d79-8fea-9d430c2c9c30 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
62ca261b-5489-56a7-ad46-18a36a65f661 | note | Verifying Document - IANZ Report's
0d68346d-38e3-5057-af37-627bd8e459e3 | note | Conduct - C
7d6a3329-e116-5c3c-84a6-e49eda4c9c8e | note | Produce Record - C
f5434ce0-3ea4-5dfc-9449-80cf5551874a | note | Approval - N
243b7600-915b-52ad-8bb2-7eeaa7975d5c | note | Witness Point - Y
| checkpoint | Source Property - Coarse Aggregate - Crushing Resistance
d7e57929-9383-5a77-be2f-f71e0dad7bea | note | Controlling Documents - TNZ M6, RNZ 9805:2009
00bc6d26-0e94-57dc-8af6-6a9ee9f7b39c | note | Acceptance Criteria - <10% fines under 230kN minimum
ecbe1cbc-bad3-5b0f-8a21-78933b7832f4 | note | Method - Sample Test - Crushing Resistance
86b55f05-6945-5d3a-8ddc-cfebf6b04bf5 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
49e243a7-aa02-5ca9-ab2b-f37776887c69 | note | Responsible Person - Surfacing Project Manager
1345639a-a18d-5cbd-a261-cc7d858cae9d | note | Verifying Document - IANZ Report's
f89acacd-b0d7-506f-be3a-fccdf8f45a83 | note | Conduct - C
78c24796-5315-5615-aa80-bc324c3ce29c | note | Produce Record - C
5ba9d50c-f693-59ac-a860-543ac128835f | note | Approval - N
77a18928-2b0c-5386-9829-8e995b318ce2 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Source Property - Coarse Aggregate - Weathering Resistance
26dff4a7-9adb-51ee-a120-770085004c0a | note | Controlling Documents - TNZ M6, RNZ 9805:2009
6a135b11-d6eb-5c05-843d-25db8e054e2b | note | Acceptance Criteria - AA or BA
7fa3e53f-681a-59f6-b480-287047938958 | note | Method - Weathering Quality Index
ecd503a6-b978-509e-9ecd-3caa85e39e20 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
cc74eeb8-d30d-5b60-949e-7729d6e30290 | note | Responsible Person - Surfacing Project Manager
216f6ae4-2797-53a3-87f0-1ff5184796af | note | Verifying Document - IANZ Report's
242dddc8-f0f9-5680-8602-3248d693bab2 | note | Conduct - C
ae58c68e-912a-56b9-a74f-ed97215f4669 | note | Produce Record - C
b6fe7e5e-b1aa-5bf0-bd32-ed412ca116c3 | note | Approval - N
1a84a739-a654-5d9a-872d-593aa8c852ac | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Production Property - Skid Resistance
03bc6637-eaee-5036-91da-abbad7dd24b1 | note | Controlling Documents - NZTA T/10
1baa66f1-7017-5da3-8b32-0cf2fe795c72 | note | Acceptance Criteria - Meet Skid performance Requirement
db88bb25-bc2f-5972-8fea-e82a21329f57 | note | Method - Aggregate Perfomance Method
73c4b8ec-9b28-5e54-b98e-e4dbc286cf8b | note | Frequency - Each Site
b9a34901-f181-536a-97f0-4ece7fbb2483 | note | Responsible Person - Surfacing Project Manager
c71c4dd5-6137-5e6b-b455-126c7345e7ab | note | Verifying Document - IANZ Report's
8791e797-3003-59cd-b409-fe599f2d2b98 | note | Conduct - C
f2e7352c-1cb4-5271-9abd-c87727522de2 | note | Produce Record - C
22525574-ba5f-5b84-9acf-718ded4ef161 | note | Approval - N
edd7e18c-d07c-57b1-96d8-77861ca8ffc5 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
fdf176e1-6d7c-5779-8c79-4acbc6dd91af | note | Controlling Documents - NZTA P/17, M/6
578c50f9-ed98-5667-bdb9-e6d7ab94cc2a | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
16d8960f-070d-5742-b241-da026b85684a | note | Method - Sample Test - Cleaness Value
e10b2284-76c9-5dc9-8284-b6ba1163216c | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
0eb9f481-d04f-5a12-8063-04d2470bea11 | note | Responsible Person - Surfacing Project Manager
09d6a45c-0ffa-5b64-a105-e5df72e6f4c1 | note | Verifying Document - IANZ Report's
0f5e7795-f409-51b0-a546-15f94235f5dc | note | Conduct - C
208e5169-e138-5c55-a60a-4f4f70a5461d | note | Produce Record - C
79d9f48f-00a6-54d1-8b1b-264fed9e9f82 | note | Approval - N
cf3b51ed-08ce-5541-b4a6-704b022641c2 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
bdd1f154-5fbf-5278-9a6e-d5ac90c21a76 | note | Controlling Documents - NZTA P/17, M/6
090390ae-c285-5d5c-ad67-cc77f83a9863 | note | Acceptance Criteria - As per Table 2 and 3 NZTA M/6
222b6289-cf92-51b8-abb0-e5cee8b2a270 | note | Method - Sample Test - Particle Size/Shape
3b94f83a-95b4-5a40-963f-69bffd128f1a | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
412cb962-7da8-53fb-b7c6-0273499ef1a9 | note | Responsible Person - Surfacing Project Manager
06d50ac6-cf31-5e96-a4dd-89beabdef8d9 | note | Verifying Document - IANZ Report's
92028b5e-e20d-5e45-b1c6-e88addaed743 | note | Conduct - C
6b609d2d-7b4d-5b97-aea9-0df0acd86417 | note | Produce Record - C
585866ec-cbb7-5b9c-a37a-da5dc1174f9f | note | Approval - N
0f0073a7-42c7-5370-9631-98f179a6d057 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
89784388-69c3-5897-adb1-54c8e9dcad7c | note | Controlling Documents - NZTA P/17, M/6
a10a255a-bf34-54d8-8d92-64917f25b571 | note | Acceptance Criteria - 98%
bb3a7d5a-75b6-5124-9ec2-2c432d70162b | note | Method - Sample Test - Broken Faces
b775a482-1ce8-5b0a-98ff-04b2f6e0af46 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
3da7e6c1-3e96-5887-8313-08ed1e117a86 | note | Responsible Person - Surfacing Project Manager
dcc0d4a5-ffcb-5258-bff9-4aef0ab194b5 | note | Verifying Document - IANZ Report's
edc6b0fe-ab80-525c-b745-6a50c2a74b90 | note | Conduct - C
595a1b86-5f26-561a-b794-74f370acf98d | note | Produce Record - C
00d070e4-9246-5aee-a1de-b0d36f9e8849 | note | Approval - N
3fdd8498-525a-5868-9d91-7631109e1f87 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Chipseal Designs
d63cdaa0-9bed-5db3-8aa3-695e9e10221f | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
419840ce-4431-5579-9ce7-8bd85f5f0a3e | note | Acceptance Criteria - Client Approval
d739ab17-b33a-5285-a8b6-7dbc7b9e9588 | note | Method - Review
840c044d-57be-5597-a8d7-1850a9da438f | note | Frequency - Annual
4f803c35-596a-5bb2-bbcf-fdd85908eab9 | note | Responsible Person - Surfacing Project Manager
fc9ac6d5-d4c6-56f0-9b47-3ee73182e331 | note | Verifying Document - EBOP NOC Design Report Acceptance
026f6dd9-6141-55b2-bd0c-f4b43084c085 | note | Conduct - C
63f074c2-3ddc-5623-b69b-d8725da6f204 | note | Produce Record - C
d2aec7e6-98e9-5ed7-97fe-44790512861b | note | Approval - N
3cb8804a-38a1-5f88-92e2-bb65891790c3 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Finalise Sprayrate
5bcff4f7-83e8-5530-99e1-fd2059472be2 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
ff715ea4-2290-5411-bd24-204fbbafa517 | note | Acceptance Criteria - N/A
08afed7e-d0c9-5322-b2b4-35f1a6fa6fd1 | note | Method - Review
f0a84043-65e3-5648-a465-6f66e880d7db | note | Frequency - Each Site
bcf3d9d3-4828-5adc-a259-6b08e3e82b87 | note | Responsible Person - Surfacing Supervisor
74fb9340-1893-5168-a6c1-297515a4a483 | note | Verifying Document - Site/Spray Instruction
b1d2092c-e7b9-5309-9f45-a55b9effe09e | note | Conduct - C
4e370a97-aa46-5398-ac8c-e662f8e9d8b8 | note | Produce Record - C
0d4ac45d-57ed-560a-81c6-ffc5e47a460a | note | Approval - C
d59aaf2b-9eac-54ad-a336-f064c7fed754 | note | Witness Point - Y
| checkpoint | Check weather
d92777d0-1652-5868-a1a1-d6d9bc0ba472 | note | Controlling Documents - N/A
b7654760-c2d4-560e-8d9b-36ea7af70e7e | note | Acceptance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 10ºC and rising. No rain forecast
5bf6b327-3448-5b20-9006-cf39519bf15e | note | Method - Weather Forecast
b290d234-2eb2-5eef-94aa-0dc0fd311e28 | note | Frequency - Prior to establishment each day
5927d8f0-f807-5a86-acdc-c218d4d832cf | note | Responsible Person - Surfacing Project Manager
a10a85a5-5426-5c30-bfab-6c2b6fe76a18 | note | Verifying Document - Daily Report, Chip Sealing Quality and Site Record
a88aeffb-b1a2-5901-9466-959a09b5e975 | note | Conduct - S
8bd0b39f-b0fd-58c0-87e4-e086ecda5193 | note | Produce Record - S
d936093b-be33-5383-9f30-1909d1d13ddc | note | Approval - C
3e6a2033-c675-5565-bd39-e0c3d5ee5fc2 | note | Witness Point - Y
| checkpoint | Ensure limits of site are marked
cbcea6b4-ebe4-5896-b21f-16239bdc07c8 | note | Controlling Documents - EBOP NOC Design Report
c164cea7-07f0-544d-91a1-08dc8728d3c0 | note | Acceptance Criteria - Visual Inspection
2a7fc58b-e098-5c73-8d8f-04c912b3733e | note | Method - Visual
3873a3c3-d1f9-58c0-8e38-2ec39d8a2998 | note | Frequency - Prior to start sealing each site
7b639423-0359-58f7-aa96-cb3a62071e44 | note | Responsible Person - Surfacing Supervisor
93215d41-4bec-5359-a0e1-32a75ed5676d | note | Verifying Document - Chip Sealing Quality and Site Record
6def69ae-bf7c-5a0d-bbf6-23fece7b6257 | note | Conduct - C
20736d01-6778-5f9c-b00e-47659fa55064 | note | Produce Record - C
6bb46bbb-d942-56fe-8e55-ca853ae9763c | note | Approval - C
4d34984a-6691-58cf-beae-0639f05f32d5 | note | Witness Point - Y
| checkpoint | Establish TTM
e20a08c0-f767-5d92-bbeb-0f5e590ae199 | note | Controlling Documents - TMP
13e07b1a-7293-553d-9eaf-e363f1637312 | note | Acceptance Criteria - Comply with TMP
75aadb6f-7196-5187-9fcc-052c2058f56f | note | Method - Visual
8052c57d-3195-5983-b13c-46c5ba3e9357 | note | Frequency - Each Site
b41aa152-07a5-50b9-8343-9b2a2a3e74da | note | Responsible Person - Surfacing Supervisor / STMS
ff5e0f13-aff1-52cc-ab60-f66503054bd6 | note | Verifying Document - Daily Diary / STMS Record
21c4f38a-9259-5d74-8a72-518ce0b0cf12 | note | Conduct - C
f3fa97c4-2904-51c5-8e4a-ee000fceec6b | note | Produce Record - C
c041be63-fb05-578c-b6bf-977550949a2a | note | Approval - C
e6f4430c-8263-59cc-8009-15139b80a7c9 | note | Witness Point - Y
| checkpoint | Sweep surface clean of deleterious material
8cbae5ab-66b2-5438-9eab-43e9352e784f | note | Controlling Documents - P/17
da88e645-4fd7-5f0d-9752-6d7c82668951 | note | Acceptance Criteria - Visual Inspection
b7dae83d-b3ca-5b05-9c36-26d9dc8ba038 | note | Method - Visual
3fd6fff5-df9a-5326-908f-5bfa3aaa779b | note | Frequency - Each site, prior to start of sealing
4864dc9f-0e1d-5c07-9d47-b7a497f1c8ed | note | Responsible Person - Surfacing Supervisor
89909079-c623-5ad1-af90-d36d51cad28d | note | Verifying Document - Chip Sealing Quality and Site Record
495da30c-677e-5101-984f-6af0b47719c6 | note | Conduct - C
0261a89d-b75d-5a38-83a5-d8edd9375544 | note | Produce Record - C
a1b11aa5-21c8-5e8b-8084-d85aa41d98bf | note | Approval - C
bc35e917-45ec-5bbb-9ffd-8f3e75de7c7e | note | Witness Point - Y
| checkpoint | Record ATP's on site
51c863fb-4112-557a-8582-a59617265858 | note | Controlling Documents - N/A
b8f7d646-4226-5c1e-a928-8dea1af8debc | note | Acceptance Criteria - Visual Inspection
d893e2b2-717e-5775-8ae7-3065042d7a40 | note | Method - Visual
231446fe-81fb-56ea-bc49-f53ff8cbce62 | note | Frequency - Each site, prior to start of sealing
c65a56f1-b485-5726-9319-8c2eb4ccd75b | note | Responsible Person - Surfacing Supervisor
915b9143-4bb0-5891-a24b-eab4cd8ecac4 | note | Verifying Document - Chip Sealing Quality and Site Record
6d4558d1-6724-58a0-8baa-734b209f92ff | note | Conduct - C
16c01632-83c0-510c-9b57-734381b26eb0 | note | Produce Record - C
8a0c2fe3-6fd7-5b82-b97d-628a9dbd6ac8 | note | Approval - C
030121a9-7a7e-52b9-8eff-894662230cdd | note | Witness Point - Y
| checkpoint | Confirm correct treatment(s) and chip
4193b441-972b-517c-93b2-66317e2a1d2b | note | Controlling Documents - EBOP NOC Design Report
83869c6c-d344-5103-9589-c97cf5ecdd7a | note | Acceptance Criteria - Details/chip correct
64e49ec9-9ce1-524a-a2a1-820a02a78a56 | note | Method - Visual
9489f7df-68c3-5b28-bd0f-1bf26d58bbac | note | Frequency - Each Site
407b9e27-d196-516f-9020-a03452107a74 | note | Responsible Person - Surfacing Supervisor
d86a23a7-1c00-592a-afde-ccad4ca31c2d | note | Verifying Document - Chip Sealing Quality and Site Record
c58df816-4e59-5d71-8668-484f5e86369d | note | Conduct - C
eef8cc9c-5b63-5ba8-a6d4-996728b71f40 | note | Produce Record - C
46aebcab-9f68-5b31-b9e8-62891b76f0a7 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Cutback Bitumen Blend
4443dc5d-5804-5438-918f-f6831516737d | note | Controlling Documents - RNZ 9803_0513
22e14c2b-351b-5fee-a1f2-07212fdda255 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
87d209bc-b0d8-587a-85a5-8ecc096f9c8c | note | Method - Sample and test
6f1ae831-637c-5961-b305-925022363780 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
55353e7c-3d95-577b-ab39-77d67ae351d5 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
427368bf-7110-5fb9-b383-b04f20624907 | note | Verifying Document - IANZ Report's
27979559-c76d-5993-8106-8cfb908aeea4 | note | Conduct - C
901c1df2-09d7-5a25-8c27-a23bdc4057e0 | note | Produce Record - C
11d3fd64-52dd-5964-b821-fcf1cdd30594 | note | Approval - C
b39b7ef0-a18b-5664-934b-7dd6ba2373ba | note | Witness Point - Y
| checkpoint | Bitumen Application Rate
d4cb6c28-b065-5b2e-86a8-47f41407c730 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
d5a69582-d281-513d-9dc5-bc6d8d73b90d | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
2dfa5b19-a00f-5aa9-9ede-69e1c6415850 | note | Method - Test, Review
b63b6ab9-1761-52e5-9d5b-595790691ec8 | note | Frequency - Per Sprayer, Per Site
f5ca97c8-2baf-5ed2-9f25-8e03f27b28eb | note | Responsible Person - Surfacing Supervisor/ Supervisor
858208ca-e997-5eef-9aac-8a02c67a3138 | note | Verifying Document - E/2 Certificate. Spray Sheets
2bcee15c-9e03-5586-bd0a-51df278183ee | note | Conduct - C
324ce84a-26dc-5385-95f1-09d0a93c2422 | note | Produce Record - C
a74163d2-e180-5eb3-960f-3b8b4cfcaaa0 | note | Approval - C
9abeac2c-b9c8-5949-a977-1ee45a08a31a | note | Witness Point - Y
| checkpoint | Chip Application Rates
d3a1cbfe-0854-5081-a314-24377a3dcad3 | note | Controlling Documents - Chipsealing in NewZealand
4a1f007e-6aed-5fbc-b93e-02d0aa3e757f | note | Acceptance Criteria - As per Chipping Guide
b6b5d261-0643-5e71-a2b8-0d3a16a3ca8b | note | Method - Visual
d7ff7cb9-1ea1-5dd0-add3-856d3a4d9041 | note | Frequency - Each Site
bbb33740-f9ef-53d6-86e2-0a776df1ee94 | note | Responsible Person - Surfacing Supervisor/ Supervisor
71650e1a-fd82-5867-92f6-f43df89c9246 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and
a4091d43-b0a6-5b2e-bd4f-e1cb369838a1 | note | Conduct - C
9cd941de-2867-54dc-a378-d8b33908b5de | note | Produce Record - C
6170cfcf-c505-5c80-b470-e56c045d2df3 | note | Approval - C
a34d8585-c3fb-5097-a68a-b1d8b8570bd6 | note | Witness Point - Y
| checkpoint | Rolling
dc90f101-981a-5881-aa05-16c4217951d8 | note | Controlling Documents - Chipsealing in NewZealand
3b030af9-e600-525b-8ee1-213172045039 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
aa50cde0-4b49-5262-b334-be12d9fc12ca | note | Method - Visual
0439e6b2-a3c6-5478-871b-27299d1f979b | note | Frequency - Each Site
8fe532e9-ffd9-55fe-992f-e422447e91c2 | note | Responsible Person - Surfacing Supervisor/ Supervisor
93ffedd8-737f-54dd-b6d9-8a5d623874ab | note | Verifying Document - Chip Sealing Quality and Site Record
c43eabea-49ce-5781-ac89-f5cefa07ea4a | note | Conduct - C
3b17cfd7-d9a7-57c7-9e7d-b36092b007ed | note | Produce Record - C
e0718b64-f239-5869-a3ab-439f985532a5 | note | Approval - C
b2fc4ad1-2a7d-5b75-9d3f-a870c23eccb5 | note | Witness Point - Y
| checkpoint | Cleanup
7d6965f6-e095-52f5-95cd-336dd947bd42 | note | Controlling Documents - Chipsealing in NewZealand
8482dd5a-b19c-5dc9-9ea0-e37440d99eed | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
9c6bdd0c-70a9-5d96-ad01-a1deb3c64bf6 | note | Method - Visual
bf9dd376-295a-5a61-8aeb-de37e7fef1e9 | note | Frequency - Each Site
da8edd02-0b19-569d-a438-0f3122cbec01 | note | Responsible Person - Surfacing Supervisor/ Supervisor
56cb6b48-dea0-5268-ba3c-883ab5dd9ea9 | note | Verifying Document - Chip Sealing Quality and Site Record
ea6d81fc-94b8-5cff-87e8-a564adfde264 | note | Conduct - C
751e74ae-8102-58c6-9e78-91bb5d2561c4 | note | Produce Record - C
2336326a-a9a8-5229-910a-4fbc623ed06c | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Post Sweeping
bab29157-aca0-5ad6-aa2f-ab3ff5cc63ea | note | Controlling Documents - Chipsealing in NewZealand
18955e02-69b5-54d5-8fa8-10e1bf86cee3 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
b4ca1272-2d78-51be-9a0f-85d2f50c68d4 | note | Method - Visual
59d69906-8cea-5679-92a9-95f5bb6ea300 | note | Frequency - Each Site
e94d1d26-77f2-5a42-9b89-4483517fc1f0 | note | Responsible Person - Surfacing Supervisor/ Supervisor
dfa6780d-9449-5ac8-8005-b16551b402b6 | note | Verifying Document - Site Record
36ba0b67-b361-5e7c-9990-ace66bc61b50 | note | Conduct - C
28e3c67f-5627-5c60-a22d-ba206f1f7377 | note | Produce Record - C
2ea352ca-d279-5e84-994f-25959f7eea1b | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Linemarking and RRPM Reinstated
47180287-0199-53a1-aca4-20c521d924ba | note | Controlling Documents - MOTSAM
2c8aa1c0-c379-58f1-8d4d-b14ef593617b | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
418b2329-ce72-557e-a816-d8d3a6273432 | note | Method - Visual
902bbff1-d000-52d2-a6c8-3edf9c12f82c | note | Frequency - Each Site
794e3f76-2157-5137-a411-cc8f88199f1e | note | Responsible Person - Surfacing Supervisor/ Supervisor
33e01229-f251-56a4-95bc-7a44a36c044d | note | Verifying Document - Site Record
8af0768d-ffe8-5884-aa7b-e2019972033d | note | Conduct - C
ea6330ec-04f5-52ea-b7a3-8151a81036d8 | note | Produce Record - C
3c4e0c79-665d-52ea-b03c-6117bdac7e4c | note | Approval - C
6acf5fdd-8d7e-5351-a8e9-78d0575c626c | note | Witness Point - Y
| checkpoint | Removal of TTM
5273dc42-2dc2-58de-aad3-fab51a722337 | note | Controlling Documents - TMP
c607cec1-6c30-504c-b2c7-457a15fb54de | note | Acceptance Criteria - Comply with TMP
35386539-4e2b-5a1c-b1a2-f1b9a99bea15 | note | Method - Record
4f9de630-726f-5b66-8d45-e24aead1c280 | note | Frequency - Each Site
604e94b9-5b61-53ac-9564-458d0879f3af | note | Responsible Person - STMS/ Supervisor
19989e23-b4bc-5d0f-96e2-e266575821bf | note | Verifying Document - STMS Record / Daily Report
de8e6ba8-0eb2-5f3b-88ba-0beebe5f404f | note | Conduct - C
78b3e912-a1f9-5de1-8031-29a20ded918a | note | Produce Record - C
0cf65ab6-e5af-59ec-bdc7-7e7d1f5011c8 | note | Approval - C
ee874796-a0f3-54ed-961f-cbb134eb5db0 | note | Witness Point - Y
| checkpoint | Resurfacing Construction Completion report
5feca96b-22ae-5370-ba03-9826b832a553 | note | Controlling Documents - NOC; MS 6.1.3
facb7460-1809-53d3-9ca6-50c619754e1e | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
1ba85f23-58ba-5ec9-af52-30c3376dc6ba | note | Method - Record
b376e0e7-32cd-5455-a938-0b501df22e36 | note | Frequency - Each Site
930b7a98-07d8-50b9-a72c-e702a789c044 | note | Responsible Person - Resurfacing Construction Completion report
d507f3af-edaa-5f78-8a6b-9085e40a9392 | note | Verifying Document - Daily Report / STMS Record
eb931bbc-fa20-5936-a8ca-1e44d59179b1 | note | Conduct - C
b6e2c26b-3d1d-5961-9404-907d2bb9ce93 | note | Produce Record - C
2f16e699-48d0-5542-9407-729b4a89f532 | note | Approval - C
3ff112d5-abb1-5200-a190-f762b75075f4 | note | Witness Point - Y
| checkpoint | Chipseal Post-Verification Testing and Report
5ee83c9f-914c-53c4-87bb-0e435aff19e7 | note | Controlling Documents - NOC; MS 6.1.3
99a496f9-1df1-5612-9718-a6b7b40e8f79 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
0afca9cd-2dbf-5eab-a406-2666136b54c9 | note | Method - Record
f22020ec-6717-5e48-904a-724cd757ef4d | note | Frequency - Each Site
f723ceea-8429-54db-9872-c939e5a68755 | note | Responsible Person - Surfacing Manager
6df30470-1232-588d-a1d6-acd7894ad46c | note | Verifying Document - Chipseal Post- Verification Testing and Report
614421c6-258b-5968-98ef-78df2bec3f85 | note | Conduct - C
6fd36fd4-e357-5982-9a5a-62e2e629f225 | note | Produce Record - C
81fd6b54-34e6-53b7-8fc2-03286ff3cca3 | note | Approval - C
| signoff | HOLD POINT
| section | 6. Close Out
| checkpoint | Post Construction Walkover
c912de83-4076-5045-adba-6056d46c1edd | note | Acceptance Criteria - Formal Agreement
1a9e55c8-c577-54a0-af40-dc004bdfd440 | note | Method - Visual Inspection
5800ef61-707e-598e-9a0f-49a6f119fd93 | note | Frequency - Post seal sweep
8052f8d2-d69f-5db2-b947-96af050618b7 | note | Responsible Person - Quality Controller, Supervisor and Engineer
00276dff-5c18-5379-8bbf-a871ec41e762 | note | Verifying Document - Meeting Minutes
6175949c-9405-5525-83df-fb325388b2d2 | note | Conduct - C
1cc1f081-193f-5870-9234-f1a175414f17 | note | Witness - C, S and E
ee777291-e95d-5223-b34f-3c289e639641 | note | Produce Record - C
e73bff9c-9b68-5805-bc7e-1154532a9bcf | note | Approval - E
821bfb69-a706-5f61-a14a-243fef53f054 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Pavement Rehabilitation Construction Completion Report
12368158-94ff-57d9-bb10-17e7b975361c | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14- 001_601 Maintenance Specification
a71204b5-08af-5963-ba2f-852e7f70b567 | note | Acceptance Criteria - Engineer Approval
53fdc3e3-0cb4-5909-a35d-59f89bc8906d | note | Method - Visual Inspection
276191cb-368d-58b2-806a-b2f2e69e0149 | note | Frequency - ≤2 months of 1st Coat Seal
9fb6b42d-15e5-5508-b58d-cb1b4237a240 | note | Responsible Person - Contract Manager/ Quality Control
609033da-04fd-5b4b-a3c8-ea0cdfcd060e | note | Verifying Document - Signed Report
b45037f2-e8d0-5b59-be30-0f209c55d865 | note | Conduct - C
25cecbdd-e16a-5a35-b351-52fb6e684d3a | note | Witness - C, S and E
8b057f37-57b4-56c2-a139-6661caad4c77 | note | Produce Record - C
05f78316-90c5-5842-a155-2e974ffdde6d | note | Approval - E
989ef1f1-2187-5d2e-af06-afd504173bd6 | note | Witness Point - Y
| signoff | HOLD POINT
| checklist | ITP - Pavement Rehab - SH 2 - Gun Shop Hill | itp | ITP - Pavement Rehab - SH 2 - Gun Shop Hill | 3e13ce65-fceb-4370-8c3c-95bfb00d12a9
| section | 1. Procurement
| checkpoint | Design - Geometric Design
107423e9-ac4f-5983-81cc-b70b910b0be5 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
d4e55820-d638-5cd9-abc1-ed1c31a2161e | note | Acceptance Criteria - Principal Approval
8ab0913a-884f-5fb8-8f84-276a5a1ba979 | note | Method - Contractor and Principal peer review
de57d29b-6ead-5e6a-b612-b7829b9e3a21 | note | Frequency - per design revision
066c32eb-7099-5ef8-95e7-b7391f594fcc | note | Conduct - C or S
291f60b2-1a86-53ba-9b0c-69aec89fd23c | note | Produce Record - C
54fd0c98-d562-5ed8-9366-381cb2f5a18c | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Design - Pavement Treatment Design
c9194063-8770-500f-8205-8c40ffd77363 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
890cc2aa-69d1-51b0-8d48-79255961aa6f | note | Acceptance Criteria - Principal Approval
c2aafafa-9a7e-581b-aa8f-2806dc131d38 | note | Method - Contractor and Principal peer review
2472f03f-4f33-5128-bf4e-26aabeb55b30 | note | Frequency - per design
160bcf90-5658-52da-b74d-fabf58245f8e | note | Verifying Document - Approvals Register - SH30 Frosts - Pavement Rehabilitation Design Report
4bfbe954-848f-545e-b5c0-8d6e4e14051b | note | Conduct - C or S
46d186b1-cb9c-5f32-bf16-7099d9755d8e | note | Produce Record - C
083c6180-3b79-5492-bfde-a3b46dcaed37 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
06b6f66a-aab7-5085-a385-1b77e1567768 | note | Controlling Documents - Aggregate Sampling
f579d817-9b6c-5231-90d2-f7275a11aab6 | note | Acceptance Criteria - NZS 4407:2015, WSP Rotorua Sampling Guide
356c4095-8cb7-5934-9df6-141e97b6876b | note | Verifying Document - Sampling Worksheet
2c56cf5f-94bf-50ce-ac41-994b7923f294 | note | Conduct - C or S
fb423f57-e30d-5963-b2d5-8efcebb06ed6 | note | Approval - S
| checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
e0eb9166-403d-5101-9c5e-614ccb590b38 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
2c6f43cb-dcea-59e2-b78c-e5802e6c4ef1 | note | Acceptance Criteria - Soaked CBR ≥ 40
033ed35c-747f-5dcb-b888-5ddb72879223 | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
977bd4a6-41dc-59d9-850d-1e5e17731ca9 | note | Responsible Person - Supervisor
b13abe13-8abe-532d-8f29-7a0019bfcef3 | note | Verifying Document - Test Report
4c9de18e-7fe5-5f7d-9beb-856bd66be1cf | note | Conduct - Sp or C or S
3a385623-fe3f-5c05-9a0c-5e7099c5c2c6 | note | Produce Record - Sp or S
b13da174-2682-512d-b5f4-10c871ab22ff | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
7840e4de-e66e-5555-af9f-c19dde371896 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
6635ac81-05cf-5017-b94a-c46118f3df21 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
4ca45235-85b9-5fd3-91aa-132e0fa46474 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
c6ef48fb-fd04-51b5-ba7d-4de7b99e6765 | note | Responsible Person - Supervisor
ad78a46c-7d97-5d21-8fdf-bb9ef0569647 | note | Verifying Document - Test Report
514a9838-cdb6-5eb4-9039-761f996416b7 | note | Conduct - Sp or C or S
70cebdf6-2475-5ae5-90db-d8b85d09c17f | note | Produce Record - Sp or S
ad6b1f3e-568a-5741-8497-0b730bec5331 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
9d747c7b-7314-57eb-9d60-9e162a9b4e34 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
16dede97-d4d9-56b7-8d80-fe9f5914200c | note | Verifying Document - Sampling Worksheet
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
2e2c081e-2b9b-5bfa-8e09-c77463772bf1 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
e04fb41e-4a1a-5895-b322-c320208edf96 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
f2ebfeb3-7aae-5b2a-a027-b7881f6fc1fd | note | Method - Crushing Resistance Test (NZS 4407:1991, Test 3.10)
4f2133d9-f2d0-5e0e-bed9-2209eae77395 | note | Frequency - One test for every 10,000m³ of source material
9419bd1f-8875-59bc-8fbb-d9b14eefed69 | note | Responsible Person - Quality Controller
b05bbf10-117c-5f6b-bd00-fef3319c5c81 | note | Verifying Document - Test Report
298b46ee-dcaf-5340-9310-1a291c9be022 | note | Conduct - Sp or C or S
a0162858-8274-566f-b2be-61018a184eb3 | note | Produce Record - Sp or S
63d15a08-6e69-505b-ab8c-3fbc64ae0e9b | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
06dd8ed3-8215-5ce1-a384-d1091cd1bf22 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
a8d06f1b-1188-502d-8475-1587955a873d | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
9073d09f-7744-5c91-8aff-da05b6d7c2dd | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
79880d02-44d0-5656-b4d7-baa0dac14f50 | note | Frequency - One test for every 10,000m³ of source material
e8cff594-63e4-5d32-aba4-2549318ec597 | note | Responsible Person - Quality Controller
8a9335fe-caad-5217-8c02-2673e9693e80 | note | Verifying Document - Test Report
c1d07b46-e857-5f0b-af9d-22606a6a56b7 | note | Conduct - Sp or C or S
8f24f283-df72-5c40-a8f9-3c1f619da15a | note | Produce Record - Sp or S
bfd7922d-bcf5-57e4-ad4d-8527f8cf1040 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
953edb9c-1271-5d78-a81e-0bc5b69e791b | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
78eea177-3ba3-5f62-a1c5-9f13a40c20be | note | Acceptance Criteria - Soaked CBR ≥ 80%
1c50bc02-e4b0-56a2-b5d7-cc75615e1db7 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
4ecfb879-8902-5e2f-bc10-0ac57e0281a9 | note | Frequency - One test for every 10,000m³ of source material
f098b587-6ec8-568f-8005-2d7df56636a6 | note | Responsible Person - Quality Controller
7dce3131-e0b9-5160-9f04-1258d51ff955 | note | Verifying Document - Test Report
f9d14cbc-db7c-5dcc-96df-eda5bc57ac10 | note | Conduct - Sp or C or S
b21baf79-5fe6-5349-a154-4cf2e4740665 | note | Produce Record - Sp or S
7d4e62c1-5703-5f39-a11d-e8f29b9a929c | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
2762a5d3-9099-5c3d-985c-e843c6a2cfaf | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
b4284f5b-c509-593f-b57a-860b1741d0f3 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
b3cebe74-4405-552f-918b-f14026594fde | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
671d66c7-584b-50e7-9ec9-bb0a1d738a63 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
7cb9cdac-471e-57e3-9b55-5e935095069f | note | Responsible Person - Quality Controller
5b3a68f5-fed1-52e2-9591-fb364c032d37 | note | Verifying Document - Test Report
4577c329-f545-5cc6-b7fa-822d8aba5524 | note | Conduct - Sp or C or S
310b697d-7219-5efc-bbc6-adee83eab078 | note | Produce Record - Sp or S
6fa6bc0c-371d-5c59-99da-2773993162a3 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
00fb154b-fd34-5db4-b38b-81718cf37bee | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
a423e781-6d3f-5767-9031-1122125851b9 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
bcf57a08-bdfd-557d-8e38-8c69b34d0737 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
a2f414f1-c60e-5382-be35-73f097512711 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
fc52479e-255d-5fa1-97cf-71f15a28e8ce | note | Responsible Person - Quality Controller
ff076281-7c4f-586a-90cc-6a7bf74b3cd6 | note | Verifying Document - Test Report
8cbf8cbc-be2e-5aa9-bfc3-f5b4021e0fe5 | note | Conduct - Sp or C or S
7729decf-f1f8-58be-8d71-5a9575f6b371 | note | Produce Record - Sp or S
db1b93f9-b10c-5e01-8f98-f8b48d53697a | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
b0a2b6f1-f25f-5b41-9b1a-32500a54031d | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
53d381b3-f5af-57b0-9192-2f421bfe87d7 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
c7073bd9-2554-540b-87a5-9ce850a7a3cc | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
59ba12fa-5c9c-5fe8-a5b3-c3df4c80b4a1 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
d029d5b6-135d-5b73-be9b-aa9e64292655 | note | Responsible Person - Quality Controller
fc06a82e-9228-5368-aafb-bbbb82e9a474 | note | Verifying Document - Test Report
795f5ed6-b7eb-5f74-8143-7d92cf8b489a | note | Conduct - Sp or C or S
7e17bb30-b13d-54c2-8bd4-caadf34c8a10 | note | Produce Record - Sp or S
4d954167-3e35-5dce-af8e-2e79a0397929 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: Cement - Stabilising Agent Selection
2a3c237c-ef68-5cce-aba7-32611c828800 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
b7b9543d-83e5-5f25-8ab2-ef7977547654 | note | Acceptance Criteria - GP
6c90e117-f77a-53ba-9285-1a09cc2c8511 | note | Method - Visual inspection of supplier docket
97b045ea-2413-5361-86f9-73043020a176 | note | Frequency - per truck load
614c1ce2-37dd-5ccd-830b-9a58e5786d52 | note | Responsible Person - Quality Controller
f4030a20-6178-56a6-aa77-9a286df7a625 | note | Verifying Document - Supplier Docket, Supplier Cert
2ad73def-269a-5cc5-bcea-cb65c557cc89 | note | Conduct - Sp or S
0060a935-6644-54b8-aae7-aded1760ae1a | note | Produce Record - Sp or S
e83e582e-726f-5a8b-9cea-e8a9233f8fc0 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Water - Water draw for stabilising
05607bbd-8f47-5692-834a-aae906fa10ca | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
10de6da9-d480-5489-9342-0e49197ecb04 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
b080a6cc-c0cf-511c-9779-53cc50c31a48 | note | Method - Visual inspection of hydrant use form
75f1cbe5-0cf7-5ca5-9e4c-f0f8019cf399 | note | Frequency - per truck load
4d392614-a24f-5ae7-bac1-8a3ac872f23e | note | Responsible Person - Quality Controller
3b010b68-a302-5d6a-a978-140f676c0880 | note | Verifying Document - Hydrant use form
8d47db80-ee99-509a-909d-7d4cb9588c78 | note | Conduct - Sp or S
373509b3-ad69-5f28-b981-d500b4cea0ab | note | Produce Record - Sp or S
8f49526a-25c5-5ab8-8cb6-0a6d2dd82678 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
b2fc08b4-9be7-5736-8ab5-8cd0d898f0f3 | note | Controlling Documents - TNZ F7 Specification
db45667a-97e1-550e-b2a9-9eec7893cbdb | note | Acceptance Criteria - Details on Docket
06f6d29e-4d3c-5149-ab79-2cb19a4b54bf | note | Method - Visual inspection
b911f617-093d-5cc4-9601-5cfd3135912f | note | Frequency - Per Delivery
bbad6c22-85ca-54e8-84b5-a8bb678f51f9 | note | Responsible Person - Quality Controller
28550950-c888-5f2a-a1ed-1e43d4e693b2 | note | Verifying Document - MDS
f98c2c0c-3515-5b33-a7a8-fe90ca497519 | note | Conduct - Sp or S
d614bf99-0b9d-5da0-987b-035bb3893247 | note | Produce Record - Sp or S
b359d531-55a3-5755-8369-c38bf38bc521 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geogrid - Geogrid Triaxial Tx160 or similar equivalent
2831cb4f-1c84-50b6-81ac-e4e797042ce6 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
0578ef82-291a-5691-9c2e-f3dc1b7eaba6 | note | Acceptance Criteria - Details on Docket
e9c20ffa-a7f0-55c0-98f5-bf05f16da759 | note | Method - Visual inspection
4b32913e-3359-59fb-972f-094a3e3f3eb9 | note | Frequency - Per Delivery
859cbbbb-7973-537a-873b-1e03cc188949 | note | Responsible Person - Quality Controller
0c59c444-712c-5da3-a9bf-442e39bb91a1 | note | Verifying Document - MDS
04a28586-c108-5e8c-a126-aecad101a7da | note | Conduct - Sp or S
51caf911-ca9f-5655-a334-740398165194 | note | Produce Record - Sp or S
9b91ee47-dfd9-566b-86fb-a18d5e295a60 | note | Approval - C
| signoff | HOLD POINT
| section | 2. Pre-Implementation
| checkpoint | Production Testing of stabilised material - OMC/MDD
3a92f546-a256-5b60-b341-345b753b120a | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
3b984458-dbae-5ec3-93f9-4df471d571ad | note | Acceptance Criteria - To obtain OMC & MDD
dd401880-1d05-5c88-bafd-ce82b67d7898 | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
fa2bd936-f160-5154-ba66-4343bc391a78 | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
ecf82e1f-3ea7-5921-89b7-4fd3bd788054 | note | Responsible Person - Quality Controller
9cd66cbb-dc2d-52be-84a1-d470c6acf6ba | note | Verifying Document - Test report
e1d5b399-b22a-560f-9f20-4980f8830347 | note | Conduct - C
ba36469f-95d4-5cb5-9de9-9b3ba5397251 | note | Witness - C
158b0e83-785e-50ee-8ca8-12ce5dcdf131 | note | Produce Record - C
ec7e16c9-1cc7-55db-ad13-37c11a089bc0 | note | Witness Point - Y
| checkpoint | Production Testing of stabilised material - Solid Density
6fe6bf0b-a4db-50d0-bf79-f9f13fdcde28 | note | Controlling Documents - TNZ B/5 section 7.7
f6692b28-6d55-5f95-8e95-8b51bef7a0a5 | note | Acceptance Criteria - For info. and use in MDD calculation
e2465d13-ad62-5c12-9505-6650d2663302 | note | Method - NZS 4407; test 3.7.1
74b547fd-e69f-52a9-b764-eae051570473 | note | Frequency - Once on commencement and if any materials chage
0f861bc3-4203-5cfa-85a4-6f81b5d50ff2 | note | Responsible Person - Quality Controller
08b10c0b-d2dc-579e-8cb3-3ede7ff4ae34 | note | Verifying Document - Test report
9bc43fad-6c5f-511f-b3cb-4ca5a0522c55 | note | Conduct - C
142a0df4-f917-5451-853f-87ae078eed7e | note | Witness - C
aff5a204-12d1-5219-9986-d67d61461dfc | note | Produce Record - C
a5bfa6a9-9c50-503a-8d69-0d3e6aec201d | note | Witness Point - Y
| checkpoint | Project survey setting out
4776a337-8d4e-5b1d-8e70-a0e95d1a5f2a | note | Controlling Documents - Reference from Project Drawings
67cc5015-15df-5aea-aed9-7109f8408598 | note | Method - Survey/Mobile Roads, Marks with Dazzle
3f8ea119-8dfc-5cf9-9755-6de7a694b4b6 | note | Frequency - Chainages for every different pavement sections
bcebe894-054f-5821-9c15-7275917c7cf3 | note | Responsible Person - Subcontractor/ Engineer
04002e7c-7a7f-5926-8419-a16d9fe0cd8a | note | Verifying Document - Construction drawings
3ff90d19-69d3-5143-af26-8ce739bfe776 | note | Conduct - C
731c5bbe-dbdc-5750-a91f-a05598a9e0b6 | note | Produce Record - C
| signoff | HOLD POINT
| checkpoint | Records Management (i.e. it is known what documented records are to be kept)
0d044366-5c29-5b42-9d38-51ea0672e29f | note | Controlling Documents - ITP and QMP state what quality documentation is required
fa6f947a-77fb-587a-8bee-c92071fc78d2 | note | Acceptance Criteria - Filled in and Signed ITP
0f605ef6-788a-55e3-9e97-b10b66dcbc33 | note | Method - Visual inspection, recording and approval
55721af6-900b-50de-b406-3a98716e1784 | note | Frequency - As per hold points in collaboration with the programme
e795b0c4-7bbc-59d8-995c-626e123730b3 | note | Responsible Person - Quality Controller
46bb97a4-2c36-5006-9a5b-0e9aa133235d | note | Verifying Document - ITP and all referenced documents
fec95226-7dad-58f9-b588-07ce3e8f67ec | note | Conduct - C
9130da10-e077-5477-898a-7d6e8b1e6b9f | note | Produce Record - C
a4b6cc18-ff64-5b17-91fa-c33293f6b612 | note | Approval - E
| signoff | HOLD POINT
| section | 3. Construction - Pre-treatment Digouts
| checkpoint | Pre-treatment Repair Method Selection
8539f7fb-2e29-55f3-9a83-a7a366ad80d3 | note | Controlling Documents - Site specifics to be confirmed
49f4549e-cf2d-5ce5-8304-2dfdad3c6bf4 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
e83de189-4024-5f30-a46d-3bf75b52abe0 | note | Method - Scala Penetrometer on Excavation Floor
b39cf101-78b7-5b45-932d-ba461535ab33 | note | Frequency - As required
43ca5b07-b75e-5a0e-a047-158aa7381924 | note | Responsible Person - Quality Controller
348a8ae3-9398-551d-9c97-cd8f1d93902b | note | Verifying Document - Agreed treatment plan
66d32c05-2e2c-57a7-8866-64b9c273b6ca | note | Conduct - S
7e49c167-e806-5d12-9ffb-363e2a4c1363 | note | Witness - C
361a8d19-3957-5767-bb06-98b7ed392587 | note | Produce Record - S
a025f2f9-ad34-53c0-a6d6-9abed472b333 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Excavation floor drainage
3a91885b-c313-5bfa-898a-04e8d03736a2 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
1a6826dc-5765-52db-9e7e-225d389e6518 | note | Acceptance Criteria - 4-8% toward edge of seal
39995bc3-c907-56cb-9049-2f2f44284039 | note | Method - Digital level
5005946a-51c7-5d17-aa41-93fde74daad2 | note | Frequency - As required
f40c3b0f-d755-5338-ba8a-6c1d19607745 | note | Responsible Person - Quality Controller
4971c1b4-eca8-55d6-9406-c2f7aa706817 | note | Verifying Document - Dig out QA form
f4f70056-3a05-5c65-b371-2d904f780210 | note | Conduct - S
d66aa060-abae-59a8-a47e-b22de05d0877 | note | Witness - C
d34f04a4-989c-5dd5-9410-8fc7ef399ea7 | note | Produce Record - S
fee393aa-20fd-563f-ad5b-cb07a0b1fe79 | note | Approval - C
1ef49507-a4f4-5efb-b2b5-a49db05601bd | note | Witness Point - Y
| checkpoint | Subgrade material hardness, Check base of excavation
2d220406-dfaa-5279-8def-64a83269bd8b | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
0d07e8f7-8d0a-5e39-afa8-4a6783ffe20e | note | Acceptance Criteria - Scala > 3 blows per 100mm
e3cb9bc3-a0c9-5a4e-a5cc-2aeac326fa43 | note | Method - Scala Penetrometer test on base of digout
c4a6888f-8bc3-5db9-9ca2-41bf221338a7 | note | Frequency - As required depending on size of digout
91c7a770-b481-51ec-bc06-a6b4d45b0af5 | note | Responsible Person - Quality Controller
e151bc5e-bfea-5585-a970-892161ecb3e7 | note | Verifying Document - Test report
7b90cdb4-95f9-58c8-ba30-39c5f19ceade | note | Conduct - S/C
f5f5bc7e-bff5-501a-aec5-dc971f5ba376 | note | Witness - C
e7a84aff-81d9-553f-bbe1-15b4efef095c | note | Produce Record - S/C
253c5094-1726-5c8d-b301-60a75ad626f2 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer
4e60cfbc-e925-5111-b3f2-5ce56928c5ec | note | Controlling Documents - TNZ F7 Specification
e04eefbd-1b7f-51e7-813e-8dc5908efebe | note | Acceptance Criteria - Meet TNZ F7 Spec.
cf7a55b0-f194-5b70-b1b3-83a2be0adf11 | note | Method - Visual inspection
e75efdbe-5d6e-56d9-93a1-d19337053fd3 | note | Frequency - Per Delivery
0f43f564-afce-537a-b1e5-e579608eaaed | note | Responsible Person - Quality Controller
5eb6ce23-8e97-5f23-b465-a386e2b975b3 | note | Verifying Document - Certificate of conformance
aea4dc75-f4c5-5180-80ff-bf7403dd7593 | note | Conduct - Sp or S
baa8362d-0da5-5305-ad74-7b1878b98a49 | note | Produce Record - C
cbacca88-a269-5581-944e-074fcc048bd1 | note | Approval - C
2d30d709-3b16-526f-96c1-d6559e57fd2a | note | Witness Point - Y
| checkpoint | Geogrid Triaxial Tx160 or similar equivalent
190816b0-f21d-5db4-a4bc-92c16064d043 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
34483fae-ac07-5fbe-9f7d-b582a82d4144 | note | Acceptance Criteria - On the list of approved materials/suppliers
72a98bde-11d6-53bc-b4ef-3cd664a93d61 | note | Method - Visual inspection
64cffc73-c76c-5a72-a398-ecc0befbfaf0 | note | Frequency - Per Delivery
f115d721-0e6b-533a-be22-2546e123c60c | note | Responsible Person - Quality Controller
7eedc625-e00f-5cd4-a813-98412c50314c | note | Verifying Document - Certificate of conformance
ce0116e6-5aa3-5a58-9534-7ba95b84d5de | note | Conduct - Sp or S
a67e341d-6d36-5b4f-93e2-7ccea3d0974c | note | Produce Record - C
95f2e955-62df-5468-9f40-5075d0e60f87 | note | Approval - C
92bd01d5-9b40-56da-a4b4-25159edb7d0f | note | Witness Point - Y
| checkpoint | Place and compact GAP65 in digout area
23f14734-1c1f-5ffa-91cb-5a8f8d489e94 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
5777b746-5249-5160-b980-887f7f833fdb | note | Acceptance Criteria - Clegg > 45
f0b84a97-15da-5b99-9600-07625113d2d5 | note | Method - Clegg Test
f52337e9-22eb-5b0b-966f-2e153cac032c | note | Frequency - Min. 2 per digout
0f51bd8e-0a3f-570f-8392-0318be3b2111 | note | Responsible Person - Quality Controller
be577a4e-fe5f-555f-89a0-b736ac110e20 | note | Verifying Document - Test report
4804ffe4-c2fb-59dd-bc6a-3dfc2b2fc071 | note | Conduct - S/C
f1cdfc31-3b4d-5fb6-83a8-3c7e80067938 | note | Witness - C
68561996-425f-5c5a-bd8f-80bbb479e9ee | note | Produce Record - S/C
336c74c1-d521-5d22-8a12-3bd6b573c63b | note | Approval - E
| signoff | HOLD POINT
| section | 4. Construction - Granular make up and In-situ Modification
| checkpoint | Place M/4 AP40 Basecourse Material
3685c99f-6912-5592-874f-95e1f723a4d6 | note | Controlling Documents - TNZ B/5 (section 7)
de3b03f3-97a4-52d8-a098-58b802921a26 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
cd2f8259-9b6a-5b0f-b7b2-b3f436f8bd2e | note | Method - Visual Inspection
126ab04f-6e86-5dfa-a2a9-598169766e55 | note | Frequency - On completion of placement
1f48589a-cb37-5e1a-9878-f7594f804e42 | note | Responsible Person - Quality Controller
145ae7f6-24e8-5d2b-9609-9ce21af137ac | note | Verifying Document - Photographs and Daily Site Record
8f1aabcc-2f71-599f-b8fc-ad608275376d | note | Conduct - S or C
6e99a8b0-4e4a-5660-9845-a307763db932 | note | Produce Record - S or C
32f05d16-c6f2-5156-af98-bab41682acab | note | Approval - C
89ee5a6b-ad71-5121-9a50-f359ae836089 | note | Witness Point - Y
| checkpoint | Spreading of Cement
0f91d731-0d03-5332-b2ce-bbaad43747f2 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
d95dec9d-4ae6-53e0-b666-0310069cc325 | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
a37ffcea-21df-5421-aefb-0693592ee09d | note | Method - Mat test (1m² canvas) and Average Usage Test
6d0f2692-6903-50f7-ba9f-a1e68284de30 | note | Frequency - per 400m² and upon emptying the spreader
0981c20f-f8f2-598a-89e0-d978343cd230 | note | Responsible Person - Quality Controller
e87c934d-5b3a-594c-b959-5d0daa581d93 | note | Verifying Document - Mat Test Form and truck dockets
7778cb01-01c1-52df-865e-2289d30aee78 | note | Conduct - S or Sp
f399c103-86bc-5262-bb5a-73fb1c2a56a8 | note | Produce Record - S
504889d0-1ce6-5763-b3b9-a41e58550656 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Addition of Water
610bdf3e-f0ed-5cfe-8c38-4ed6a94e843a | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
3314dd13-00f9-5215-a36f-5c3b12eb4e92 | note | Acceptance Criteria - 90-100% OWC
44e71db8-f1c3-5b77-8044-74fb3fc08016 | note | Method - Nuclear Densometer Testing prior to Stabilisation
9052690b-2085-5bf3-a92b-bd79d9a4648a | note | Frequency - ≥1 per 1000m² lot
7609d261-e11f-5a5e-85ea-c9136f668a64 | note | Responsible Person - Quality Controller
837aa8c6-34d7-5826-8b13-93e7dbf227ba | note | Verifying Document - NDM Record
83a4da09-f8b8-53f0-9f3f-23733fc2391f | note | Conduct - S
23868bea-11f8-54c5-8b88-8d832afc70fe | note | Produce Record - S
ebd823e4-5a5e-50f3-849c-3ef948037902 | note | Approval - C
2f8c8a13-79c6-5f6b-a9f9-815ea0f72133 | note | Witness Point - Y
| checkpoint | Cut Depth
863b1dfc-20c8-5878-8ef2-8873432e6342 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
2d46c89c-6445-5541-8b02-05834deef059 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
082a103c-2d27-5665-bcfb-f7d2d3f4b820 | note | Method - Physical Measure and Visual Record
f032c68e-8067-57e6-8b99-78a8e1bac28c | note | Frequency - ≥1 per 200m of cut length
de42f92c-6a65-58bc-b936-2be6dcb5e442 | note | Responsible Person - Quality Controller
80ff9df0-28c2-518e-b6e7-a1dca15786f7 | note | Verifying Document - Photographs and Daily Site Record
d8d81c72-1997-5247-90d0-c2138bac14a1 | note | Conduct - S
4ef5cc0d-0338-58e2-b64e-955ead12b642 | note | Produce Record - S
b53882ff-87b8-583e-b585-33b390562b41 | note | Approval - C
aa0f6a28-93a1-570a-8c4d-03653672eeba | note | Witness Point - Y
| checkpoint | Longitudinal Joints
2cd5317e-a0c5-516f-9421-da8da74f942f | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
fcb956da-e48c-5218-adf2-111d48c714aa | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
37a4d49d-ac3c-5cf7-80eb-b7c7efecfaab | note | Method - Visual Record
b3a52142-cced-57ba-8d8d-5ec6db8523a1 | note | Frequency - per sucessive cut
59d4cbe6-163f-52d9-8abc-fcd6e72e5c59 | note | Responsible Person - Quality Controller
8ec4503c-8fec-5585-9fa0-8c23a76ed0f8 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
67b7d0b8-2b7b-5c5f-8675-1b7c9c3ebe9e | note | Conduct - S
ddee0120-b6fd-5c30-ace3-1d23ca2f5219 | note | Produce Record - S
0b395627-9094-5457-9124-07b6390c6577 | note | Approval - C
aa45e9eb-b4a6-5e94-9eb1-7998cdbfcd95 | note | Witness Point - Y
| checkpoint | Continuity of Layer
157fbffa-d403-5249-a034-4ad4b6df8cd5 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
2df69900-8061-58dd-9358-20b2a0c09c26 | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
c6aa3241-1591-5f66-91c9-3210f5b9d928 | note | Method - Visual Record
493d9de5-7bbf-5dd1-ac76-0cbe648591cd | note | Frequency - per sucessive cut
f5f0fb2d-9c00-560c-9510-46555f99e067 | note | Responsible Person - Quality Controller
5d08f7c0-2d3b-5b99-8502-6509ff5bfec0 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
afdaec16-8ce0-591f-9cb0-fee50f936721 | note | Conduct - S
16f5b835-c943-5781-a6ed-791f5d5a874f | note | Produce Record - S
b5aa2f56-601a-5234-989f-c90b4c0444ff | note | Approval - C
fbad2d9f-bec1-55fb-89e8-568009e8af9d | note | Witness Point - Y
| checkpoint | Stabilised Material Particle Size
cdbea8fb-f8c3-5276-a34d-57f6dc4775f6 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
3e7e47b4-e147-5589-83f9-5c0fb6186c24 | note | Acceptance Criteria - No excessive breakdown of stabilised material
283943ca-9738-54e2-bdcf-43213e818a91 | note | Method - Visual Record
56aaad7b-7c20-50a7-9a08-28d9693313eb | note | Frequency - within 20m of each section and then regularly based on material variability
df7a3502-45c7-5a2c-bd7a-3946bbee8077 | note | Responsible Person - Quality Controller
ae4dd630-4b45-5708-95ae-105d728b45ac | note | Verifying Document - Photographs
af14383c-e67b-5d3d-ae78-361fa824e2e5 | note | Conduct - S or C
d3605879-cc5f-5b13-9e9c-5b00a1097aaa | note | Produce Record - S or C
abe1d4d3-dfed-510f-aae1-cc4c49aa12a7 | note | Approval - C
25ce2100-a389-531c-a0e5-bcda7ee351d6 | note | Witness Point - Y
| checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
c3ab32e8-926f-5492-8084-efa63c6678a5 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
e412d153-ef61-5bef-ac3c-4009fb9e51ee | note | Acceptance Criteria - To provide MDD for NDM testing
f1be30c3-7162-54e5-94c2-544e0e43eb0f | note | Method - Plateau Density Testing
b92a7ba0-1c73-5972-b61c-c2f80d8f4167 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
54c63c44-bfb9-5f2e-8ccc-f2e4d937e957 | note | Responsible Person - Quality Controller
5d410623-ae3b-5592-928c-3aa07310a528 | note | Verifying Document - Test Record
c8e43763-a103-56c4-8078-0e8ce566232e | note | Conduct - C
f36d4763-3383-5e11-a6b6-28ae717b27b3 | note | Produce Record - C
84e83b41-8cc1-5dc2-8b80-675e1cecb46c | note | Approval - E
614bb2af-e799-5ac1-bc4c-1fdb8b8b1504 | note | Witness Point - Y
| checkpoint | Establish Compaction Target
b18695ae-cd5c-5fc9-9c4a-5f5618457bfb | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
5c5571ac-748c-5c8c-9fdb-b58808a9463b | note | Acceptance Criteria - To provide MDD for NDM testing
3e7e32a0-964d-5db1-b476-71e4f3e3cdda | note | Method - Plateau Density Testing
f329b1c4-d3c8-5b2e-a640-d71de2e55525 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
a0d0aa82-e1b9-5796-b78e-55763c0fc7c5 | note | Responsible Person - Quality Controller
424faefe-adcd-575f-82f6-ea2eddbd8813 | note | Verifying Document - Test Record
6afa53fe-f0ac-5f33-b8d5-b95149bceb4e | note | Conduct - C
300910c8-133a-5e09-9bec-a5776f54988a | note | Produce Record - C
98f494a5-8de2-56dc-b4a7-c34b8f424c55 | note | Approval - E
bf3642fd-1816-54c0-8000-05f69b5fcd38 | note | Witness Point - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
d1c42048-3587-5eae-a7e7-c9ead2b3214d | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
555fd9ce-308d-58e7-b021-c17560b04e9b | note | Acceptance Criteria - To provide MDD for NDM testing
460a95cd-66b3-516d-aef7-c87290beedbc | note | Method - Laboratory MDD at OMC NZS 4402 test 4.1.3.
3d177c24-58a0-5d59-905f-1a8a4d98df03 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
efa1a722-3921-53f2-a4db-0b8543593d1c | note | Responsible Person - Quality Controller
a4ea4672-69ba-5b54-9a3b-1c685281d225 | note | Verifying Document - Test Record
a4f5ee7b-a5c0-54b3-997d-2261f958a372 | note | Conduct - C
c597fd33-db5b-5105-8a4b-c414bd15961b | note | Produce Record - C
f7f4b5a3-a1ba-5948-8ae3-fd582f68387b | note | Approval - C
900a213e-4eed-5ff2-8ff3-b12a13714bfa | note | Witness Point - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
e4319f42-8ee0-58e0-925f-d380e681a4af | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
b797564b-e516-5f39-a965-6d9047408519 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
d0df37cc-f668-51e8-8df9-5e6421ebfdbf | note | Method - Plateau Density Testing Lab. MDD
37a52d03-bf92-5997-ac10-ad1c3a21b6f0 | note | Frequency - At commencement of construction and whenever materials change
8b683196-8d2f-5499-854d-4e752c731b0b | note | Responsible Person - Quality Controller Engineer
ddd74041-c865-5313-8b91-974b765e25bd | note | Verifying Document - Notice to Contractor/ Notice to Engineer
6057e766-1b14-583d-b015-79252973427a | note | Conduct - C
2cb864ce-1432-5b71-ae5a-2b6338864c13 | note | Produce Record - C
0c03d074-42ae-59e4-bea7-33371370eaf3 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Compaction Acceptance
13188e0b-78eb-5e33-99f2-5640d2f03564 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
99469903-d382-5c38-9538-c65635cbabc4 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
b2382e15-67c6-5dd4-b2bf-b80db5e1fd83 | note | Method - Nuclear Densometer Testing
3cc1f3d1-26c2-5d43-965b-1bea7d835b8d | note | Frequency - ≥ 5 tests per 1000m² lot
4378f5c5-b34a-5518-acac-e3e8b5bc1052 | note | Responsible Person - Quality Controller
33d5edb8-d791-5590-abb6-42474eac4749 | note | Verifying Document - NDM Record
0511bb98-69cc-501c-9e0d-1c47499b903b | note | Conduct - S or C
4d5b223c-6c4b-524f-b346-d2bc9060d5a5 | note | Produce Record - S or C
54d382ea-873d-56a2-934d-4cd070639675 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Control Testing (if required)
01a52aa2-5513-5f1d-baba-a3d3f29908c8 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
93750689-eb4b-5af3-b56d-e239e1d28ed0 | note | Acceptance Criteria - Nil
ae548335-543d-57c1-9098-2932e1294a7d | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
5efe09f3-abe7-5be5-afb3-7aeaf32186ac | note | Frequency - when agreed with the Engineer
b24b0578-610b-5749-af51-c7768e224347 | note | Responsible Person - Quality Controller
07dcf0ad-2924-525e-9a54-74a32a1abd91 | note | Verifying Document - Test Report
2065b75d-76ac-5c17-9ae6-3c2bd912196e | note | Conduct - S or C
d2953614-d34d-5a39-b9ef-00ca12c28ddf | note | Produce Record - S or C
e33aa850-90d1-5102-9962-f7ae5e105047 | note | Approval - E
| checkpoint | Surface Smoothness
3ebca2fc-8134-5c73-a858-1bad700efd63 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
2aa6f5cf-a9a0-59ae-aa2f-d99b123c8bf0 | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
23506622-c931-5ee7-8ccf-cbabe3f50e6e | note | Method - 3m Straight Edge
e751e7be-aa3a-5570-801d-3d2a25ef15c5 | note | Frequency - during construction and prior to seal
7317ae95-a3f8-5da1-a822-8a9807da9308 | note | Responsible Person - Supervisor
4bcff4b1-256c-559a-b231-125a1fdd40d2 | note | Verifying Document - Photographs
fe78135b-b74a-54e9-b699-e4a0ab670c28 | note | Conduct - S
4c1d5b2c-ff1e-5f22-bce7-17d149078145 | note | Produce Record - S
032e2fe5-89d5-5739-af55-f25997575299 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Shape
958fd826-d539-505c-86b5-789ed34a32f1 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
19cff7e6-4af6-589b-9310-c4ff2de4396d | note | Acceptance Criteria - Between -5mm and +15mm
b3f93d83-3e84-5844-a346-2b74206bd229 | note | Method - String lines or Survey Asbuilt
f5af1128-12ab-5563-8cba-c9b4e9889ff9 | note | Frequency - during construction and prior to seal
944a6fa0-0f5f-59eb-8ac9-c623b8ab4a60 | note | Responsible Person - Supervisor
c6ecda17-d4e6-5ba0-8078-f7bfeb45d9aa | note | Verifying Document - String Sheet/Survey Asbuilts
d8f742fb-9cb3-5421-82e1-3dbcdab2a9be | note | Conduct - S
12957bb6-1ebc-50de-85c5-1268a0fb9c0c | note | Produce Record - S
be5de09c-8fcb-559c-a5ff-0b5e53baa3c7 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Cross Fall
7685927d-1af6-5b36-a3d3-3f7b15fc0c24 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
6b31eb61-faa1-5317-a63c-77c77b83b477 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
693a1ee2-186c-56cc-a538-87e483f5b98f | note | Method - 3m straight edge or Survey Asbuilt
27137ba1-e77b-59ba-b3c1-51bbd007e6da | note | Frequency - during construction and prior to seal
9ca0d1c5-868c-5fdb-a832-f2a2bed79680 | note | Responsible Person - Supervisor
aa56a037-fbe7-5661-9ffa-1f980a8fe926 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
31f122b3-04fe-5272-ae32-bcaf15b38cae | note | Conduct - S
58c9a68c-60c4-514f-89c3-2b12b179e983 | note | Witness - C
4b813e46-d7f8-5a89-8ecd-f04d3c6a5542 | note | Produce Record - S
35c96fea-8c17-590c-8019-b6a16804329c | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Finish
2fc7b51e-6d8b-5f1d-9938-27da54c5f4ab | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
b10e5a44-4331-5769-adab-6086674de128 | note | Acceptance Criteria - Tightly bound matrix post sweep
29171051-7b8b-51b2-b8e5-a5d01fbbcb7c | note | Method - Visual inspection
55201dd6-9264-5e2a-85d9-0babcff49188 | note | Frequency - prior to seal
f9fb7850-73eb-5812-b610-47a02e758e89 | note | Responsible Person - Supervisor
0f2390f8-2a6c-53b0-bce4-ea400bf962a2 | note | Verifying Document - Pre-seal inspection sheet
36b69f07-4ee4-53b9-a123-b9a211ea264b | note | Conduct - C
af9641ee-8403-5f9b-a095-a6e025c4998e | note | Witness - C and E
7aebfd79-0ecd-524b-a34b-01c1dd0f229c | note | Produce Record - C or S
1c75c775-72c8-5f1d-9c6d-43d36ba6b746 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Degree of Saturation, DOS
53a8107b-846f-51cd-b670-a687bd354715 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
12f120ca-0e08-54da-bd9f-0e5024152ace | note | Acceptance Criteria - ≤80%, however 65% is ideal
0fb4124a-4be5-5abf-a47e-88a178da8610 | note | Method - Nuclear Densometer Testing
e1425262-0814-5afe-bae1-0a966f0dac19 | note | Frequency - ≥5 tests per 1000m² lot
0258f03b-1189-5130-87d6-a9d5392dff93 | note | Responsible Person - Quality Controller
1edd4368-be02-5dfc-8003-c65d01a8a2eb | note | Verifying Document - NDM Record
0a26a54d-624e-5fdc-85be-a60565db613a | note | Conduct - C
b35e0d1a-64b5-59fd-b677-a810a13841b0 | note | Witness - E
f5571af6-25ce-5f6a-89fe-c451fc05aaba | note | Produce Record - S
28a97942-191b-502c-950f-9e21eba83218 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Roughness (NAASRA)
c93c8629-272d-538e-8c71-f69576ae35dd | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
a3ac5681-fa77-5142-a285-5ca5a1c3ba1e | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
9a11a3c0-36b4-5012-9ccd-e49f11a0caee | note | Method - NZTA Maintainence specification section 6.1.2
28f51550-c794-5e27-8113-7ada221e4255 | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
765bc6ac-b934-50f1-9ea4-96affd7662c8 | note | Responsible Person - Quality Controller
10beed81-2f1e-5774-8e38-83675869b7b5 | note | Verifying Document - Test Records
70beb6be-fc26-5038-8066-e0879c2218a0 | note | Conduct - C
b17ab2c2-1d77-557e-8910-115a71e23c88 | note | Witness - E
f152f48e-d1ab-57f3-8a2a-7c167f021d68 | note | Produce Record - S
06c86698-269a-5349-8e2c-278c7fa2f1f7 | note | Approval - E
| signoff | HOLD POINT
| section | 5. Chip Sealing - 5.1. Procurement
| checkpoint | Binder - Penetration Grade
11b50573-e9c3-5a51-b6c0-9ea55065cd4f | note | Controlling Documents - TNZ M/1
aeea2684-78af-5ae2-942b-d59a93ae062e | note | Acceptance Criteria - Table 1
db9f6e91-1fa1-5da6-940f-21327253d820 | note | Method - Property Test
a7ccb29e-0019-545d-a886-ed42de74df4a | note | Frequency - Annual
9bbaa313-2705-50da-af78-91944a7aa454 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
db7d1908-1d03-5d62-b059-57154a329d07 | note | Verifying Document - IANZ Report's
0a66f4aa-f461-5b5a-9438-2931b875171a | note | Conduct - C
618784dd-adad-531e-a5ec-cc9aac1e8a84 | note | Produce Record - C
ddf91912-2703-5c65-b8b3-cda240008d90 | note | Approval - N
f4eb6e6d-034f-5377-9b39-cfad8ca470c5 | note | Witness Point - Y
| checkpoint | Binder - Polymer Modified Emulsion
d3df5a93-13dc-5b7e-b239-4568b75ac2ef | note | Controlling Documents - Higgins Internal Specification
15c998ba-2376-521a-9c53-44c9a321418b | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
7f207c15-b99d-5993-a7bd-8cdb67cb0707 | note | Method - Property Test
0d88026d-b20b-586d-adaf-e4f5f3b66323 | note | Frequency - 1/100,000 litres supplied
758bea4a-8724-50a8-9396-7cdc59eac1cf | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
d092d59b-d5d8-52ee-8726-ea58df06094c | note | Verifying Document - IANZ Report's
98324aba-02e2-55ca-b1a5-5cd0dea4814c | note | Conduct - C
e739e655-6847-56fd-a65f-945024124da9 | note | Produce Record - C
29c3347c-ebd8-576d-be4a-e9d76314b8db | note | Approval - N
f9c0b1df-7a5d-5fea-bde2-6ee137935a95 | note | Witness Point - Y
| checkpoint | Source Property - Coarse Aggregate - Crushing Resistance
2ad54ccc-87d6-5ff8-8b44-e0a3e82386be | note | Controlling Documents - TNZ M6, RNZ 9805:2009
b46cec5c-0500-52ca-b979-a195769173b2 | note | Acceptance Criteria - <10% fines under 230kN minimum
43d3d3fd-d322-5e19-9cf9-061a7a7a0216 | note | Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
6dd25652-cd7d-544b-bf50-7f35b19325ba | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
954b2e3e-8937-5399-a388-9f2a3e554165 | note | Responsible Person - Surfacing Project Manager
d73667ff-d93b-5892-a11c-a92a8279b5bf | note | Verifying Document - IANZ Report's
831ab6e1-056e-5792-91a9-9ed88e5b0e5a | note | Conduct - C
9827bfa4-4b38-5db6-af0f-b8fa4a395ac9 | note | Produce Record - C
bba9696b-4f12-558b-8165-1eac1c27697f | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property - Coarse Aggregate - Weathering Resistance
b259a287-6f93-51e9-bbee-af1c75696e63 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
a6094176-d1a2-51dc-9ddd-51a19f1bcab6 | note | Acceptance Criteria - AA or BA
864dcb1f-a14b-5547-b55d-0875929b435f | note | Method - Weathering Quality Index NZS 4407 Test 3.10
fb8ab532-a016-5b2c-a0cf-5c6727d31300 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
8a31594c-5c04-51ac-bd69-51d82a6300b5 | note | Responsible Person - Surfacing Project Manager
1d9bb3c7-2fce-51f6-afd9-41bf3e3963fb | note | Verifying Document - IANZ Report's
79269be0-d64b-5d17-b4b5-d22cad087c56 | note | Conduct - C
8ba542b2-9548-5793-8f73-8af220b81358 | note | Produce Record - C
5c10d680-0a5e-58eb-8072-5777db98782e | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property - Skid Resistance
f785fdb3-48c0-59b8-804c-fbf58ca5021f | note | Controlling Documents - NZTA T/10
ea3c60a8-6c63-5d43-a8f1-2aad1ad1f6ae | note | Acceptance Criteria - Meet Skid performance Requirement
d37969df-d06f-5334-8f10-b92ce7c66a4f | note | Method - Aggregate Perfomance Method TNZ T/10 section 12.3
9503ad0a-7ac1-5087-9e44-22876f9f958c | note | Frequency - Each Site
0c59236a-376d-5a1f-b155-48d780784816 | note | Responsible Person - Surfacing Project Manager
f9a1d436-3416-5570-950e-dc6007ae8857 | note | Verifying Document - IANZ Report's
51419a51-e825-5119-88e4-e1e498ebd224 | note | Conduct - C
6bf9829e-f814-5e36-8971-c71d38fd61d9 | note | Produce Record - C
ffb149ac-75e2-54c4-a67c-7a19a96377e2 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
16d0f00b-a5ef-5595-9976-511f8f6bd63d | note | Controlling Documents - NZTA P/17, M/6
a5c1614a-6037-5b26-b47f-c7c6bae8f29d | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
25034e6e-f3bb-5925-a953-9f15a3d24f2c | note | Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
47d72a61-a242-50f0-8103-283dc647ee3b | note | Frequency - Per Stockpile
2d89a5fc-1914-5925-a157-53f1bd1a5830 | note | ○ <100m3 - 1 Sample
5a412376-036f-5eb3-9843-a6a399d6b5d7 | note | ○ 100-500m3 - 2 Samples
e7937aa9-de26-5d81-9f5e-f00913f56054 | note | ○ >500m3 - 3 Samples
5346ea20-910c-529a-a4ab-e8ce817da851 | note | Responsible Person - Surfacing Project Manager
3c737f2e-4914-5d09-8b4c-2bc990fdf333 | note | Verifying Document - IANZ Report's
32606881-cd0a-5127-b5af-cf33d55ad0ec | note | Conduct - C
5f49f499-596e-529c-96be-90136114112b | note | Produce Record - C
93568b30-13f6-5447-8b27-896f7fffd49c | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
a82545b7-6c86-5c52-91b8-465ce84e2993 | note | Controlling Documents - NZTA P/17, M/6
774421d9-e364-5e45-8b15-bbabfacdbc86 | note | Acceptance Criteria - As per Table 3 NZTA M/6
2d9d15ed-10e7-5eb8-8a32-48b8b1f6ed9b | note | Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
1610c344-b030-5755-ad81-76a19dc05c2b | note | Frequency - Per Stockpile
59b839c8-13d7-5144-8893-c16bca5e86ca | note | ○ <100m3 - 1 Sample
857f2c66-38d3-536f-90e2-9d0fbb9e1e5b | note | ○ 100-500m3 - 2 Samples
550d7e51-6009-5ae9-a1e5-f9ffeeafde60 | note | ○ >500m3 - 3 Samples
9f60971e-c95c-54d3-8048-04739712a6e7 | note | Responsible Person - Surfacing Project Manager
7d08c303-dffa-5da1-86bc-9ecf1bfd013f | note | Verifying Document - IANZ Report's
bb939b59-ceac-5306-902d-5312a6616bbc | note | Conduct - C
fafd0957-19ca-5522-b962-cddfd8064d6a | note | Produce Record - C
4d009cda-7778-5350-b97c-5df9dd150431 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
0ab3a939-e1ac-5674-a31c-93960092df43 | note | Controlling Documents - NZTA P/17, M/6
6bde34c9-c6c2-5448-9b8b-0a57ce37657f | note | Acceptance Criteria - Min. 98%
991963a6-56c5-54f1-8124-09001e0ad3b1 | note | Method - Sample Test - Broken Faces NZS 4407 Test 3.14
d24ed362-d184-5d27-b325-41f58443e53c | note | Frequency - Per Stockpile
058dd20e-3fb3-5e1f-9f4c-e05aec20d39a | note | ○ <100m3 - 1 Sample
1862fc63-1660-5588-8026-d18c10909f13 | note | ○ 100-500m3 - 2 Samples
9b7f46b9-6169-5a4b-bc91-67e3c6fa44f1 | note | ○ >500m3 - 3 Samples
9f11e34b-1bc5-5d2e-be72-80eb9b60cf49 | note | Responsible Person - Surfacing Project Manager
434aaccb-a66c-5afc-bacc-8074622afddb | note | Verifying Document - IANZ Report's
6826c0a6-0a4c-5486-a871-5b9a395682b8 | note | Conduct - C
ad206642-4c5b-5dc8-9bd8-3f785f31c6fc | note | Produce Record - C
90941f7e-070d-5e2a-9532-34e7a1655ca6 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Chipseal Designs
1a053b81-6c7f-55c5-8b9e-031a21136a40 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
29e4007b-cff7-516c-88b5-5245ca772800 | note | Acceptance Criteria - Client Approval
2517800d-0a5d-5cbc-80e6-ef92232f830e | note | Method - Review
66719ab1-d06a-577f-8dfd-e9f09c369d05 | note | Frequency - Annual
f6ce55e1-a4ff-5899-8544-89601e79e0a7 | note | Responsible Person - Surfacing Project Manager
3b1c5e9e-37d1-5c37-8be6-67283e039677 | note | Verifying Document - EBOP NOC Design Report Acceptance
51ee60b0-3967-5fc5-b309-eb37bf907a17 | note | Conduct - C
a53225c3-1be3-5f3b-9473-d71e6118c81a | note | Produce Record - C
95f31857-fd67-56a3-96fa-93fb8afb020c | note | Approval - N
| signoff | HOLD POINT
| section | 5. Chip Sealing - 5.2. Construction
| checkpoint | Ensure limits of site are marked
b577270b-c776-5fb5-a818-da7640734ffe | note | Controlling Documents - EBOP NOC Design Report
0723c899-a455-5565-bac3-dcd94120825d | note | Acceptance Criteria - Visual Inspection
af15cfbe-8da0-580b-8992-6b5f0dd33ba0 | note | Method - Visual
d09ceee7-2025-5ffe-8eb8-29f5d198487f | note | Frequency - Prior to start sealing each site
8a2c684b-b4d2-5e10-9be7-469850279866 | note | Responsible Person - Surfacing Supervisor
faf990bf-87ca-5c9b-9f9c-3f415c81376a | note | Verifying Document - Chip Sealing Quality and Site Record
5d83620c-ca42-569a-b8ff-a975e7954daf | note | Conduct - C
ba90f0b5-b416-5e16-824b-eac092418ba2 | note | Produce Record - C
fe8a951f-12a3-5150-a714-ea9a10c39d3a | note | Approval - C
c0a3dca7-6f70-5745-a32a-19c5dbc01c49 | note | Witness Point - Y
| checkpoint | Sweep surface clean of deleterious material
d92642e8-eb3a-5f60-a3f5-5f3afc8ef91f | note | Controlling Documents - P/17
e0788201-8a76-55cf-b168-29ae1a899d9a | note | Acceptance Criteria - Visual Inspection
3c95abd4-6717-5c81-b9b5-c8747b9ef497 | note | Method - Visual
9386946c-510a-5662-8cb1-9adcd6cefbbe | note | Frequency - Each site, prior to start of sealing
b8000a17-7ed5-5a1e-91f7-becfdcd5ca5b | note | Responsible Person - Surfacing Supervisor
ef6ac720-d58b-5c92-8136-837e523cafbf | note | Verifying Document - Chip Sealing Quality and Site Record
e7017769-4282-531d-b27c-2e5f5f4ca4cb | note | Conduct - C
4f5de56f-84fa-5414-bd69-7d704491f554 | note | Produce Record - C
0c4d8e9d-367b-5e58-9cab-569a928c7f2c | note | Approval - C
46f1734b-e135-5747-ab49-eb92fcc7552c | note | Witness Point - Y
| checkpoint | Record ATP's on site
cabd0cba-96a5-5182-9e38-67b73a167a9b | note | Controlling Documents - N/A
ca237597-6509-51f2-9cbc-838514b156ad | note | Acceptance Criteria - Visual Inspection
25be30a5-9661-5a93-bd59-d9127c5b7822 | note | Method - Visual
1cfaab34-2fc8-5e09-b56d-4765f8235a08 | note | Frequency - Each site, prior to start of sealing
37ed087b-c336-56fe-b03e-7df0ab3a1002 | note | Responsible Person - Surfacing Supervisor
7e024781-1356-5494-9221-ac6dc88f2d6f | note | Verifying Document - Chip Sealing Quality and Site Record
b239f41d-1b58-53d5-894a-ef0900465818 | note | Conduct - C
30169aa9-ff47-52c5-8d07-933a3ccd0c0e | note | Produce Record - C
169c1618-44e9-595b-8530-20322804bae0 | note | Approval - C
e9d6cb9f-b126-5054-a88f-dabd4a252a6c | note | Witness Point - Y
| checkpoint | Confirm correct treatment(s) and chip
4230a693-b1a7-5d05-b3ab-84a8e16ae178 | note | Controlling Documents - EBOP NOC Design Report
64b5e880-8d63-5894-b87c-65d82ad244dd | note | Acceptance Criteria - Details/chip correct
fb07c74f-b3dd-5a97-9888-e5dd02745112 | note | Method - Visual
2001fff0-727c-5593-848f-e5d29a2f63a6 | note | Frequency - Each Site
15225e4a-e662-5faa-9be5-9f4d5425eeaf | note | Responsible Person - Surfacing Supervisor
047b4ebc-44ff-568d-b557-58864e8e3dc5 | note | Verifying Document - Chip Sealing Quality and Site Record
c2e1bfb7-c6b0-59b7-95fc-21ff40d9b439 | note | Conduct - C
ffca6441-1f4b-5933-bdd7-b700498ae7b8 | note | Produce Record - C
4faf99ed-21e2-5d2b-a342-327d8a043400 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Cutback Bitumen Blend
5144e51d-52c2-5246-bb9d-3fda4b4b2734 | note | Controlling Documents - RNZ 9803_0513
45eca55d-e520-548b-9238-56db4742bbbc | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
4ec2fc5a-4822-5342-b7cc-107484a433ce | note | Method - Sample and test
e947f270-4af7-5244-b9a3-4734303ae768 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
18138025-1e6b-5a66-8432-5d13d0b144a6 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
8317190f-71e8-5675-9f5e-9592e800141d | note | Verifying Document - IANZ Report's
d2de796e-5a58-5a73-8c0a-8faccfa0cd11 | note | Conduct - C
28b2a1d6-4a87-52b0-9e92-b59f394041ea | note | Produce Record - C
ff899140-bd0d-5713-b108-5e6da501308a | note | Approval - C
6f28028a-12a2-53e2-b57a-d3cd5bbe1248 | note | Witness Point - Y
| checkpoint | Bitumen Application Rate
397e9783-80b3-5663-9cd9-7c55ec0f83f8 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
0b41ee69-c7b0-5748-876a-b7397e24bde5 | note | Acceptance Criteria - Current E/2 Certificate, +/- 4% per Spray Run
13374c60-2646-5801-882a-f6907839a0cc | note | Method - Test, Review
5a2dd7c3-c0e7-57e3-90ad-91a6356dada6 | note | Frequency - Per Sprayer, Per Site
bee5b11c-660b-5332-90bd-9a64138758f8 | note | Responsible Person - Surfacing Supervisor
647477ce-1fb7-5835-8f02-74d6f77bd23f | note | Verifying Document - E/2 Certificate. Spray Sheets
19a8c92f-eb40-52b6-b2a2-3b46f63e12d3 | note | Conduct - C
61ccd2da-f12d-51e1-a331-003874227ab4 | note | Produce Record - C
371a3400-4695-50f7-85b2-ac5133a40a51 | note | Approval - C
acc89649-2596-5faf-96a3-52105d81d834 | note | Witness Point - Y
| checkpoint | Chip Application Rates
6f0c4f3d-bab5-5017-ad26-ab9587427fc0 | note | Controlling Documents - Chipsealing in New Zealand
7ec99ef4-e554-5103-9255-41f0fc68209e | note | Acceptance Criteria - As per Chipping Guide
42d6bb26-4974-5f0a-ba2e-20aadd4f0ce7 | note | Method - Visual
f27557d2-2a68-50fc-b735-ab84684d39c7 | note | Frequency - Each Site
4cadf218-7e97-54ab-87ac-53399928e424 | note | Responsible Person - Surfacing Supervisor
c0245769-73aa-5128-8761-3a6749c65de9 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
1766cbaf-1079-5d5c-bc73-b1c185c22ebf | note | Conduct - C
136ba556-d242-5804-a4bb-e029dfefd6aa | note | Produce Record - C
3e435d9b-fc4d-5465-82bf-3ba1ec9da6c8 | note | Approval - C
a64c1474-ee9f-5ead-bc95-3bb11a250af9 | note | Witness Point - Y
| checkpoint | Rolling
c5371312-c7c5-5c37-a97e-cb9b9012a872 | note | Controlling Documents - Chipsealing in New Zealand
147cf08c-06ee-57bc-bd6e-fa52dcc24bc7 | note | Acceptance Criteria - Minimum as per CS in NZ - Bit volume / 3600
15f4108b-1109-5d09-a5aa-b84ff5593661 | note | Method - Visual
c174ffd2-6694-5314-a1e2-bb2cfce5eba2 | note | Frequency - Each Site
6742a9c6-47cc-5aa8-a8ec-b0151b3c9cc2 | note | Responsible Person - Surfacing Supervisor
4e663b18-4a58-5936-ad95-d2c7d7ba9210 | note | Verifying Document - Chip Sealing Quality and Site Record
4a742030-d11a-5597-8031-8e7077f9a201 | note | Conduct - C
4e06437e-4059-55b0-94d4-ac76d107d59a | note | Produce Record - C
79c53101-282a-5eca-8554-a67f02cda5a1 | note | Approval - C
80afdfe8-d7d6-5b07-b2f3-30722ead534f | note | Witness Point - Y
| checkpoint | Cleanup
5f5d3d2f-6d6e-50af-9bf5-8b6ad19ba650 | note | Controlling Documents - Chipsealing in New Zealand
fb5402e8-25c3-57ef-b509-06ad09ed06fa | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
3103f79b-8bf5-5bf4-b9db-f3398e6e15a8 | note | Method - Visual
2512af08-3783-5256-ad9b-5572db8a1cdb | note | Frequency - Each Site
a947bea2-cf0f-50cb-ba8d-b835ffda70f4 | note | Responsible Person - Surfacing Supervisor
1935d6ca-73bd-51a2-99e3-c29f7aac3ac6 | note | Verifying Document - Chip Sealing Quality and Site Record
1a2b25ee-21c4-5574-87f4-837f630b55c4 | note | Conduct - C
cecc5773-ba2b-5b41-9d61-cb7f24e187a7 | note | Produce Record - C
19129f93-4315-5d6e-96aa-a8d57e83f4a7 | note | Approval - C
1484dd74-e589-5572-8b58-30a6453b1867 | note | Witness Point - Y
| checkpoint | Post Sweeping
581b3d46-ca3c-5970-97a5-376b87631629 | note | Controlling Documents - Chipsealing in New Zealand
d15adef7-34f0-5172-a3a5-72e881750978 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
e9b48e0c-1399-53ed-b7dc-9b3b313b3fc2 | note | Method - Visual
d43f0b8e-407c-5bcc-9f30-9b74960ba2e5 | note | Frequency - Each Site
2c11c702-a145-5a39-aa00-83444eec3971 | note | Responsible Person - Surfacing Supervisor
3e59bb4e-b366-5fcb-b635-459a156da38d | note | Verifying Document - Site Record
652b5c9b-1dfb-5e9a-a8da-6877afe75dc6 | note | Conduct - C
9bef121a-b36a-51ea-a820-92b74aec30d6 | note | Produce Record - C
adac4322-1aec-52b8-8eb4-6b41c332569c | note | Approval - C
a5d66bc4-e77f-5fbe-9bea-00c70c57f106 | note | Witness Point - Y
| checkpoint | Linemarking and RRPM Reinstated
d0ba5490-2be8-599a-9702-31e0cb2ee480 | note | Controlling Documents - MOTSAM
97e36ed5-9dfd-50bf-b536-7e13cd771981 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
173d6bc5-4acd-5f1a-b4ba-4e96ffbff48b | note | Method - Visual
5c4d1f5d-8b46-544d-84b1-69bc04a2190d | note | Frequency - Each Site
efeab261-0c46-5155-a6c0-b4fc383b9c83 | note | Responsible Person - Surfacing Supervisor
10b1e687-6712-5943-a6f7-0d5c8675b2b7 | note | Verifying Document - Site Record
9abc7659-306a-5925-b15a-9e18544b131e | note | Conduct - C
cd989dee-b284-5b7b-9407-b99b53d42c68 | note | Produce Record - C
6522c895-f801-5766-a6d5-6813d945bae6 | note | Approval - C
82ba988c-b198-5a23-9530-64bd4038d848 | note | Witness Point - Y
| section | 5. Chip Sealing - 5.3. Post Construction
| checkpoint | Post Construction Walkover
7cec67ce-0184-576c-aed5-16f768318cb3 | note | Acceptance Criteria - Formal Agreement
96559bed-b43b-5a60-8a55-d9289e747cf8 | note | Method - Visual Inspection
fca354d3-e81f-5493-be5d-44c767a9ee07 | note | Frequency - Post seal sweep
d184e7c0-6996-5030-b984-1e0d1f233568 | note | Responsible Person - Quality Controller, Supervisor and Engineer
0bcd0ead-440d-5993-9066-5da85328445e | note | Verifying Document - Meeting Minutes
d49f6b21-1ea9-5213-9dcd-fe40c7f450c5 | note | Conduct - C
f00a61b3-d15c-5318-85d9-178bab2bd8d2 | note | Witness - C, S and E
fa71f380-433e-574e-ab1f-2ed52e7ad022 | note | Produce Record - C
428fb1c0-9779-5375-952c-fd024d5dc2e4 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Resurfacing Construction Completion report
ec68be8a-56f4-591e-b581-c7bf5416741b | note | Controlling Documents - NOC; MS 6.1.3
1431834a-2379-59e6-a525-7c4019b67f45 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
ee6956b6-7456-5479-b0e5-46a66c02680e | note | Method - Record
5142fc83-39c7-5cc0-8872-9d0a57819305 | note | Frequency - Within 2 months of completing the annual resurfacing programme
d3dd2953-115d-596c-bed4-8f747bc30d36 | note | Responsible Person - Surfacing Manager
1a6c6009-3d04-5b8b-bb82-9a775f8b8cb0 | note | Verifying Document - Construction Completion Report
5bd9d68a-25d0-5cc0-8a5f-58a681837e04 | note | Conduct - C
7420c64d-bbd3-5744-be3e-7dfb82bac8d4 | note | Produce Record - C
e7e3e57c-a100-56d1-b665-2655691190be | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Chipseal Post-Verification Testing and Report
eb2733cf-401b-5a50-b0a8-41f8366b1569 | note | Controlling Documents - NOC; MS 6.1.3
bf9fd620-2994-5e61-a605-8805cddc3f91 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
afbd19f3-e285-5ad9-baeb-f0dab2f0bd1c | note | Method - Record
982e88df-c7bc-5cfa-b32e-a0398de164c1 | note | Frequency - Each Site
188f5c9e-e357-5f70-ba0c-23ef24e72229 | note | Responsible Person - Surfacing Manager
eae58090-3522-5d69-94bc-04871f7c1335 | note | Verifying Document - Chipseal Post-Verification Testing and Report
5c3dddb0-4acf-571f-a1da-7a77f0896e77 | note | Conduct - C
828170e4-0eff-5417-9c0b-b4eb3ac73488 | note | Produce Record - C
055140fd-35be-53db-920a-7c4407b3f3a9 | note | Approval - C
| signoff | HOLD POINT
| section | 6. Close Out
| checkpoint | Pavement Rehabilitation Construction Completion Report
4e014987-681d-5c87-8752-cb47f766be70 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
3380f768-dbc6-54e0-9a5b-dd1ef396f773 | note | Acceptance Criteria - Engineer Approval
d55278b0-573e-5e56-94fa-c9df0b018f85 | note | Method - Visual Inspection
1de7f163-1dfa-5dd8-916b-95cadacf1083 | note | Frequency - ≤2 months of 1st Coat Seal
2262ad5e-ddb5-57ac-b806-a0d5eee9d901 | note | Responsible Person - Quality Controller/ Contract Manager
a5c3a535-1756-5b2a-8534-37afc4f6db6a | note | Verifying Document - Signed Report
2a424a31-771a-5c45-8490-f3b91c88d392 | note | Conduct - C
65d0a40c-49d5-5319-9c0f-a8e313db9828 | note | Witness - C, S and E
b9a443ea-412c-51b4-b501-560d16e9b04b | note | Produce Record - C
745795ed-0580-5905-a4d3-db0db261b7fe | note | Approval - E
| signoff | HOLD POINT
| checklist | ITP - Pavement Rehab - SH 2 - Omeheu Drain to Canal | itp | ITP - Pavement Rehab - SH 2 - Omeheu Drain to Canal | ee86c0fa-257c-4579-8d03-7470719d7b4c
| section | 1. Procurement
| checkpoint | Geometric Design
37710344-6b0e-5222-9125-65fef8367e4b | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
41910ccd-0de3-5082-8609-cfdae685ca06 | note | Acceptance Criteria - Principal Approval
2ef1bb96-3056-57be-a5c3-e00dd9e46944 | note | Method - Contractor and Principal peer review
42693430-4ca6-5b41-9d13-b3d8dd47974c | note | Frequency - per design revision
ebe9919d-f7d8-5dd6-906a-b7bd4c6c3ac9 | note | Conduct - C or S
f83d7335-86db-584b-995a-2e71bebc765f | note | Produce Record - C
201d2a15-7b94-5714-b6d1-3c49afbd7271 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Pavement Treatment Design
fc84ac02-5ce7-5b53-ac63-0743acd88297 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
efb1c352-75ba-5ec6-9fd8-243b771ab6fd | note | Acceptance Criteria - Principal Approval
d2f8561e-34f0-5bf1-ab02-f00da523b22c | note | Method - Contractor and Principal peer review
69d68b0a-500f-5392-a229-7e4bca85efb8 | note | Frequency - per design
4c792240-0bb4-5575-bf56-3e7de871ecd9 | note | Verifying Document - Approvals Register - SH30 Frosts - Pavement Rehabilitation Design Report
2bdb1f0a-f32d-51a5-9f1a-15a5ef9f7ca8 | note | Conduct - C or S
d3ec347f-d984-5844-9328-288f75cf5bba | note | Produce Record - C
adf2c6ff-ada3-5e70-aa13-418ee999fec5 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
7cfbf798-abdc-5042-a71d-4d88115b03ac | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
9e224743-d8ee-58e7-82ac-cd0ee556d768 | note | Verifying Document - Sampling Worksheet
cca6495c-fec9-5202-80c5-c3267a2a2dcf | note | Conduct - C or S
93489cd9-f65a-5a2f-a960-5a911029fcf4 | note | Approval - S
| checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
6bf8cac2-d17c-5105-9e4e-d0d06c2d60f9 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
6e2754d1-3d7c-5064-8759-054978f4e8e1 | note | Acceptance Criteria - Soaked CBR ≥ 40
ced7bc25-6998-55b8-80cc-c9287f1c9d61 | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
061ac942-79d6-57b9-a961-0d318e29a1bb | note | Responsible Person - Supervisor
13fd5d6c-6c14-5338-9b21-161cb7788fac | note | Verifying Document - Test Report
0b090f84-7670-518f-815a-522e008e8dfb | note | Conduct - Sp or C or S
5c83eae5-03fb-5107-837e-da6699076890 | note | Produce Record - Sp or S
74c09e96-3dbc-5d77-aa9a-3fa883a67163 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
fdfde7f4-06f4-5762-b9c2-acf72b1e61c3 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
50f1c9d7-d13e-584c-9109-cb6f344b50ae | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
1bb30ea4-1975-597f-9c5a-c437685c2ac3 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
531a5c63-2be3-5fb9-ac22-b3bb7d8e98ce | note | Responsible Person - Supervisor
dcba20f1-c3b7-5df9-bfdb-6fcade62782f | note | Verifying Document - Test Report
8d35032d-e487-5a56-957d-fef36ca1c30c | note | Conduct - Sp or C or S
3e18d2bf-6890-593d-bf27-3fd7eefb85dc | note | Produce Record - Sp or S
eb4159dd-ee27-597d-bbca-324f03540ca1 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
ca49d654-b7e8-570d-acc1-3d36bc373cfc | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
6620f5c4-84ab-59e9-a2b8-01a24474eb3e | note | Verifying Document - Sampling Worksheet
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
df0d13e2-4547-5c20-b415-779a07150802 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
f8ddd7e4-3c7a-5d42-8461-dc6fd056bc2f | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
1287b521-7f05-531a-bf7a-b7505e4de0de | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
2b764bbc-1eec-5254-9050-c952588fec7d | note | Frequency - One test for every 10,000m³ of source material
dcab605f-2a3a-55fd-9d0a-a2cdee180cb5 | note | Responsible Person - Quality Controller
aebbfd91-9b7b-59f9-8386-a0211ecac834 | note | Verifying Document - Test Report
bc3c509d-801e-511a-9ac9-21db49f0aecc | note | Conduct - Sp or C or S
f995507f-6475-5c4d-ac3d-63f216b0b6db | note | Produce Record - Sp or S
8af7886b-1db2-5c1e-ad19-ff4d225156bc | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
fc295dd6-2647-598f-86ac-205402619b32 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
e71c92b7-15aa-5b34-8a5c-1542d4cd9a13 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
ae6363e2-0da1-5141-b09e-4d29e650050a | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
b8b276cf-4bab-5024-93ca-d16e4473b6bf | note | Frequency - One test for every 10,000m³ of source material
ce401bbc-c182-5a55-a4b8-b9d5635adadd | note | Responsible Person - Quality Controller
ec5b7f27-8947-52e4-8fb7-cbb6f3a8018e | note | Verifying Document - Test Report
e33c6b62-1a1e-5bbc-87a3-a9c7c168431f | note | Conduct - Sp or C or S
c50948ab-5b33-5728-a99a-d0a6315f8da2 | note | Produce Record - Sp or S
74c56a38-f593-5e46-89fd-bc750daa7a43 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
80ac6835-5d01-5d52-b341-846c87dd9ee8 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
e0d940c5-24a3-500e-9588-47066f18800e | note | Acceptance Criteria - Soaked CBR ≥ 80%
4d421a5d-7c03-5c0b-96cc-85500c24a346 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
220c93bf-5a0d-526f-8177-a832072d78d0 | note | Frequency - One test for every 10,000m³ of source material
d89e1aa0-ebb6-594d-9b32-945303b1b504 | note | Responsible Person - Quality Controller
1aa9c987-0729-5393-b1c0-a8ca2b3c3b09 | note | Verifying Document - Test Report
adab7c39-d16a-5e63-9982-03be20cea262 | note | Conduct - Sp or C or S
39de5996-b312-5c86-8729-2e19d2132ebc | note | Produce Record - Sp or S
23ba1596-521f-504f-9e23-106297b1e29d | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
0bc2dfd1-47e9-5447-885a-12edd0c93edf | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
d3fec3f8-69fb-528c-b3de-992d9eadc2a8 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
c97b9f4c-71b5-51ab-8fa4-4dd3288cefde | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
0e32550f-8bf6-59a0-b182-9b049559bc7d | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
bcd57154-a7fc-5df4-8366-c80e57534c61 | note | Responsible Person - Quality Controller
4ca04bd9-45b5-5ab7-b0d8-b914d04d558d | note | Verifying Document - Test Report
d3f3580d-ae46-56e9-b1d0-48a1739959a9 | note | Conduct - Sp or C or S
218e6d3f-d858-5f05-b0bb-ed43b7359de7 | note | Produce Record - Sp or S
ad9e5294-4d1b-57c9-86ab-45193f63efc6 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
e969939a-adad-55cf-b388-168bb45e31e7 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
5e3c29bf-0c9c-52a1-b125-7b81e0809993 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
989ef919-e617-528e-b49e-809caac25d3a | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
2c38a5e6-1416-5387-bac5-b812b863d964 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
96c4c41f-7fc5-5c2e-8527-575e08599407 | note | Responsible Person - Quality Controller
1a5ff827-9d33-5eb4-b79d-2214a0de84ba | note | Verifying Document - Test Report
d9ec3c4c-5c52-573b-8c82-228e160112a1 | note | Conduct - Sp or C or S
a4ad9c34-4e94-52e9-9d42-d20b5bf6a089 | note | Produce Record - Sp or S
d789144b-ac12-5176-a284-bf9a74bc6036 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
00180045-a01f-5c6b-8546-a2322789edf6 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
729fd044-6fa6-5063-b0f2-a28de363ea54 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
c8801cb3-b09d-5497-ab82-8e95bdea2b8e | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
46b31b4c-84ed-51f8-926b-6f734cca9f4b | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
d2632c29-d475-5a69-90ea-3170cb51301d | note | Responsible Person - Quality Controller
e799a3cf-0e25-5de3-8d40-df99c2b2068d | note | Verifying Document - Test Report
972ce80b-b102-5d17-ac28-c56624e5b14e | note | Conduct - Sp or C or S
4f25d4e8-9e60-560b-8345-b411e62275a7 | note | Produce Record - Sp or S
7423bd38-bf7a-5bc2-ac12-925dadb41532 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: Cement - Stabilising Agent Selection
816bd918-8532-52e3-bf3e-64d0f217ec0a | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
6f3a0084-c153-5a82-8044-004acdcebb67 | note | Acceptance Criteria - GP
6f320174-5bc7-5fdd-abb9-2479182a944b | note | Method - Visual inspection of supplier docket
a12be322-1521-5a99-9cba-cb1c840073a4 | note | Frequency - per truck load
5d718443-551b-5a63-9002-82995911a1bd | note | Responsible Person - Quality Controller
47448331-a9cd-5375-8ff6-4692976293e7 | note | Verifying Document - Supplier Docket Supplier Cert
08d65ba1-e777-5304-a1b7-f5a1ef56cbd5 | note | Conduct - Sp or S
97e02cf1-4911-5c3e-afc6-4df188e47185 | note | Produce Record - Sp or S
3a504d6c-d0d8-52c6-b846-ce7755f257ea | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Water - Water draw for stabilising
30bdab61-625c-50dc-b562-7ea01cf5b69b | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
f5ae8517-191b-588e-9119-a82c878db369 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
6d985f0c-f25d-53c3-b14f-04e727c94e70 | note | Method - Visual inspection of hydrant use form
2f1ae37f-4ac1-52bd-946b-652e28147efd | note | Frequency - per truck load
7f611a67-0036-5ca7-8c6f-ccfac059470f | note | Responsible Person - Quality Controller
4a64cf0f-bd8e-5186-b322-e45daf31cfd2 | note | Verifying Document - Hydrant use form
4dda05b8-2fff-50c5-9537-27471e814d7b | note | Conduct - Sp or S
761417e6-f812-5b97-9868-0399afec3ae0 | note | Produce Record - Sp or S
f292cbcb-3db5-5f4b-9315-af1efa1f0b2c | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
ef68a90b-afd2-50fb-a2ac-b8d52e561f48 | note | Controlling Documents - TNZ F7 Specification
fb2eeaea-3403-58bb-8d86-4a811de0fe2d | note | Acceptance Criteria - Details on Docket
933ba10b-cfd3-553a-99b2-f2af7e1598bd | note | Method - Visual inspection
1fc1a7d4-bd03-549f-9adc-db4300b1474f | note | Frequency - Per Delivery
1740bf62-6bf9-5304-98de-1d88157613f0 | note | Responsible Person - Quality Controller
16705c0b-5a4e-5494-ab06-17e8052873a8 | note | Verifying Document - MDS
195d9378-c0cb-583a-b184-588e3ef0422b | note | Conduct - Sp or S
cea2aded-61dd-54a0-929b-d1a2ff46bf13 | note | Produce Record - Sp or S
4c7e3aae-be68-5272-8bae-f361724f870f | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geogrid - Geogrid Triaxial Tx160 or similar equivalent
3834e315-cdfd-569d-9b94-788b13ad082e | note | Controlling Documents - As per NZTA list of approved materials/suppliers
249af23c-8aad-5821-a593-84bab10a47d6 | note | Acceptance Criteria - Details on Docket
87f60b1f-0194-596c-8c0e-043626345715 | note | Method - Visual inspection
0ae419e0-97c8-5555-a960-d127a7e230bc | note | Frequency - Per Delivery
0e77ab95-f0a5-5ada-8f8c-73795a3747d8 | note | Responsible Person - Quality Controller
de7c361d-4210-509c-8425-a3e74bed20cb | note | Verifying Document - MDS
8bc3a036-6ba4-597b-a1c7-e54d22c19a7a | note | Conduct - Sp or S
be28ff69-dca1-5223-9cb0-f5c2a5101a8c | note | Produce Record - Sp or S
170c4b43-044f-5700-a64a-5b30db68ac51 | note | Approval - C
| signoff | HOLD POINT
| section | 2. Pre-Implementation
| checkpoint | Production Testing of stabilised material - OMC/MDD
b3b10c12-1998-570c-81c8-738607a59aa2 | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
55c8e646-d956-5467-a900-6617c7e6740f | note | Acceptance Criteria - To obtain OMC & MDD
cb303a9f-7a94-5b86-8dea-d13f500325ce | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
7d647e48-ab6f-5361-b792-c66fa71c5b50 | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
df1bafdf-44d6-5c65-9d94-40d11151a814 | note | Responsible Person - Quality Controller
2d3ea92a-197d-5bb1-89e7-a2f2b363ace4 | note | Verifying Document - Test report
5d4eccb6-fda3-5459-b5ab-761849687c56 | note | Conduct - C
f14eca4e-a6bb-5c30-bfa9-879e8059d1ea | note | Witness - C
302ccba3-df1b-5d32-b625-4eee2fac8afe | note | Produce Record - C
6e8c07f8-2345-5a12-a622-805f47a4e9a5 | note | Witness Point - Y
| checkpoint | Production Testing of stabilised material - Solid Density
e4ce0207-4ec3-5118-a894-62a6d5827644 | note | Controlling Documents - TNZ B/5 section 7.7
dc5ecab1-e772-523b-b066-764cb4953820 | note | Acceptance Criteria - For info. and use in MDD calculation
beb6ed90-2585-5d7f-9835-7321b3975dc6 | note | Method - NZS 4407; test 3.7.1
e76ff461-a103-5096-8866-590710e1b5d0 | note | Frequency - Once on commencement and if any materials chage
62c013d6-a2f3-5175-8f5f-96fbe457f1da | note | Responsible Person - Quality Controller
038268c9-97ac-56d6-8c25-b55eb29373f9 | note | Verifying Document - Test report
b8f1056a-9237-5f61-9e9a-5187ff5d5f64 | note | Conduct - C
ca60d184-c888-5adb-b5be-90269a10057e | note | Witness - C
d1c381c0-e0a6-5899-9f1d-d6b8fd39b37b | note | Produce Record - C
24527211-1412-5212-a871-509f0a9be53f | note | Witness Point - Y
| checkpoint | Project survey setting out
acc062ed-4200-5cd3-9a5b-1c0876132001 | note | Controlling Documents - Reference from Project Drawings
1265698d-5a0e-5e11-9088-b16228b348fe | note | Method - Survey/Mobile Roads, Marks with Dazzle
423d7a90-0cbb-57e7-b934-6f6ecd9084f5 | note | Frequency - Chainages for every different pavement sections
f10b86c1-34ed-5c58-bc2e-81bd7b305081 | note | Responsible Person - Subcontractor/ Engineer
928b81b3-459e-5d58-8d8a-528c25e78f27 | note | Verifying Document - Construction drawings
e949db89-1f02-579a-94a9-13fb56f5831d | note | Conduct - C
22415a26-b5e6-5c0c-a35e-4632673c2942 | note | Produce Record - C
| signoff | HOLD POINT
| checkpoint | Records Management (i.e. it is known what documented records are to be kept)
e96f792d-f362-5c96-ac10-df69ff5b1b41 | note | Controlling Documents - ITP and QMP state what quality documentation is required
cc85d628-0f6a-5b55-9b39-dd28fd3eca90 | note | Acceptance Criteria - Filled in and Signed ITP
0a571aa3-bd4f-5649-bd56-d286b9db7edb | note | Method - Visual inspection, recording and approval
05e50d1f-285c-5c96-a5d1-e5f4b5919347 | note | Frequency - As per hold points in collaboration with the programme
69ac768d-ba2b-5c0e-9a51-cdd10a2d4ec6 | note | Responsible Person - Quality Controller
2eca2d54-c7e5-578a-90fb-7dd0f3ed9c0e | note | Verifying Document - ITP and all referenced documents
8de3d6f8-8a0e-5ae0-88ab-adc78eea8f6f | note | Conduct - C
fb3ddaf0-f7cd-5c37-840d-edefe1e2c73b | note | Produce Record - C
243e04e8-3edd-56ef-8654-e1d4e24ca326 | note | Approval - E
| signoff | HOLD POINT
| section | 3. Construction - Pre-treatment Digouts
| checkpoint | Pre-treatment Repair Method Selection
b8e991cb-a50a-5aba-97ae-3cd4d97deefe | note | Controlling Documents - Site specifics to be confirmed
3edff51e-5106-5e79-bd84-1ca0adfadb64 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
7b2aa9e8-9a25-58f8-9e5b-fdda9035107b | note | Method - Scala Penetrometer on Excavation Floor
083ca916-c3a4-52d0-8a84-db5f58641aa0 | note | Frequency - As required
80d2b0af-5d09-56d1-8a34-0312e6bb3e55 | note | Responsible Person - Quality Controller
845dd74a-214b-561b-9fc5-c4e5355a6a2a | note | Verifying Document - Agreed treatment plan
3ba13dae-232c-5103-97fc-008d9f105e3c | note | Conduct - S
c5905110-bb3f-5e4b-bf29-9dad393f25b2 | note | Witness - C
6bd529b1-1261-52ce-bd05-8dff8a3a5312 | note | Produce Record - S
ef6b907e-237f-5745-afdb-67bb65011122 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Excavation floor drainage
13acd78a-b125-5e8f-806a-62930c7ca773 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
246b891f-cfbf-56f0-ba0d-9eece0c7bcce | note | Acceptance Criteria - 4-8% toward edge of seal
95324d47-c6ba-5d2c-a5b3-d6f1f0bea5a7 | note | Method - Digital level
4948e499-cdb3-532d-8ffb-a1a00aabd26a | note | Frequency - As required
5e1402d1-0479-59af-be36-6a05bc1b7361 | note | Responsible Person - Quality Controller
f70a18f2-4cdc-552f-a400-25e131a16d4c | note | Verifying Document - Dig out QA form
96ee320c-cb00-5f29-9532-fe164c1cfc70 | note | Conduct - S
6f4c4b15-dc9a-5abf-9bc7-2e299f62e2d8 | note | Witness - C
09998993-45f0-533d-879a-d5efbf939b72 | note | Produce Record - S
026a90ab-02d4-5b35-ae4b-c19e28b59efe | note | Approval - C
270bcc77-407c-5d99-964b-f177e5837cf6 | note | Witness Point - Y
| checkpoint | Subgrade material hardness Check base of excavation
a32b1fd0-02e9-5cd5-a862-c74010a6932b | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
b9f01c4a-db9c-53c8-a264-884ee48c0159 | note | Acceptance Criteria - Scala > 3 blows per 100mm
44eda73a-cfe0-5ccf-a052-fa1073cf20d0 | note | Method - Scala Penetrometer test on base of digout
10c3629d-236e-50ed-a702-862ea989e7d3 | note | Frequency - As required depending on size of digout
d807f50e-1d78-52d6-be78-61f8c10230bb | note | Responsible Person - Quality Controller
91b819b7-2737-5411-ae84-a0cf0d83a6c2 | note | Verifying Document - Test report
e7ac67d3-6f61-5264-859a-3c6c4643284e | note | Conduct - S/C
92b13323-53ab-5158-a4e9-5013ccb3715d | note | Witness - C
da0281b3-e8ef-5188-97ab-01078357648f | note | Produce Record - S/C
766c13b9-fca8-569f-9728-45d33d276d44 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer
9c79d8ab-a2e4-5768-bf0d-8039d7bc78b7 | note | Controlling Documents - TNZ F7 Specification
99502607-c1b6-548f-9abc-ca42c973a93f | note | Acceptance Criteria - Meet TNZ F7 Spec.
ffe8fa97-a259-5e8f-87b2-cc5671091388 | note | Method - Visual inspection
861161b8-166c-5444-a758-7fe4b52af8f8 | note | Frequency - Per Delivery
fe89151a-fcc2-5f77-ba0f-25758965883d | note | Responsible Person - Quality Controller
ccf2df57-f02d-5234-80d5-eb3da94e8c42 | note | Verifying Document - Certificate of conformance
ee836485-81ed-56f8-b16e-ba8b1e28260a | note | Conduct - Sp or S
c2ae6d7c-06d1-5382-b0ab-5c5545f8f661 | note | Produce Record - C
3b271393-2c1e-5a48-839d-f0507a008625 | note | Approval - C
893163be-1b42-5b97-91da-6998ac337ee4 | note | Witness Point - Y
| checkpoint | Geogrid Triaxial Tx160 or similar equivalent
834ced85-30cc-58aa-9b52-9c4a43ff919d | note | Controlling Documents - As per NZTA list of approved materials/suppliers
1c30629e-dbd0-598e-ab98-f18bdf35630d | note | Acceptance Criteria - On the list of approved materials/suppliers
4cb8c8a7-73c2-5af1-8384-039a30194a40 | note | Method - Visual inspection
2ffe5fca-f1f0-5a05-9b20-0bc8dc2ea62e | note | Frequency - Per Delivery
523c8173-285f-51a1-9443-c64aad8d4387 | note | Responsible Person - Quality Controller
f8776fa1-fa14-5afe-aa86-4cac93ced370 | note | Verifying Document - Certificate of conformance
796a8192-acfb-58ae-a66d-d4765f1fcecc | note | Conduct - Sp or S
313a95d6-0a7e-5166-a860-ed1dd50ca907 | note | Produce Record - C
27c7f4fa-cc14-5984-908a-58aedfbec750 | note | Approval - C
a2ef534b-e2f6-5371-984f-2ffbf9a1e14f | note | Witness Point - Y
| checkpoint | Place and compact GAP65 in digout area
2ef64018-97b9-51f4-96c4-fc54cd47d36e | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
e4ab6c24-cc1c-55f3-8893-ce9d276d8a12 | note | Acceptance Criteria - Clegg > 45
cb5b758c-96ef-501e-b2f1-e2fe05d76117 | note | Method - Clegg Test
eb826dec-98f3-5e5c-9fdb-6c8e35c931af | note | Frequency - Min. 2 per digout
bc4bfb97-5014-5388-807c-59420efc10b0 | note | Responsible Person - Quality Controller
039b6743-c07e-5d68-b754-24ef7d821a39 | note | Verifying Document - Test report
9c20b4a9-db02-5c0d-86cd-f28d884f0ac4 | note | Conduct - S/C
b0edfaff-cf83-5dd1-a78a-5dbc9627d750 | note | Witness - C
be5dce6d-6639-5bfc-ace9-74d479c3e97b | note | Produce Record - S/C
c9c71f9d-00fd-5ca6-a8ea-c969c781ad08 | note | Approval - E
| signoff | HOLD POINT
| section | 4. Construction - Granular make up and In-situ Modification
| checkpoint | Place M/4 AP40 Basecourse Material
63a5d350-00f3-5239-8f6e-784137b2d4e3 | note | Controlling Documents - TNZ B/5 (section 7)
87fe79a8-503f-5ece-b4bf-7746dc7d5e14 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
70b054c2-f4b2-5d1b-b272-7dc23bb790d5 | note | Method - Visual Inspection
9ac4cc5e-4c10-596f-9e64-9abaab3d8b05 | note | Frequency - On completion of placement
096d75f2-8cff-56eb-a004-8a37dc943148 | note | Responsible Person - Quality Controller
95c3d6ca-f011-5c32-91a5-9689915fcb31 | note | Verifying Document - Photographs and Daily Site Record
afb116cf-5279-5201-8aaf-c9ba43b97c07 | note | Conduct - S or C
ef9434ab-6f8c-5f55-9015-17f5aedd49cf | note | Produce Record - S or C
dcdae83c-489f-5524-afb6-2070b010909d | note | Approval - C
4866cb8c-7a9a-5b41-9bd4-d4bd7be2c014 | note | Witness Point - Y
| checkpoint | Spreading of Cement
c02dba6c-50ea-5059-ae40-4d64958955ee | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
e4b1c151-5ecf-5b33-877f-51b74df12f20 | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
052eb174-d87f-5eb6-945e-f0940f7e0add | note | Method - Mat test (1m² canvas) and Average Usage Test
8f077e1f-b6bc-55c2-a349-83658e74c714 | note | Frequency - per 400m² and upon emptying the spreader
20503c95-8a33-5017-8428-0aad4b81623b | note | Responsible Person - Quality Controller
b5bb8778-a8cf-568e-94aa-1d7db982bcf9 | note | Verifying Document - Mat Test Form and truck dockets
707bee18-91ca-543e-a435-9cbc93a68861 | note | Conduct - S or Sp
6d87970d-6186-504e-8066-73a76fc88117 | note | Produce Record - S
c3549e66-5505-51b9-a47a-82be57379c98 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Addition of Water
4f94eedc-55cd-5cc1-9369-ddbd7df3f289 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
a7c26101-bf0d-5178-bfa1-aba8525ee507 | note | Acceptance Criteria - 90-100% OWC
0fc5809d-6180-533f-ae85-9b3d5eb22baa | note | Method - Nuclear Densometer Testing prior to Stabilisation
c364eb37-a75b-54ef-ae8e-2451829d8de4 | note | Frequency - ≥1 per 1000m² lot
c63d8e1b-9bc8-5bad-bb2c-ecaf276b5d8a | note | Responsible Person - Quality Controller
e060d1c6-9842-53c5-95f1-7fa75ecb2411 | note | Verifying Document - NDM Record
03b113f1-ed37-5315-aaeb-d20dba6f6ddf | note | Conduct - S
926d1c27-76fd-5774-9317-b7133a9a4a8b | note | Produce Record - S
ea993f24-3153-5d93-b32a-a7c468e0ea51 | note | Approval - C
41bfded4-7e33-5dd4-b8c2-6f73c4552aab | note | Witness Point - Y
| checkpoint | Cut Depth
e813319d-382d-58ad-a4c7-5fde2980932f | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
beaec470-8e44-5b4c-b0af-4b6602ef81bd | note | Acceptance Criteria - -5mm and +15mm of design stab depth
018c1dd5-c5cd-53c7-9c5e-d313e46e915d | note | Method - Physical Measure and Visual Record
810e1ebc-bf49-5fcc-af1d-fb4d9e406b01 | note | Frequency - ≥1 per 200m of cut length
a909578f-48e9-5fa2-b28e-e10a5c2cf292 | note | Responsible Person - Quality Controller
9064ef74-bd72-5602-9f0d-81b506bf316e | note | Verifying Document - Photographs and Daily Site Record
6f38c68b-9f66-525a-b8f6-1f7e127d3263 | note | Conduct - S
1f7a8c65-1f24-5824-abff-5ed436e1f214 | note | Produce Record - S
3d747b63-5821-56da-97e7-5e1773942b68 | note | Approval - C
11311c64-98c1-5814-b886-f5047a911b11 | note | Witness Point - Y
| checkpoint | Longitudinal Joints
d64ec32e-2499-5264-ba01-e598f4dd445b | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
cfc49a52-eb65-5e69-9f2f-c12378558957 | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
5c2ec1a7-b1f8-5cc4-840f-dda6cd1c1b1f | note | Method - Visual Record
2d27359e-9913-5520-b4e1-8607dd5cf460 | note | Frequency - per sucessive cut
e2369a1b-ad6a-57d8-a649-9f0ee4d90ccd | note | Responsible Person - Quality Controller
36c372b7-7b6d-52cf-a886-18619b248cef | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
d24d3d14-09fc-589b-bd54-729eb9b42845 | note | Conduct - S
db3f0183-874d-5196-8ca7-002e36ecefa1 | note | Produce Record - S
e0bd7033-8e0d-5282-8f89-4fa6a616160a | note | Approval - C
643ff7e5-2c80-55e0-aa57-d0773a57e583 | note | Witness Point - Y
| checkpoint | Continuity of Layer
4d3cc128-8f3d-5ab9-bb45-cdab05d0680a | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
8a85751f-e286-5aeb-a9cf-da3a85e76209 | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
07b40518-5ea7-51d4-a511-fe145ef537ec | note | Method - Visual Record
30ce0441-dbf5-5a9c-aa60-cc9b0072eb17 | note | Frequency - per sucessive cut
a0d7148c-97a9-5a4e-abbb-4767c9f9d29c | note | Responsible Person - Quality Controller
71f37558-7b2b-5dd1-949c-f8a3030b9de9 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
092fe302-57a2-5f73-991c-9ca72f0efcb9 | note | Conduct - S
72c427ed-f985-5a4d-84ab-0f98908d717c | note | Produce Record - S
98e82a79-4cbb-58fb-b2f7-70ee2aa69322 | note | Approval - C
f6700d6b-1b81-564f-bcd6-b417021c43d5 | note | Witness Point - Y
| checkpoint | Stabilised Material Particle Size
2a8f62fa-f634-5ed5-a903-466be776b960 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
46b8e8a1-ae2e-5c09-8139-980e62babc72 | note | Acceptance Criteria - No excessive breakdown of stabilised material
6cc2c085-6307-579b-b7b3-daee4dcd7777 | note | Method - Visual Record
afc474c1-8089-58e5-b908-7499d47f086d | note | Frequency - within 20m of each section and then regularly based on material variability
5d94932e-e43a-526e-8d86-4f30923a8df1 | note | Responsible Person - Quality Controller
6d38956b-74ee-5248-962f-229b11fe5844 | note | Verifying Document - Photographs
e566e11e-4e56-56d5-afa4-ce464fdcea22 | note | Conduct - S or C
e96c7006-d2a3-5cb8-9990-9ee2953beaaa | note | Produce Record - S or C
51eeff94-f997-5a11-bef8-6453728df7ae | note | Approval - C
eb6baa1c-354c-5138-9410-9d69cec3c1cf | note | Witness Point - Y
| checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
2cbad177-379a-56c8-9dbc-c33692951db7 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008
4ca0bf1a-fa7d-5cc7-ba4d-0c9f764d60ca | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
e1c5ad4b-0c6a-5dbc-98fa-f5c64f8e19af | note | Method - Plateau Density Testing
bcdca8f1-4b94-57db-bac3-0ca7064d3c04 | note | Frequency - 1 time, or additional tests when material changes visually
aae22d0a-23dd-56a9-9541-7d0153b5a388 | note | Responsible Person - Supervisor
d71cb353-7803-59cc-ac7f-0622f099251d | note | Verifying Document - Test record
f3e76136-ec86-5fe4-ac29-282a80db3cbf | note | Conduct - C
dc1b9098-fdab-5ad3-b305-d94e749fc4ed | note | Produce Record - C
0b3113c4-ea59-577f-bd67-0a2a10ab8bf6 | note | Approval - C
8517e52b-127e-5b4e-8aa4-0daa5f0388d7 | note | Witness Point - Y
| checkpoint | Establish Compaction Target
44729fd1-18aa-5c98-b67a-a503b2a55a3c | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
3524347e-01ed-5af5-a2f2-bdef36bbea3b | note | Acceptance Criteria - To provide MDD for NDM testing
8d73bd17-4fb2-589d-a432-94c376b50b8f | note | Method - Plateau Density Testing
427d97dc-0439-575a-88cb-c8ca87fce2c2 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
dd18252d-52b0-57b4-b284-dc238da84504 | note | Responsible Person - Quality Controller
1bbf54d9-f33e-5956-bf8c-2daa2322c3e7 | note | Verifying Document - Test Record
4d48066d-5888-5827-9f4d-52cb19197e70 | note | Conduct - C
d869a64b-d0ac-52e9-a17f-de3347b75818 | note | Produce Record - C
e29444ec-aa27-5ea3-816c-bc2b7694ae68 | note | Approval - E
f3a4435d-fca8-5f4c-ad96-3cd926fa4c61 | note | Witness Point - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
658a97d5-86dd-5777-aea9-8065f07a99fa | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
1fcb32a0-4154-59a0-a702-207b4006ffed | note | Acceptance Criteria - To provide MDD for NDM testing
7194b65d-b9df-5d69-9ca9-9a8e8c53790e | note | Method - 'Laboratory MDD at OMC NZS 4402 test 4.1.3.
434cd0a4-9cc3-53af-a63e-ea1f2feed225 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
82822b89-c346-5711-bfc7-47371d1c19ef | note | Responsible Person - Quality Controller
0cdcb23d-59d3-56ba-ba2f-b649ada256bc | note | Verifying Document - Test Record
cb66b300-0daf-5881-a595-228466df8066 | note | Conduct - C
45da85e7-52f3-57fc-a957-b84db30bcf09 | note | Produce Record - C
39c5c033-864a-5abc-a7c7-cfe313cc2039 | note | Approval - C
fb4417b9-5b5a-5400-aa0a-8e9c0647aefa | note | Witness Point - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
5a6ba513-bc09-5c96-b9f0-0ae53180fe2a | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
8679b652-b664-55bf-9424-871a079a1956 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
3ae5983d-6385-5ff2-bf25-be6b1391fb01 | note | Method - Plateau Density Testing Lab. MDD
1a8a0cdf-78e8-5b91-adb8-2cb2eaaf2ec8 | note | Frequency - At commencement of construction and whenever materials change
1e87ba45-d8b6-55fb-bd73-39c5cdec1564 | note | Responsible Person - Quality Controller Engineer
520c352b-f642-517c-996d-bcd03bac47ff | note | Verifying Document - Notice to Contractor/ Notice to Engineer
664f7634-5a8c-516a-9c2f-39789ac6ab37 | note | Conduct - C
adf00cd4-fde6-568f-9240-2d186f375be2 | note | Produce Record - C
1353033d-d619-5297-97ea-99813866e1dc | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Compaction Acceptance
f7ef044c-e149-58cc-82e9-a665f29121dc | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
7d20ee12-8e5f-5b40-8ce5-5d86e5e075ad | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
26b164b8-25d2-537c-aeb7-a236e943201f | note | Method - Nuclear Densometer Testing
c7ddaae7-6ebc-55a4-8fe7-2d8841a5a2d0 | note | Frequency - ≥ 5 tests per 1000m² lot
db722f06-ee1e-50f9-b493-1817d813e08e | note | Responsible Person - Quality Controller
eeed15a2-5f3d-5a47-9ca1-fe58719d580c | note | Verifying Document - NDM Record
1ac65119-cd03-5d8a-9034-ad82ccbd5d7f | note | Conduct - S or C
db3aa4c4-9f12-5599-8f5a-3bebcd2c6425 | note | Produce Record - S or C
c26db1b7-1fbe-5510-9ac5-f2a59dbfdff3 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Control Testing (if required)
f940a326-f5ac-5f56-ae76-d615781b4101 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
2d541ad2-2d87-58e9-9694-8c7d08f964b5 | note | Acceptance Criteria - Nil
48b8b5a6-b28e-5c87-b522-b5f68469baa6 | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
4838fe62-080c-564c-9d5c-96cac0a52636 | note | Frequency - when agreed with the Engineer
f4cd5960-0a90-5585-8718-1555d8620cee | note | Responsible Person - Quality Controller
a20ebfb7-e59b-52f0-8bf4-d92637dd8280 | note | Verifying Document - Test Report
09730d5e-421b-5ab8-8fd0-d05896adc99d | note | Conduct - S or C
edb52438-07a2-5ed6-8195-8bf9c18f78c7 | note | Produce Record - S or C
69a9484c-a4a0-5b2d-b100-ea6c42333803 | note | Approval - E
| checkpoint | Surface Smoothness
ec80fcc7-5fb9-5f80-ade2-81effa51673c | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
5e32fa01-1e6c-5404-8377-c094d0371c48 | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge No water ponding
6838e7b7-0bf0-5d15-a114-0e1c047d6056 | note | Method - 3m Straight Edge
16ea6815-bda6-54ea-a781-be441ef711a6 | note | Frequency - during construction and prior to seal
065a2d12-86d6-5193-af53-031e154f31fc | note | Responsible Person - Supervisor
13382e04-f067-5548-a51b-aafcfb3e246e | note | Verifying Document - Photographs
08572b22-1dca-588b-86c4-609f5a83dc71 | note | Conduct - S
7e76d993-8aa8-539e-b9cb-19e4243a2e13 | note | Produce Record - S
c94a2150-7e89-500d-b620-29928761604b | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Shape
7ce9b69a-c0cd-5ac7-a635-019b6c8c2aa0 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
c6d3f196-9e2e-5e40-9979-41d37056c771 | note | Acceptance Criteria - Between -5mm and +15mm
4f1513fd-ff79-51d8-9151-7b1b5be44a4d | note | Method - String lines or Survey Asbuilt
11757ead-e11d-5d5f-a159-fa6265c49cdf | note | Frequency - during construction and prior to seal
90215019-d2c3-5e0c-a91c-83c1f06d6084 | note | Responsible Person - Supervisor
46750e5a-5261-591b-81f6-81b77cba7ace | note | Verifying Document - String Sheet/Survey Asbuilts
4297d408-1726-56a3-aae5-d71f316f0614 | note | Conduct - S
5ed265da-74e5-57f2-9459-be522010e266 | note | Produce Record - S
b839e079-10e8-51d2-951a-c0047b045a9a | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Cross Fall
29877168-7223-52d5-85bd-636201999800 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
3a8d528d-9bca-52aa-808e-ccd38d2119e1 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
d792f0d1-f322-5892-a6e6-4f857b567376 | note | Method - 3m straight edge or Survey Asbuilt
e8515eb5-2ca4-5313-bc31-4d814e64a7aa | note | Frequency - during construction and prior to seal
7273b0a7-ce13-568d-9705-5e36b060b696 | note | Responsible Person - Supervisor
4ca5d9b8-1581-5f4e-84e4-186375b2028f | note | Verifying Document - Cross Fall Records/Survey Asbuilts
0806a5f1-3ea2-5de0-b194-ec20a2e48569 | note | Conduct - S
6a407681-805c-5649-a943-f677873fe5e3 | note | Witness - C
27a72512-f938-5278-bc37-1ec6f17ec16a | note | Produce Record - C
500982ed-bd53-5629-aa92-7ff754cbf23b | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Finish
f3ff9603-f67a-5506-9dd4-8f41099569a7 | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
16380ab4-eaea-52cb-b319-b645596885ab | note | Acceptance Criteria - Tightly bound matrix post sweep
44347903-fb95-5f08-8322-e63823f10746 | note | Method - Visual inpsection
67920cfe-c03b-5f7c-974d-00ac2469bb48 | note | Frequency - prior to seal
0367dd60-d487-5d56-a7ee-210a608125f6 | note | Responsible Person - Supervisor
2b0521fa-bb97-5d82-aa6a-7758bd14dff7 | note | Verifying Document - Pre-seal inspection sheet
ee36304e-b329-54ec-ab7a-af36cb2cd501 | note | Conduct - C
3b57c7d9-5d06-5d02-bc50-d1a00dcc2715 | note | Witness - C and E
7176e5fc-61a9-5de6-a256-1931fad78396 | note | Produce Record - C or S
945dcf41-8e6d-53a1-92f5-ccac398e7a9e | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Degree of Saturation, DOS
a88385d7-bc80-5030-9407-a2a3058b9e86 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
67f5eab9-225e-52ba-a99f-ec5587ac3cf2 | note | Acceptance Criteria - ≤80%, however 65% is ideal
b2b05b65-682b-5783-82a8-99d31be39a3c | note | Method - Nuclear Densometer Testing
2ea7c6a9-7cbc-59ff-b775-77cde1bcfb42 | note | Frequency - ≥5 tests per 1000m² lot
ab93b190-c407-58e6-aa93-7227795040cc | note | Responsible Person - Quality Controller
642e9677-f317-5027-b7f4-14569ec289ed | note | Verifying Document - NDM Record
b65c5102-cf93-5e73-896c-a1e9c26073ef | note | Conduct - C
cfa5a1a1-c32e-5dff-ab54-a0be9704cf93 | note | Witness - E
0155e12b-620f-586c-85fd-46aa20bc5888 | note | Produce Record - S
516a57f3-2a66-5868-87a0-df111081e893 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Benklemann Beam
5f3c009d-53ba-561b-b971-6fc37bcf4e3a | note | Controlling Documents - 'NZTA T/1
bdef9205-aee1-5dcc-8fb1-704dd695b0f4 | note | Acceptance Criteria - Using a MESA > 0.1 for asphalt carriageways < 10% of results to exceed 90th%ile Avearge < 0.9 90%ile of 0.9mm Maximum 1.0mm.
bda5e638-c2ba-57d3-bc50-a22d4f58fd16 | note | Method - NZTA T/1
1ad58468-c092-5403-8074-2c2e8f096215 | note | Frequency - Alternating wheel Paths at 10m centres along alignment.
f17e6dad-ce0a-5b4f-9cd0-2ad5c9fd8548 | note | Responsible Person - Quality Controller
72dd3757-cbff-5d70-9397-282aad789dd1 | note | Verifying Document - Test Records
b25fde49-1f43-5518-88a9-d964c4f7615d | note | Conduct - C
85978753-3386-50c6-9962-c721ae996a45 | note | Witness - E
7a081a76-3356-53ce-9ad1-1c12f1075e67 | note | Produce Record - S
9c35a38a-01b2-5493-9960-fb137c5ffcb7 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Roughness (NAASRA)
50fd6391-c048-56cb-a83b-c7160cfc097e | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
62460767-8afd-5bb3-8f24-860a11c6c8f7 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
29237399-7d62-5aad-b416-8bf55ea74a90 | note | Method - NZTA Maintainence specification section 6.1.2
a425e419-58d4-51b6-8813-7abc2e4c59b8 | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
2b413457-370b-5d8f-9ef4-2c1701ed0609 | note | Responsible Person - Quality Controller
ed0f6550-7a50-5cf9-b408-a08170db9ff7 | note | Verifying Document - Test Records
4c6ca685-2786-5701-b670-a10070d6bbdd | note | Conduct - C
ce66da6f-ad5a-5f0d-b7f0-b11d24db8e2a | note | Witness - E
35d0fcc9-dddc-5abc-9488-4190aa99b19a | note | Produce Record - S
0c2ef487-bc0c-5b54-aa6e-5ee05aec6c5b | note | Approval - E
| signoff | HOLD POINT
| section | 5. Chip Sealing
| checkpoint | Binder - Penetration Grade
bfa223b1-4b06-5fb3-99cf-187d04a60e05 | note | Controlling Documents - TNZ M/1
960ffca8-524c-58c8-ad25-415bec17e8e0 | note | Acceptance Criteria - Table 1
faae3b89-cfa4-5c88-8ff3-af1a71429af5 | note | Method - Property Test
26de2600-c254-54bc-8cbd-4f5216e79624 | note | Frequency - Annual
3bb71fdd-14e9-59c5-b60a-6e357cb26440 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
29424f41-c1c6-5b93-a018-6936afe232f3 | note | Verifying Document - IANZ Report's
d2473be4-eac0-58a0-817b-8a621f002037 | note | Conduct - C
d0db16f6-eba4-5762-871f-aa13bdfde0b1 | note | Produce Record - C
c275bfb3-7739-5d88-9e34-1591ab28bb64 | note | Approval - N
e156a60b-381a-5421-a2cc-d43f9643bd3f | note | Witness Point - Y
| checkpoint | Binder - Polymer Modified Emulsion
0884428a-bf50-5a3d-ba78-c1e5a6f26a73 | note | Controlling Documents - Higgins Internal Specification
33e7a512-7dc1-59c2-8d44-0261059d44f3 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
a3965243-33bd-5696-be9d-ed02aaa2c66d | note | Method - Property Test
115c3320-2c4b-59f3-860f-52f23c989683 | note | Frequency - 1/100,000 litres supplied
33409de4-fc0d-58b8-96f5-ab6d1a449f04 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
32b7dce8-3869-54f8-82a6-209da16763c8 | note | Verifying Document - IANZ Report's
c8a54a16-9547-5fd3-90f0-f40a75fbd82c | note | Conduct - C
2258c4c5-4dff-5af7-bd6e-8165bb7823a2 | note | Produce Record - C
4351cff6-7ace-5c71-8ed0-d6a6afd3dbe5 | note | Approval - N
baeef317-6128-5da5-ab28-6a526c2cb0b9 | note | Witness Point - Y
| checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
694c2f69-0f28-580b-b2fb-18fbaab15347 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
1d35b64c-1dbf-539e-b692-0e559fd92dd5 | note | Acceptance Criteria - <10% fines under 230kN minimum
2a6b2137-7ae9-52e8-9bba-7a1781e12896 | note | Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
34ed4b3d-9ef5-5eea-aec3-f2a7ab3c024a | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
64a4b98a-2fe2-539a-8c0f-43392c19c11e | note | Responsible Person - Surfacing Project Manager
63ab40a7-7047-500f-94c3-bccc2ec672a7 | note | Verifying Document - IANZ Report's
5dbf9c6c-1f78-541a-9887-d4e631227756 | note | Conduct - C
9748c8ec-1e35-54f4-8836-6fd3b9666afb | note | Produce Record - C
4f7db9c4-7089-501e-8eef-405b7f1c84f8 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
e5864485-3925-545a-a27f-f7b78a700cc0 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
37e38494-8665-5ca0-b77e-10d8ffaebbba | note | Acceptance Criteria - AA or BA
fbd61445-3465-5014-be81-6ac2d9830d36 | note | Method - Weathering Quality Index NZS 4407 Test 3.10
97e40a28-dc88-5be8-b2f2-a90990d4d846 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
c200ba49-1e5b-57fb-bc55-dcaefbbf8792 | note | Responsible Person - Surfacing Project Manager
adfa43d2-a634-53ff-b507-5e69492a7d93 | note | Verifying Document - IANZ Report's
89e0987f-f3d9-5d99-b4ab-82174267c9d6 | note | Conduct - C
ae4fdc18-6b28-5033-a2b0-22122689db4b | note | Produce Record - C
047366cc-63ff-5ae6-a3e5-b4d7b57a5188 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property - Skid Resistance
3a4d5c57-e5ac-5c11-8b0c-5b0a8ab11fce | note | Controlling Documents - NZTA T/10
8c43b71e-08b4-5a78-926e-ff2d47b896e1 | note | Acceptance Criteria - Meet Skid performance Requirement
07e69e1c-90d9-50b2-8483-04bade252003 | note | Method - Aggregate Perfomance Method TNZ T/10 section 12.3
e64c2108-9f77-5c2e-9674-135a2dcfb3c3 | note | Frequency - Each Site
24d7128b-e4cd-5ddd-9903-b1f45719e7ed | note | Responsible Person - Surfacing Project Manager
26f99175-44d7-5a7c-87c2-351cc8f4597e | note | Verifying Document - IANZ Report's
4680f4b0-0a8d-599a-8405-7428c1e53af8 | note | Conduct - C
c8eedc64-e184-547d-beae-72b75e9e38db | note | Produce Record - C
76ad4795-3537-537a-bd49-e764522f0032 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
6716eb48-5464-5ee8-a252-ef29550f4f94 | note | Controlling Documents - NZTA P/17, M/6
ff1c409f-15ed-55f7-8bd4-d268744c45cd | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
9a67b9c9-dd86-5454-a4d0-9862d2553885 | note | Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
50ce60ce-e979-5dac-9d03-7f4f7d2bff15 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
76fdedfa-9b05-540f-a245-b091da13f73b | note | Responsible Person - Surfacing Project Manager
f66df60f-c5bd-5543-97ed-98c0e3d72e6e | note | Verifying Document - IANZ Report's
410a2999-0d65-5c25-a578-a0d065d3c9de | note | Conduct - C
e478d991-4983-5a7e-a63c-1c359f3eea77 | note | Produce Record - C
206e2b1f-f64b-578b-bc9d-3472554ae8a2 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
0c2d26a0-0ec5-5e6e-82d9-8858f5e2d4ea | note | Controlling Documents - NZTA P/17, M/6
ec25fed3-c591-5b35-8afa-dd5e01bcfa44 | note | Acceptance Criteria - As per Table 3 NZTA M/6
24cd6293-7f5c-529d-ace9-3a8244100859 | note | Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
eb1d8758-653f-5fda-ac9d-32417646cd13 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
a5720d5e-f531-5d35-b515-5ac7f3f049cb | note | Responsible Person - Surfacing Project Manager
127dea8d-a255-5d07-9a75-2ca2bab431ad | note | Verifying Document - IANZ Report's
c3261a7e-f518-5a38-89fd-8dbc1ea7f72b | note | Conduct - C
7f9e172f-b3b9-524a-8725-cc9805d34a10 | note | Produce Record - C
997cc726-d1f3-5827-966b-06099076e141 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
23e9ad28-828a-5afb-8201-8ee4e5db9459 | note | Controlling Documents - NZTA P/17, M/6
1ed6168e-6ba9-55f7-b6e7-30492a18e90a | note | Acceptance Criteria - Min. 98%
5eed4883-c89d-5ac1-b4f8-9c7b79dfbf16 | note | Method - Sample Test - Broken Faces NZS 4407 Test 3.14
6049b559-0709-568e-9a8c-d5ef35752283 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
fd56073a-a1c5-5162-bfa8-5c5cabf66d90 | note | Responsible Person - Surfacing Project Manager
28c877f0-7b9a-5546-8792-ee8c19bd6497 | note | Verifying Document - IANZ Report's
ba4691f7-8b01-5ad0-a33d-2933d9ff825e | note | Conduct - C
f9857189-f2ae-5014-9ff7-5c2ca257b46b | note | Produce Record - C
282bd022-bb48-587d-82d0-d8b92511d796 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Chipseal Designs
3756a0d4-dbc7-5b85-b5d0-c9557e37b185 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
9bcac818-ab74-55bc-af51-ca41e6783ce8 | note | Acceptance Criteria - Client Approval
d76c8b29-3dfd-5571-98fc-d465f59a9d12 | note | Method - Review
ffd31efb-2dad-58fd-ba72-98979ef3005f | note | Frequency - Annual
819614d9-13b8-5ea3-8c7c-903203b2a7bf | note | Responsible Person - Surfacing Project Manager
f8e0ceca-5132-550a-8149-3ae54d9aea9b | note | Verifying Document - EBOP NOC Design Report Acceptance
83c98f0e-2d9e-53c8-b178-7dae248106b3 | note | Conduct - C
f93ae1fd-2030-5b29-9548-c7397a71c70d | note | Produce Record - C
6fcdf19b-3152-5577-8422-ceffd51723a5 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Ensure limits of site are marked
0ac4a61a-96af-508c-80bb-ccf23210a262 | note | Controlling Documents - EBOP NOC Design Report
efd17ef9-0445-5966-b5a7-b189fe01f26e | note | Acceptance Criteria - Visual Inspection
1e4c72fe-d613-5205-84c8-0e2742140c52 | note | Method - Visual
0277da8d-edac-5376-b289-8c7c9db5a00d | note | Frequency - Prior to start sealing each site
e4a9be28-e78f-564f-ac58-bcc6ba0de480 | note | Responsible Person - Surfacing Supervisor
3ff08f08-e98e-5752-b0e1-23406fb730e2 | note | Verifying Document - Chip Sealing Quality and Site Record
f28ccd2f-a250-5cdc-860a-f970df4440d3 | note | Conduct - C
3b3d82fa-bf57-55b6-9f8c-e78c6659bd87 | note | Produce Record - C
e01f61cc-745b-56b5-a635-3b1ed56f5cdb | note | Approval - C
7b7ea427-5ee7-59a1-842e-375476929bcb | note | Witness Point - Y
| checkpoint | Sweep surface clean of deleterious material
6331fd09-fbda-561e-9540-c8562ad9c27b | note | Controlling Documents - P/17
a6a98f85-b199-527a-8153-9921f2ed40c3 | note | Acceptance Criteria - Visual Inspection
eabbaba6-883d-5a1c-a92e-9c8379ffa173 | note | Method - Visual
8465ba32-c488-5a0c-b212-9135a762d0d0 | note | Frequency - Each site, prior to start of sealing
bd640dba-806b-5279-8901-2a207dabcae2 | note | Responsible Person - Surfacing Supervisor
0b76c50f-c18a-5048-bf16-2b492fbb3624 | note | Verifying Document - Chip Sealing Quality and Site Record
d257fc26-4e8c-5154-8984-e69d69eba179 | note | Conduct - C
789fc2ed-92ab-5f65-8d42-abca15c18592 | note | Produce Record - C
353937ea-ca72-5280-9cb4-e70d3c5aaf3f | note | Approval - C
ddc506ce-164d-576c-885f-4f552c14fed9 | note | Witness Point - Y
| checkpoint | Record ATP's on site
317444fd-82dd-5954-8c36-89127e86f696 | note | Controlling Documents - N/A
16a33d13-a535-5186-bef0-8836581556ed | note | Acceptance Criteria - Visual Inspection
5646a636-b95f-59e9-add4-4c33a1164a9b | note | Method - Visual
90e0e43f-8b25-5b1f-a289-53feed52dcdc | note | Frequency - Each site, prior to start of sealing
3f227396-a443-541d-aefe-8dacab6dc014 | note | Responsible Person - Surfacing Supervisor
15eca0a1-c3df-5d94-a386-ebb73cbecbbb | note | Verifying Document - Chip Sealing Quality and Site Record
ff95392c-01db-5dbb-8ea5-c8083c0b2cff | note | Conduct - C
e9deb0b9-5b1d-5e1a-bc2d-00fde33bb6ee | note | Produce Record - C
928a1fe7-8412-5cc8-ab7f-17f448bf1f68 | note | Approval - C
8ebd01c9-bfb6-596e-aae1-c3b384f448e1 | note | Witness Point - Y
| checkpoint | Confirm correct treatment(s) and chip
c0cb0615-2119-5044-932b-2e661f11f233 | note | Controlling Documents - EBOP NOC Design Report
837f8f7e-ef39-5092-ba32-b80d8b4c42ed | note | Acceptance Criteria - Details/chip correct
e34a0938-7104-5eb4-bbd6-e6107a4387aa | note | Method - Visual
a9966396-8412-55b3-87f6-c33fbcd26021 | note | Frequency - Each Site
b1f383e7-5380-5b5d-8c21-f6703796d83b | note | Responsible Person - Surfacing Supervisor
c568b196-31c6-5c4b-a81c-c5db4252ff5c | note | Verifying Document - Chip Sealing Quality and Site Record
7e0d8eea-3f28-5f7b-b4ae-e8d2d268a9d9 | note | Conduct - C
587320e3-3106-50db-a7fb-216e56ce5aa3 | note | Produce Record - C
dde231ea-46e4-5af7-85f7-df4af60fb971 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Cutback Bitumen Blend
0a7fdce6-1a7b-534a-96d6-00e12e7c720b | note | Controlling Documents - RNZ 9803_0513
16c33624-ab12-5e1c-9107-3178ac0ab934 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
dd91a190-d0c9-58aa-ae63-4790281284a2 | note | Method - Sample and test
1bc72a87-21e3-561f-8eff-75377b56bd26 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
70a53b4b-7bcc-58b9-b13e-605a0db34138 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
228abed4-5c93-5c62-bc17-f02a6883c1b3 | note | Verifying Document - IANZ Report's
a1e10084-13dd-5851-844e-afcd6d1cfb9e | note | Conduct - C
97a11557-01d5-58c6-b4fd-bdf2b786cc6a | note | Produce Record - C
7893c801-1f49-505c-8d84-81fca9d944cd | note | Approval - C
cd97b6ef-e4a8-50d6-ba0a-d27482c36ac9 | note | Witness Point - Y
| checkpoint | Bitumen Application Rate
66c565c0-5996-5fa8-bc83-ac13dac30102 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
6b26240f-3e3b-528c-b1bf-e20066d7658f | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
80990fa3-618e-577d-9cb2-f4c3d4a2d356 | note | Method - Test, Review
1a29cb61-d838-5aa9-b2ae-f8168061c299 | note | Frequency - Per Sprayer, Per Site
e8681153-86c7-5d41-9437-37245ca5d4f7 | note | Responsible Person - Surfacing Supervisor
94591c42-7e14-5c76-8c22-7a6518287978 | note | Verifying Document - E/2 Certificate. Spray Sheets
c874f79b-6138-5ef4-bbba-ff03cdead450 | note | Conduct - C
5c3368d3-48d4-5993-8800-e49c6599afdf | note | Produce Record - C
0fbc759a-ede6-5031-b91d-e12c02b24c94 | note | Approval - C
05e017c4-f6d4-5cb1-ac1a-f6ed45077dc8 | note | Witness Point - Y
| checkpoint | Chip Application Rates
43d6084e-c428-50b7-a269-746c34187f3c | note | Controlling Documents - Chipsealing in NewZealand
60fff4e4-8a5e-568b-a172-981678371a2f | note | Acceptance Criteria - As per Chipping Guide
72fbe4ab-f36b-528f-b1c5-b4f4b822f2ed | note | Method - Visual
e642c39a-9afe-5e55-8184-685272f0d6fb | note | Frequency - Each Site
5f1d7739-3242-5d41-b1ea-dd55ff2bcdf9 | note | Responsible Person - Surfacing Supervisor
6641f9c3-b7f9-5f2c-9817-1cd9eeaafd23 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
6f1452ee-b3fc-575f-8991-6b1bc8f30d29 | note | Conduct - C
0e081aa7-3cda-5109-a715-df2db0708395 | note | Produce Record - C
86a5b634-ddb9-56c4-8590-7bc5e9d730b5 | note | Approval - C
e630f910-fd1d-58f9-9803-316a0553c798 | note | Witness Point - Y
| checkpoint | Rolling
86da7525-bc95-50d8-ab9d-e356a636e059 | note | Controlling Documents - Chipsealing in NewZealand
f6f81ae7-b365-50cb-8660-75135b995383 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
0c0c606e-da98-594a-b650-abb4041bbce9 | note | Method - Visual
96be5f10-1ae1-53cd-a4a7-eaa57b2af047 | note | Frequency - Each Site
762625fb-d27d-5b2f-8a2b-859cbb050cae | note | Responsible Person - Surfacing Supervisor
d442dd00-bbc7-532e-944c-48d0f8701ed3 | note | Verifying Document - Chip Sealing Quality and Site Record
7136eaa8-c5ad-5b87-9373-666bd2f17fed | note | Conduct - C
c4d27a78-61b0-5ad4-ad1c-5a064deba3cc | note | Produce Record - C
d93918d3-2884-53b2-8c7c-ae514337e89a | note | Approval - C
6288db74-9d54-5f06-b69b-1424e75c5c92 | note | Witness Point - Y
| checkpoint | Cleanup
14dbfc9c-d2a3-5689-bafb-adacc7e6e224 | note | Controlling Documents - Chipsealing in NewZealand
57d021cf-c83d-56a5-a3b6-77fc6a8b81f8 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
92ffe9d0-f865-5663-aae2-77a225ec48bc | note | Method - Visual
76d6ce85-029d-5987-ba4b-8edd408f33c0 | note | Frequency - Each Site
148486dd-c139-5ccd-bc5e-d08821528b0a | note | Responsible Person - Surfacing Supervisor
b789bfc4-2289-5cb8-8554-4df2f31ac198 | note | Verifying Document - Chip Sealing Quality and Site Record
4cf509c3-c472-552f-83f2-016237455654 | note | Conduct - C
fdb0b18d-d93d-5424-abbc-030111abac02 | note | Produce Record - C
083a6338-4e76-5dbb-87a2-e32f9df34899 | note | Approval - C
f5c5f0fb-d40a-5fc5-8b21-0e665ccee2b2 | note | Witness Point - Y
| checkpoint | Post Sweeping
47c2dc52-0244-509c-993b-62e8213e219b | note | Controlling Documents - Chipsealing in NewZealand
9d417684-edb4-5e9b-b23d-c02910f54c1d | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
ea60a879-3ccd-5b7f-b32a-467e3ac6c8c1 | note | Method - Visual
06245e7c-41b5-51e3-ae38-70c645227d15 | note | Frequency - Each Site
77b79eab-60b8-5722-87ec-c81c0ac5184e | note | Responsible Person - Surfacing Supervisor
2b00215e-6553-53e3-a563-e90a2c5449e7 | note | Verifying Document - Site Record
d3751db6-3791-5ec3-8543-7e16aca85c8b | note | Conduct - C
edcff9d5-b8cd-5bdb-beb9-a1ee2b305453 | note | Produce Record - C
57a8b5bc-75c4-50f8-b9ee-52b1071194c0 | note | Approval - C
2cd75d6b-d29e-5417-8828-6dd61de9bf91 | note | Witness Point - Y
| checkpoint | Linemarking and RRPM Reinstated
5b2a8759-bbfb-5a52-bf84-37fa4f90eb63 | note | Controlling Documents - MOTSAM
ac53efd3-507d-517f-bc14-8d36deae3e36 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
0ba8e5fb-52b1-56e1-ba2f-914caa9d2c8f | note | Method - Visual
65e7904b-60bf-50a5-a8d3-8d8398a4984c | note | Frequency - Each Site
f62f9376-fdb4-5261-a418-1cc1e66eee23 | note | Responsible Person - Surfacing Supervisor
203d5237-e07a-583c-bf47-bdd4ebb48ba8 | note | Verifying Document - Site Record
3a77dad1-d219-57bc-a9b3-3ecc062e7814 | note | Conduct - C
6d1f798e-a983-584d-9644-a0fdca07c4ce | note | Produce Record - C
dc33ac2f-3156-552b-b8f6-fcc599c08ad0 | note | Approval - C
f73ee13c-1ab5-5b0e-ae37-f1763a9ec83a | note | Witness Point - Y
| checkpoint | Post Construction Walkover
59502f80-b188-56af-bdc6-d54d174c6acd | note | Acceptance Criteria - Formal Agreement
099031c0-aed6-520d-a9fc-5a5515b15269 | note | Method - Visual Inspection
8648fab9-eb1f-5129-a4c4-78a03fa8c18a | note | Frequency - Post seal sweep
ddf403c6-60f4-5006-a31c-a5a5f27299d5 | note | Responsible Person - Quality Controller, Supervisor and Engineer
32df7e02-6915-5097-a04b-5329ce3d1ec4 | note | Verifying Document - Meeting Minutes
77765ece-837c-5ee8-9083-92fb85c83234 | note | Conduct - C
dc767fda-1f06-5b95-b2ff-ae71e2472314 | note | Witness - C, S and E
8df952ec-4088-5a3c-a6fb-6fbb48482558 | note | Produce Record - C
9d87db4f-c330-5c9a-96ac-b5ad57527b76 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Resurfacing Construction Completion report
5a8cc672-08a4-508b-a91a-9956f381398f | note | Controlling Documents - NOC; MS 6.1.3
be41944d-6de4-558f-b80f-14ef9befecd5 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
6ce38cb4-c54e-58c1-9dfd-59f60633119f | note | Method - Record
6d6839a0-d67b-5757-a237-4bdf79bf129f | note | Frequency - Within 2 months of completing the annual resurfacing programme
8360c47b-e4f7-5785-99bf-9355fa8db2ac | note | Responsible Person - Surfacing Manager
b11a2705-6a21-5610-8dea-1971f2cdf806 | note | Verifying Document - Construction Completion Report
c272460e-bafc-506f-8c83-0e9a62154606 | note | Conduct - C
a3ff56b5-4907-5303-977c-ac41c19ba7de | note | Produce Record - C
c05c6f75-e3b7-5717-ae72-a82c69bc7a6b | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Chipseal Post-Verification Testing and Report
fd60a80d-8708-5a64-b74f-0eb035764019 | note | Controlling Documents - NOC; MS 6.1.3
0f865259-a8e3-5282-a46e-b127e8811f62 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
03c70815-b270-5b3a-a596-6668f0a33bee | note | Method - Record
7bfadd51-c01e-5339-9555-94df5e782be1 | note | Frequency - Each Site
76ebab6c-409d-5857-b0bd-b3644f0d311b | note | Responsible Person - Surfacing Manager
fe222ad6-df8a-5ef2-b038-54d35736cf23 | note | Verifying Document - Chipseal Post-Verification Testing and Report
6cdb14f6-402c-5978-9c22-489997143aca | note | Conduct - C
f8a11588-e277-52f0-b1b7-a974c1789ffd | note | Produce Record - C
599a4e81-bec7-5583-ad8d-b8fca5341511 | note | Approval - C
| signoff | HOLD POINT
| section | 6. Close Out
| checkpoint | Pavement Rehabilitation Construction Completion Report
9bb712e3-2b7f-55f5-bddd-350bbf83e887 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
961daab0-bc19-5e6f-952e-87af63fdc7f4 | note | Acceptance Criteria - Engineer Approval
d6c1eded-e8c2-516e-be84-dff5b5309f92 | note | Method - Visual Inspection
fd2d1072-40ab-524c-9b8d-6ddbb168b5cd | note | Frequency - ≤2 months of 1st Coat Seal
921c1079-5329-5a1c-8528-4289471d173d | note | Responsible Person - Quality Controller/ Contract Manager
782e3729-1462-55f9-9576-813b1ab12ee1 | note | Verifying Document - Signed Report
8e4688ef-793e-522a-9dae-6482dd3af673 | note | Conduct - C
295bfd13-be24-5c0e-9855-30cc6f438a02 | note | Witness - C, S and E
547a8b0a-2cdd-5b23-8d07-368899589894 | note | Produce Record - C
7e88d209-9618-5abb-b465-2283c919cc21 | note | Approval - E
| signoff | HOLD POINT
| checklist | ITP - Pavement Rehab - SH 30 - Phillips Cattle Underpass | itp | ITP - Pavement Rehab - SH 30 - Phillips Cattle Underpass | 0c78a845-d710-476a-9299-cdb41de756f6
| section | 1. Procurement
| checkpoint | Geometric Design
55891a7f-c4dc-5098-bf55-f704b63c2f8f | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
357bfb22-014d-5cd1-afb2-b043cd16b227 | note | Acceptance Criteria - Principal Approval
aae5c1f1-44a1-570b-8585-8e3d301d7d99 | note | Method - Contractor and Principal peer review
5f411046-8972-5d35-a32e-043528a495e9 | note | Frequency - per design revision
61ec7a46-7022-5886-af89-a70c15e76aa4 | note | Conduct - C or S
024aca0f-7a13-5ce8-b2ba-956acd5aaf8a | note | Produce Record - C
9d88c9df-8872-5dec-afc4-476f061ac873 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Pavement Treatment Design
0ab5eb4d-9d21-59cb-9378-d55e60af3347 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
ec527ab0-3cbe-51fa-95c4-7479f4f9ab51 | note | Acceptance Criteria - Principal Approval
90847fe4-8767-51b6-a931-2b3da277b35b | note | Method - Contractor and Principal peer review
89170e3a-8700-5bd3-880b-d3e38850ce23 | note | Frequency - per design
e939a987-a258-5a79-b4e2-66aad21bb449 | note | Verifying Document - Approvals Register - SH30 Frosts - Pavement Rehabilitation Design Report
aa88ef64-f137-5618-9145-034a92b3cb4d | note | Conduct - C or S
97e65601-3fcb-5c6e-a65b-a5b343429aac | note | Produce Record - C
cd5f226d-e55a-5183-8a5d-489b6dde193e | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
504b5c96-98c8-585b-a1ab-f4b23edb0f4b | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
2282f519-131c-545d-b3a0-f2c459c444b3 | note | Verifying Document - Sampling Worksheet
9cb9efdc-b7bb-5253-ae5d-12c8b72b9c63 | note | Conduct - C or S
01507049-50f9-5094-8951-45a72a298383 | note | Approval - S
| checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
2ce10fe2-8888-580a-84e8-50202f741dfd | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
ee155eaa-65b5-59b9-ad7b-b6db088c40e6 | note | Acceptance Criteria - Soaked CBR ≥ 40
0a86caff-ecfd-5391-89da-cd493d0c5605 | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
5029bcf7-9971-537d-b192-b97ab9026689 | note | Responsible Person - Supervisor
7216e995-91e2-59b9-acbf-05a8b1241a64 | note | Verifying Document - Test Report
77f08dd3-a2f8-588b-baa9-6d380748de16 | note | Conduct - Sp or C or S
3422bc27-fce8-549b-932b-cc26cdfa8dd2 | note | Produce Record - Sp or S
82d36674-2b9f-5e99-b44a-735384794044 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
ec60ce5e-2de1-5b34-a9f7-47879ebde8ef | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
0b404064-3515-58e9-9166-4c91635800ee | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
22d75be4-236d-544a-a4ad-b27ed2797378 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
363f74da-660e-5fac-b18e-7fe076980fea | note | Responsible Person - Supervisor
afd558ea-8f20-5377-95ec-6fcaff8a42ae | note | Verifying Document - Test Report
46b1b790-7457-55ec-95b3-e84c4a8ec02d | note | Conduct - Sp or C or S
98495e40-2b4f-5ea5-becd-0173ed8c7d06 | note | Produce Record - Sp or S
bc83ce9d-cc7c-5361-89e6-6e0adbfee9a0 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
b3f4bdbc-9078-5b37-83f4-44539b6269ad | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
d95eb089-7306-5269-b88d-b6fdb30fa7d4 | note | Verifying Document - Sampling Worksheet
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
bd3f3789-fe2d-5d1e-8922-6b08335f463c | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
9539f934-a40d-5058-8ffc-06b56105e828 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
9989b261-19b5-5b50-938c-ea96eb92f749 | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
06f5e424-fbfa-5131-8e0a-193a29753b9a | note | Frequency - One test for every 10,000m³ of source material
fb5a0c37-ea2c-5052-a386-e751f6e2dcab | note | Responsible Person - Quality Controller
f2094d7a-9c3d-5ad6-8d6b-d8e81d9cbceb | note | Verifying Document - Test Report
faad4441-5b45-54a3-886c-c39a2868cd53 | note | Conduct - Sp or C or S
665d6cb4-be36-5ed4-a2d2-02fd65633cb3 | note | Produce Record - Sp or S
4c798835-c006-516c-9741-9d0b2b327ea5 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
5ed6197f-9975-520a-a11b-2c8ccd59c734 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
9966411c-dd63-579b-9489-12dba6091e15 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
efcfdc8b-bec7-51ab-aa37-d10972ee6a13 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
40420efe-0ea3-5f2c-ab50-eb2281df9447 | note | Frequency - One test for every 10,000m³ of source material
68ba98bc-bb32-57b1-ad82-f6da4d557587 | note | Responsible Person - Quality Controller
a3b8865d-10b5-594b-8555-6b0c123e2d23 | note | Verifying Document - Test Report
55522b2b-6113-5e00-a5cf-549459dee3d2 | note | Conduct - Sp or C or S
01161f33-e3f8-5e8e-9572-9c9be1d77ede | note | Produce Record - Sp or S
2335fa82-b3e8-569a-9fc1-eed253961317 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
70e13dda-d6d6-573b-bb7e-352a9007ff4c | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
3ad0b210-2b0d-538a-8398-7ed05d7fbf01 | note | Acceptance Criteria - Soaked CBR ≥ 80%
f805eda1-621b-5d4c-b38f-b61a38460eef | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
a596b3ab-ac43-5128-ae4d-2785fec4af54 | note | Frequency - One test for every 10,000m³ of source material
7831b8ed-3c16-5b51-a75c-68e110fec0c8 | note | Responsible Person - Quality Controller
a6d84c22-37bd-5c6f-b8e0-57a62b690730 | note | Verifying Document - Test Report
b5196858-24ab-5cea-80df-a101c5c50d77 | note | Conduct - Sp or C or S
63517228-4fb9-58f2-82a5-5a0c53b2f968 | note | Produce Record - Sp or S
f831ae56-ddc9-57b0-8258-4297a5d0357c | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
809723f8-90b9-5d4d-b92a-9123111616e4 | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
7ce51850-0aaf-5cc1-bb5c-1c9800948a6d | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
2f592cd9-2ee2-52a3-87d4-f86421b68596 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
c0c2d977-bf7c-598b-a514-2a6537a9bfb3 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
49b28434-674a-58ea-9206-efb859d396d1 | note | Responsible Person - Quality Controller
ebc1006a-a472-5f87-ac47-66a92fef3b55 | note | Verifying Document - Test Report
122491c1-1eb1-59f0-9d94-9e179709dd87 | note | Conduct - Sp or C or S
aa8677af-7608-57f7-b39b-09f36bcbf371 | note | Produce Record - Sp or S
73d02d57-fb8d-5663-b0bd-89f04e9bb45b | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
57f594a7-2c09-57ed-9453-4ceb4ac61290 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
fd08cac7-8cad-536d-bce2-674182446f1d | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
3fa9b995-b902-5aa4-a38e-abc49f2c2cbf | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
2cdc575f-b359-55f9-83d8-cd1c0d834537 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
cab172c4-f0eb-5699-aa70-4ce310d9eeaa | note | Responsible Person - Quality Controller
f91aafe8-a7df-5ce6-a31b-26de19226ab1 | note | Verifying Document - Test Report
224afb40-de32-5783-a1ae-db4ed9c680ad | note | Conduct - Sp or C or S
5326eac6-daa6-5c8e-a4fb-9174097c1f7e | note | Produce Record - Sp or S
1c5cf813-cce5-562e-a13f-7f35300faeed | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
3550926a-ad61-5ff2-8b69-90de87efe148 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
68049b71-0f11-57ce-9dba-1ce1d1f98bda | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
079b9885-8d56-58f3-9ff9-04e0beaf0dd4 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
e7a15a41-8337-5588-8c2a-cb05507dec10 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
c197c53a-e019-511d-9afc-626d6c15d9e5 | note | Responsible Person - Quality Controller
7ad9e03e-fb44-5607-a3db-9b2769ed7129 | note | Verifying Document - Test Report
423b6510-61d6-5fe1-bc2e-e960d3f6aa62 | note | Conduct - Sp or C or S
693ccc65-fded-5081-a5fd-93a4e7af6519 | note | Produce Record - Sp or S
4dc50eea-e1c1-5814-97c7-27eccef79886 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: Cement - Stabilising Agent Selection
092606c3-d180-52e3-aebb-b35ff784b408 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
59b6c0ed-9bdc-550f-9755-bde92d40f3e9 | note | Acceptance Criteria - GP
9b8e21f8-cbaa-57e5-b52e-19ed93693361 | note | Method - Visual inspection of supplier docket
3c2cfa6b-c8d7-53b4-9044-fcf550d30f0f | note | Frequency - per truck load
2a868333-53ad-5498-abc5-11e1550ff1c9 | note | Responsible Person - Quality Controller
7655dd7f-720f-5f11-824c-c0c8678c1907 | note | Verifying Document - Supplier Docket Supplier Cert
c9219f40-5451-5c57-b4ed-c0b2438720bd | note | Conduct - Sp or S
befcb422-fead-5934-a22e-3c2fec873958 | note | Produce Record - Sp or S
56bb8c6a-d6fd-59f8-8695-f51ede26b49c | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Water - Water draw for stabilising
999c90a7-187c-5426-9ffb-699552e7bc78 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
83a13912-49ce-5e63-a32d-1d6de508d8e5 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
3cfdd9c4-8613-5578-8f5b-113e43f2536d | note | Method - Visual inspection of hydrant use form
d0f0afbf-69e9-5129-9ad8-c577de3fa83c | note | Frequency - per truck load
d33bc701-a219-5c02-965c-d0a2c0da29f5 | note | Responsible Person - Quality Controller
ab009f79-ed8c-5e23-a200-677480138a2d | note | Verifying Document - Hydrant use form
46714acf-3d48-5d67-84fe-63384d8db541 | note | Conduct - Sp or S
e1ccbf3a-ce1c-5a4c-9d9d-368a0bc46603 | note | Produce Record - Sp or S
067c30ab-1901-5ea3-8705-8c7302925134 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
9ef1abdc-0026-57b8-8996-c4739e32ae01 | note | Controlling Documents - TNZ F7 Specification
912e56ac-42bc-5d62-b035-e1a48f418f0b | note | Acceptance Criteria - Details on Docket
951baf73-a33b-52fd-896b-23356ecaa6a3 | note | Method - Visual inspection
ce95786b-02e4-5757-a727-0cc6ac7f5913 | note | Frequency - Per Delivery
43c40ca2-0873-5b98-a140-949cc83c97ee | note | Responsible Person - Quality Controller
904bbc09-5e76-5937-b8cc-f0c77c5d8836 | note | Verifying Document - MDS
2fcb9e6a-6f0d-5093-9989-f4c017cc6a41 | note | Conduct - Sp or S
376ae653-a462-56b2-86a1-5b1b1f11f24b | note | Produce Record - Sp or S
0f33f9c5-9125-5641-8c0b-07c2099b3004 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geogrid - Geogrid Triaxial Tx160 or similar equivalent
dfaec27c-edee-5a3a-a2d7-b783bfeaddd7 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
120aeea3-fd67-5a3a-9f45-46ddd51d805a | note | Acceptance Criteria - Details on Docket
c5ac1482-02aa-59a1-b19f-341f6dfc7b00 | note | Method - Visual inspection
6b4d5287-d0ef-5b24-ae40-e45ae522fdc8 | note | Frequency - Per Delivery
1e7ca707-fa24-5103-a943-524b0eb2c99a | note | Responsible Person - Quality Controller
8e4c0926-20d0-5367-ba5f-65b030c42436 | note | Verifying Document - MDS
2b1c67d2-19c4-590a-a7a3-b88f39b40e8d | note | Conduct - Sp or S
ab756d41-0fb2-5106-a2a7-5431dc8c7237 | note | Produce Record - Sp or S
7a5e4e24-ca41-5d44-8233-dab6e6f9d2e8 | note | Approval - C
| signoff | HOLD POINT
| section | 2. Pre-Implementation
| checkpoint | Production Testing of stabilised material - OMC/MDD
8deb2f80-a173-54e1-929a-09bca044e6bf | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
44469f1e-5ee6-5bd7-a3d5-3607e6f38f84 | note | Acceptance Criteria - To obtain OMC & MDD
550272a3-01fa-5355-973f-9fed35e07926 | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
0e908431-f3b4-572e-8b5e-61736827dba9 | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
cfc1df8f-2c85-5a00-a2a9-0de500ecb47d | note | Responsible Person - Quality Controller
a3837227-4efc-53ff-b899-4b28fb38f151 | note | Verifying Document - Test report
9fe1ef19-c20f-5352-9977-784c7495c3d7 | note | Conduct - C
87fe813d-3352-52e6-8e67-504c0986f4d5 | note | Witness - C
eecfaee2-3a6d-5144-851b-6a88673a2c8b | note | Produce Record - C
3c598d6b-9d74-558d-936a-0a8e23379b62 | note | Witness Point - Y
| checkpoint | Production Testing of stabilised material - Solid Density
7586d53f-b2c0-56f9-a9ee-ee4ff4778b03 | note | Controlling Documents - TNZ B/5 section 7.7
b1e2121f-936b-5c77-a5f1-438389b2ac8f | note | Acceptance Criteria - For info. and use in MDD calculation
b4e080cb-e664-5177-8679-d1453a41eb00 | note | Method - NZS 4407; test 3.7.1
9f7a958f-7011-55d9-9daf-1c89d8811ca4 | note | Frequency - Once on commencement and if any materials chage
28032fe4-7461-5961-ade5-83e4a91fd7aa | note | Responsible Person - Quality Controller
ee5a12ae-eaa9-571d-861e-e573e37f65de | note | Verifying Document - Test report
8432d9fd-03d0-51aa-91c4-1051f40e9641 | note | Conduct - C
19a218e3-3ca0-55cb-b6fa-52021f57fdf3 | note | Witness - C
4c80064d-da98-5df4-b179-0f31975146d3 | note | Produce Record - C
52e236b9-3b9a-5c03-bd09-f018cf3e378e | note | Witness Point - Y
| checkpoint | Project survey setting out
136b207f-8125-5565-b9ca-b169d3f1e343 | note | Controlling Documents - Reference from Project Drawings
cf8fdb06-85b5-511d-9116-433a43643bb9 | note | Method - Survey/Mobile Roads, Marks with Dazzle
15a468d6-a339-5c99-914d-be95bd8f432d | note | Frequency - Chainages for every different pavement sections
cbe1ca24-9315-5013-9760-f42a228c243c | note | Responsible Person - Subcontractor/ Engineer
8bded849-a63e-5a2a-a857-816db9770bfa | note | Verifying Document - Construction drawings
b68ee945-e2a8-5989-bc8c-c7193213a280 | note | Conduct - C
f3052849-82a9-506b-bc18-5cb79b01770d | note | Produce Record - C
| signoff | HOLD POINT
| checkpoint | Records Management (i.e. it is known what documented records are to be kept)
7e80666b-14a6-505e-b0cb-c5c327f1fffa | note | Controlling Documents - ITP and QMP state what quality documentation is required
b72e5fe2-9487-5b64-98a8-8050152939a6 | note | Acceptance Criteria - Filled in and Signed ITP
6f5361b0-da69-5687-81fb-81b95c8e6479 | note | Method - Visual inspection, recording and approval
4ee5fef7-2a2c-5bfc-bf5f-f0655ca3d0a8 | note | Frequency - As per hold points in collaboration with the programme
b12fe1b6-bd30-53de-a0cc-bc57bf72bf79 | note | Responsible Person - Quality Controller
c7ead943-0ccb-5bb6-a76b-dbba295429a6 | note | Verifying Document - ITP and all referenced documents
9abe68dd-0a09-55b6-bf28-11f40613a5cd | note | Conduct - C
b03f028e-6368-57c8-9498-c8c4d0d4e1ac | note | Produce Record - C
aa0a0a23-a871-5079-889f-c6862bbfab55 | note | Approval - E
| signoff | HOLD POINT
| section | 3. Construction - Pre-treatment Digouts
| checkpoint | Pre-treatment Repair Method Selection
d95fe112-fd8b-5ed7-8e87-a0c10830d5e9 | note | Controlling Documents - Site specifics to be confirmed
d6473fc1-7682-52b2-9744-998e4cd557dd | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
4de8789e-7876-5f28-aa77-c04bf5cb6db6 | note | Method - Scala Penetrometer on Excavation Floor
acd67c86-10a5-518d-8f24-fcc96de06927 | note | Frequency - As required
a6ee5a22-d0d8-5594-88e5-bdef68c44d68 | note | Responsible Person - Quality Controller
61dd06c7-c04c-561b-8a81-f3e46f22f9de | note | Verifying Document - Agreed treatment plan
1ad99f79-ce0f-585e-8943-c47205b91e54 | note | Conduct - S
a3e3d616-cebb-576c-b96b-94d908c4d2ef | note | Witness - C
1760e00e-0a14-511b-81a7-b57e8534a269 | note | Produce Record - S
23a07626-7349-5b54-99c6-94767ca7a320 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Excavation floor drainage
2b341eea-be51-528f-a710-45cd0f973a3d | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
ffb8a814-4811-56fc-9546-31102bebad62 | note | Acceptance Criteria - 4-8% toward edge of seal
15d6ca3e-aba2-5558-8e4f-7c78608b973f | note | Method - Digital level
785e459f-a736-5d8e-b014-f642ddbc425d | note | Frequency - As required
75912ba5-4785-5d0d-8382-2d7f5ca2eb4c | note | Responsible Person - Quality Controller
ed0374ef-e549-5421-8afc-c1442bdf908e | note | Verifying Document - Dig out QA form
01de7cb3-9062-5f79-92e0-babd98755989 | note | Conduct - S
9dd83c90-fe63-53a7-850d-380b4ccbca7f | note | Witness - C
0acd5072-2438-5e39-8ab7-b551116ef746 | note | Produce Record - S
a9ed1cf3-3958-56a7-8cf9-5671f7f8b323 | note | Approval - C
7fb504c9-a703-53e5-a87b-ca6d3e689ac4 | note | Witness Point - Y
| checkpoint | Subgrade material hardness Check base of excavation
edb94024-3390-5727-a60b-e63402b86742 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
d31ed717-7d32-582f-9664-8668146743b7 | note | Acceptance Criteria - Scala > 3 blows per 100mm
c8596a49-780e-5c34-af33-792947bbf0ec | note | Method - Scala Penetrometer test on base of digout
dc106a45-669b-53d4-ae69-ff655f4f0d03 | note | Frequency - As required depending on size of digout
dc726961-216e-5562-abe2-0c61624a28e4 | note | Responsible Person - Quality Controller
8d85f121-e32d-56f1-a55b-480600067ed7 | note | Verifying Document - Test report
b5ad9a3f-53ec-5dff-9cb7-8d24f51ff3ff | note | Conduct - S/C
74c59bfc-159d-587d-8053-7370fb025517 | note | Witness - C
90dc5e89-53dd-555d-99a1-6319cf945c08 | note | Produce Record - S/C
5ad6339c-d7fb-59ed-83da-78341c001b4f | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer
21d80e12-8fd6-5d6b-8124-ae2c64bd755a | note | Controlling Documents - TNZ F7 Specification
27690506-adbb-5235-a3e2-c521e490ece1 | note | Acceptance Criteria - Meet TNZ F7 Spec.
166d95e0-3c7b-5158-b9d0-b9d2ffb9b3f0 | note | Method - Visual inspection
420cb83c-894a-505d-915f-d7965961370c | note | Frequency - Per Delivery
c8e373ce-bba1-5123-b95d-aec0ba6d4f14 | note | Responsible Person - Quality Controller
34c124a3-f071-500d-bb59-021694062653 | note | Verifying Document - Certificate of conformance
ce4af8db-ebfd-51b6-84b6-c9d01365b93c | note | Conduct - Sp or S
152973df-1585-5ffe-b8f2-518ce17f9b07 | note | Produce Record - C
41607740-d13b-5d62-a434-2a1066cc6856 | note | Approval - C
4e2d3f16-1adf-5b1a-b506-4b6aea30bc92 | note | Witness Point - Y
| checkpoint | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer
98511352-b103-5df5-af5e-f4b139f8dbff | note | Controlling Documents - As per NZTA list of approved materials/suppliers
2399dfad-47bb-5288-9a4d-a578b7b4e745 | note | Acceptance Criteria - On the list of approved materials/suppliers
6cccc034-db8a-51c0-b211-97e906faed32 | note | Method - Visual inspection
02e1a62c-312c-542b-a96e-68365dff1481 | note | Frequency - Per Delivery
39a05df9-94b6-5540-806a-70f899cfa187 | note | Responsible Person - Quality Controller
4f946cf9-f417-5d5a-90e2-f484352cab4f | note | Verifying Document - Certificate of conformance
06ce9acb-fa19-5e49-a8e8-a4982c96282e | note | Conduct - Sp or S
061be56d-e01c-50af-9add-f826af78eb58 | note | Produce Record - C
7b4443f8-b3cf-5812-9862-ca6782d284ef | note | Approval - C
2f119ab0-b56e-540c-9ecf-910ba2507940 | note | Witness Point - Y
| checkpoint | Place and compact GAP65 in digout area
bca6d3c9-8628-502d-b5e3-ca6d70fcf2b2 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
bf42960b-7d48-58ac-8cc5-4816e0c7b284 | note | Acceptance Criteria - Clegg > 45
4ce235c7-d28f-5f7e-8307-a8ee2c970eb4 | note | Method - Clegg Test
ec33289e-91d4-5166-b9e3-6df4db1a3317 | note | Frequency - Min. 2 per digout
0999a935-5d0c-52b8-9dba-76e185bd46da | note | Responsible Person - Quality Controller
082802ef-8577-5d3b-8957-8bb056ab5b09 | note | Verifying Document - Test report
37fad31f-924e-5fd7-b1ab-376d71c14e14 | note | Conduct - S/C
9510db57-749c-5b2e-9748-882dceeda1d5 | note | Witness - C
0417e6cc-9353-571f-b74d-bfb071f2d277 | note | Produce Record - S/C
06b6d03b-ffb1-599d-8a02-9c81e0d80c82 | note | Approval - E
| signoff | HOLD POINT
| section | 4. Construction - Granular make up and In-situ Modification
| checkpoint | Place M/4 AP40 Basecourse Material
dd9a6536-ff9f-5b07-a7e2-12d2a287c221 | note | Controlling Documents - TNZ B/5 (section 7)
6e2a8181-5b77-5634-bc00-3b1ac40fc4db | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
31a62351-e961-514d-9210-3b591ff21c7d | note | Method - Visual Inspection
00f8d5a4-ce11-5b1c-8dd9-b9dbcef25a50 | note | Frequency - On completion of placement
a4c188fd-c14d-54fc-afba-57cb202de52f | note | Responsible Person - Quality Controller
1a7f99e3-8649-5ec4-bd08-7af99afb7783 | note | Verifying Document - Photographs and Daily Site Record
f7414495-b715-517d-81b9-6b5df8e00780 | note | Conduct - S or C
b75f1b65-244f-52a4-bd6a-4cc5b6454748 | note | Produce Record - S or C
25fba074-4003-5afd-9684-26de8ab0031c | note | Approval - C
646b10e2-0bbc-5616-9b17-74a42992eb87 | note | Witness Point - Y
| checkpoint | Spreading of Cement
998ef0fb-a211-5e41-8c55-c3a95b0cd7fa | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
84b3c6d2-f839-5084-b072-3cf42b6233ca | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
4323d15e-84fd-50e7-8aa7-2ed1c07ea5e0 | note | Method - Mat test (1m² canvas) and Average Usage Test
7b7d97b8-4305-5773-bd68-885bb293140d | note | Frequency - per 400m² and upon emptying the spreader
b5ddc6d7-5c79-5d28-94af-7c770dcabeb2 | note | Responsible Person - Quality Controller
6a7cd99b-7510-59aa-adf8-da905d09e393 | note | Verifying Document - Mat Test Form and truck dockets
6b7fe9af-f420-5aa0-b708-e6403c8c50c8 | note | Conduct - S or Sp
1f27f60a-9f57-52f4-97dc-74d9154821bb | note | Produce Record - S
06393bfa-b43b-5456-abbe-0efa3e848250 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Addition of Water
84e0d9a9-6da1-5b18-95d4-5285011a00be | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
13bb0348-9b80-5ec2-a41f-f4ba39dffdf8 | note | Acceptance Criteria - 90-100% OWC
dfd2c056-a53a-5005-9f9b-380a8b6718f8 | note | Method - Nuclear Densometer Testing prior to Stabilisation
64968012-0079-573e-afcd-a49fc9d53a7d | note | Frequency - ≥1 per 1000m² lot
311b43f4-6281-5f76-b33b-ff29ebb26a3f | note | Responsible Person - Quality Controller
d4add81d-b46f-5739-a712-f721f44d7656 | note | Verifying Document - NDM Record
6f663f76-d643-56e3-9bfe-cbf59191dfb3 | note | Conduct - S
eeef8d1e-a61d-53c4-a65e-602293e174a4 | note | Produce Record - S
6da2e637-4bc1-534e-821e-b22eb9d493d7 | note | Approval - C
7d388d76-832f-5b53-b75d-7e27e3160e10 | note | Witness Point - Y
| checkpoint | Cut Depth
74df6b11-3f01-5dfe-9562-cde0f5025686 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
a48e2c65-2deb-5c71-930e-3949e7f3278b | note | Acceptance Criteria - -5mm and +15mm of design stab depth
0f94ecb4-83bf-55cf-98d5-af4b393ee336 | note | Method - Physical Measure and Visual Record
247705f2-04e8-5e04-bc79-c16e98268ca4 | note | Frequency - ≥1 per 200m of cut length
1cb6e6e2-ca9d-5945-8059-2e99204712ac | note | Responsible Person - Quality Controller
973eea8b-ae5d-558b-8525-ab2312172019 | note | Verifying Document - Photographs and Daily Site Record
03afbeb9-55f5-524c-8453-724b59c1b9c1 | note | Conduct - S
d21ee9c6-dbec-5537-b21d-0f27cab14e9d | note | Produce Record - S
731cbf80-ddd6-551c-953d-03ba487df1cf | note | Approval - C
d50ff9d8-f9d9-535b-88fd-d33e1b31f5a8 | note | Witness Point - Y
| checkpoint | Longitudinal Joints
1b109225-0fd4-5c2a-8318-0bd452c43044 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
3383b630-c519-5bd6-af26-4a5e7e374f59 | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
8ab11ed0-c9f3-5be6-b81e-59414c3ff572 | note | Method - Visual Record
a1b7e51b-9ccd-5bee-a5c9-3271cd023891 | note | Frequency - per sucessive cut
17eccc7e-a521-5514-b773-0c00003c200c | note | Responsible Person - Quality Controller
7b7200f0-9284-5a06-aea3-a3f2ff191255 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
0071d16a-c054-5c39-8844-f2359332a698 | note | Conduct - S
b93e2374-8fde-5d2b-bbb0-07532e0c41df | note | Produce Record - S
e16d8e18-48d0-57d4-abb7-bed929efcdf4 | note | Approval - C
6878f6c2-5507-5b73-832f-77af706b9397 | note | Witness Point - Y
| checkpoint | Continuity of Layer
c084f7f8-5a12-5875-acac-1c34f463c43e | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
2145bdcc-ca6b-5c80-977f-9518df5c8d4e | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
0e711b17-e528-5ffd-a626-bb403849854e | note | Method - Visual Record
355d73a0-fa9f-5b3a-a987-acffc66ddd61 | note | Frequency - per sucessive cut
fa5739d1-fe81-5636-a316-de1f12176c19 | note | Responsible Person - Quality Controller
7b62636c-cf60-5970-a808-bc80877131d9 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
27c71267-1815-5815-abe9-c2bc6cb1273b | note | Conduct - S
d9adecaa-cc88-5e18-b018-05de8d211d6e | note | Produce Record - S
fad05c63-8a3a-531b-899b-402afbd19932 | note | Approval - C
a5fbc7d4-fc44-50eb-afba-e0078fbf5d41 | note | Witness Point - Y
| checkpoint | Stabilised Material Particle Size
14caa18c-694b-5189-867f-06334b64f66a | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
2e40037e-f030-5bf7-9609-761b3096484b | note | Acceptance Criteria - No excessive breakdown of stabilised material
43ab1fc6-07df-5f44-acf0-d787e0a64c6b | note | Method - Visual Record
56072037-8490-5035-ba38-ded4f47b99db | note | Frequency - within 20m of each section and then regularly based on material variability
6e9d9675-d10d-5859-b465-69a6bea71736 | note | Responsible Person - Quality Controller
7cdf0da0-ac99-5ea1-959f-d42f1f60b021 | note | Verifying Document - Photographs
c7e1966a-1ddd-58d1-8887-d2cca5ce0c04 | note | Conduct - S or C
464336ec-33c2-562d-9eae-a4b6b40863bc | note | Produce Record - S or C
a5e979a5-7874-53c1-8209-fb913dfabfd3 | note | Approval - C
51a90eff-a78e-5408-a09f-3a790dd36075 | note | Witness Point - Y
| checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
483bb4ac-a45f-5c2e-8200-6b811c12cfa6 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008
db829b98-124c-57f3-9d26-45c33ddd6539 | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
f7c2cd94-5fa3-52e4-a4ed-def01bea88e3 | note | Method - Plateau Density Testing
bc20c2c0-cd12-506a-b7f0-990599067307 | note | Frequency - 1 time, or additional tests when material changes visually
b9aa6c0e-bae5-56fe-b51a-186ddb81a135 | note | Responsible Person - Supervisor
ba164849-1b64-587a-ae8d-57e8c4b6dbae | note | Verifying Document - Test record
05c8b6c8-f145-51b5-a788-710e276ad54a | note | Conduct - C
c3c7eb7e-3a24-53b5-980f-5c91bbf5e173 | note | Produce Record - C
9a730f2d-39e4-5eb5-b28c-6f7fcd9ef559 | note | Approval - C
ca23655a-9abc-5387-a339-5f9fcd7c5720 | note | Witness Point - Y
| checkpoint | Establish Compaction Target
ed976a97-00f7-5dee-9843-94e48856e7a4 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
eb1ee92e-69f4-5c9e-b74f-56239860957a | note | Acceptance Criteria - To provide MDD for NDM testing
97126762-e456-520c-bf8a-ba2a6cd83d88 | note | Method - Plateau Density Testing
3a0c3129-30cd-5a85-b4a9-8870e62aa0b7 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
464c4fab-3bc3-510b-9b92-798203a05103 | note | Responsible Person - Quality Controller
6405c9a2-99fd-5926-b7cc-d263c792fd28 | note | Verifying Document - Test Record
29c2316e-eb62-5ed8-bf3c-ed7e3dcd6007 | note | Conduct - C
4f2bb2ab-37db-5c07-8b71-b892f9a48630 | note | Produce Record - C
30d147be-2677-5a40-aeca-b03f7631567b | note | Approval - E
078cdbbf-1dbf-5cb6-9dd1-4a7bde667abe | note | Witness Point - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
de434d66-bc90-50eb-a093-a270ab8ecf1e | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
25de266a-2ecc-5c57-bd3a-881ad320f7be | note | Acceptance Criteria - To provide MDD for NDM testing
b58dfd39-a01a-5390-9055-ef3fd0a9223e | note | Method - 'Laboratory MDD at OMC NZS 4402 test 4.1.3.
676e10ea-ceff-5e9c-a362-766f022b416b | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
f838e195-127b-5cae-89ef-d600ef99dc24 | note | Responsible Person - Quality Controller
4f9370ed-fb45-5d92-ba65-9482e04c6c9b | note | Verifying Document - Test Record
f49f0410-7e10-5dd6-bcf1-05743e891c4a | note | Conduct - C
05eac426-109b-527b-b811-800bcc2b1d6c | note | Produce Record - C
c2eba2e6-50b0-5581-a0b9-7ae5f406926f | note | Approval - C
8cf65d8d-3a00-56ef-baa4-1ef82f85b826 | note | Witness Point - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
1d2811d1-8b66-522c-8ca3-11e86c5dec7e | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
4df3c65c-ce91-5de6-8291-92dbd026368c | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
a0fb484b-8ac3-52ca-9ed3-dbc65b970b25 | note | Method - Plateau Density Testing Lab. MDD
10c92016-5bc6-53be-8256-131247933d70 | note | Frequency - At commencement of construction and whenever materials change
a4b69acc-16c0-5c8a-86cb-3b366e531d5a | note | Responsible Person - Quality Controller Engineer
3c6db2fb-dbbd-5aa5-8a3d-9cc7315d4715 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
0ebc781f-2c4b-5d2f-b910-1c5da7602645 | note | Conduct - C
4bfac193-0e64-5d81-84af-799412ca7e06 | note | Produce Record - C
b1779027-084d-5cce-aa7a-cf9aab7e3c60 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Compaction Acceptance
dd783c85-1ed4-55c1-aa64-599002eaae96 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
5bd2df2c-97e3-5c57-b512-b8978addfdf7 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
6fbd2bdf-cf54-5059-9a29-0987fbf91b19 | note | Method - Nuclear Densometer Testing
889a876e-0d4e-510d-a3fd-a4ef8bfe31a8 | note | Frequency - ≥ 5 tests per 1000m² lot
c4ac198a-ff6e-5236-ad1b-a6039d0106d1 | note | Responsible Person - Quality Controller
75a382ab-3090-54b7-9700-79d480de1d37 | note | Verifying Document - NDM Record
bfdd3098-648b-507a-b107-0e86148415df | note | Conduct - S or C
914a6ee6-5a66-5811-bc3f-bf3b3380a298 | note | Produce Record - S or C
53c4bd42-24cf-52c8-ac0d-330530dd9749 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Control Testing (if required)
d65e26af-0a22-55ac-b5be-13f28a5245ac | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
ab2beff9-c351-56ef-a951-c0d8716972ec | note | Acceptance Criteria - Nil
63a7f532-108e-5e6a-bb02-d39f0915c220 | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
c658654c-2185-59a4-abc9-e515e7604876 | note | Frequency - when agreed with the Engineer
bb8deab2-ccd7-5e7e-a506-875561d96288 | note | Responsible Person - Quality Controller
e394788f-43cd-5c8d-9c38-b8911d2b7e76 | note | Verifying Document - Test Report
f4a22173-49d0-5830-a533-9b9cc3be4d88 | note | Conduct - S or C
07a7a13f-5e9e-503c-9c57-b89faf20bb4b | note | Produce Record - S or C
87c8cbd7-2ed9-588d-a194-c67652b6e2f0 | note | Approval - E
| checkpoint | Surface Smoothness
00f021ca-edb6-55f1-ae5f-8d6540403900 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
6b196ada-6b5e-50a6-985c-4fa68e1872d4 | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge No water ponding
1168fec3-f10e-5cd9-88a3-b6a31a1b06d5 | note | Method - 3m Straight Edge
75efa989-7688-547d-8431-29c677f06d20 | note | Frequency - during construction and prior to seal
b362186e-7e12-5bbc-b9d4-08b90a6b4bf8 | note | Responsible Person - Supervisor
df44e4f7-83ed-539a-90a3-501335d8019b | note | Verifying Document - Photographs
cfbc29c0-6f63-5656-bb26-270fbf4b81f4 | note | Conduct - S
610d8147-0ac5-5e3d-9bc8-3f9b76d1bfd5 | note | Produce Record - S
1cdc2582-69b6-5b73-be2a-dd05b7511298 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Shape
59efc286-1186-56af-bedf-eafc1179d626 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
fef76849-6597-55c5-a493-2095c1f328d7 | note | Acceptance Criteria - Between -5mm and +15mm
a2268143-c82c-5da5-9035-e7aa6f00aee8 | note | Method - String lines or Survey Asbuilt
a28f8490-db12-5b91-926a-ed28d8e51f56 | note | Frequency - during construction and prior to seal
22dd41e6-c676-517b-a0bd-82f777adea85 | note | Responsible Person - Supervisor
6e5ed88a-8c4e-592b-a3c9-4eef3c14dcdb | note | Verifying Document - String Sheet/Survey Asbuilts
0d16b8a4-4b17-5ebc-861f-0334bcdba203 | note | Conduct - S
c828d8a3-ad3d-58c0-95ff-7a57e19ed17a | note | Produce Record - S
3bbd0bfb-efa3-5c13-8765-ec3f7c920b65 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Cross Fall
8ee3db6b-d78f-51d4-aba5-4720a1048b08 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
9c19dbef-f3bf-5839-999c-5a0149e76f8b | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
86972e94-3aa6-567c-b1ec-17d95a1f763b | note | Method - 3m straight edge or Survey Asbuilt
80570d4a-c954-544c-a7ba-aa8d85d8cd85 | note | Frequency - during construction and prior to seal
5f10a288-93b8-546d-ae01-05af398bd0be | note | Responsible Person - Supervisor
97072470-5bc4-5f6b-a359-2e5b13cac767 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
00c32272-360b-5598-88bd-ff9308ca58a3 | note | Conduct - S
2095d62f-b59e-5156-8d37-47560dc01bf6 | note | Witness - C
58b5dde1-abda-5a55-98bf-ac7efd43de87 | note | Produce Record - C
1e932b8c-06d9-5eba-9d49-846dfc1771fd | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Finish
717ecd0d-5d93-50ed-8abd-0d945d938b75 | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
39fd4be2-3d7d-53d2-a10f-f81fa8136a34 | note | Acceptance Criteria - Tightly bound matrix post sweep
0135664f-e0f9-53c4-9e0e-a22c01a15502 | note | Method - Visual inpsection
f384feb9-e296-552f-9c54-7432c42aaad6 | note | Frequency - prior to seal
75371d36-8152-522d-a796-1f7b23608ad8 | note | Responsible Person - Supervisor
565d250b-fc28-5cf8-aeb8-ce8b268045a3 | note | Verifying Document - Pre-seal inspection sheet
a6ca1b5e-4ee9-5178-bb51-f32609e88789 | note | Conduct - C
83d92f4f-f1dc-5e9e-82be-78864d3531fe | note | Witness - C and E
18fccf80-5e57-5150-b3ed-8cdd6cd7f83a | note | Produce Record - C or S
42ac604b-bfd5-55b5-ad4a-a1e67c276162 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Degree of Saturation, DOS
60536808-1241-5278-b0e8-bd42404af827 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
20264316-9bc4-5055-a6fc-2fb3bd92e98a | note | Acceptance Criteria - ≤80%, however 65% is ideal
ce361aea-c49b-552c-95c3-bdc374ee7139 | note | Method - Nuclear Densometer Testing
729f34cf-194a-58d1-9a48-85d02b2d0b7c | note | Frequency - ≥5 tests per 1000m² lot
e9ea0bbc-92c7-5155-a2bb-e7a63317004b | note | Responsible Person - Quality Controller
295c06f9-d526-5a91-871f-ecb24a8f5733 | note | Verifying Document - NDM Record
b878d0e9-24c8-5e3e-939d-aef74f9ef6df | note | Conduct - C
c65a81ed-6940-515f-8d62-3fe95d8da4d2 | note | Witness - E
ac089038-5bdf-561b-9aad-8c1af2a3b1ec | note | Produce Record - S
b1f8f3e2-3647-5139-8624-447600e2755a | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Benklemann Beam
723c1133-07f3-5f9e-b929-4ba29c2e8a91 | note | Controlling Documents - 'NZTA T/1
be6b1f70-32f8-592f-a6f8-7c78be43acba | note | Acceptance Criteria - Using a MESA > 0.1 for asphalt carriageways < 10% of results to exceed 90th%ile Avearge < 0.9 90%ile of 0.9mm Maximum 1.0mm.
5494ede7-efb2-5aca-a0f1-5933e01af5ba | note | Method - NZTA T/1
badcb3b0-a882-5217-9b1c-fb0a797af063 | note | Frequency - Alternating wheel Paths at 10m centres along alignment.
6f671b9c-99cc-5dc7-a2b2-16fb5628395d | note | Responsible Person - Quality Controller
38ac6f43-572a-57b1-9b3e-eb3db354d3cf | note | Verifying Document - Test Records
d4a7d4aa-7829-5724-a17a-30399501c9e5 | note | Conduct - C
7b0f5214-92cf-53b5-af2b-b4dd28a567c9 | note | Witness - E
dbe35027-7bb7-51e4-b5f3-4d19b2909edf | note | Produce Record - S
a122c8eb-e225-590f-ba4a-b8ca3bca5cbb | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Roughness (NAASRA)
8a9aa307-cb30-5093-b9b8-eaa297130319 | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
a1a2de1a-575d-5e43-9300-131d0ace28a8 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
685ebafb-2b21-5498-904c-859e1e67652e | note | Method - NZTA Maintainence specification section 6.1.2
5474685d-a999-5d37-889f-7e7f7b671221 | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
8e3f8d09-0825-5fbb-ae90-b16dd3c06567 | note | Responsible Person - Quality Controller
86ecc7bd-9d4e-5bee-a2f7-f7cba1fdf6a8 | note | Verifying Document - Test Records
1a6a1382-d552-5668-be98-76d7fb3ebb3b | note | Conduct - C
b52da706-87ce-5003-baa3-c378255e2b1f | note | Witness - E
5435e09e-6761-580c-8a6d-281c75cc0a98 | note | Produce Record - S
1eaa34d1-1cd5-5ebb-aff0-9d13544d8c1b | note | Approval - E
| signoff | HOLD POINT
| section | 5. Chip Sealing
| checkpoint | Binder - Penetration Grade
c6ec25a2-857d-5758-afa0-4adcb1fecdbd | note | Controlling Documents - TNZ M/1
65e4cd91-dce2-53ce-82f9-4e39fe6050c6 | note | Acceptance Criteria - Table 1
b07382b7-1992-5ebc-a5f7-c9b1b0d91492 | note | Method - Property Test
878ff148-02fb-5532-a525-37c7427f4dee | note | Frequency - Annual
f6f8313e-b79c-51b5-a9ec-e74e8bce12b6 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
7a26917c-da3e-5d07-8e51-e897c98fbcaa | note | Verifying Document - IANZ Report's
455ddaa0-c0f5-563b-99ca-397f5664c871 | note | Conduct - C
214ae2b7-f141-53dd-b1b0-957f51977dac | note | Produce Record - C
e5216d5e-7de1-5f24-b4ee-051491ae9e27 | note | Approval - N
d02585d4-ed7c-59d0-adab-43a7d3a2d1b0 | note | Witness Point - Y
| checkpoint | Binder - Polymer Modified Emulsion
000e0a7d-952f-55d9-aeb2-ef0ccee1a52f | note | Controlling Documents - Higgins Internal Specification
24469e81-8f27-5b4a-a8d6-1e67eabbc6af | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
3613f76f-a2b9-5e2c-9d06-0464679a7cbf | note | Method - Property Test
d40917a5-2040-5a26-b137-c23ef548e579 | note | Frequency - 1/100,000 litres supplied
5b00414f-b3ef-5742-8d8f-c185ecf17715 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
7201f22a-4d48-5493-a047-efcb43dbff21 | note | Verifying Document - IANZ Report's
ec3f2418-a79a-59c7-89ce-18d1f196217a | note | Conduct - C
0452d11c-f893-5c97-b308-e72197a8dfe4 | note | Produce Record - C
e78aaabb-1a4c-5613-babc-7289defc05e8 | note | Approval - N
56006dd3-561c-5dc3-8503-3569413657d7 | note | Witness Point - Y
| checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
3abbdc33-4a27-56ce-bc58-d681bfd43e73 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
87c5481b-8e12-573b-a828-679e020457c0 | note | Acceptance Criteria - <10% fines under 230kN minimum
9d18ba28-3927-5d42-acbf-5ec050c079a6 | note | Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
3655044f-1512-5f7e-986c-b8f91b346aa7 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
b441338c-3fe3-5272-a38e-4115db7f8b81 | note | Responsible Person - Surfacing Project Manager
acf5d97b-9685-59c4-9dc0-c24caa710851 | note | Verifying Document - IANZ Report's
84421a47-a80e-5811-8493-f0baa06b7c06 | note | Conduct - C
3e433163-ec29-5cac-8b12-62a4878ddcbd | note | Produce Record - C
bfe54e4c-f7b2-55bc-8b96-301a011cf7f0 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
0eeb743c-be5e-51a0-8b83-b6e2899991ed | note | Controlling Documents - TNZ M6, RNZ 9805:2009
bab80eba-2109-5c0b-8fd6-39ded7d6a1a6 | note | Acceptance Criteria - AA or BA
165c0ff8-73fd-52f6-bc8a-989ecf8e361b | note | Method - Weathering Quality Index NZS 4407 Test 3.10
310c1029-dbf3-558e-8bee-8f461dd2fdf3 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
e1c0c8ed-3ff4-5565-a931-26b76a6efe0b | note | Responsible Person - Surfacing Project Manager
bf54fc5c-1196-5148-bec1-9f48297ab665 | note | Verifying Document - IANZ Report's
49c64d21-dae4-5dae-bb8d-e72ecb329a93 | note | Conduct - C
2a2aad5c-35f6-5bd7-b665-e41497dde62e | note | Produce Record - C
6a81ee04-c803-50c2-abd5-36ea2e68fd53 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property - Skid Resistance
9368cab9-c0d3-5bc3-be99-6a19c94a1716 | note | Controlling Documents - NZTA T/10
475905b8-ad33-5160-8158-a5d8e4eeb52d | note | Acceptance Criteria - Meet Skid performance Requirement
10dccd32-86fc-51f4-a6de-3a55d027f421 | note | Method - Aggregate Perfomance Method TNZ T/10 section 12.3
3cd70b20-e592-5afc-8cf6-8ee09f9555d0 | note | Frequency - Each Site
375f3aa7-9d8b-5cc3-8a2f-0d4b48d3e524 | note | Responsible Person - Surfacing Project Manager
11ccb447-b3f4-54c7-8e9b-d5ef0b1a5cad | note | Verifying Document - IANZ Report's
5d22b135-fdb7-52c0-af6a-3de80002f87e | note | Conduct - C
87220dca-90b2-544f-ae65-733af9d9c627 | note | Produce Record - C
941de711-8406-569e-96d7-33bb8b2a5de0 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
112939f3-830d-50ce-a48d-524124a26e5b | note | Controlling Documents - NZTA P/17, M/6
889db103-b9cd-5b06-a9fa-34aee77dbde0 | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
04b4af0e-3768-5a66-bcca-3bb070166b46 | note | Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
23f9d6c8-1f47-5393-b05b-c406666d23ec | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
a7880ab3-a7e5-57e6-b82f-66964a0310ba | note | Responsible Person - Surfacing Project Manager
b383ee8e-115b-5994-bf7e-15acc41f98bb | note | Verifying Document - IANZ Report's
1b2a388a-d392-58b1-9e1d-261473dd94aa | note | Conduct - C
e7d2f8f7-d42a-5501-8b30-dd0307e6bd69 | note | Produce Record - C
08493e55-5efb-57c3-989d-bb390c93bf81 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
8fa258c8-874b-534d-bb97-d3320c21b045 | note | Controlling Documents - NZTA P/17, M/6
a9ee7e1a-94c2-5ce5-87f3-7aa00249438a | note | Acceptance Criteria - As per Table 3 NZTA M/6
29fbc6af-955a-5dc4-b325-1068c0ba7059 | note | Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
11ce17ae-5d0f-5c17-aa0c-4d109d0b22b1 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
daaab824-1651-564a-a52e-93034b7d2fb2 | note | Responsible Person - Surfacing Project Manager
80b32252-98e6-5f5b-a13b-4d65af56376f | note | Verifying Document - IANZ Report's
d759ebeb-3124-5c5d-9116-e1cd9596f4c3 | note | Conduct - C
76ff7bcd-71f4-5aae-a9f9-b4c69238ab13 | note | Produce Record - C
b975a082-9e71-52d0-8745-975418a31084 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
e6763c95-a1f4-5b0c-b338-125dee02f608 | note | Controlling Documents - NZTA P/17, M/6
a44ac682-d894-59f6-b747-307826ff31c3 | note | Acceptance Criteria - Min. 98%
f8539811-4986-5eaa-899a-042cfcc92278 | note | Method - Sample Test - Broken Faces NZS 4407 Test 3.14
807b670d-1ae4-5368-aefd-bd83bef362ff | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
4b2d8e3c-ec41-5dc1-9981-ea5bd2799093 | note | Responsible Person - Surfacing Project Manager
154200be-28e4-522b-b7be-97b9ff2a10a2 | note | Verifying Document - IANZ Report's
f30bf298-43f0-5588-9bad-270be195dad8 | note | Conduct - C
9bf6288a-91fe-5d95-a8da-a2376111c493 | note | Produce Record - C
5a015b17-37ce-5c1e-be6c-979d99eebb72 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Chipseal Designs
c606527f-79db-532f-b169-ab23334e42c2 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
47e4ce9b-5362-52b7-b3dd-e46a4858e570 | note | Acceptance Criteria - Client Approval
20c55538-07bc-54c6-82fc-1720fff514d2 | note | Method - Review
a5ef98dc-0d0e-5233-aac3-efc53502663d | note | Frequency - Annual
79569a5e-1717-573d-82ce-50e173c8862f | note | Responsible Person - Surfacing Project Manager
ab5f1780-37e6-5c68-978e-7daa61c15ee0 | note | Verifying Document - EBOP NOC Design Report Acceptance
341f6b74-b964-596e-baae-4f3030b9863b | note | Conduct - C
8819e77c-d2fb-5aeb-a6df-af61daea61ef | note | Produce Record - C
43e03ecc-708c-5994-9ee3-f356a4f1db91 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Ensure limits of site are marked
09729a6d-d4d7-5c37-82ce-cb0a79f61979 | note | Controlling Documents - EBOP NOC Design Report
507a4395-c8de-5767-af88-fe2fdfda26fb | note | Acceptance Criteria - Visual Inspection
81c2c4c7-c955-5e0a-9200-01d9c2586829 | note | Method - Visual
42607468-a20b-5b9d-b237-ba996e98efb4 | note | Frequency - Prior to start sealing each site
04faef22-841f-5c28-9f47-e3e37853dad6 | note | Responsible Person - Surfacing Supervisor
ab16241b-9ef7-50f8-9e44-577730511c61 | note | Verifying Document - Chip Sealing Quality and Site Record
f434c720-7da5-5bba-8e3d-d95fd7de2fc2 | note | Conduct - C
253e9086-865b-5323-aa5a-129cae9c9468 | note | Produce Record - C
ce39e9d7-fd23-5f04-bafa-57652b4945e1 | note | Approval - C
f1a6a1e0-056d-51db-9e68-94edaf639f6e | note | Witness Point - Y
| checkpoint | Sweep surface clean of deleterious material
e9a0573a-8a1a-5a24-936b-dec60c0042c0 | note | Controlling Documents - P/17
d7175571-c875-5fc3-b01b-c946357fbfe6 | note | Acceptance Criteria - Visual Inspection
fb288205-4b65-5aae-bdde-9f09ad9e3d56 | note | Method - Visual
29963351-ea8d-5717-b7fc-1c6e9d2e13c1 | note | Frequency - Each site, prior to start of sealing
0392294a-b677-59d8-8e90-677ee9ac2eee | note | Responsible Person - Surfacing Supervisor
9bece01e-28b0-5795-a9b6-27170ddef7f8 | note | Verifying Document - Chip Sealing Quality and Site Record
6582f98a-1693-5c33-8247-38f1af0867d2 | note | Conduct - C
9d957d3e-4b18-55b4-bd68-d70f09f38141 | note | Produce Record - C
14fc1dc9-df51-56ac-bdbb-b32b63b52bad | note | Approval - C
b815e0c9-d97e-5b86-9654-0ab92bc319ae | note | Witness Point - Y
| checkpoint | Record ATP's on site
fd7eea25-9c69-569e-a801-2af7244f3054 | note | Controlling Documents - N/A
036141fa-5f34-515f-a35d-da4d6d7ad354 | note | Acceptance Criteria - Visual Inspection
5b0d4752-0183-58ac-9c96-2d4eb6614f8e | note | Method - Visual
ec1d1522-5625-511c-9ac2-26a63da2a07a | note | Frequency - Each site, prior to start of sealing
e541f0b7-20c7-5ab4-9750-122f15975bda | note | Responsible Person - Surfacing Supervisor
c0dd873d-3fea-503c-9e2c-c55d947415fb | note | Verifying Document - Chip Sealing Quality and Site Record
048ddea9-b87d-50d5-a5dd-c9e8b499d2c6 | note | Conduct - C
e33f2067-9496-5be7-89da-23fac86a33e5 | note | Produce Record - C
2639736e-fded-5f90-a44f-58f33bfb364f | note | Approval - C
780ecea3-88ce-5494-adff-77964fccc58b | note | Witness Point - Y
| checkpoint | Confirm correct treatment(s) and chip
fdf48158-c824-5af6-b0be-07fd160ff3a2 | note | Controlling Documents - EBOP NOC Design Report
f7c7b1ce-b304-5698-8a79-cf6e98031d39 | note | Acceptance Criteria - Details/chip correct
d9b183ce-2c6b-5c33-b212-a3ac58ad07d0 | note | Method - Visual
358f5230-3c92-5707-8a33-a8ce59f7c843 | note | Frequency - Each Site
8aa4da72-550a-5579-8b6b-f3a08af3e134 | note | Responsible Person - Surfacing Supervisor
f3ea0bae-b23b-5803-b51f-61b494f95b9f | note | Verifying Document - Chip Sealing Quality and Site Record
fdd00913-c6ad-5571-91ad-4a909db4b175 | note | Conduct - C
b7f0924c-28f4-575f-8460-cb8464071b1b | note | Produce Record - C
03b95ec1-b9dd-5701-a0ac-3c08579b36d8 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Cutback Bitumen Blend
1ebb6dd6-5309-57c9-bd19-a17a6c5140ac | note | Controlling Documents - RNZ 9803_0513
7959dff3-2791-5748-8ecd-2930136cc283 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
8a528c02-98ea-5ba7-b5ca-6baa7ef49534 | note | Method - Sample and test
644a1e9c-6ed8-594a-afdd-276b12f9e0d0 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
f3665172-801b-50a9-8512-bf118d8cdf53 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
c3844b43-86a7-5708-9c1a-aa5c7eed6b82 | note | Verifying Document - IANZ Report's
b15ea5ec-1eea-573d-8e98-8dc232f09cbf | note | Conduct - C
a2b11f1c-49da-5357-88b7-4357ad97e76c | note | Produce Record - C
96630544-1f97-56c7-b278-f4bb9db69e4c | note | Approval - C
71915116-bfd5-52d8-9eee-f71cd61a1f9d | note | Witness Point - Y
| checkpoint | Bitumen Application Rate
262e913d-5347-5e30-9cbd-84ad4cf42553 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
9f01da81-c074-5a47-a54a-44c984787ca2 | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
54a5da73-58b1-5d84-a1ee-c98020232431 | note | Method - Test, Review
6030537b-e207-5de7-8fee-e6bf2a6402ed | note | Frequency - Per Sprayer, Per Site
b7030b24-88f8-59da-a5c1-b3c6b1d661ee | note | Responsible Person - Surfacing Supervisor
5f4a5e52-5dca-51c3-9979-2135b805689e | note | Verifying Document - E/2 Certificate. Spray Sheets
9f5ebfaf-ea67-5f3e-84b9-1894335bbb5a | note | Conduct - C
0f4f1c13-0f87-5b41-8f60-28e82928b59d | note | Produce Record - C
63b70e40-8acc-5335-a50d-fb1859988109 | note | Approval - C
5e352b19-7ca6-5478-bbda-4250631290c1 | note | Witness Point - Y
| checkpoint | Chip Application Rates
7f7b8ec1-db86-5da5-8b8d-78d85b9f3a6d | note | Controlling Documents - Chipsealing in NewZealand
de1907c2-9a6f-567d-9cc3-c9d3e4a87640 | note | Acceptance Criteria - As per Chipping Guide
e79631bc-f427-5d6f-a857-a9fe3f522a34 | note | Method - Visual
6457960e-dbbd-5fd9-8a57-0c9f2267a5fe | note | Frequency - Each Site
48165e2c-f2c8-5711-93f2-1ed7f740c302 | note | Responsible Person - Surfacing Supervisor
5a1b014b-6d79-5927-a3c9-d7ec956fc965 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
f6e4c1e9-4737-5b46-a1c6-a57ff3918487 | note | Conduct - C
1438d41a-54e6-5ba2-b709-e1d474289b91 | note | Produce Record - C
6b820fa0-62d4-5446-940b-5f99c16d9b48 | note | Approval - C
1a76bb1f-d2ee-5ec0-8871-e29fead7c106 | note | Witness Point - Y
| checkpoint | Rolling
8b19b1f9-1b05-59ea-bf72-29bfa2b6f977 | note | Controlling Documents - Chipsealing in NewZealand
fe77b84f-d42b-5b33-8fe0-afe230e4ab84 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
44335deb-30d4-5abe-aa6b-d5470655a751 | note | Method - Visual
2fda0517-202f-5f2c-9867-b1b4c9116f5b | note | Frequency - Each Site
ab058c96-49f9-52d5-81db-9bfe88004253 | note | Responsible Person - Surfacing Supervisor
07ef51d0-c4b2-5f64-9aac-b7ac96e55613 | note | Verifying Document - Chip Sealing Quality and Site Record
70cd166a-164d-5a07-8793-9f91512da8c2 | note | Conduct - C
d8e49900-7fdb-50b9-97fb-3814218d40f5 | note | Produce Record - C
507c7fbb-5e72-560f-a8bf-f5789cef1119 | note | Approval - C
983457ae-6856-5dff-bf8f-8306c92856cc | note | Witness Point - Y
| checkpoint | Cleanup
82a0b75c-47ec-5e6f-a8ab-1b074f9bc9bd | note | Controlling Documents - Chipsealing in NewZealand
91e222d2-41fb-5620-9163-134844fa105c | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
2807698c-dfa1-5594-ae15-07b6b1d624f1 | note | Method - Visual
3c82e1d6-0149-5e1c-9f7b-908c2dedad06 | note | Frequency - Each Site
278bea54-13dd-581c-a81f-3f72d1b145f3 | note | Responsible Person - Surfacing Supervisor
01f24957-bf89-58af-820c-bcd5269d431d | note | Verifying Document - Chip Sealing Quality and Site Record
cb66a1be-49b3-5e1b-a982-17698b0f965f | note | Conduct - C
8c44946c-0458-5f6a-b71a-a4a906a7746d | note | Produce Record - C
209852e4-eceb-5334-b2f7-06401e715590 | note | Approval - C
e600b80e-3215-594f-931d-1d77f3b7c948 | note | Witness Point - Y
| checkpoint | Post Sweeping
61a04050-b4ce-5208-9b5b-22066a3f4dff | note | Controlling Documents - Chipsealing in NewZealand
63395485-c60e-5720-8041-16ffacd360f5 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
d7d2dad3-bc19-5b4b-985f-e94f305ffff0 | note | Method - Visual
037fbff0-eff3-5d49-8ad8-5352f9906402 | note | Frequency - Each Site
9e566d52-22e5-53ff-87fb-34f9b8fcff03 | note | Responsible Person - Surfacing Supervisor
b0f6db93-3978-5df7-8c3c-d09a23c914bb | note | Verifying Document - Site Record
b00381f0-062c-59c0-a3a0-72329966f748 | note | Conduct - C
3ca74df6-708f-515f-a7e7-281572fa3dd9 | note | Produce Record - C
ed68d523-2c9e-538c-b213-d4e882b70e1f | note | Approval - C
ec04deb9-b2d8-5a50-a6c1-8d39fc6bf599 | note | Witness Point - Y
| checkpoint | Linemarking and RRPM Reinstated
0d55f54f-954c-5a88-9fba-96945053606d | note | Controlling Documents - MOTSAM
b8d8f534-d1ed-5191-8b62-9a87c8ce3041 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
8d73ac67-da9d-5f12-a025-c6b1870b5ea4 | note | Method - Visual
b106d560-73d2-5579-84b3-811a7be8a094 | note | Frequency - Each Site
5a73436a-8f73-5f02-a836-0ee9317a1715 | note | Responsible Person - Surfacing Supervisor
50cfeb8c-fee1-511f-b735-fb0a01b13859 | note | Verifying Document - Site Record
8b0e4938-d4ba-5f55-9c50-4409ca0e3e48 | note | Conduct - C
eca9160e-955c-50ed-9ea2-7e4fddf2bf42 | note | Produce Record - C
5c05b05e-300b-5545-b03c-fd83ca1feb7a | note | Approval - C
4daaf312-5a72-549e-bd59-7a93dccbbac6 | note | Witness Point - Y
| checkpoint | Post Construction Walkover
724a1ef2-9b28-5b56-b036-56b5b8f9d342 | note | Acceptance Criteria - Formal Agreement
1fbdad21-9096-5011-abf1-3b40f060a05e | note | Method - Visual Inspection
53bcde7e-f8c4-562e-98a8-47c84be400c1 | note | Frequency - Post seal sweep
2db3a8cb-7332-55ad-bf38-d2d50e79c6ba | note | Responsible Person - Quality Controller, Supervisor and Engineer
af8521b6-beed-5ed5-af56-4da74ea9ebbc | note | Verifying Document - Meeting Minutes
99ad159d-d74b-50b8-83f5-c8521d720b44 | note | Conduct - C
8322c963-bb8b-59b0-bcfe-237816334177 | note | Witness - C, S and E
8bd46504-5b13-5871-ad19-6277e45817e3 | note | Produce Record - C
73df6001-0888-5862-a4a2-030da181033f | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Resurfacing Construction Completion report
b253889e-bd97-598a-a7f2-f779066d7741 | note | Controlling Documents - NOC; MS 6.1.3
99d07436-1c60-5d0c-88d7-b4112bc2d9c2 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
1a676398-ca73-5704-9cf9-a121480c8137 | note | Method - Record
42d2788e-53db-5ce6-9d89-c216c5a1b989 | note | Frequency - Within 2 months of completing the annual resurfacing programme
c662f65a-ced2-5eec-b5a1-8f2f83d7005e | note | Responsible Person - Surfacing Manager
db21ae16-20ef-5a21-a6f0-9713b5ac6b65 | note | Verifying Document - Construction Completion Report
e0bbef4c-dc63-5963-bb51-59d421a2fa6a | note | Conduct - C
85a8dafc-364b-51b0-a412-d582692d0d74 | note | Produce Record - C
36064714-1e6c-5a41-ab31-e42863a06805 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Chipseal Post-Verification Testing and Report
f2c757f5-fa97-5ae0-9f3e-d87d6394851b | note | Controlling Documents - NOC; MS 6.1.3
ad7ba93f-d401-5e3a-aba2-9462e074a4b3 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
bfd47ecc-3c06-5bdf-874d-746d75c4dfb5 | note | Method - Record
5dc78fcd-112a-59aa-aca5-f13d08a09394 | note | Frequency - Each Site
897614c0-1338-57f4-8518-f66b7cab0bc8 | note | Responsible Person - Surfacing Manager
a224e3a4-f854-56a4-a7e2-4fa6d340e125 | note | Verifying Document - Chipseal Post-Verification Testing and Report
c133809e-a32f-5fcb-bc1b-e38b3882e770 | note | Conduct - C
145c1e2b-4b89-5eb4-a924-99ff4f7969d4 | note | Produce Record - C
6ac86b9b-451a-5fb5-bb1e-ed783aa0bc35 | note | Approval - C
| signoff | HOLD POINT
| section | 6. Close Out
| checkpoint | Pavement Rehabilitation Construction Completion Report
8e432038-32b5-5639-8b9f-6d17933bd1d7 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
e71fcca8-75f9-58d3-b365-3dfa4d5dd7bc | note | Acceptance Criteria - Engineer Approval
52cba968-8aa4-5030-9ba6-5417d48a025e | note | Method - Visual Inspection
45bed24f-66bc-5480-99c5-a86238bada6a | note | Frequency - ≤2 months of 1st Coat Seal
4a44269d-7496-510e-9bbc-9da0103a4d43 | note | Responsible Person - Quality Controller/ Contract Manager
5f4b720f-7c5f-547a-8683-b13e39a372a6 | note | Verifying Document - Signed Report
68cd3cf4-06a9-50ed-aef0-0034e6256e17 | note | Conduct - C
31fc978a-703b-57bb-8de7-8abd8c56c875 | note | Witness - C, S and E
d6c95536-aa92-58fe-8489-3a0ea6251c5b | note | Produce Record - C
d0eb7022-6f74-5c4f-bde6-ca2173490cdf | note | Approval - E
| signoff | HOLD POINT
| checklist | ITP - Pavement Rehab - SH 30 - Regional Boundary - 01 | itp | ITP - Pavement Rehab - SH 30 - Regional Boundary - 01 | 04d1a778-50e3-45be-8056-356f10f2b7b0
| section | 1. Procurement
| checkpoint | Geometric Design
6797b391-571c-5ff6-a862-56075381857f | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
c9bf72e7-045f-5ede-9aa0-54d903a6a37a | note | Acceptance Criteria - Principal Approval
e5eade26-bf4e-5b89-a5c4-39f85b84045c | note | Method - Contractor and Principal peer review
ab1fa6d9-0e10-5df4-97d9-109ac239fa7e | note | Frequency - per design revision
ad3d7647-aa4d-5b1e-ae1c-4e82801f20c8 | note | Conduct - C or S
2295f10f-89a4-59ca-a545-7d822fa250e8 | note | Produce Record - C
1acd1d9d-754e-554f-935e-dc5ca31c52b7 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Pavement Treatment Design
3432bdfe-8563-5245-b89f-7bef33ce84c0 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
b06f8d09-dd87-5e27-8d2e-f7981b992ba1 | note | Acceptance Criteria - Principal Approval
4640d712-e827-56f5-82a2-a916cc740bd1 | note | Method - Contractor and Principal peer review
876ec3db-5534-5417-a2c4-2b39240972f3 | note | Frequency - per design
f11cdbd1-8df2-54ac-b49c-076ce2c12a6b | note | Responsible Person -
2f08d389-cf19-5569-9d3d-c3ac65728ed6 | note | Verifying Document - Approvals Register - SH30 Frosts - Pavement Rehabilitation Design Report
855e94ca-8f8a-51c0-b408-6085488117ef | note | Conduct - C or S
62899407-ea43-5ee5-899a-4826075455df | note | Produce Record - C
56c084f3-4f10-5160-a415-9ea23ff0d0dd | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
5f45335c-1f7d-5faf-b6a4-213322e91587 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
260b9ec9-1b09-5004-b092-de868746a8e6 | note | Verifying Document - Sampling Worksheet
e1083618-f7d8-5101-bd03-cf8c9eb93725 | note | Conduct - C or S
8f10b29c-ff65-5c8b-8aba-871bea11402f | note | Approval - S
| checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
05b8342e-cc45-5965-9e1f-41b928ae5678 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
bbc25732-0826-5ac0-b55a-ec0eed6d69fa | note | Acceptance Criteria - Soaked CBR ≥ 40
a59410cc-7c49-5b04-bf26-26a2642e518e | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
845b891c-60b2-5ace-aa9d-6675485148a3 | note | Responsible Person - Supervisor
98be216b-4557-5365-9451-5f008fd8816c | note | Verifying Document - Test Report
d91c171e-3f3b-5b20-91be-234c6d87941d | note | Conduct - Sp or C or S
44cdf47a-e810-55ea-b69f-70e572524c72 | note | Produce Record - Sp or S
5ca300d0-9908-5f95-bad1-8d05cff4b9ad | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
1393f070-2721-58fb-af1e-45499d374c90 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
36035ea7-39a0-5a4e-ae78-30f42980d4aa | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
18550b84-b9d0-5ccc-b94a-f27a930ba849 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
2bdce23b-4df9-5e2d-9eb8-185215007390 | note | Responsible Person - Supervisor
0d0c35f9-9ee7-5ad7-8b40-7b6a12702164 | note | Verifying Document - Test Report
f3fd00b7-4fb9-5bc9-b0bc-2b8424c20408 | note | Conduct - Sp or C or S
17ba5076-89f2-5934-900a-86851c40fcc2 | note | Produce Record - Sp or S
afd3960f-e3ba-509e-b07b-b2a0203e0252 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
8392a2ca-940f-5d1f-a33b-839776122767 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
d4a66c99-2d7b-5feb-a98a-5a121ca9d974 | note | Verifying Document - Sampling Worksheet
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
4a9785ce-38ae-5029-94f4-b6201cfe16f7 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
05e14a08-9d82-56e1-b967-c07d53597d82 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
e15dc2a0-5afe-5e9a-a3d3-1109d58684db | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
1671f2c1-514f-581b-b1d6-d133a7283033 | note | Frequency - One test for every 10,000m³ of source material
8f073e6e-2238-5fcd-b34f-39ff691a4d25 | note | Responsible Person - Quality Controller
34b6b92c-15df-5b7a-9ae4-14e53fb89707 | note | Verifying Document - Test Report
44c73571-b341-5f51-bb01-b8099c2d9c8c | note | Conduct - Sp or C or S
f70b9521-163a-5d2e-b11b-87c8789bf163 | note | Produce Record - Sp or S
4fd8fe3c-278c-5ec0-b6d3-a1675f5a5aa5 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
2d264988-0c0e-5be2-bf9f-bc759cd57fe8 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
8a9e0f9d-8c06-544d-8b95-6f365a94de29 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
4e051254-caf3-5ab0-9916-6dab80ea6a22 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
389b2636-c3da-5edd-b4c0-85ae44b20a6b | note | Frequency - One test for every 10,000m³ of source material
2622821f-7c44-5068-a69d-6420979d0b9b | note | Responsible Person - Quality Controller
f4cf4082-dcc3-57b0-8cc7-554fc985280a | note | Verifying Document - Test Report
97d90c96-c8ea-58a8-a4f1-e04d37432609 | note | Conduct - Sp or C or S
effa4c06-c0ee-5ad8-bf08-f0186ede042c | note | Produce Record - Sp or S
61c5ed98-c6f5-5ea9-a37c-0120daed7bdd | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
04fad4b9-0ff9-50a9-8601-b6b5fe3962b3 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
acc02f12-a36e-535a-8687-636fab2d9ef5 | note | Acceptance Criteria - Soaked CBR ≥ 80%
486828fe-c834-5aab-995d-337cb3e3894c | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
c7f620b6-36b1-5963-9cf4-e1cca162e0be | note | Frequency - One test for every 10,000m³ of source material
9aac538d-5006-5fea-aaca-926a02f1460a | note | Responsible Person - Quality Controller
f174cb2a-127f-526a-9a62-43717bf741c0 | note | Verifying Document - Test Report
9b1ffb67-528b-5302-8897-62bc88af6b7b | note | Conduct - Sp or C or S
7c976a09-78ae-59ab-8422-c71d1bf882dd | note | Produce Record - Sp or S
68421efa-4550-5c5f-8524-8c46a8c13769 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
804f225b-4106-5773-b55e-95c2e7501b86 | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
bba3afe4-6421-5bd4-a590-deaac90c7a89 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
00c9401f-1a43-5541-adc0-52c3758fbeb0 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
44883079-3472-55dc-ab30-eceb097fe082 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
096c500d-7e7c-5a77-b3fb-e7fc72aca465 | note | Responsible Person - Quality Controller
e7a0f2dc-8ba2-575c-af89-984fefffbfee | note | Verifying Document - Test Report
be83551b-eea7-52ff-82a9-7a5121fd02d2 | note | Conduct - Sp or C or S
cdc57115-9c78-5c7f-b9f3-71350d0c07d7 | note | Produce Record - Sp or S
211a3038-4d69-5465-9c50-e59de430c8fb | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
8dd75882-e50f-5ce3-afa0-1be64f0cdf75 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
8e3060e6-9923-5920-b81b-5d573a0f61fa | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
f0bda516-442b-55da-bac7-9b494962bc43 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
ed98eac7-0ccd-5532-bade-4f81ff854b98 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
07d28490-afe6-5903-8c9e-2151d9cd84ec | note | Responsible Person - Quality Controller
0735eba0-bf8f-55ee-b9ff-90312bb0ff20 | note | Verifying Document - Test Report
86f66818-f0a7-5e9a-88b4-cda3606ab978 | note | Conduct - Sp or C or S
aa7e9b27-688c-567a-bb0a-9fd9553ee9b8 | note | Produce Record - Sp or S
8c93a06f-c8cf-5420-9363-3d494a470530 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
a15f4cb0-445d-5dff-aaf4-f852cd672318 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
4e7dc21f-9354-573f-b931-30295f18f084 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
b89dc7a8-f290-5f35-b6a0-6e1af47d9592 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
bec2fec0-3a46-5fbc-8c9c-aa61e519ca67 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
d89bdbac-7ce5-5291-947d-7cc9ff93cd5a | note | Responsible Person - Quality Controller
18e58682-941f-5b90-bac0-5ae7ff187dd3 | note | Verifying Document - Test Report
1a302070-b6a5-5553-b368-94ed6167b0f5 | note | Conduct - Sp or C or S
da752420-dfd0-535b-8dd5-137b872ca1c1 | note | Produce Record - Sp or S
9fb33f71-0ab4-5b06-9835-f9997257c852 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: Foam Bitumen - Stabilising Agent Selection
0c83141a-0416-5eb2-8e24-6a4069e689c7 | note | Controlling Documents - Foam Bitumen (4.0.0) - TNZ B/5: 2008
4305da8c-9ebe-54ce-aaf1-2d94e30286f4 | note | Acceptance Criteria - Foamed bitumen shall be produced from 80/100 or 180/200 penetrationgrade, The bitumen shall comply with TNZ M/1 and shall be able to achieve a minimum expansion of 10 times
8b868017-8277-55af-86de-3085e450494f | note | Method - Record binder grade. Conform to Specification
e307d1ca-b6e5-5a84-9ecb-da198d4a3b8c | note | Frequency - Per Batch
773a7a6f-cced-5e4e-b5b1-2eadc97b176f | note | Responsible Person - Quality Controller
ee43efa4-5b42-5796-828b-96295b94468f | note | Verifying Document - Test Report
5549c7e6-9864-53d5-bbfb-8a3134e01ab5 | note | Conduct - Sp or S
0ad7bd4c-be4c-58f2-91d3-06b1937b87ec | note | Produce Record - C
8084d5e8-a980-5d32-bd33-1f0d510a389b | note | Approval - E
ffce5856-13b1-5b0d-ac32-d701eaabc047 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (1)
fc3e53b9-2ccf-5db1-8e3d-069fbb6288c2 | note | Controlling Documents - Bitumen (80/100 or 180/200)
9a16b946-22e6-5cc5-a339-13426a3e2be2 | note | Acceptance Criteria - Record binder grade. Conform to Specification
1ad58ed4-3094-5f9e-bc80-245564a9a158 | note | Method - TNZ M/1
685920df-c35f-5f81-8cb9-8611ee417e03 | note | Frequency - Per Batch
ca0d11b0-b5c2-5f01-b536-710669d7ea6e | note | Responsible Person - Quality Controller
b4580805-307f-56b1-97b0-d60b062e3d73 | note | Verifying Document - Test Report
4f93ee50-a8a0-5369-b6de-5166b39bda2e | note | Conduct - Sp or S
| checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (2)
ab91dc21-72ed-550d-9731-46ec77aa9869 | note | Controlling Documents - Foaming Optimisation
d06fba5a-388c-5761-a6bb-925d35053c10 | note | Acceptance Criteria - Determination of optimum foam water content
4ea64f07-7bcf-5700-adb3-353ae5cf3955 | note | Method - NZTA T/19: 2020
86db97d0-a3ff-5a92-b0da-637bb5624492 | note | Frequency - Per Batch
65c36a82-acd8-5069-bbde-c2fcb57e8d12 | note | Responsible Person - Quality Controller
7e899b0d-09e4-5d3f-8e32-f3874d7dab2e | note | Verifying Document - Lab report
fb4d0a92-c482-5d34-a2fd-69bfa4eac6d4 | note | Conduct - Sp or S
| checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (3)
d4ea25a0-768c-5907-8107-3de8ffe040dd | note | Controlling Documents - Indirect Tensile Strength, ITS
ea8edcf9-1bd7-5199-84ba-ace6fde69f16 | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa, Soaked ITS: 150 kPa to 350 kPa, TSR ≥ 70%
516ad219-2f19-56e1-ae34-116cebe6f0b5 | note | Method - NZTA T/19: 2020
addc677e-2fb2-50ac-887f-59c4a3fa62f3 | note | Frequency - 1 Optimisation test per aggregate type
26941cc4-d3cc-55be-9614-77f644730e84 | note | Responsible Person - Quality Controller
17c6ebb5-90ae-54b3-8abf-17d074471a87 | note | Verifying Document - IANZ Report
024b4db8-450f-5029-b575-c7bab07c72f1 | note | Conduct - Sp or S
| checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (4)
3a20dd4c-c808-5e0a-ab3f-4c794eb93358 | note | Controlling Documents - Unconfined Compresive Strength, UCS
37999d59-70b7-5d0e-964b-6d678e82a55e | note | Acceptance Criteria - UCS is used to calculate MR(Phase 1) and MR (Phase 2)
1eae6050-8997-59a3-a0fd-ccb05219a5cf | note | Method - NPTG Guideline
f7c0c6bb-0b77-5316-a6c9-457b3389645b | note | Frequency - 1 Optimisation test per aggregate type
8913d570-8141-55ea-bfa1-87c2414d4147 | note | Responsible Person - Quality Controller
4beb7270-2cb2-5d40-96cc-76243cfcc176 | note | Verifying Document - IANZ Report
a1bcf130-fcfd-50e2-87d1-d8d37539a84a | note | Conduct - Sp or S
| checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (5)
75e1bfa6-cded-5aff-858e-4bcce6fd52a2 | note | Controlling Documents - Modified Maximum Dry Density
7782a290-df6f-5e1b-9ab9-d9334d0f174e | note | Acceptance Criteria - To determine target density
e5369a81-ab27-58cf-ba2b-79ced622d5e4 | note | Method - NZS 4402.4.1.3
6e31feaf-1fde-5200-aa40-c5550c7ded07 | note | Frequency - At Optimised Binder selection
4155ada2-2810-530d-85ae-29432db94e7a | note | Responsible Person - Quality Controller
802ce3a2-9f1f-55dd-ab99-ae0296802910 | note | Verifying Document - IANZ Report
5fc82642-3e29-53dd-ad8f-ef0ea74d47f1 | note | Conduct - Sp or S
27b98db7-0942-56a4-96ba-37a73451bd7b | note | Produce Record - C
f2d6cb96-1351-5677-9793-87088341769d | note | Approval - E
2ab9da5b-67f5-5606-8fb7-c739c2576af5 | note | Witness Point - Y
| signoff | HOLD POINT
| checkpoint | Materials: Foam Bitumen - Water draw for stabilising
3a4ea0ee-36bc-5770-bfd2-8f0454a35727 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
1324a249-d926-5820-a0b6-c723e51be28b | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
6115c707-4729-5793-9d0d-d8bb29a0ab02 | note | Method - Visual inspection of hydrant use form
85efb1b7-239e-5f59-afc9-82c353111aa6 | note | Frequency - per truck load
10c11548-631d-5383-98d4-df133b270bd7 | note | Responsible Person - Quality Controller
2b13d7d3-c29a-5b14-b7b0-588ce1966c9b | note | Verifying Document - Hydrant use form
56651a2b-e055-50d0-bd1b-5fef38dc7527 | note | Conduct - Sp or S
59399936-14aa-584b-a198-aba4f81938ef | note | Produce Record - Sp or S
46b460c9-e90a-50c0-ab48-4cadfb6524f9 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Cement - Stabilising Agent Selection
e9f12537-d51f-58c8-8547-1d5f80b4b590 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
1dd2e202-0909-5e1e-8c04-b205fa9dea8e | note | Acceptance Criteria - GP
a7e390ea-f6f2-54fb-8e4c-3acd8eca5038 | note | Method - Visual inspection of supplier docket
5d8f7081-9cd9-56c3-a25b-1c4dc8e89817 | note | Frequency - per truck load
46dab3f9-bf59-5495-b2d1-365b2a8b5ba1 | note | Responsible Person - Quality Controller
1d65617a-25bd-5665-926b-05c3aa1cca42 | note | Verifying Document - Supplier Docket, Supplier Cert
cfc19f91-73b6-54ef-9323-36b8a1ff3b54 | note | Conduct - Sp or S
bf835fa3-73b4-548e-90da-25b5b82cd531 | note | Produce Record - Sp or S
eb5d5ab4-3764-5a68-ba84-b3d38bb0fcaa | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
24e8091e-0f62-56c4-afa8-f1dcb4215a60 | note | Controlling Documents - TNZ F7 Specification
a17e6e87-7c42-5bf9-998d-746fca096e5b | note | Acceptance Criteria - Details on Docket
0832ca99-436e-5d31-be6d-5a2d5212a0bd | note | Method - Visual inspection
0bf34e40-146b-5f0e-bd93-d44d9aeb06dc | note | Frequency - Per Delivery
017787a9-5a30-510a-90d8-0238da716b60 | note | Responsible Person - Quality Controller
8589ae78-d495-5cc5-899b-379ea35f7a70 | note | Verifying Document - MDS
ce45b1bf-bd42-5e52-89f0-3f0aeefc18dc | note | Conduct - Sp or S
54ea5ad5-83f2-5fb9-a825-4583352b48ca | note | Produce Record - Sp or S
8ead4d31-12f2-5a0a-ba43-92fd832d395f | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent
0d84e8bf-907c-539c-a021-a7f63fe47a05 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
8303cebc-c3a0-50d7-bb67-438be3018803 | note | Acceptance Criteria - Details on Docket
cafc9b8b-67be-511b-b7c2-38e0ab3dfca3 | note | Method - Visual inspection
a128eb69-337c-5090-bd2e-871064cfed4a | note | Frequency - Per Delivery
f8c4b228-8146-5afe-a357-86074725c575 | note | Responsible Person - Quality Controller
6005a5e6-50ac-5be3-8890-67468f907e4b | note | Verifying Document - MDS
e14b471c-9123-52b5-8a33-512b24f5a556 | note | Conduct - Sp or S
6e9d9730-0e1a-5ae7-845f-0a7a858dff1c | note | Produce Record - Sp or S
e514d58f-cd4c-59a7-bc6b-df7df6c20df4 | note | Approval - C
| signoff | HOLD POINT
| section | 2. Pre-Implementation
| checkpoint | Production Testing of stabilised material - Solid Density
cb7a9535-4c8e-55c1-aa38-3cba479b1c41 | note | Controlling Documents - TNZ B/5 section 7.7
57f06d12-fae0-5211-bc9f-fc59367e0e4a | note | Acceptance Criteria - For info. and use in MDD calculation
01b6700a-b263-5a89-939c-3cc72e88889b | note | Method - NZS 4407; test 3.7.1
47523f02-9530-539c-baba-294612b40860 | note | Frequency - Once on commencement and if any materials chage
19b221eb-4770-54a6-ba59-51f760d33093 | note | Responsible Person - Quality Controller
032381f1-eba8-52d3-b59f-506cc1f574c6 | note | Verifying Document - Test report
54ab00ba-b8cf-5bf4-bce2-44e4f5fecadc | note | Conduct - C
481aa137-928c-537c-aeb5-6d6331c61107 | note | Witness - C
114fdcca-76b6-5d11-bdf6-368d01d9a2c8 | note | Produce Record - C
b9f53a6f-a248-59ec-be37-91635c73c99f | note | Witness Point - Y
| checkpoint | Project survey setting out
60382007-54eb-5d3a-8442-598d6a7a82cf | note | Controlling Documents - Reference from Project Drawings
06db5471-9f47-5bbc-80f8-9dbe62c5cdec | note | Method - Survey/Mobile Roads, Marks with Dazzle
29d8a768-c3b3-5122-bc93-33b4ee6afd24 | note | Frequency - Chainages for every different pavement sections
28c2a709-fbb6-5827-9694-e29c6a2fbe92 | note | Responsible Person - Subcontractor/ Engineer
48f6bf5b-df01-55a1-a0ae-c9aace0e1cb7 | note | Verifying Document - Construction drawings
eb14c243-e6a4-535d-89f2-539841195e3c | note | Conduct - C
d593bc04-6293-5b05-a13d-c4e95bcf531d | note | Produce Record - C
| signoff | HOLD POINT
| checkpoint | Records Management (i.e. it is known what documented records are to be kept)
26c3e425-a99e-5804-bd6e-77d32352fd0c | note | Controlling Documents - ITP and QMP state what quality documentation is required
cec39810-14ac-5df4-8581-b9996688fc13 | note | Acceptance Criteria - Filled in and Signed ITP
c1a831dd-b9e1-5376-b5c1-35e855226141 | note | Method - Visual inspection, recording and approval
3e643cf1-0ec6-591b-b94c-64c8a42242a8 | note | Frequency - As per hold points in collaboration with the programme
f15b7dc1-9614-5e54-a364-a878d04bec51 | note | Responsible Person - Quality Controller
d8ad60e9-6883-5192-86aa-7c6633e282de | note | Verifying Document - ITP and all referenced documents
d157d1cc-759d-5994-9807-739208c6dc6e | note | Conduct - C
3bfaf461-f845-577f-8260-00e0029d5d6d | note | Produce Record - C
648c86c0-7144-54ad-97b6-a2305b0363f1 | note | Approval - E
| signoff | HOLD POINT
| section | 3. Construction - Pre-treatment Digouts
| checkpoint | Pre-treatment Repair Method Selection
943816ae-f66f-51e6-b565-f1962ea26efc | note | Controlling Documents - Site specifics to be confirmed
ce435d7c-2f86-5fb8-b788-60abb20c4c43 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
16138fbb-1766-5e4b-b669-c6f77bcedc74 | note | Method - Scala Penetrometer on Excavation Floor
5dfbb173-836e-5e7a-97b8-9cfb3b2820a5 | note | Frequency - As required
d54140fd-4676-586b-8d4e-0d4a36e3f001 | note | Responsible Person - Quality Controller
d03593bb-871d-52c3-b149-062b9a8418d9 | note | Verifying Document - Agreed treatment plan
96a5d7f9-3c81-5dc3-a86a-eb50a0422a4b | note | Conduct - S
0ab562d7-c1ca-5157-9284-ccbed382ac6c | note | Witness - C
8c0fa475-3407-5d86-ad81-41fe48651586 | note | Produce Record - S
7d6606bb-e535-5c53-b8b8-92a05b4675df | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Excavation floor drainage
5317b388-fd2c-54e2-ab9f-8d03ca43fb7f | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
74791a2a-b7b1-50d3-990e-4eefc41909f8 | note | Acceptance Criteria - 4-8% toward edge of seal
7ac8b270-d639-5c10-8931-0b0fe1493089 | note | Method - Digital level
dd442af9-67ec-51e4-9bb7-6938d06c9456 | note | Frequency - As required
26a979fc-5c2b-58f0-9b0d-d2fc9c74e9ed | note | Responsible Person - Quality Controller
16162c97-9b7b-53de-b9e8-77713506109b | note | Verifying Document - Dig out QA form
fa1a975d-cf1c-554e-b616-1e201048ff49 | note | Conduct - S
b4326a9a-dcb8-5aa5-9d17-ab22d0723f0f | note | Witness - C
ac0c32e6-a3be-57a9-b021-e6c6a618323a | note | Produce Record - S
12b6db29-4604-52ef-9490-270ee166757c | note | Approval - C
55e6b6d7-d3bc-5a85-bba1-d06da76b6683 | note | Witness Point - Y
| checkpoint | Subgrade material hardness Check base of excavation
4dd9daa4-969c-5398-84b2-9760d070884c | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
dc87ccfe-2325-5080-b549-a26a21fe9bd8 | note | Acceptance Criteria - Scala > 3 blows per 100mm
e1a85c77-bcd7-50e2-8d03-0b548a1db3ba | note | Method - Scala Penetrometer test on base of digout
25ad511d-5c5d-5043-8a95-6fba87e46e22 | note | Frequency - As required depending on size of digout
8571d4e0-ff7b-5a88-a7a3-dcad7c040ec1 | note | Responsible Person - Quality Controller
d0096581-4a5d-52ae-ae7d-8329e9974b8d | note | Verifying Document - Test report
fbd9c873-1c50-5e46-bf66-82ac0aaf505b | note | Conduct - S/C
6633b0ce-d8bb-5894-97ad-fdc9b741c752 | note | Witness - C
3ebdf6ce-92d7-5803-bab1-ae299a999ca8 | note | Produce Record - S/C
a3794077-918c-52ce-b9cc-e41d11e9babb | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer
00c9210a-9f75-548f-b321-fcbfe0baf7f9 | note | Controlling Documents - TNZ F7 Specification
c59df627-9bd0-5294-8c06-1c7f82a0007a | note | Acceptance Criteria - Meet TNZ F7 Spec.
7a0da479-73cc-5488-823c-3eb8325b0c2b | note | Method - Visual inspection
fe3eaf79-9ff6-58a2-b0d7-f90327e7e68a | note | Frequency - Per Delivery
4a07ef0c-bcb9-5b11-86ff-51e3891e5b01 | note | Responsible Person - Quality Controller
77ad15ca-f68c-55e4-b4ed-1f10cff44369 | note | Verifying Document - Certificate of conformance
0cb56eb1-37e7-5ef0-881a-a40ada460b14 | note | Conduct - Sp or S
a34eacf6-8ea7-53f6-aafa-6a6499212b5b | note | Produce Record - C
59aebf47-eff5-53b3-b214-2e28c155dbba | note | Approval - C
3f2f04a8-77a5-55f0-999d-9bcd9eddaf61 | note | Witness Point - Y
| checkpoint | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer
32586eaf-e5c9-570d-8383-ab2da93c1c2a | note | Controlling Documents - As per NZTA list of approved materials/suppliers
74c89d68-61b9-5f86-9cac-ad781024c000 | note | Acceptance Criteria - On the list of approved materials/suppliers
3a3b94df-0a59-5f40-b765-714194895428 | note | Method - Visual inspection
229578d6-74d0-5004-b76c-e88fb8ec5cdf | note | Frequency - Per Delivery
b207b542-fb96-511a-8f1f-e4ebdda10d4a | note | Responsible Person - Quality Controller
71e92e7c-9f50-5ba7-ae93-c4080330072f | note | Verifying Document - Certificate of conformance
4dd0274f-7b7e-588c-838a-a63782b6dfec | note | Conduct - Sp or S
c8123273-e6f5-54fe-b4b3-22d38e529f98 | note | Produce Record - C
ceb4e2e0-208f-5cc5-b0a8-e17ae8344983 | note | Approval - C
b73f2a18-6ea0-5562-902b-04ecbaabfb8e | note | Witness Point - Y
| checkpoint | Place and compact GAP65 in digout area
df3cc912-900c-557c-a735-ae9ed109e885 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
d0a7bc80-f7f6-5175-a60b-81abf2dd8b54 | note | Acceptance Criteria - Clegg > 45
0eeea014-0f1c-5890-9804-a24b36515073 | note | Method - Clegg Test
cf30653d-2b04-524b-8c8e-fe7a47b4d1ac | note | Frequency - Min. 2 per digout
43605698-1a3b-572e-80b8-ed05761f15d1 | note | Responsible Person - Quality Controller
7d8c38a7-d643-5482-b761-251a5ffd36bc | note | Verifying Document - Test report
57d7e084-4da4-51ef-9821-78c64b921d40 | note | Conduct - S/C
3ae39ed7-fee3-5491-a9cc-bfbbea83afce | note | Witness - C
2ed92659-65c0-55dc-9db7-8eb81f348840 | note | Produce Record - S/C
b474e51c-a49b-5076-9c4c-af3cdcb7e476 | note | Approval - E
| signoff | HOLD POINT
| section | 4. Construction - Subsoil Drain
| checkpoint | Excavation and installation of Subsoil drainage
e5ddcca4-a7e7-5ba4-8c8c-1a525aa7ddb5 | note | Controlling Documents - Site specifics to be confirmed /As per instructions from client
2c78a99d-522b-5447-a3c2-f5c0fc612d84 | note | Acceptance Criteria - Visual inspection
9d6ff4df-e014-5b94-a994-f80f6fd328bd | note | Method - Visual inspection
0c56563d-5607-5a4d-8bb3-34861e27c50a | note | Frequency - As required
c851564c-b91d-5245-b139-cf34a0e8b168 | note | Responsible Person - Site Supervisor
b4da4e3c-5dc5-5d18-8ab7-da86e42ddb08 | note | Verifying Document - Photographs
2ec97d75-d0b9-53ff-88d0-71c3ea193cfe | note | Conduct - S
36f99cc5-748f-54dc-870c-8f4b4f990024 | note | Witness - C
e55a632c-2c9d-52ea-a9ac-d0c193458fa2 | note | Produce Record - S
f64f4d1d-8fe1-5572-9250-6a229986f266 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Subsoil depth and discharge point into SW system confirmed
3b532f83-6507-5756-9368-78218f08653c | note | Controlling Documents - Site specifics to be confirmed /As per instructions from client
e46739f4-002a-56e9-853c-21a4f73034f9 | note | Acceptance Criteria - Visual inspection
36488231-ce63-5e77-a544-bb9254b78375 | note | Method - Visual inspection
79589b22-e149-55aa-b63d-54f6173c5114 | note | Frequency - As required
67080d06-2af0-5d43-aef4-6fd0d0f3ae84 | note | Responsible Person - Site Supervisor
65946024-bd63-533f-a6a3-a55309397856 | note | Verifying Document - Photographs
5cda8779-8fac-5154-a384-ea088a09a334 | note | Conduct - S
fce71bb0-2b0f-584f-9955-d88650708bc8 | note | Witness - C
51c799df-2430-5293-922d-c62d10d09c14 | note | Produce Record - S
d62ecdc3-6c48-5ead-810c-07809a0d777a | note | Approval - C
bff6d4d2-beae-573c-80d5-071fee88501d | note | Witness Point - Y
| checkpoint | Subsoil drainage materials
6263f748-bb36-53b5-ad01-6fdbd2319dd6 | note | Controlling Documents - TNZ f/2
2c84ed62-e4de-5466-8bcd-ac3256fd9e5e | note | Acceptance Criteria - Comply TNZ F/6
d8d6ea9e-1c1f-5112-a416-dfcf81917971 | note | Method - Docket and test reports
859fa0ec-4c9f-5f99-a6f4-d1b7b7a8775c | note | Frequency - Per Delivery
2253f333-7f77-51b1-a0a6-b618b04adc4c | note | Responsible Person - Quality Controller
c7a40625-e1be-59ae-a86a-c17ee158389c | note | Verifying Document - Test report
18e987d2-3bad-5d99-818b-7754c977801e | note | Conduct - S/C
02aec8ca-80da-5102-8d55-85df13b29f97 | note | Witness - C
f516f613-08e1-5af3-a6c0-da37d0bff78c | note | Produce Record - S/C
ac6a025e-3293-53d4-a342-33a793d0ac7a | note | Approval - E
453307d4-63e6-5a1d-bf85-541fc9ed017b | note | Witness Point - Y
| section | 5. Construction - Pre-conditioning, Granular overlay and In-situ Foamed Bitumen Recycling
| checkpoint | Stabilising Depth
e69f0250-2fba-5dc8-9aaf-95e2bf193b47 | note | Acceptance Criteria - -5mm + 15mm of design depth
76017c19-ffaa-5b5f-90d7-b7b8b67091b5 | note | Method - Depth measurement
906243d1-bad8-595e-87a3-0a99e60ce19d | note | Frequency - every 200m
0c58ed93-5444-51f8-858a-1263246f07ec | note | Responsible Person - Quality Controller
1b15aca0-ad7d-55af-8ebf-3f00e4ca29f1 | note | Verifying Document - Daily Site Record
bfeecc7c-7cd8-5cbb-ae41-9d12bf04205b | note | Conduct - S
638fcf43-768f-5621-8363-5407a57672ee | note | Approval - C
972ef617-2e95-52cf-9024-8d190f1ece40 | note | Witness Point - Y
| checkpoint | Visual Inspection post hoe (1)
4652f4d9-b1c9-5407-b9b6-eb88cbed22b8 | note | Controlling Documents - 6x4 truck fully loaded or similar equivelant
9f1ae97f-f89d-5322-afb5-737d3e99238c | note | Acceptance Criteria - No identified movement of the pavement under proof rolling and for subgrade contamination
85203683-acea-5b9b-8073-4a796adf7da7 | note | Method - Visual Inspection
aef2f4bd-82b8-5eda-a3a5-b335d59c7223 | note | Frequency - Each Subsection
561bf189-6069-5756-a8a7-d2f00a65b218 | note | Responsible Person - Quality Controller
7efa34d9-fd90-5cf1-b157-138c80418716 | note | Verifying Document - Daily Site Record
9b653861-6e80-5348-bed0-cdc5b5c07db0 | note | Conduct - S
57415cd4-17ea-5769-859b-2e3d4f1937e4 | note | Approval - C
7de23658-718b-5ac5-999d-1827ef522603 | note | Witness Point - Y
| checkpoint | Visual Inspection post hoe (2)
bcd22f4e-0379-53b6-9aeb-2dcee20c7f16 | note | Controlling Documents - Particle size to be 50mm or less
5c8508c0-c68b-5e8d-a29b-ca12c98f3d59 | note | Acceptance Criteria - Materials as described in design report - grading and PI suitable for FBS. No large slabs of existing wearing course or strongly bound base
f8799b28-3d0f-5ddd-88e8-450ec88682be | note | Method - Visual Inspection
713e135e-70f0-511c-aab5-b255088abefe | note | Frequency - Each Subsection
dd610433-9a81-5ab6-8b28-32a5859b6140 | note | Responsible Person - Quality Controller
52537b0c-cfd9-54e0-a8c1-9bf0e28f1934 | note | Verifying Document - Daily Site Record
d23bcd4c-b5f2-5423-a864-434f1e5139b2 | note | Conduct - S
bf96d26d-5d25-5cf8-bc75-16649fc86ba3 | note | Approval - C
b3cf48c9-5c28-51a1-b600-dc06ac9b1f9a | note | Witness Point - Y
| checkpoint | Place M/4 AP40 Basecourse Material
b1ee586d-6956-5c26-93f3-1579e5296271 | note | Controlling Documents - TNZ B/5 (section 7)
f7d02d98-ace0-5f04-8aa1-20145634d0c5 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
79b35ce0-7d55-5aa6-901d-ee5c9fcee470 | note | Method - Visual Inspection
de38dc53-b9d2-5e16-abaf-2dbffd48ba4d | note | Frequency - On completion of placement
562e15e6-15f9-571a-ae7a-8298cbe264c0 | note | Responsible Person - Quality Controller
61673726-f032-55b8-b537-f2f6cd120e71 | note | Verifying Document - Photographs and Daily Site Record
41c96993-efcb-55ad-9019-7186a55dcde5 | note | Conduct - S
931f94f3-2eed-5abd-a175-529ee004bc5c | note | Approval - C
b1ed3de2-87e9-578d-becf-536dfda68163 | note | Witness Point - Y
| checkpoint | Surface Shape
b1316183-2d98-50ba-b7f6-21aeab0fd3d6 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
9daaf983-d0bb-50a3-b5eb-6a7cc4927547 | note | Acceptance Criteria - Between -5mm and +15mm
e8e42f6f-de54-5069-9c1b-ea8957255cc1 | note | Method - Visual Inspection
4d61ba47-6bfb-5748-8b16-56832dc33780 | note | Frequency - 1 per 20m
16011a94-6a8c-59e8-8be7-84e1b24d0ddd | note | Responsible Person - Supervisor
dd55cf1c-61fe-59a2-a2b2-65c7dcd34384 | note | Verifying Document - String Sheet/Survey Asbuilts
74b1c214-8395-5a36-88dd-a68a6c07e3b1 | note | Conduct - S
7b95c27f-0b6c-5f7e-80b0-403693df037b | note | Produce Record - S
ad68ab3c-e98c-5a88-b344-28ac3f333441 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Cross Fall
dcb19cf3-e898-5ec0-8b95-baa9a9f604b9 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
0fd8ef28-ab16-56f3-beba-cea97eb2625b | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
ac101470-3a37-56f4-87d4-979aeca2b2c8 | note | Method - Visual Inspection
1af69ad7-1b69-5cee-9dc3-9cf813732dba | note | Frequency - 1 per 20m
85aa492b-a267-572c-929b-755f8cf02e05 | note | Responsible Person - Supervisor
67191c0b-11f3-5106-af0f-3aa222edf6c7 | note | Verifying Document - String Sheet/Survey Asbuilts
fba2fb9a-486f-5da8-8fc9-caa18ef44565 | note | Conduct - S
b99ead72-44c5-5c5c-88b0-d95b2eec9cfe | note | Witness - C
91701410-e44a-5155-b857-304f182b0e08 | note | Produce Record - S
1aacecb7-4f0c-553e-b56b-be783612ac84 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Production and Injection of Foamed Bitumen (1)
20c3148c-011d-5e6c-88db-144b0c713a6a | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
3e045587-9de1-5c89-a22a-0761e9b44850 | note | Acceptance Criteria - Monitor bitumen pressure and bitumen flow on display. ± 5% of specified rate
a4ee9a7f-75a5-56a2-baee-a091a1163983 | note | Method - Monitor
4ed1c985-399a-5661-80cd-7c7d84c56ef7 | note | Frequency - Continous by operator
2f41af33-5e90-584e-bf6f-4972da1b1696 | note | Responsible Person - Quality Controller
e4d015d6-6c61-5bf2-a0c2-0af0c7c4ff51 | note | Verifying Document - Daily Site Record
b99fad83-05ee-5755-9480-d9289791d6e4 | note | Conduct - S
cde40531-ff21-55db-875a-1afb264f1bc9 | note | Produce Record - S
b199f616-2fce-53d6-a829-65e0f9a09688 | note | Approval - E
8c3c1cd8-e138-5913-a65c-7973f61f0045 | note | Witness Point - Y
| checkpoint | Production and Injection of Foamed Bitumen (2)
c8838931-511d-564a-b7c1-30d92accb30d | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
fc7405c6-632c-57ff-8854-8371eca51aa5 | note | Acceptance Criteria - Bitumen Application Rate. ± 3% of specified rate
2a4a3bbf-9915-52fb-8bdd-383bab1d0193 | note | Method - Record
d9b95ad2-be74-5b51-9fb8-741129dc7590 | note | Frequency - At the end of each run
9a05dee7-5cce-5b7f-8a9f-892a853f523e | note | Responsible Person - Quality Controller
21add605-8cf6-53f5-b7c9-46d0d3e434ac | note | Verifying Document - Daily Site Record
8509e10c-92f4-5596-88f4-d94258bed841 | note | Conduct - S
81ab6f43-a785-5c61-bb59-f6f05b67628b | note | Produce Record - S
a779db8e-9d9d-5582-91f2-7feb7f384382 | note | Approval - E
cfadb52c-ac1f-55a4-b043-a6715a1a7c37 | note | Witness Point - Y
| checkpoint | Production and Injection of Foamed Bitumen (3)
40d21e2f-783f-565b-89c3-83d2073e0397 | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
8a29636b-402a-54db-93af-fc26f32486c7 | note | Acceptance Criteria - Average Bitumen use test per tanker. ± 2.5% of specified rate
05cf55f5-fa4c-56f8-af24-aae106d980a4 | note | Method - Record
a4ec1a6b-8008-5c86-972c-d8f8270c9761 | note | Frequency - Reconcile daily bitumen use with Area Stabilised
22076516-00c9-5e66-a8ec-d92322f48469 | note | Responsible Person - Quality Controller
0d88e717-7e05-52ad-9f49-60faa41c641c | note | Verifying Document - Daily Site Record
b684edcc-592e-52d1-bb60-d5fcb77ce7d4 | note | Conduct - S
d208e607-99d4-570c-a198-1af382bcffbd | note | Produce Record - S
a1b91045-18a0-5b50-9357-dc9e314dbd23 | note | Approval - E
8dba1f94-69cf-54aa-9af5-0397f5ec04ea | note | Witness Point - Y
| checkpoint | Injection & Mixing of Water and Foamed Bitumen
4d511037-4e69-58cf-9543-37f00eb41813 | note | Controlling Documents - Foam Bitumen - TNZ B/5: 2008
a00e4754-37c4-55a0-8384-50b3daa6b9f7 | note | Acceptance Criteria - Mixed material free of bitumen blobs or streaks. Overlaps minimum of 100mm
f3b7eafa-29ea-5c66-9d32-1f04c71c5706 | note | Method - Visual and hand squeeze test
19ea196d-8c70-50cb-86ee-b3d6688924ce | note | Frequency - On-going visual assessment
ba9026ea-0d09-5d9d-b8eb-23726f4abe6e | note | Responsible Person - Quality Controller
2769a2ea-2048-57a0-8eef-ac2af4340a11 | note | Verifying Document - Daily Site Record
6be87df1-d775-50d9-906c-914717f7e362 | note | Conduct - S
42966b0c-3eed-5e87-950f-720fba5e02de | note | Witness Point - Y
| checkpoint | Spreading of Cement
106b50ed-0420-5954-a217-b098e09e9111 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
b8520a9d-06c4-5fe8-9a1a-4d3e4bb6ae52 | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
e6572cb7-af6b-5df1-a0e8-2f61bbb55a62 | note | Method - Mat test (1m² canvas) and Average Usage Test
56c94711-b6bf-56f1-9663-e23602801eda | note | Frequency - per 400m² and upon emptying the spreader
9b5bb5ba-363c-5548-b84d-5a52b4bb0a21 | note | Responsible Person - Quality Controller
315bbf80-9f8e-5057-b3cc-67c1ad33b2d0 | note | Verifying Document - Daily Site Record
764e4921-5d36-553d-bcfe-4b405f44b643 | note | Conduct - S
c4e701a1-05e6-5397-9b28-5b8e25f1efde | note | Produce Record - S
edfe2a8e-b5a1-5417-911c-15b2c186e0e5 | note | Approval - E
df4fbd0e-7978-5e37-8f6b-d687b54c908e | note | Witness Point - Y
| checkpoint | Addition of Water
62f2dbf2-da2c-59cc-ae77-ca14664f05c1 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
ce2df953-d5d9-536c-8f82-80c327e40fa0 | note | Acceptance Criteria - Material held together post squeeze and not showing excess moisture
4e7673d9-b3d6-55c4-a8f9-302a3c541268 | note | Method - Squeeze Test
fe9e9345-2cff-5d6f-a741-452f1adb2418 | note | Frequency - ≥1 per 1000m² lot
032d39fd-d16c-58d6-ac4f-ae775f8952b2 | note | Responsible Person - Quality Controller
2c0a91f1-9548-5440-9ffa-0d468932d175 | note | Verifying Document - Visual
dd58ac45-f151-5739-8880-59694acefbe1 | note | Conduct - S
49aa886e-9758-5949-bb3f-1b29f121a8e1 | note | Approval - C
d9dffd18-c72a-5d3a-98f0-1bbf5671a505 | note | Witness Point - Y
| checkpoint | Cut Depth
58fe8b0e-fec2-5105-b6cc-d5199f0b58d6 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
c62e9620-4687-5dc3-bb8a-581f6a6551cb | note | Acceptance Criteria - -5mm and +15mm of design stab depth
9077554b-4f7f-5af6-96cf-1c77891d0c46 | note | Method - Physical Measure and Visual Record
386faa8c-bf87-5126-8b11-18b2629591c9 | note | Frequency - ≥1 per 200m of cut length
acd7afc7-398b-5fa1-8339-bc5c41df4237 | note | Responsible Person - Quality Controller
2c2cc0b7-1878-5600-a525-3423cbe118f7 | note | Verifying Document - Daily Site Record
618b10f6-bcb6-5e46-8b94-87c43bf0be84 | note | Conduct - S
7dd05fe4-9559-5eb2-8897-1487a27fa3ce | note | Produce Record - S
5f01111e-942e-5858-b36a-8e154395d892 | note | Approval - C
4d724c9c-c09f-541f-9f57-db6b81cbd068 | note | Witness Point - Y
| checkpoint | Longitudinal Joints
f535acab-58fe-526a-94c3-f4e7dd116959 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
a349fa1e-3c86-585d-b22f-8a19c5a0c9c4 | note | Acceptance Criteria - Minimum 100mm
d4a7866b-65c6-5620-a9ab-a9982b6a15fc | note | Method - Visual Inspection
e2265924-46d6-58db-9ab9-a527d37e5c47 | note | Frequency - per sucessive cut
67f6035c-f4a5-5f8b-8beb-9ad501b6ba9d | note | Responsible Person - Quality Controller
9fb6da93-9574-53f3-871e-f87171486403 | note | Verifying Document - Inspection
248fcc52-c35f-59cb-a6e1-ea25f8e9983f | note | Conduct - S
9fec462f-83ed-57bb-ae6e-b4bb67214c30 | note | Approval - C
444c3dcc-08f2-5580-bb8d-54bade7ae2ff | note | Witness Point - Y
| checkpoint | Continuity of Layer
9a3377a0-11b7-5f56-8303-3b117bce29bb | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
536b022d-877a-50ff-93d0-bee2cef11295 | note | Acceptance Criteria - Lateral overlap 1m for cement, 3m for bituminous stabilising agents
ac3644bd-c71b-5222-8112-4ee2b9788a5d | note | Method - Visual Inspection
dd2e8678-5895-54a4-b5d4-c82c961c449b | note | Frequency - per sucessive cut
605b8444-3fbe-5c49-b7c2-2dd3d9b93a8c | note | Responsible Person - Quality Controller
1c6aa7f0-a486-5e03-96c8-894b8ac0384a | note | Verifying Document - Inspection
c43c99fd-6ad1-54fd-a672-ad8db486a428 | note | Conduct - S
0542ae69-6546-5c26-a4af-86cecc70e494 | note | Approval - C
727e664d-63ee-57c3-b564-b0a57b1035f5 | note | Witness Point - Y
| checkpoint | Stabilised Material Particle Size
a6d801a7-4287-55b9-a40a-440b10f3163a | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
8ede62dc-c995-58dd-9321-0efa601022bd | note | Acceptance Criteria - No excessive breakdown of stabilised material
206d163a-4cda-5cf6-bfef-7504de0a05f4 | note | Method - Visual Inspection
52660ee2-378e-5ef0-ba66-9ccd5761127a | note | Frequency - within 20m of each section and then regularly based on material variability
301bdb45-58cf-5e49-beb4-987a724e565d | note | Responsible Person - Quality Controller
d9c2d6cd-3d86-53dc-941a-c01bfb9b7aa7 | note | Verifying Document - Inspection
b2782a8d-f928-5fd2-9dee-5ea86c69c188 | note | Conduct - S
15107dab-8e4c-5d1e-bcf8-3b1e4cb87dee | note | Approval - C
50d0a796-8e35-5aed-aefc-6ca5a8ef7470 | note | Witness Point - Y
| checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
c8d186e9-c005-5c38-a98d-7c94a438e896 | note | Controlling Documents - Technical Note, Compaction (7.7) - TNZ B/5: 2008
19d84f36-7818-5afe-a368-0c336ddfedc2 | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
971b49ca-0b84-51f6-beea-8546f931d0d6 | note | Method - Plateau Density Testing
9a86e915-52e9-5e7e-9822-5468409e4143 | note | Frequency - 1 Every 3000m2 or once daily, or additional tests when material changes visually
13838e09-730a-5494-9b12-83a0d5327ada | note | Responsible Person - Quality Controller
d9a33e01-568d-5cf4-908a-ea13668ed53a | note | Verifying Document - Test record
098d62dc-bcdc-5702-9db6-ca23b98a30f6 | note | Conduct - S
d20e9f28-bfee-5b6b-8867-9b342dc77219 | note | Produce Record - S
3ab78a0b-efd3-5c08-8896-d1f8f44620b9 | note | Approval - C
9865ae42-f1e7-59db-b2ab-f2c7691640c6 | note | Witness Point - Y
| checkpoint | Establish Compaction Target
47750474-e3e2-5a01-a6c1-1e8c939d282a | note | Controlling Documents - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
773077ed-c2be-56d1-b331-99b367c66397 | note | Acceptance Criteria - To provide MDD for NDM testing
f33da710-d7fa-592c-9a4b-86e5d85c95a2 | note | Method - Plateau Density Testing
f6226085-4ab6-55fc-88e3-7fb024fd6134 | note | Frequency - 1 Every 3000m2 or once daily, or additional tests when material changes visually
a82b7e45-8742-58da-8c32-5f841875ecd0 | note | Responsible Person - Quality Controller
4081ae51-dc24-56ea-a726-318f7832a3ea | note | Verifying Document - Test Record
b9ff7bfc-09b0-55da-955c-e84f58ff034b | note | Conduct - S
be3fc7a5-e8f3-5332-8f6a-24126fbcf521 | note | Produce Record - S
49bea81e-6124-515f-8671-bc000c2e2392 | note | Approval - E
b4b97bc7-11ee-515b-adcd-4c1b2b1674b4 | note | Witness Point - Y
| checkpoint | NDM Moisture Correction
a3ca911f-96d1-576c-ac33-d1a505d35854 | note | Acceptance Criteria - Correction offset to be applied
b7c66768-c586-52f0-9176-d1b9534e88b7 | note | Method - Field Sample and Laboratory Moisture contents
8698b0af-fd6f-50d7-888d-91af64891ffc | note | Frequency - 3x Moisture contents per single plateau test carried out
59ef0284-c348-548e-b215-1b7c8878839c | note | Responsible Person - Quality Controller
d1142721-346f-593a-9f15-875127bebf51 | note | Verifying Document - NDM & Lab MC
3a3ae2f5-b2f2-509d-ad62-098c603f32b0 | note | Conduct - S
5df16c25-45b8-5d22-9ebc-0b75dda176e2 | note | Produce Record - S
22d99163-6ecc-5765-8bcd-a8abe7d2252c | note | Witness Point - Y
| checkpoint | Foamed Bitumen QA Sample (1)
65d92947-25ec-5f28-aeb7-3b1a1565b187 | note | Controlling Documents - Indirect Tensile Strength, ITS
1dbb210c-c8aa-5b24-bcfd-03c79265f4dd | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa
ecb45cc9-b5a0-5222-9e68-3b197dea5b44 | note | ○ Soaked ITS: 150 kPa to 350 kPa
0bc53464-8ec2-59b8-87da-d1e3e2ec6952 | note | ○ TSR ≥ 70%
93f5fa2f-7008-532f-a66a-86f2b9cb743e | note | Method - NZTA T/19: 2020
beab828e-46d7-59a5-8bf3-9d4264b00127 | note | Frequency - 1 Sample per 3000m2 or once daily, (4x ITS and 1x UCS per sample)
d9d80345-8ec3-5f21-8141-aca2a1604552 | note | Responsible Person - Quality Controller
a20ea572-81c9-5843-bd6a-c82c110ada2b | note | Verifying Document - IANZ Report
13b5988e-6d08-5cdd-97cb-d983255cea8c | note | Conduct - S
7c39f268-b886-57f5-b14b-5e968bb0f308 | note | Produce Record - S
e24499e4-2406-5e00-97e6-7c179dfbdc3b | note | Witness Point - Y
| checkpoint | Foamed Bitumen QA Sample (2)
0a1a8114-2761-545e-8c2c-a6194a6fdfdc | note | Controlling Documents - Unconfined Compresive Strength, UCS
cdcd47e7-429c-5045-a2a4-8b0a55070c5b | note | Acceptance Criteria - UCS is used to calculate MR(Phase 1) and MR (Phase 2)
09e35fe0-8acd-579d-bd12-64b245bdca02 | note | Method - NPTG Guideline
e311e8dd-34c0-5b25-a9f3-d4820bab9eda | note | Frequency - 1 Sample per 3000m2 or once daily, (4x ITS and 1x UCS per sample)
27d63e8f-9dc8-5d43-bb09-40be892394ac | note | Responsible Person - Quality Controller
23e6c241-89c7-5ed3-b991-1e0f9d38ba11 | note | Verifying Document - IANZ Report
56530406-8d57-5b0a-8c55-15e6bf3bc943 | note | Conduct - S
f6e7982b-ff44-510d-9c78-86a020e6b1bc | note | Produce Record - S
02300f55-3fc4-524f-94a7-80c97c94211a | note | Witness Point - Y
| checkpoint | Compaction Acceptance
18e0f45a-cbe6-5509-81f7-634888ee1725 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
be6e5956-6edf-5c66-8e4d-36d16522dfbc | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
05a9e10e-9ba7-5d17-b7c6-0a4541f61dc8 | note | Method - Nuclear Densometer Testing
c6639d6b-4d92-5dd1-b0ce-08253c94ea9d | note | Frequency - ≥ 5 tests per 1000m² lot
55130817-bb44-564f-bc72-d138b8395d5d | note | Responsible Person - Quality Controller
fccd911f-8bf8-580e-9cf8-5116bf1860dd | note | Verifying Document - NDM Record
65e0beb0-3995-5265-8c5b-e7f095236f61 | note | Conduct - S
f1f0f28f-965e-5b63-aa3c-14257bf2b2c2 | note | Witness - C and E
b4c2fec1-6750-5762-bf74-0bd165c784d4 | note | Produce Record - S
787523f5-f4a1-5436-a29d-cd1777a3e46f | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Surface Smoothness
fa8486d0-f3e0-55cf-89f3-9f3f1083cc52 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
d739e8ce-5af9-5af2-8658-65dfd0a2284c | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge. No water ponding.
34c930a3-22e8-5f26-8ec1-876b03dc5255 | note | Method - 3m Straight Edge
b9b2447c-3944-581e-9f91-ba53f76e37a3 | note | Frequency - During construction and prior to seal
3ec2bb13-3b2c-524b-9dfe-442a0e1b611f | note | Responsible Person - Supervisor
18b2adfd-d61e-514f-920a-751a3c6930c7 | note | Verifying Document - Photographs
d6ad6911-eca9-5528-845e-6d33f29422f1 | note | Conduct - S
73fd24e8-e8e5-5b49-8756-bdabe6eae36a | note | Witness - C and E
990d7f93-25a2-594d-9ed9-3ca359a2d869 | note | Produce Record - C
9f4e03a0-3199-58ac-8e49-8cc8fcfc8164 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Shape
01314736-277b-535c-9ab6-d539c6c79534 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
0c1c43b6-9adb-5285-a051-ab3a3739b640 | note | Acceptance Criteria - Between -5mm and +15mm
b6b614ea-d93d-57b6-83fd-94b9d1b9651a | note | Method - String lines or Survey Asbuilt
632151db-1e26-5ec4-b973-07a03c144908 | note | Frequency - During construction and prior to seal
4ed1ceac-d6ac-54bc-9290-dc340a4a56e4 | note | Responsible Person - Supervisor
2edf0c57-d398-5c76-91be-ac698fc3bbf2 | note | Verifying Document - String Sheet/Survey Asbuilts
2a5bb4f1-3e55-5bec-9972-d74e914c0899 | note | Conduct - S
89e64eb4-334b-598b-8aef-970f60fda0c2 | note | Witness - C and E
aa29c5ad-feec-58e9-a30c-220a17ecf613 | note | Produce Record - C
6eba3902-254b-5440-ba72-016ae543e9f0 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Cross Fall
619df3f2-9849-5aef-8fce-ca1b6fe4c06b | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
d87920eb-f8fc-5637-84cf-600353f50fdc | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
49724ef5-1f75-56a3-b53e-299202363553 | note | Method - 3m straight edge or Survey Asbuilt
d7c8d1e9-bfd7-500d-b513-d5541ec3c196 | note | Frequency - During construction and prior to seal
d2b4134b-cca8-5b2b-b76a-85d641e8e75d | note | Responsible Person - Supervisor
73df9628-bf1b-57e1-a6f3-ac7e64b5ad1e | note | Verifying Document - Cross Fall Records/Survey Asbuilts
5b742640-3cad-5e9d-a385-cdb9b7bd11f2 | note | Conduct - S
08a2d41f-5ab7-5ed1-9c53-29115639dbb2 | note | Witness - C and E
f038a688-6af5-5ce7-9409-b515a5fa9949 | note | Produce Record - C
16f20bbd-8d9e-56d8-b3af-0b8bf62d35c4 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Finish
d61948a4-8028-54b4-885b-88dc6d850c11 | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
fc9727f0-883e-59b9-976f-cc343b57afa0 | note | Acceptance Criteria - Tightly bound matrix post sweep
23844842-9f3b-589c-af8a-01b6a906b549 | note | Method - Visual inspection
8ba5cb71-55ad-5270-acea-55e909e05939 | note | Frequency - prior to seal
cd112f65-0aa4-514b-8b0e-434d63396690 | note | Responsible Person - Supervisor
bef3918b-784d-5e47-b451-37847af322bc | note | Verifying Document - Pre-seal inspection sheet
f98b7a7f-d206-52ad-b172-bbe5212757b7 | note | Conduct - C
9dc0eab4-2d5e-5fba-aef2-e337371e2586 | note | Witness - C and E
88aacd5c-bef0-5780-bba5-d665ac440b87 | note | Produce Record - C or S
3dbacc7a-7b5e-57ec-bf2f-1014ace599fa | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Roughness (NAASRA)
2a201897-03dd-5a11-b0d1-6d8a3ac226ab | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
5ce2e69b-2906-5baa-adf3-6305b2b803cd | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
9c0821e7-e824-504a-a5b7-4f46df0b4c01 | note | Method - NZTA Maintainence specification section 6.1.2
9624cff0-7763-5f4e-9564-301195e81ef0 | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
14fbbd9b-b34d-5a00-b5cd-c87cd1fe35b5 | note | Responsible Person - Quality Controller
5c485b5c-4e7e-5c8c-a80c-c0107987c1ca | note | Verifying Document - Test Records
14100c14-b096-52a7-a0a7-b87600fe4d76 | note | Conduct - C
8aa90822-6994-5a34-a91a-484a10d871cb | note | Witness - C and E
c19dec80-259c-5eb9-94f7-b45aa869560c | note | Produce Record - S
372b9c69-af38-53fe-a6b1-688f639c75a5 | note | Approval - E
| signoff | HOLD POINT
| section | 6. Chip Sealing
| checkpoint | Degree of Saturation, DOS
2f23b843-896e-5257-94d1-44a7e64ffa6d | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
c833fa82-7ad3-53d4-972a-4fb3a1b33d34 | note | Acceptance Criteria - ≤80%, however 65% is ideal
2a096f02-d319-55c7-81e0-ab5f0dac075b | note | Method - Nuclear Densometer Testing
17c8bf79-1fd8-520e-b0f8-c68cdb3b7600 | note | Frequency - ≥5 tests per 1000m² lot
b7559a1e-11df-5c96-9c98-6bb2a5f82050 | note | Responsible Person - Quality Controller
81f327cd-d869-5456-b062-2fec124d0246 | note | Verifying Document - NDM Record
f467dddb-449c-5fe0-a3dc-e64eeef14ff6 | note | Conduct - C
9f46cbe1-60d9-5e83-846a-ae56ff0a8ed9 | note | Witness - E
338fbe74-f6ca-596d-9bf0-24b3b20c9091 | note | Produce Record - C
6ca03581-fba7-5433-a7bc-c73e5a08fd47 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Binder - Penetration Grade
f02c9f4f-7ba0-5634-99c4-758e7daf5154 | note | Controlling Documents - TNZ M/1
986954d4-db95-55c9-86ba-ed193a22677c | note | Acceptance Criteria - Table 1
a7bc9da3-644f-5d90-b3b8-757c5634d662 | note | Method - Property Test
cede2f2b-5631-5312-b969-a0cde58f9b80 | note | Frequency - Annual
be996572-a07d-5ed3-b275-a194af6c986f | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
f18f01b6-5686-5230-8e9e-e73d3df90ea6 | note | Verifying Document - IANZ Report's
52abc30e-cd25-585d-af82-e6262a40a63f | note | Conduct - C
6e8c2fb5-17e4-5eb9-855a-6959fe35038c | note | Produce Record - C
59ef0002-c799-5925-a873-efccc881968e | note | Approval - N
eed90188-46a1-53c1-974a-c7a6068dc7ec | note | Witness Point - Y
| checkpoint | Binder - Polymer Modified Emulsion
a739f7ab-4d8d-5352-9746-4a78bc5efe10 | note | Controlling Documents - Higgins Internal Specification
5483b983-db2e-543b-8e9c-17056e0d5699 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
02486dde-2705-5c8b-818f-f25274e558c0 | note | Method - Property Test
40cbaa80-869c-5297-86ce-efb7a2ae6f28 | note | Frequency - 1/100,000 litres supplied
a8a9fe44-d63f-5209-9ea5-35a0dd357ed7 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
ce191dc6-80ba-534f-8661-6df6956905b3 | note | Verifying Document - IANZ Report's
8ef058c0-d976-5d54-8a72-1a17a9746360 | note | Conduct - C
2eb3bab1-bc0c-5f56-aa5f-775a8d67b9e0 | note | Produce Record - C
0cfc38c3-9b39-576f-8465-772a6cae4147 | note | Approval - N
86018c9f-2bb2-5769-90b2-3e6d42c19ac1 | note | Witness Point - Y
| checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
4afa13c5-6929-5e84-bd90-4946c454d694 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
7f0efa1c-9b32-5a29-83e8-8a7a632eebce | note | Acceptance Criteria - <10% fines under 230kN minimum
3702030f-5cd8-58b2-943b-36135e30c3f1 | note | Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
32d1075f-a139-53bc-9316-b57504a3ac84 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
f5bc5964-cbdf-5def-b596-c5872fa35ac6 | note | Responsible Person - Surfacing Project Manager
d86d8666-0ef5-5a49-9320-b1889e907203 | note | Verifying Document - IANZ Report's
16161627-d349-526f-81da-9036a488b9ea | note | Conduct - C
529fed18-b2b9-5914-8cdc-1659b085b7d0 | note | Produce Record - C
d10950ff-dff5-5a3c-9bff-789c9d048f69 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
71af0d8a-daff-51b5-9c09-6e8d0787811d | note | Controlling Documents - TNZ M6, RNZ 9805:2009
9c2834f9-8d55-51e8-8c9a-984d7267d0d8 | note | Acceptance Criteria - AA or BA
a664a36c-85d9-508f-888e-ae9ffab02a5f | note | Method - Weathering Quality Index NZS 4407 Test 3.10
6c410fb6-e28d-5777-9301-07dba5c4ecf4 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
d44dfe58-671b-5887-aca4-979693addded | note | Responsible Person - Surfacing Project Manager
ee952a59-11fa-5bc9-805e-398b2e8b6f32 | note | Verifying Document - IANZ Report's
fdaa861b-44cc-56ec-b9fc-073c58f7c5df | note | Conduct - C
e2ac328c-a0f4-58e9-b830-a3053e31a694 | note | Produce Record - C
396396cc-817d-5266-9cec-bb0db346e40c | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property - Skid Resistance
513b4beb-e343-5555-b112-6c8eec24c8cb | note | Controlling Documents - NZTA T/10
ac5ecbf6-2b16-5cc6-a765-35d99a038824 | note | Acceptance Criteria - Meet Skid performance Requirement
3b484f3d-4ffa-5dd0-8985-4f18a8816307 | note | Method - Aggregate Perfomance Method TNZ T/10 section 12.3
ce1e0fa2-9a9a-5875-8109-b1c1081aa134 | note | Frequency - Each Site
a1faa224-1ff0-59b4-9c75-715ce25361d1 | note | Responsible Person - Surfacing Project Manager
ca6a1a03-1e3d-52cf-89c7-a88799617209 | note | Verifying Document - IANZ Report's
9b62cc3b-2fdf-5f4d-96f6-7ea6885cf829 | note | Conduct - C
2019ea16-5dcf-51e3-b9cd-7c02c8e90f10 | note | Produce Record - C
1866a5a1-1859-5f09-9f45-dcab805f8776 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
aa495490-0204-56bc-a238-b09881385b4c | note | Controlling Documents - NZTA P/17, M/6
10c7c23b-5b2d-5bdb-a8f2-5cdad4124e5f | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
40c4bb71-1ef9-5ca2-bde9-c4c4a9ae863a | note | Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
8e415c2a-4760-5584-80b1-d2d09557cc43 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
841bdb06-9e71-5005-b6e9-180877647e5d | note | Responsible Person - Surfacing Project Manager
57f9d468-6380-58cb-bdc5-9e2e58c8d314 | note | Verifying Document - IANZ Report's
3da4b334-6e68-5422-aa39-18999c1811a2 | note | Conduct - C
8f08eb2d-fc4e-5133-8eb8-0f235ed8c07e | note | Produce Record - C
363615cf-a27a-5956-823a-82dbff59acd4 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
87fcb3fe-129b-5cf1-914b-604fc0d1e919 | note | Controlling Documents - NZTA P/17, M/6
02f78097-b708-5a17-9746-64cf7c98d7d8 | note | Acceptance Criteria - As per Table 3 NZTA M/6
d9df5020-8c72-5b0d-a144-2da6c5399df4 | note | Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
46df24fa-14ae-533f-8e58-42e20e0c3a63 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
7ba34baf-5c64-5cf2-aa05-37ff33cea474 | note | Responsible Person - Surfacing Project Manager
b12280d5-0663-525a-b823-3fc6785f3010 | note | Verifying Document - IANZ Report's
c4270d62-7862-5cab-9fe5-c9c4366bcd97 | note | Conduct - C
b1d78a0c-dc9f-58f2-9a1f-9b0c906561a9 | note | Produce Record - C
4e10b912-2567-57d8-b030-00da23f65cba | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
6cb4cc9c-4ced-5a62-b7bd-7100a58c0c38 | note | Controlling Documents - NZTA P/17, M/6
4873f109-4c9b-52d3-84c0-df9dc3402fe1 | note | Acceptance Criteria - Min. 98%
965d1816-713e-5367-ad33-b4ffe7fb6550 | note | Method - Sample Test - Broken Faces NZS 4407 Test 3.14
cab8f781-65a1-55b8-a586-e6486bd78258 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
44a92dd2-b219-5f85-893f-43351a1038d8 | note | Responsible Person - Surfacing Project Manager
7425a008-d243-5218-b866-6f4b93c03831 | note | Verifying Document - IANZ Report's
662f03a0-d55b-51e6-82d4-d8e238998af1 | note | Conduct - C
1ca963e4-efe6-5072-a876-c64196bb5cac | note | Produce Record - C
af5cc560-4ca0-52f9-8047-1059bebfa6db | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Chipseal Designs
4505ae41-8f07-53d2-bcc2-ecd3ea207907 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
94076128-1659-5c9e-91ae-f18b859234ed | note | Acceptance Criteria - Client Approval
394deeca-ade3-5d66-a5e7-bf5fc2b5b124 | note | Method - Review
ff1cd7a3-fc42-5909-821c-233363959827 | note | Frequency - Annual
63b415bc-9432-56bf-b17f-db541bded0fb | note | Responsible Person - Surfacing Project Manager
ba08e3ef-85ac-5469-ad07-17a70ce55798 | note | Verifying Document - EBOP NOC Design Report Acceptance
19e64825-8433-544c-a5f8-79815af8a752 | note | Conduct - C
3103a996-0966-5fe2-aec8-538891817c93 | note | Produce Record - C
ef74e3f3-8db3-5584-b8ae-e5ceacc124f0 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Ensure limits of site are marked
d3df0d92-bc8c-5efd-ad4b-3ffeec3b7a4f | note | Controlling Documents - EBOP NOC Design Report
00c542d0-8dfd-5136-bfe6-2ffa88a532c4 | note | Acceptance Criteria - Visual Inspection
b2b27c73-3edb-577f-900d-962883a109cc | note | Method - Visual
594e12a7-c9a4-51ef-91ae-823f784fb2ae | note | Frequency - Prior to start sealing each site
4651dac7-d88b-5efa-924a-f6bd62ec6297 | note | Responsible Person - Surfacing Supervisor
ad7b56c4-081e-584e-970a-55d0e7a0faa4 | note | Verifying Document - Chip Sealing Quality and Site Record
3d03b6db-402b-5adb-aed1-0180db058d8c | note | Conduct - C
26f9e9d4-b675-583e-a741-bf33c6868cbd | note | Produce Record - C
f31373b7-3646-5489-8d03-4325912f756c | note | Approval - C
f19518e2-b41f-537f-a29a-6bed8d207dc8 | note | Witness Point - Y
| checkpoint | Sweep surface clean of deleterious material
b75e8c86-8e65-5bbf-8f07-fc80ad3c057c | note | Controlling Documents - P/17
00d6a0d9-6234-51c7-8ba6-e8897931ef87 | note | Acceptance Criteria - Visual Inspection
0370d2f9-7e45-58bd-9793-0d333a3be61a | note | Method - Visual
fd7be8c1-4806-5dbd-b2eb-3b04a527b3ea | note | Frequency - Each site, prior to start of sealing
53fdf6a9-87e4-5716-8e92-e1747c3fe487 | note | Responsible Person - Surfacing Supervisor
20bb7a89-83ef-5d5d-bde1-cb6f4ec9cedc | note | Verifying Document - Chip Sealing Quality and Site Record
f018117e-1af4-501a-9c04-6f26f0962630 | note | Conduct - C
609f5d68-0297-501e-9708-dab148bf89b2 | note | Produce Record - C
e77f3579-1df5-52f1-9a5f-294f5642308b | note | Approval - C
b64a5a32-dfb8-539b-be19-746898a11994 | note | Witness Point - Y
| checkpoint | Record ATP's on site
ff25defe-0cf1-52dd-9520-c6e1b07525e3 | note | Controlling Documents - N/A
63657515-9e8d-5dbe-a632-3aa90f2c83b6 | note | Acceptance Criteria - Visual Inspection
03b32349-3352-5fdb-a051-5b36e68209bf | note | Method - Visual
40ef2f1b-bf71-5b97-a0af-85e9c4f7f04f | note | Frequency - Each site, prior to start of sealing
bf28c70b-8438-546a-b748-461a133e74b2 | note | Responsible Person - Surfacing Supervisor
8ce0033d-d0e1-5450-893a-e5ca7c702db7 | note | Verifying Document - Chip Sealing Quality and Site Record
e9342ce4-4f3e-58d6-a75e-226fe1d9678b | note | Conduct - C
6d656d49-24bd-52f8-a047-08b5b80317ba | note | Produce Record - C
8500ce6e-fa04-5c3a-a471-48a7e33013f9 | note | Approval - C
4edbdb27-512f-5b8b-8b2c-b04a96b64797 | note | Witness Point - Y
| checkpoint | Confirm correct treatment(s) and chip
b908c6b0-9920-5abd-ae0c-6e62e7d94bbe | note | Controlling Documents - EBOP NOC Design Report
a7333838-51cb-5014-a96d-7f12579b72dc | note | Acceptance Criteria - Details/chip correct
ccc7d6c4-fcb2-5075-9ae7-73ca216cfc0e | note | Method - Visual
e5a38cce-9fee-5633-924b-2a194d635853 | note | Frequency - Each Site
9ad77aa6-be17-5651-b3aa-66259aced718 | note | Responsible Person - Surfacing Supervisor
927b761c-7b95-5c1c-a9c4-1345862762e4 | note | Verifying Document - Chip Sealing Quality and Site Record
4d6c14d6-048b-5d6a-9e79-8e7b4f02e3cf | note | Conduct - C
34144531-6021-50a4-85ef-2ffbdb69daa6 | note | Produce Record - C
e5acf4d8-3230-50b4-91cd-0ec98d80a5bc | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Cutback Bitumen Blend
f0cd7a42-759e-5ecf-9053-9799456e535f | note | Controlling Documents - RNZ 9803_0513
971fe106-4a6d-548e-9f79-94a7f5090cf6 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
3efc5221-a03c-5217-8b02-375beb9d9301 | note | Method - Sample and test
aabb6822-4786-5f67-967d-edf66784c3d5 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
5c7cb49a-7a0d-5e26-bbac-db1230d6c4fa | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
bd593108-97f5-58fd-883e-7efa47d0ec40 | note | Verifying Document - IANZ Report's
21179939-1b84-5752-894f-82419df52f48 | note | Conduct - C
b69643b5-806a-5d7e-adf7-a64e551f9d7d | note | Produce Record - C
3a13a7d4-2300-59c0-a5a8-fa30f1e3c745 | note | Approval - C
673e462b-b875-579d-a4ba-325e542a58cb | note | Witness Point - Y
| checkpoint | Bitumen Application Rate
a11510bd-9494-59d2-bf52-e31ac5e82f33 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
23971c52-ce31-5b0f-9cd3-bbabeb34e118 | note | Acceptance Criteria - Current E/2 Certificate, +/- 4% per Spray Run
41da3168-c6cb-54e8-84eb-111cf4f63556 | note | Method - Test, Review
dd156d8b-dd33-5ec2-8104-00ab425dd8f5 | note | Frequency - Per Sprayer, Per Site
f70a5b5c-0795-5248-b2d7-83a9ba099caf | note | Responsible Person - Surfacing Supervisor
6cc2dea2-17ae-599c-8b08-97447362173d | note | Verifying Document - E/2 Certificate. Spray Sheets
a044f65d-23d3-5932-9ba7-e2163284aa54 | note | Conduct - C
89ab165b-0214-5c49-9f31-ed293eebe3c9 | note | Produce Record - C
55958bb6-c791-5130-9d75-0f7405030a2b | note | Approval - C
3b4e3ded-d8e6-5513-bf0c-2ad975dbe121 | note | Witness Point - Y
| checkpoint | Chip Application Rates
d38641bd-99e0-57c4-89c8-1e5ae4d4c891 | note | Controlling Documents - Chipsealing in NewZealand
01788c5c-7d23-55e7-9d32-b983e5063f29 | note | Acceptance Criteria - As per Chipping Guide
dbd4a404-4ec7-55f7-a64c-f9d1473a6721 | note | Method - Visual
abab3f94-ea07-5dcc-ba27-113094f5b18a | note | Frequency - Each Site
ec7e3d0d-5c9a-5238-b798-949898550bc2 | note | Responsible Person - Surfacing Supervisor
024f3015-7771-50e1-90c5-c5f32e6286af | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
85faf4b0-1999-594e-b14d-9dae93e6c696 | note | Conduct - C
4c50be5b-a369-5de0-af35-9dc43c42a5b4 | note | Produce Record - C
90d58aa3-2f15-50d4-9275-46d3c0fe60f6 | note | Approval - C
7c812d3c-5d1d-5b92-9599-17d84c80f4a2 | note | Witness Point - Y
| checkpoint | Rolling
f0306a71-e208-54a5-9cf0-70d80553954e | note | Controlling Documents - Chipsealing in NewZealand
aae59e69-24e4-5281-88f0-7b7e563590d4 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
3bc4cef2-6325-5a59-98f4-607a5e3b8629 | note | Method - Visual
bc9f3198-c08e-5dea-8a9f-a2664efee0d4 | note | Frequency - Each Site
c369e298-13ef-5308-acba-9a57bc08ab66 | note | Responsible Person - Surfacing Supervisor
2b11bb70-d169-5af4-8333-dd19b2ce17b5 | note | Verifying Document - Chip Sealing Quality and Site Record
8cac97a1-a5dc-5753-a862-7b5661f3dc0b | note | Conduct - C
07a2da98-7d3c-5651-81be-a8fcc6ce258d | note | Produce Record - C
9b6bd281-6cae-5b51-859f-02f327003d5b | note | Approval - C
213db05b-6bf7-5448-8bcf-5380953fb259 | note | Witness Point - Y
| checkpoint | Cleanup
6c9fbc21-7a72-5e54-9ad2-9578e8ba1e04 | note | Controlling Documents - Chipsealing in NewZealand
70061498-e686-50b6-a55f-b01a0f3b9ed8 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
fa3089bf-9645-5cdd-895e-9c77ac20f5c7 | note | Method - Visual
1dba2bbf-0cbe-5c15-8ece-1cf7a59ff8e0 | note | Frequency - Each Site
f9cb6f3e-6340-5039-a1a5-fed0385ced7e | note | Responsible Person - Surfacing Supervisor
098b33c9-9bfe-525a-8083-6ffa749ba9ad | note | Verifying Document - Chip Sealing Quality and Site Record
d033cd8c-e91a-5816-ba79-64a507b8a4b4 | note | Conduct - C
df47e1f2-9b4a-51bc-9af3-c69a0e603435 | note | Produce Record - C
6a9d04b1-d81c-5198-9854-3e0c327d9641 | note | Approval - C
2849be88-04fb-5815-96ad-7aca7d23c08c | note | Witness Point - Y
| checkpoint | Post Sweeping
ecd4b764-2d86-5395-a9b8-193a2e9ae9c5 | note | Controlling Documents - Chipsealing in NewZealand
ec790e72-5271-5824-9b67-0913f8113f88 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
b1048e58-6995-5d63-9faf-3ab2ad263a59 | note | Method - Visual
4d3e3925-fb3f-527e-8c20-dda04870cee2 | note | Frequency - Each Site
84221588-2604-50ac-921c-b6bb77931291 | note | Responsible Person - Surfacing Supervisor
d2b50831-8158-5883-81d6-a334a599ff9b | note | Verifying Document - Site Record
7c5adf65-aa99-5c36-9925-bed4698b8ce5 | note | Conduct - C
4d5238f5-b9a0-5e9b-adff-949c2f194ae2 | note | Produce Record - C
b97f4918-1c03-5a31-ba0a-7d2dcb20d884 | note | Approval - C
4c607b0e-8011-5a11-ae24-177521745530 | note | Witness Point - Y
| checkpoint | Linemarking and RRPM Reinstated
5a6d53b7-3fae-539d-9e50-68e2fd368100 | note | Controlling Documents - MOTSAM
87ba58ca-62df-57b6-bf2a-8fa5af97f7c7 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
d616fd63-5298-55e0-b9da-e3a860579fc8 | note | Method - Visual
a7636d15-1902-568a-a987-4378ab48827c | note | Frequency - Each Site
8478e872-2564-5b10-9520-0c48a1d1221c | note | Responsible Person - Surfacing Supervisor
b9d01beb-72be-5133-a50f-9d49a6e73b09 | note | Verifying Document - Site Record
4b53b047-fb68-5824-ba53-9a2c401d4dce | note | Conduct - C
a51e93da-4876-5507-a354-aec2874d3b35 | note | Produce Record - C
ec36a270-9227-5164-ab7f-e2d2f98be295 | note | Approval - C
b260ecfc-368a-5f36-b225-3917800075bd | note | Witness Point - Y
| checkpoint | Post Construction Walkover
adcb90f1-9dba-5e68-822e-4a83b6bf7126 | note | Acceptance Criteria - Formal Agreement
31265251-6aa6-5a4b-8fa7-f3b35064203d | note | Method - Visual Inspection
6618a5a7-0263-5ae9-b272-3448f80970d9 | note | Frequency - Post seal sweep
af04e5b0-9fe5-5779-a1c1-f64ced686329 | note | Responsible Person - Quality Controller, Supervisor and Engineer
c7b6e8b5-e422-5436-aac2-e5ef8f6e61e5 | note | Verifying Document - Meeting Minutes
47c508e2-ccce-519f-a908-9516541a14bf | note | Conduct - C
80e9b3d6-ebe5-516e-b284-5feed7a5ab8f | note | Witness - C, S and E
b23ab176-a4af-5011-a350-689144d11cc5 | note | Produce Record - C
9ab4dc4d-e49a-5297-a355-9a51ba5a27cc | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Resurfacing Construction Completion report
f6c5108e-4368-5bf4-aae3-1e324c3bcb82 | note | Controlling Documents - NOC; MS 6.1.3
fd04e570-98c0-55df-9ac2-9b8cadf45552 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
d1f7e8f1-a9fb-5264-826f-3849e64e3b43 | note | Method - Record
4a33bdd5-dbb7-507f-890b-997cbb378526 | note | Frequency - Within 2 months of completing the annual resurfacing programme
0eb90a12-dc64-5e75-a7ef-2687697a15d3 | note | Responsible Person - Surfacing Manager
a02c9328-af6f-5239-aac7-f242d7380cd8 | note | Verifying Document - Construction Completion Report
8d8980bd-1cd9-54fd-aeb7-c0cb89a6dc72 | note | Conduct - C
4b4f87fe-92f0-5441-8e22-d10bdc99e75f | note | Produce Record - C
a2acf7dd-dd06-5d62-bf4c-c1d0e6e2f3c9 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Chipseal Post-Verification Testing and Report
56e2bcfd-4b97-5261-97cf-33f8c5515e6b | note | Controlling Documents - NOC; MS 6.1.3
5af547a8-c8d9-5d17-88b2-771e0b232cf8 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
336cf75f-b4e1-575e-9546-b77f57c323f9 | note | Method - Record
26c7c74f-80c3-5e2e-947f-d69ea773d578 | note | Frequency - Each Site
92210f22-8646-5060-97d6-7edbd7a5648b | note | Responsible Person - Surfacing Manager
d93c230e-6133-5e02-9240-ff6a20cebf99 | note | Verifying Document - Chipseal Post-Verification Testing and Report
381dcbdc-6b08-582c-a369-2f3cf34677d5 | note | Conduct - C
d417cf6d-13ec-5884-a6e1-1f97881dd22e | note | Produce Record - C
31506d2a-ac7d-5112-8609-dcfb54130253 | note | Approval - C
| signoff | HOLD POINT
| section | 7. Close Out
| checkpoint | Pavement Rehabilitation Construction Completion Report
22130298-c540-5e00-9a38-c9003a12c223 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
71b2fc4b-5343-5905-9979-fb2b08b27bb1 | note | Acceptance Criteria - Engineer Approval
db594a68-139e-50ff-bc85-6ae9354b7b7a | note | Method - Visual Inspection
76d428da-4728-5633-9f7e-e37428b5e177 | note | Frequency - ≤2 months of 1st Coat Seal
5ac2acfe-7330-53eb-b5ef-a3fac14be75e | note | Responsible Person - Quality Controller/ Contract Manager
61a87441-d564-5b1c-9eb6-981dc118f30f | note | Verifying Document - Signed Report
a9fdee95-c5d0-5840-b68d-45f0fec109d0 | note | Conduct - C
0d400f2f-0ed4-59b4-ae65-e4477c777c49 | note | Witness - C, S and E
90efe621-4740-5f86-a0c9-5c3556ed025f | note | Produce Record - C
fb659a4d-7ebf-5432-8c1a-b26bbac16368 | note | Approval - E
| signoff | HOLD POINT
| checklist | ITP - Pavement Rehab - SH 36 - Kaharoa Road South | itp | ITP - Pavement Rehab - SH 36 - Kaharoa Road South | 9423e53b-6dcd-4d41-bcdc-ec2e14642554
| section | 1. Procurement
| checkpoint | Geometric Design
2d4596d2-944c-55d0-a044-ffde9fab1d56 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
0cb9bf15-3ef7-53f2-98a8-af00896cc881 | note | Acceptance Criteria - Principal Approval
f832b364-6eca-524b-9a9d-471289a7543c | note | Method - Contractor and Principal peer review
5d7e0a57-c55f-54f7-abd1-5a9b9528bfc4 | note | Frequency - per design revision
b1d06ccf-cd6c-5392-aacf-6ce6902a142b | note | Conduct - C or S
7fbbfd95-58c1-5520-92cf-db3a26f5432f | note | Produce Record - C
ab2d3352-b6d9-5860-b491-a2c3ddccc683 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Pavement Treatment Design
4db457a8-ba94-5880-ae94-16d5eccc7826 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
63fc8a46-46e9-572f-bda8-3c87dcd6393f | note | Acceptance Criteria - Principal Approval
650fc772-5a2b-5e19-ac41-389b07606981 | note | Method - Contractor and Principal peer review
9417a9fb-607c-5152-95cb-ad7b4c0a1b64 | note | Frequency - per design
c7317b46-f04e-5447-bc3f-e9991cb319c0 | note | Verifying Document - Approvals Register - Pavement Rehabilitation Design Report
922a03ba-9e70-5ce7-99df-ce3b6af2e669 | note | Conduct - C or S
80b45320-b3f0-57c7-b99f-c6b8d7c3ca24 | note | Produce Record - C
26faf3f7-3851-5da4-807f-0b3ffd4c4dbc | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
533637bf-fc13-54b3-b5e1-4b96bac12b7f | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
d56e0836-5158-5533-b5bb-23510d801b2a | note | Verifying Document - Sampling Worksheet
adbe4b92-f355-5a96-aa75-986d8cf2503c | note | Conduct - C or S
7c71eab4-1e04-5dd1-83ad-a91ce43842f6 | note | Approval - S
| checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
ea0b32ec-b8d4-518f-81d3-9077b56417a5 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
92bcbd89-8b2b-5b1b-8f06-ef39812bebf0 | note | Acceptance Criteria - Soaked CBR ≥ 40
344402c1-ec89-5c2f-9a85-8369865cba55 | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
448a4dd7-0323-5af4-9fa0-b9a06ed6b5cf | note | Responsible Person - Supervisor
b8f66286-21fe-5599-87e2-220a544fd037 | note | Verifying Document - Test Report
694ca1c0-c24f-5201-a1e1-f20862fb8319 | note | Conduct - Sp or C or S
164bf214-2ac0-50a5-89f2-344a50e69e03 | note | Produce Record - Sp or S
4f9c4db8-b9a5-5414-b4be-f351b7bbf6b5 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
55ce88ec-80c6-5208-9022-9ec83884e4ea | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
9a035835-8066-54c3-9335-20b6a9037cb7 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
a8884b26-6e07-54ce-983b-0d06a90311bb | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
96292080-297e-577a-aac0-a2490da0efde | note | Responsible Person - Supervisor
cc113fb2-ea8e-52c6-997b-b445f45fb4f8 | note | Verifying Document - Test Report
485eca4d-4a0a-55e1-9fc4-303ce2f7d91e | note | Conduct - Sp or C or S
f6811b9f-3cab-51dc-bd8d-537639909f06 | note | Produce Record - Sp or S
26741ed1-4afa-5de7-8100-a7462ecbac6e | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
64eac7b0-4a94-5586-90a2-b23f766ecf36 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
e744ad4e-dedb-5940-973b-fdd1516a49a9 | note | Verifying Document - Sampling Worksheet
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
dacb2244-e65f-552d-acee-23201f29861f | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
2a4ff228-1666-5314-93ba-9b4691e42194 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
5d0e8cbc-8d76-5d03-8e79-d6fa5f0664b3 | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
bcc91c61-428e-58ec-9abb-64a6ac555968 | note | Frequency - One test for every 10,000m³ of source material
b1fcc7a9-387b-5efa-8760-3425b0543c8f | note | Responsible Person - Quality Controller
d995ba9d-b179-5620-ba6a-04f9fc59dca6 | note | Verifying Document - Test Report
7b649238-eb0b-5d64-bbf1-368df3a22f29 | note | Conduct - Sp or C or S
51620714-ea9c-5f79-9f9e-21450e6fc2a4 | note | Produce Record - Sp or S
a4abbe8f-ea43-5372-bc31-30c02d4fc1e3 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
e1715bff-0afd-5fda-bbb4-63d2497e4de3 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
f291e498-d1b9-5a08-a93c-66242b20745e | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
4f2578e2-3466-53b0-9ea7-ac27b5a6bdcd | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
ef05fff4-6c9c-5423-8612-1095fe74eaa9 | note | Frequency - One test for every 10,000m³ of source material
3607eabe-6f5e-5d4d-aaab-cd788d34dbbf | note | Responsible Person - Quality Controller
83625949-c85e-53c3-b5f9-c779c6f03383 | note | Verifying Document - Test Report
3a653919-677b-5e31-9286-d2fbb856f6e7 | note | Conduct - Sp or C or S
0fb8df99-875e-5799-ad38-70d658905b30 | note | Produce Record - Sp or S
9da0f7f0-a1f4-53e1-8cf5-91b8439eacbc | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
7ef8f333-d4d7-5ac8-89f9-695471dec6a1 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
6db53159-3e45-5127-9450-0653fa60529a | note | Acceptance Criteria - Soaked CBR ≥ 80%
6906ada3-89a0-5ed1-9c0a-eba993f92edb | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
b6e29e0b-4556-50f7-b835-4c21699e11a4 | note | Frequency - One test for every 10,000m³ of source material
1afa2bf3-1fc6-53a3-acc2-b2bcc57142c8 | note | Responsible Person - Quality Controller
93e46d00-11d9-50e3-99b5-e0e7b95fbac1 | note | Verifying Document - Test Report
abb28785-e7f9-5843-b101-95fd656dfb8a | note | Conduct - Sp or C or S
5e6f328b-d3d1-598e-9c03-589c881ba3e5 | note | Produce Record - Sp or S
25f67c01-9322-5d3f-b167-933df19be617 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
a2d9dcc3-148a-5e07-b155-1e3890c523b7 | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
90a36e78-eb44-5570-b010-2a2bce7d804e | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
b21227f5-b6bf-5287-9f5f-e95f9f41b39b | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
82d0e350-a88e-5c8b-b48d-d92e63eb62e7 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
6eb39719-ef10-500f-8ded-236bc0127b1c | note | Responsible Person - Quality Controller
dd00680b-face-5f3d-9346-b6e8dc9a55e0 | note | Verifying Document - Test Report
d912d33b-004b-5441-83e5-456cb9212888 | note | Conduct - Sp or C or S
0f58760e-b172-50a3-b286-a6c3c779ecb5 | note | Produce Record - Sp or S
596c57ad-73d5-530c-8ecc-f1737b7dcfd2 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
69d2be0c-bff5-505d-8c72-97e685a21a47 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
f88d73b7-a4ad-549a-9a93-031241b2e190 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
9a05f47b-6e47-58a2-8362-721a2e62a7d0 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
8b081e40-92c1-5014-8272-1350adede683 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
4767ae93-7131-5ed1-9046-83327caa3b23 | note | Responsible Person - Quality Controller
1a30b19f-7828-5124-a8d0-680dd148e5aa | note | Verifying Document - Test Report
546633f1-726b-56b1-b992-3dc916941349 | note | Conduct - Sp or C or S
88873f8e-5427-537f-8256-62624fc77f7a | note | Produce Record - Sp or S
8e9a2f1b-539e-5479-a733-e087aa504d95 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
bdbb0eba-11a3-568b-a1a5-e5f816d8d882 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
ac48aacf-a1c2-50b8-ad24-c1cbf96b5c9d | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
d366f2f5-e003-5853-a930-25db5ff700ed | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
d129113d-743c-5825-aac6-dbd6d4a8afa4 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
b5580708-99f1-5514-ad1e-74187a2dbf11 | note | Responsible Person - Quality Controller
faccd150-b780-5cf1-b6da-69ffec3105b9 | note | Verifying Document - Test Report
9a97d484-abb0-58ec-bc4a-3890ac91208f | note | Conduct - Sp or C or S
174bd2ed-70db-58af-a380-e990753e6c53 | note | Produce Record - Sp or S
41cc2c8b-0691-55ae-8b7e-0266cd4c940a | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Materials: Cement - Stabilising Agent Selection
ad5f5bd8-ec8b-5947-8388-ffddf618e033 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
5447442e-c03c-591e-8ab9-415045b8f47e | note | Acceptance Criteria - GP
43cb2364-d32f-5b1b-adc2-40d07a6a6d15 | note | Method - Visual inspection of supplier docket
8d154479-d948-51cb-abe1-649800a12726 | note | Frequency - per truck load
9723f69a-f37b-5eec-a441-242891c47fbc | note | Responsible Person - Quality Controller
51d92989-d973-5d02-9053-594a498243f8 | note | Verifying Document - Supplier Docket Supplier Cert
b676a455-baeb-53d0-80e3-f671206d31e4 | note | Conduct - Sp or S
75a56a42-0dbb-5e49-a487-2583043e1973 | note | Produce Record - Sp or S
23e8f69e-fec0-5e77-b7e7-3ce65654106e | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Water - Water draw for stabilising
36fea035-5314-541c-84cf-72b2ce239ef0 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
0a5d70a9-c31d-50fa-8e4e-7bf087a05802 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
8cd3c81a-eb5f-5f54-9a72-34b2a242ec50 | note | Method - Visual inspection of hydrant use form
3c1e697d-d0dd-51e1-b0c3-264b95ae46ea | note | Frequency - per truck load
050c5a4d-31d5-5998-9883-2f2f03177500 | note | Responsible Person - Quality Controller
a65cfbd5-aae1-523f-a3b6-a12bbf12f9c0 | note | Verifying Document - Hydrant use form
61b8b6d5-a509-5692-a675-66a7f5961bf8 | note | Conduct - Sp or S
aef3c1a6-38c2-5c40-8098-9cfd05800652 | note | Produce Record - Sp or S
c577caed-6f11-575d-a2d0-217ad30b5a76 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
7a36f510-a953-583e-a9c9-2ca2e2a5cad3 | note | Controlling Documents - TNZ F7 Specification
484225e7-97cf-5336-8b40-beab3183e637 | note | Acceptance Criteria - Details on Docket
daaafd5d-1ac7-5210-88bb-27807f606361 | note | Method - Visual inspection
51e50d52-ea25-5a7c-86fd-31a89bb8a76d | note | Frequency - Per Delivery
335058a8-c3e4-5c72-8143-47857cc1562c | note | Responsible Person - Quality Controller
452bd89d-2484-5519-9605-f747a82f44c0 | note | Verifying Document - MDS
87d6b003-ab4e-502e-9418-ec5c607ef383 | note | Conduct - Sp or S
d4e41c8e-c0aa-5ff8-8e5f-c2704d117ddb | note | Produce Record - Sp or S
3ef38987-1cda-5ccd-8d22-cffb31b2f7ad | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent
78706d49-de75-55a0-a291-f725b423b4f6 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
063e98de-18ed-558e-ac4d-08dcc59c1684 | note | Acceptance Criteria - Details on Docket
8e178181-a4fe-56c4-9f74-80ce73f3f929 | note | Method - Visual inspection
75b0c512-4def-5a38-a80c-577339cffb26 | note | Frequency - Per Delivery
158491aa-097e-55da-8150-9347cf79c497 | note | Responsible Person - Quality Controller
c064f96b-bb2e-5cb2-bdfc-10e38691d37f | note | Verifying Document - MDS
2d1fe28f-cb6f-57b8-adb5-a852dd9106d6 | note | Conduct - Sp or S
6a6e36c4-dd8d-5037-aaa6-48a24eb380ba | note | Produce Record - Sp or S
39cdf57a-41d4-5491-b6b2-00ddae2d92c2 | note | Approval - C
| signoff | HOLD POINT
| section | 2. Pre-Implementation
| checkpoint | Production Testing of stabilised material - OMC/MDD
a31bcf1b-545b-5bd1-a481-1bd548f2ad97 | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
9a2c5a21-1adb-50bc-8775-48a9d8d310e4 | note | Acceptance Criteria - To obtain OMC & MDD
de7cbdce-8fa4-5537-8d58-edefa40ea929 | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
7962b460-19a6-500d-9090-e3e1551c47cf | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
989346aa-1daf-5306-a2ed-b980b4084ffc | note | Responsible Person - Quality Controller
d135680f-5980-5547-97ad-d27f73aa2968 | note | Verifying Document - Test report
6cacdffa-338c-5b71-a3b3-60afaa60512b | note | Conduct - C
1122a200-060f-5482-b072-e6a9b51af156 | note | Witness - C
4ada8327-fdbf-5ce4-acb7-bbe2e7ea8910 | note | Produce Record - C
62515aac-b75b-5cd6-87f3-60fc67190c5b | note | Witness Point - Y
| checkpoint | Production Testing of stabilised material - Solid Density
d10f5358-073d-568a-881a-a80cbf789162 | note | Controlling Documents - TNZ B/5 section 7.7
7681980d-db0d-5b48-ba3e-94450e6ee2cc | note | Acceptance Criteria - For info. and use in MDD calculation
3a4cc5d0-452c-539d-876c-a34fbed2a1cf | note | Method - NZS 4407; test 3.7.1
3d72ca88-5c2a-5b9e-81a6-902bd5faffb8 | note | Frequency - Once on commencement and if any materials chage
c4c8d312-092c-5f04-b8f3-fe098818df2b | note | Responsible Person - Quality Controller
6e2fd9f9-4cd0-5f7d-9a73-bd47f3643542 | note | Verifying Document - Test report
e0c0c1a2-cc31-5179-ace2-13f7b3eb3807 | note | Conduct - C
af2d1a6f-34f0-52f7-8607-80abf467d1cd | note | Witness - C
f51a737d-bf40-58bd-a5fd-da75cc5ae5f0 | note | Produce Record - C
61d67565-dc89-5ca1-b34b-268d18fc3845 | note | Witness Point - Y
| checkpoint | Project survey setting out
66e6bf0c-4753-59eb-bcc6-09b44c5aeb9e | note | Controlling Documents - Reference from Project Drawings
1ce0aee6-20dc-597b-b16a-66381803f16a | note | Method - Survey/Mobile Roads, Marks with Dazzle
0ff74122-8795-5c37-a6bb-5d0a1287ae52 | note | Frequency - Chainages for every different pavement sections
ca32387b-66f0-553e-8dbc-0b58da6f8172 | note | Responsible Person - Subcontractor/ Engineer
af74c8de-63b0-5089-ae7a-75c619b37ff5 | note | Verifying Document - Construction drawings
0b983238-6d56-5271-adec-92544d793b67 | note | Conduct - C
06447191-cca0-533d-a2fc-2ec60d9b3c0b | note | Produce Record - C
| signoff | HOLD POINT
| checkpoint | Records Management (i.e. it is known what documented records are to be kept)
f1d09f25-0bb4-5c4e-9482-09269c4ca491 | note | Controlling Documents - ITP and QMP state what quality documentation is required
cf64fa62-02d9-5fcf-82bb-aa05bf12a89e | note | Acceptance Criteria - Filled in and Signed ITP
f6899979-ac96-5200-828a-779c381518cf | note | Method - Visual inspection, recording and approval
5a80382a-1651-52f4-94ac-57cfbd18a936 | note | Frequency - As per hold points in collaboration with the programme
e4e3a714-19b4-5e18-98d4-5e12f19a6736 | note | Responsible Person - Quality Controller
8cdb3711-8cd5-5b8b-969d-5c7d97e1a92a | note | Verifying Document - ITP and all referenced documents
23eb6e1f-67cb-56d7-9e72-462776b58135 | note | Conduct - C
0f49e85a-beb7-5564-b2ff-b338e5548260 | note | Produce Record - C
f6ef7cfe-b2cc-57f4-94c4-d68f3c031eb4 | note | Approval - E
| signoff | HOLD POINT
| section | 3. Construction - Pre-treatment Digouts
| checkpoint | Pre-treatment Repair Method Selection
d4bf2a20-bfc9-5907-bd9d-8f93ff082c09 | note | Controlling Documents - Site specifics to be confirmed
269fa6c3-252d-5e46-adb5-3aa4ccc03f46 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
aa2ef8d2-13f8-5134-85c8-7b0ac573400f | note | Method - Scala Penetrometer on Excavation Floor
26e12e74-9592-5f88-9e93-919f1267c346 | note | Frequency - As required
f594435b-58da-5214-a516-7c75f5d651b2 | note | Responsible Person - Quality Controller
766307ee-e353-530e-a27a-38d33695a4e4 | note | Verifying Document - Agreed treatment plan
91e3415c-e60f-5d7f-abbe-937eed9f00af | note | Conduct - S
2ae95e0f-d28d-59af-879b-d4c2138ffe5e | note | Witness - C
b9ab0c4a-1547-5644-9c46-9cd74181651c | note | Produce Record - S
96da6661-999c-58c2-b9e6-5e0126771b10 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Excavation floor drainage
0e9e65af-8ed6-5e47-8735-95e2c7978a39 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
d4a20cc1-b819-5fb0-8654-5dfc5d38d68c | note | Acceptance Criteria - 4-8% toward edge of seal
07708576-05ae-52fb-a220-7ab527641102 | note | Method - Digital level
b91a7dd3-3d24-5a1d-a91f-0f53bc28c724 | note | Frequency - As required
a6cc1a1e-88b9-58ba-a8b1-fbddad84505f | note | Responsible Person - Quality Controller
614290d5-58a3-5526-9f0d-87962f2715ac | note | Verifying Document - Dig out QA form
0de76cd4-ee68-5066-a959-bdafe1a28b98 | note | Conduct - S
2cbc7540-c112-5d16-9ecf-b077a916ed4f | note | Witness - C
b5cdf5af-09e9-5e26-81b7-8d11bbf40a4e | note | Produce Record - S
918bffe9-2046-5047-a07c-0d4885608a15 | note | Approval - C
22398c52-3001-57ed-92b0-8579b6dcd56b | note | Witness Point - Y
| checkpoint | Subgrade material hardness Check base of excavation
6f091c65-5706-514f-8913-b237a878697e | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
bf443120-c446-5250-9c7c-9c3b2907dca6 | note | Acceptance Criteria - Scala > 3 blows per 100mm
62589d5e-d5c9-5608-94c5-e7348ca0a179 | note | Method - Scala Penetrometer test on base of digout
06170011-e6d1-5319-9a87-b51290d611c3 | note | Frequency - As required depending on size of digout
5b07df78-d10a-5f90-a95c-6acf1dc43e80 | note | Responsible Person - Quality Controller
b231b14f-b48c-5ec5-beca-dcb914972d93 | note | Verifying Document - Test report
3b2e3a48-c26c-5b43-9c96-937753636905 | note | Conduct - S/C
47cb3348-d0a4-528b-b541-ba623b9abf4c | note | Witness - C
abada4b6-3c7f-59a8-adbd-743c6147d41f | note | Produce Record - S/C
26451580-dc12-5c07-8722-6e9c222d7610 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer
7ff5edb1-af2e-584c-bb6b-0dbf3fa8ebb9 | note | Controlling Documents - TNZ F7 Specification
ceccbf19-7f85-5ea4-a87c-88a8bcfd8bf9 | note | Acceptance Criteria - Meet TNZ F7 Spec.
5540b9fa-82e0-56a3-8f5e-8d3c5952f2d8 | note | Method - Visual inspection
22393fe6-fb34-5533-abfe-f7c6d472a765 | note | Frequency - Per Delivery
59b4aa56-505f-5981-91e7-f189fb1a71fd | note | Responsible Person - Quality Controller
c11ecc55-d561-5853-80a8-88097a43fcd3 | note | Verifying Document - Certificate of conformance
bd6e4bda-4dbf-5987-800f-5003cc938d21 | note | Conduct - Sp or S
5c03c488-35b5-525e-9962-0c91b5a7b36b | note | Produce Record - C
72b98efd-3c9a-59c0-8e0c-664fc85c3064 | note | Approval - C
354e1f49-536e-53e4-9eb8-2f8e2b228dbb | note | Witness Point - Y
| checkpoint | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer
4edae64a-a7bc-5702-a4c7-20b6e82c87e1 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
b3e91809-f229-5eb0-8a2b-5c77cd90c4ed | note | Acceptance Criteria - On the list of approved materials/suppliers
5a4d5726-6aab-5423-baf6-0ba7f368cf11 | note | Method - Visual inspection
bbdfdc64-1972-5623-a736-2a5097fe9869 | note | Frequency - Per Delivery
e6b0df50-9126-59c9-8a1f-7d7f3805d9ec | note | Responsible Person - Quality Controller
0d17c7ce-6003-5b97-839e-9678d1954afa | note | Verifying Document - Certificate of conformance
a72915ff-5e38-5da1-a570-7558cec3f27b | note | Conduct - Sp or S
2b51259e-4193-52d0-9696-e3013ce06b67 | note | Produce Record - C
75c57150-935a-5ae0-a5a0-207ad5607eab | note | Approval - C
153859ee-d5f1-5a3a-862a-ffb353df7034 | note | Witness Point - Y
| checkpoint | Place and compact GAP65 in digout area
34607f99-dc0e-5473-aadf-3c59320e54df | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
071ec04b-28f5-503d-b5da-844c89333c6c | note | Acceptance Criteria - Clegg > 45
b62472f4-0d94-5008-8e56-ad20b93c9aa6 | note | Method - Clegg Test
26e3d9c2-a209-5f32-a670-a4366feee3f5 | note | Frequency - Min. 2 per digout
62de0698-311b-510a-ab35-2f6f2fac3d5f | note | Responsible Person - Quality Controller
3850a8e6-e224-56ed-9d71-6f717bfa8879 | note | Verifying Document - Test report
1df8201d-6a50-563f-b415-4ca77b1352ec | note | Conduct - S/C
07a779d1-f8cb-5d04-bc05-7f0a98113e09 | note | Witness - C
b0c6a2a9-fa54-5707-b876-e2783ee820a0 | note | Produce Record - S/C
0ac6d483-bca5-540b-8d00-34bc940ed5c2 | note | Approval - E
| signoff | HOLD POINT
| section | 4. Construction - Subsoil Drain & Pipe Culverts
| checkpoint | Excavation and installation of Subsoil drainage
89d029be-5fb4-5dbb-b0b1-642333822142 | note | Controlling Documents - Site specifics to be confirmed /As per instructions from client
85103664-8bff-5c06-bdff-5e8f45730419 | note | Acceptance Criteria - Visual inspection
98e1d9ec-ec62-5591-8526-8c12ee6fc4e8 | note | Method - Visual inspection
b23edd57-3800-5679-8cdd-429905d92495 | note | Frequency - As required
f879b0e6-2f77-50de-ba56-baeeb5004981 | note | Responsible Person - Site Supervisor
fb8272f2-e7d8-5720-b692-77a04583a576 | note | Verifying Document - Photographs
3aa63932-60a2-5c5d-aa9e-26c895a3b093 | note | Conduct - S
b5a5575a-1843-50fc-8381-da3b5698adec | note | Witness - C
36238d30-f960-5666-b220-30a9d497e957 | note | Produce Record - S
1552afec-e055-5fd1-9a2c-8954356656b1 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Subsoil depth and discharge point into SW system confirmed
d905e3a7-3c82-51e4-b18a-cbd7def449b2 | note | Controlling Documents - Site specifics to be confirmed /As per instructions from client
330e20c9-764f-564d-8366-a833d1d48b32 | note | Acceptance Criteria - Visual inspection
3b5f4cae-419b-59e6-b524-7b24c1fa2f4b | note | Method - Visual inspection
6db38f04-c6cc-5ade-b325-343cc8bd6cb6 | note | Frequency - As required
4aa83155-4e9b-5de6-a9d1-7e9d131936c5 | note | Responsible Person - Site Supervisor
eebb9f8e-41e6-5064-b860-e17ba64260fa | note | Verifying Document - Photographs
1ac4491e-f03a-5675-9475-761f1702a35e | note | Conduct - S
b8b755b5-6b5c-5f9b-b808-36ad2cb0ed7d | note | Witness - C
d8cde36a-8230-55e5-bbf0-71c04d06cb92 | note | Produce Record - S
c0e08af9-cbe0-5284-bb27-378d83569d3e | note | Approval - C
ffdb6ba7-7735-561e-9665-fa25cbc3cbfb | note | Witness Point - Y
| checkpoint | Subsoil drainage materials
6580387d-cd26-5f38-9891-b0f7b4ecac06 | note | Controlling Documents - TNZ f/2
9ac13e5b-51f3-5308-9d05-674188a4e3a7 | note | Acceptance Criteria - Comply TNZ F/6
0b180dd8-ce37-5a7d-bf7c-8e39fa8e9eb2 | note | Method - Docket and test reports
541f7ee5-af2e-5233-95cd-daad92ab454b | note | Frequency - Per Delivery
1e394f40-e640-5d13-837a-0a93445cf10a | note | Responsible Person - Quality Controller
2fe250b0-2131-56a6-a2e6-074f5fe14ca1 | note | Verifying Document - Test report
99f0d1e3-09cc-5204-96b7-5ad0b4fd5ec3 | note | Conduct - S/C
7cba3a87-e8e7-5373-8bb1-9725b49df9a7 | note | Witness - C
9aa940a3-535f-51e5-b9f9-cd416acf4362 | note | Produce Record - S/C
3f7e2c88-7af3-5666-b855-87f96446ae3b | note | Approval - E
000b7859-7e8e-55b9-b55d-a511e6ec3428 | note | Witness Point - Y
| checkpoint | Excavation and installation of Pipe culverts
493b0b2a-9405-540a-96d5-4b3d249b7315 | note | Controlling Documents - Site specifics to be confirmed /As per instructions from client
fd550d4a-b773-5c05-b6d3-d1a8696f2b38 | note | Acceptance Criteria - Visual inspection
5925b1a3-1038-58e8-b165-5bbf2e71187a | note | Method - Visual inspection
43ee2c5d-d97d-5694-8be4-b6a9eac1be4b | note | Frequency - As required
03987ddc-d477-5fc3-8fbf-6bfb77e58dcb | note | Responsible Person - Site Supervisor
9feebfaa-0585-5da8-8d0e-5cba39d27383 | note | Verifying Document - Photographs
617762b8-efd1-5e38-85e3-47eef2de6b5d | note | Conduct - Sp or S
50f6d9a4-3c80-50cc-931a-ac1806e2af90 | note | Witness - C
408cb901-b281-5cbb-8f0d-a4b7324ab0d7 | note | Produce Record - C
6f68649d-6f8d-5b47-8abd-df3edbe2b59c | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Pipe culvert materials
26d4590a-a3e7-587b-8c50-bcb0410eb3d3 | note | Controlling Documents - TNZ f/2
bdfb2d59-9b2e-5bb5-ae3e-9fb006ba350e | note | Acceptance Criteria - Comply TNZ F/6
d24a59fb-b1e8-5278-882e-8d1c8af76d0c | note | Method - Docket
81d05723-0de9-5dcd-8f65-87b65d52bbde | note | Frequency - Per Delivery
abe2eab4-4a7e-5718-9ded-388148cf7dca | note | Responsible Person - Quality Controller
f99f3810-55e1-55d3-92a1-0dd9f447f915 | note | Verifying Document - Photographs
ce13b90f-9a97-5a7f-88b3-944206656c87 | note | Conduct - Sp or S
d119af05-60a4-5f94-8306-d93052093a7e | note | Witness - C
38e08742-a0fb-5512-8468-8b5658f6c03c | note | Produce Record - C
175e91b5-8f9d-5e4b-98be-bfcbb4491a4d | note | Approval - C
5687f3df-3d98-5d9c-a6e8-e34d520517e1 | note | Witness Point - Y
| section | 5. Construction - Granular make up and In-situ Modification
| checkpoint | Place M/4 AP40 Basecourse Material
6bba3859-6b99-5947-8705-9f7716a79ce7 | note | Controlling Documents - TNZ B/5 (section 7)
ae0d2ea3-19a5-54dc-98df-5f62e44ee00a | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
87dc4421-9b59-5759-8bae-5e98d6614f6e | note | Method - Visual Inspection
46e1c8ef-0390-5e6e-bab7-7a21556879e2 | note | Frequency - On completion of placement
7e1397ec-8bbf-568e-94ae-563b20b5c6c0 | note | Responsible Person - Quality Controller
ac8a29f0-1e25-538e-95a9-3008e14ad88b | note | Verifying Document - Photographs and Daily Site Record
a5980b4a-9cff-5563-8709-0c9b287daccf | note | Conduct - S or C
b7a84140-bb18-5ace-a937-23874e469cd5 | note | Produce Record - S or C
43820596-817d-544f-b47c-9350762f5629 | note | Approval - C
b8063043-4103-5a9d-a5db-054f9f0ff693 | note | Witness Point - Y
| checkpoint | Spreading of Cement
ebefd500-a5e3-5946-9e6a-ac529260cbf2 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
fd3fdaa5-34b2-59e3-89d0-1b0ab2e50a58 | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
4e219d13-421a-5da1-b869-7022030512b4 | note | Method - Mat test (1m² canvas) and Average Usage Test
48fdda17-9563-5302-902e-d2f8117b0329 | note | Frequency - per 400m² and upon emptying the spreader
65e17d2e-d1ed-5a8e-8034-c175a1249a7b | note | Responsible Person - Quality Controller
c85536e8-83ba-54b2-81b2-588e40092fef | note | Verifying Document - Mat Test Form and truck dockets
423054c7-8659-5e1d-a0be-daff920ae140 | note | Conduct - S or Sp
edf3b992-cbb0-519b-80df-66c9b580c28d | note | Produce Record - S
2090a364-e934-5cb2-a2cb-b044fc8f1a54 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Addition of Water
b2235721-b78f-5d8f-b4d1-a80bf4763d5f | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
58996a2b-8b25-50cc-902b-43d23ebdb528 | note | Acceptance Criteria - 90-100% OWC
da8ace5f-c026-5589-a9ed-6138528f5fc8 | note | Method - Nuclear Densometer Testing prior to Stabilisation
e2b1cdd4-67d8-5243-b27f-f4fb4bfc47a7 | note | Frequency - ≥1 per 1000m² lot
c21a69f1-ff7b-5d7a-b0aa-964db02adb6e | note | Responsible Person - Quality Controller
1430adc3-849e-568b-b3fa-18e1f15d1d70 | note | Verifying Document - NDM Record
9015a969-9b98-51a3-9ed1-82e5e5841514 | note | Conduct - S
a28b9d7a-1eeb-5dcf-a7ba-a5f36cbb446d | note | Produce Record - S
a41323a8-6e8b-5b4b-a16f-83b1d82bc300 | note | Approval - C
235d2271-6344-5a0d-88df-458dacdb9f88 | note | Witness Point - Y
| checkpoint | Cut Depth
3318faea-5eb5-550b-8e9a-f0549d0f8f27 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
06549841-9113-5655-95b2-d74aa8c24c8e | note | Acceptance Criteria - -5mm and +15mm of design stab depth
f7816d38-c796-5449-a876-19271a06221d | note | Method - Physical Measure and Visual Record
c24e31c0-0841-5652-99f4-9922c7ef90b9 | note | Frequency - ≥1 per 200m of cut length
f9e79fe7-2d84-5195-920f-c48fef207466 | note | Responsible Person - Quality Controller
30172085-b139-5edd-834d-d70811c29558 | note | Verifying Document - Photographs and Daily Site Record
28f3bbf3-b030-52f1-b682-e7aaf8abae90 | note | Conduct - S
bde4c41b-21be-536c-899b-1dc85b311ce1 | note | Produce Record - S
d0371aef-fbb2-58b0-90ed-533c478842cc | note | Approval - C
83a87157-0efe-5ac3-9478-ac9088211e2a | note | Witness Point - Y
| checkpoint | Longitudinal Joints
eb734c3a-d730-5be5-b543-d491a46f0d8e | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
80f16fca-e467-5031-9bb3-789cecfaa9e7 | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
f54cc098-6d47-5204-a2c8-5f650bd0f15c | note | Method - Visual Record
a3b6ded9-69b1-5f44-ba4e-8479210c6ec0 | note | Frequency - per sucessive cut
6ad7f4d1-052e-53be-a7e9-e88964603d70 | note | Responsible Person - Quality Controller
8a00149f-c491-579d-acde-fb7cf892be1e | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
0acebb0e-aa26-565b-91db-24eb42c1c826 | note | Conduct - S
62e13de9-47f9-594d-a567-7b2c90326153 | note | Produce Record - S
5bc3490d-6adf-5e38-8b4b-92b41162ca8b | note | Approval - C
11c47bb0-2fa0-57d7-9a3c-e2635b7b5324 | note | Witness Point - Y
| checkpoint | Continuity of Layer
34003c3a-8fb2-5992-8edd-2f7b36f6ccce | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
8608cafe-426c-5921-ba0c-1b0f80149f74 | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
789c9c64-cc60-574b-9092-b7104ef92881 | note | Method - Visual Record
04223aeb-87b6-5fd2-a177-fc59bf83f905 | note | Frequency - per sucessive cut
22ab19a6-3123-5a21-b9be-a0f8377c18e0 | note | Responsible Person - Quality Controller
d37c8b80-47fd-5fd7-9427-edd847242d58 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
7957a260-3ef0-5b4c-a86d-491de0693e77 | note | Conduct - S
7942f355-9ba9-5032-afe1-56252dbaa241 | note | Produce Record - S
cd8a4ea5-464a-50c5-ae13-40952eef446d | note | Approval - C
f42389a2-0413-5de8-90b2-0553fcec0724 | note | Witness Point - Y
| checkpoint | Stabilised Material Particle Size
95bbab11-42a4-5323-aa8b-13b7b76d93fc | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
d7ed792f-4d5c-5c3d-85a5-91c909a6156b | note | Acceptance Criteria - No excessive breakdown of stabilised material
a8d0acfc-2f60-5aa0-bac8-9160f751f0af | note | Method - Visual Record
04d1b1b7-266b-52bc-88d1-dc9d326e18db | note | Frequency - within 20m of each section and then regularly based on material variability
d271f65a-5be8-55ea-a9ef-48bf24b1318d | note | Responsible Person - Quality Controller
252d803f-fecc-5c49-a634-629ce58fb70d | note | Verifying Document - Photographs
8369bdaa-ad54-539a-bff1-84180162d853 | note | Conduct - S or C
68880003-2785-5b06-98d8-6f0b13f977cb | note | Produce Record - S or C
8967c7e8-d29b-58f5-b70a-df68b12b698e | note | Approval - C
866cc834-910e-5a59-ba85-7c95fff7f5bd | note | Witness Point - Y
| checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
0ad1ba0f-f5bc-521f-bada-58d68f82caee | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008
cf47f00c-09a7-57cf-9258-e9d9228d3150 | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
b70f1d71-f968-5387-855c-ea0f46683307 | note | Method - Plateau Density Testing
bec503ac-8587-56d4-9c22-f74ac8b292df | note | Frequency - 1 time, or additional tests when material changes visually
ebc4b2a5-816f-5067-b966-49762fe1b075 | note | Responsible Person - Supervisor
e8a1345b-cce8-5885-871a-277d4bb5c345 | note | Verifying Document - Test record
deb583d5-24da-52fe-9125-1fe80edef583 | note | Conduct - C
db051bcc-9d61-59dc-a74a-10e9bffe0f3e | note | Produce Record - C
0aeabddd-01e4-542a-bb4a-a7883513ca1f | note | Approval - C
b0976b09-ddab-53fe-9114-e5a607213e55 | note | Witness Point - Y
| checkpoint | Establish Compaction Target
ed5267e7-e918-59d2-95c7-85369c7578a2 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
bccdc26f-4f31-5f85-883f-3d83803ae299 | note | Acceptance Criteria - To provide MDD for NDM testing
aa78c599-6f51-527e-91f5-c387155ec3a1 | note | Method - Plateau Density Testing
18f5ada3-4642-5a5d-bfc6-bda1b0c61c9b | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
a68bbfa4-da89-598c-9a3b-d8121c0a715b | note | Responsible Person - Quality Controller
3c03fd02-f9e5-59fb-a6d0-9a35b211a438 | note | Verifying Document - Test Record
9dc148c9-8780-5789-a4b8-38e21663442a | note | Conduct - C
a87a8e61-db3d-5d94-8d0a-b0fe338bde60 | note | Produce Record - C
1efb22bb-9b13-5e58-a53d-85519aee7285 | note | Approval - E
fa3e9f35-f8f0-520e-9ca8-4386cf0e954c | note | Witness Point - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
b0f35228-f652-5c4e-921a-5b14b8a677e0 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
ae1fc683-2557-5fb0-9b53-329f7f66eefe | note | Acceptance Criteria - To provide MDD for NDM testing
ff143393-a2c5-522e-bad3-e3b58b255466 | note | Method - 'Laboratory MDD at OMC NZS 4402 test 4.1.3.
44c7fe9e-3d45-573c-bcd3-7290d9a13470 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
61b3bc29-0c97-54f4-95db-d6881ade97a6 | note | Responsible Person - Quality Controller
fe4f08fc-6d77-5b50-a2c9-0488dd0b51b7 | note | Verifying Document - Test Record
6e114fe5-d1af-5692-98e3-10bf01b81411 | note | Conduct - C
737ced8c-486a-5f48-afe5-4b3a108f3224 | note | Produce Record - C
24de491c-0087-5c4c-bd0f-28aadc37c67c | note | Approval - C
7da98b9c-b16d-5da7-ab8a-36939d8590e2 | note | Witness Point - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
c7a8af5b-8bb3-5371-8ce7-b392c2db7a89 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
b8e2a214-e410-5bf7-8c06-47da16002779 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
17f7b5b5-b5ec-5afb-938e-7ad2c600ef86 | note | Method - Plateau Density Testing Lab. MDD
6df947e9-73cf-5ea1-b257-8733a23bb7d4 | note | Frequency - At commencement of construction and whenever materials change
dfe19d2a-d55e-5f7b-bcef-d7d62e91abf7 | note | Responsible Person - Quality Controller Engineer
b4c6fafa-cd2b-5511-b70f-36c6fe1f110c | note | Verifying Document - Notice to Contractor/ Notice to Engineer
c845669c-12f3-55f3-8351-2b90516ca072 | note | Conduct - C
91b4e881-90a8-560e-822b-541b10a36f3c | note | Produce Record - C
617d5440-4af9-54a1-891e-fe7db23b1db6 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Compaction Acceptance
e461578c-eb48-5b7b-a4cb-61f2ae7def89 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
907616bf-b380-5334-82e4-0d81faccbfd2 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
be0ef308-0431-52d5-b5da-a4476219e319 | note | Method - Nuclear Densometer Testing
df005181-850b-54d0-bb84-87fbf39882ed | note | Frequency - ≥ 5 tests per 1000m² lot
18b7e483-6ef4-599e-9f69-10ad6ab265fc | note | Responsible Person - Quality Controller
56c94165-b95b-590d-acd5-9d0949519afb | note | Verifying Document - NDM Record
46b9e9d8-9144-5f09-9660-20a821f172fa | note | Conduct - S or C
aa76cfd3-7467-5454-934e-d9a154f77080 | note | Produce Record - S or C
888a3427-6958-5883-a8b6-6152d20042d5 | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Control Testing (if required)
866f0911-50de-5dd0-afc5-65cc5306cc2b | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
51e5008a-fd9b-5171-aeba-f828fc7753a0 | note | Acceptance Criteria - Nil
f764340c-b52d-5fe0-998d-e98e3a3f97f5 | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
a0c31c6d-944d-5494-8ea5-159ee54b3476 | note | Frequency - when agreed with the Engineer
957b1ac0-5bf2-54b0-b9ca-2bff1d94b965 | note | Responsible Person - Quality Controller
e8b1d068-0d1e-5212-97b2-92db3288a7d2 | note | Verifying Document - Test Report
5bdcfd8b-e703-592d-b25d-839c34693111 | note | Conduct - S or C
498ec79b-30d8-5e18-bed9-c7a74902a0b8 | note | Produce Record - S or C
a1706585-4de3-5a27-8cd5-cb54e9e0fef2 | note | Approval - E
| checkpoint | Surface Smoothness
f33a74de-7c36-5319-b035-b340db57e36e | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
bf9071b4-f9b4-54bf-928f-519b75d1b0b9 | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge No water ponding
832662b6-d352-5369-88ad-0e0ca557a772 | note | Method - 3m Straight Edge
25c22c3a-1627-5a0a-9461-6212f859f0d8 | note | Frequency - during construction and prior to seal
346c1cea-c0a0-5a42-88ce-f632d3d809cf | note | Responsible Person - Supervisor
c1f53b09-59e2-5b66-9385-47c2a28f3b3c | note | Verifying Document - Photographs
1513ca41-6f59-5820-af69-ddf07a363693 | note | Conduct - S
b034a71f-a38b-558c-9849-32953915a2d5 | note | Produce Record - S
cf1287b0-a2c8-57c0-b43e-1fe815cd5da9 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Shape
4f0ea55c-24f2-5068-826d-faf13d17ce90 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
07c326ef-5a24-5545-b9e5-195762908fa1 | note | Acceptance Criteria - Between -5mm and +15mm
b8752482-0a14-54d0-ba38-56cd4257dfaa | note | Method - String lines or Survey Asbuilt
c1b3c08d-674a-5e74-ba2b-f0c71f2e3f41 | note | Frequency - during construction and prior to seal
1d058264-79e8-53f8-9571-909fdc03a5a8 | note | Responsible Person - Supervisor
856e775f-24bf-5cd8-a2f0-fba3f3a82ab1 | note | Verifying Document - String Sheet/Survey Asbuilts
53bbd09d-cd08-5339-bd4d-f1a6cf26898a | note | Conduct - S
91275727-139f-50f7-8da8-62d5c7095243 | note | Produce Record - S
ef0b1262-78dd-5b6e-b58c-81496bfbe00d | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Cross Fall
a8164bad-3f1c-5207-aaab-379c9749530e | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
df1c0293-a12d-5f74-b38f-a1f381bfb5ee | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
a46e12cb-b829-55d4-acc1-8186134158b9 | note | Method - 3m straight edge or Survey Asbuilt
650b4d9a-aba7-54ed-a53b-8def5d05187b | note | Frequency - during construction and prior to seal
1e31761b-b8a7-5420-a79b-c9dc5be7b144 | note | Responsible Person - Supervisor
98a11f0e-62f6-552e-9301-1d9a878e2b29 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
2866a1cd-35f2-589e-ac24-8565e2a9130e | note | Conduct - S
db3d9b46-bc2e-501e-90c7-6c30ba57107a | note | Witness - C
3d0b0848-7a8e-516d-95c9-e4ffa6b121ff | note | Produce Record - C
e07e8f16-a0d3-5751-b730-94e5a03831e7 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Surface Finish
eac3b462-3f8b-5873-9179-47013f7b2d7e | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
607f407c-d737-52ce-bd39-6e9ef1b87a7e | note | Acceptance Criteria - Tightly bound matrix post sweep
e1b85e03-b0bd-53ab-ae20-1373e79af140 | note | Method - Visual inpsection
e4ad992c-c58f-5f0a-81e9-8401bfdd6d6d | note | Frequency - prior to seal
f4f7e8a2-89aa-5afd-a9bc-39f82639fc4f | note | Responsible Person - Supervisor
c15a3663-3442-507f-91ae-4739b1f327b9 | note | Verifying Document - Pre-seal inspection sheet
d4a85e1f-1a46-561d-86d9-9ecf9c0daf25 | note | Conduct - C
d4ecd42a-0f76-5f5a-8dda-13c098192b7c | note | Witness - C and E
973c33dd-d87d-59c9-9963-a48b83065e07 | note | Produce Record - C or S
59bb3b76-f29d-5db2-8ae2-d8db2b5d7ff1 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Degree of Saturation, DOS
4fdbde30-3df5-5212-a7fd-c8dad87a626f | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
78af9043-e5a7-519b-8591-4e7375b78970 | note | Acceptance Criteria - ≤80%, however 65% is ideal
b49179b1-1e62-5431-921c-ee90eb68b269 | note | Method - Nuclear Densometer Testing
fe2b3f0a-5f9b-5378-af9f-d3fa983f2bb1 | note | Frequency - ≥5 tests per 1000m² lot
884c71a3-5c1e-5c3e-aa5e-59c1a7f81131 | note | Responsible Person - Quality Controller
fb91f91d-e72d-5a8b-8665-35972ea8a5ad | note | Verifying Document - NDM Record
f82ddb25-f6a8-59cb-bf65-4c1eda107745 | note | Conduct - C
6906cbe3-bc44-512e-a454-ba4e03b6f98b | note | Witness - E
cbb12825-0b0b-5847-9c7c-b7ecd76353d4 | note | Produce Record - S
9ca73803-a7e1-51a4-bb25-e18e41e759e5 | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Benklemann Beam
a275250c-2164-5ae8-8968-dbac6a23fb2b | note | Controlling Documents - 'NZTA T/1
dec281e0-304d-5876-bbba-238754dc2874 | note | Acceptance Criteria - Using a MESA > 0.1 for asphalt carriageways < 10% of results to exceed 90th%ile Avearge < 0.9 90%ile of 0.9mm Maximum 1.0mm.
9ca395df-51f0-5bb2-a91b-eb92267e8571 | note | Method - NZTA T/1
5d767b51-3078-5b79-b9f4-bff74e655b76 | note | Frequency - Alternating wheel Paths at 10m centres along alignment.
d4e93a35-4a6c-55c1-a0ed-2504500d153b | note | Responsible Person - Quality Controller
7f5534f9-9c9d-58c1-aa07-d24a2bd84f40 | note | Verifying Document - Test Records
12aa831e-695a-5d83-a6bb-e77836dfc0bc | note | Conduct - C
dd818d41-764b-5100-8d15-61bdab960e68 | note | Witness - E
adc8826f-490e-51e9-909a-b5d7d4ddddfc | note | Produce Record - S
e40f6842-b47f-5e23-8160-6f88afbee8ee | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Roughness (NAASRA)
93702237-2505-5bc4-9d2d-27a6e49266b9 | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
55603a97-017b-55ff-9c8c-6ec9ca70dd0f | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
b7c080b6-6516-5030-bc04-8b840d522cd0 | note | Method - NZTA Maintainence specification section 6.1.2
237f18b0-f261-5973-83db-8e5af9261077 | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
aeefed0a-23fe-5e03-8d48-3a54e5724a08 | note | Responsible Person - Quality Controller
b66b4330-0816-5d14-99a6-f4209f8f0dd3 | note | Verifying Document - Test Records
fa870ce2-5d7b-5745-b8ea-c1db882cae05 | note | Conduct - C
28cf4acb-7bff-50df-9979-f8172e0b5cdd | note | Witness - E
9a7c3022-b620-5250-a247-156fc47db695 | note | Produce Record - S
301834a7-6d73-5130-84dc-b2f40be67e35 | note | Approval - E
| signoff | HOLD POINT
| section | 6. Chip Sealing - 6.1. Procurement
| checkpoint | Binder - Penetration Grade
43f3646d-94b7-5567-82d4-558c228604b0 | note | Controlling Documents - TNZ M/1
35a89d01-e5e0-57ff-8e1a-2722c606f271 | note | Acceptance Criteria - Table 1
3c6b0640-dcf5-5bdc-b3e9-37eecfd1709f | note | Method - Property Test
910ab56f-16ab-5930-9e33-5797f3026b38 | note | Frequency - Annual
c55bd00f-a110-54df-8bb6-0fc232ada63a | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
33cc04cc-c248-5c3d-b52c-dfff0c7f205b | note | Verifying Document - IANZ Report's
20605bc0-8187-591b-a2f1-ddeefa45a11b | note | Conduct - C
84245de8-9518-538c-a497-f51111a10725 | note | Produce Record - C
7925ab51-69d0-5011-a5d7-81fedbc514ec | note | Approval - N
42783799-ac58-5f8b-bc0a-22d6ff82e22b | note | Witness Point - Y
| checkpoint | Binder - Polymer Modified Emulsion
5323ad07-8f9f-5fcb-b3d9-88e28ebc0f19 | note | Controlling Documents - Higgins Internal Specification
064fdb80-4edf-5213-bf93-d58750d3b68c | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
0ceb45ef-3ce5-5004-b9ba-a2285033e243 | note | Method - Property Test
e21c75de-7d51-59be-ac29-2a3175c5883f | note | Frequency - 1/100,000 litres supplied
853d78b3-a8d7-53b4-a7cc-5ea4dc5ebada | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
109f526d-bda4-5d6d-9963-7117d453121b | note | Verifying Document - IANZ Report's
cecab949-836b-50e6-9801-6cc8e374f41a | note | Conduct - C
f5463035-b210-56ad-8ff8-4a2c75303371 | note | Produce Record - C
96da1ab9-21bf-5783-b3fa-c3a213e6903e | note | Approval - N
54971ab2-42f5-51cc-a459-13c9d7273e99 | note | Witness Point - Y
| checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
4f8e105a-21d2-5236-961c-e00e64bb7d0b | note | Controlling Documents - TNZ M6, RNZ 9805:2009
d21bbbdb-ffbe-50c8-80b6-dc998660455e | note | Acceptance Criteria - <10% fines under 230kN minimum
bce03a54-9e0b-5495-acb7-a3fe9870d386 | note | Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
2975ff76-2f96-5833-85e3-753757023dd9 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
67ae927e-6632-5447-af5a-39e804ee61c3 | note | Responsible Person - Surfacing Project Manager
9c9ef027-c6fe-57b6-8ddc-861fc6a380fa | note | Verifying Document - IANZ Report's
2500f7ab-1968-54a2-87b8-6c0725b1ab7d | note | Conduct - C
1cf78c2d-b737-5cef-8133-b3c23c6d3daa | note | Produce Record - C
13ede9ec-fd23-5abd-b29e-801d97fe7b3a | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
88dee512-af12-539e-bf8b-83bfb3870eee | note | Controlling Documents - TNZ M6, RNZ 9805:2009
420f345b-8033-5fd1-b644-4810a4d1ac21 | note | Acceptance Criteria - AA or BA
863c420c-ed61-5fce-9e93-1b4d44c2071c | note | Method - Weathering Quality Index NZS 4407 Test 3.10
e6a2595b-1df4-5a8d-9012-7a7f6bc34f70 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
ab7bfc32-0733-538c-9db5-94ab7ef7cc1b | note | Responsible Person - Surfacing Project Manager
613912e8-dce1-57c7-84f0-4e5b946a6112 | note | Verifying Document - IANZ Report's
887fcf7f-0e48-5dfb-841a-95785414636b | note | Conduct - C
93cb544b-458c-5e1c-a82e-a0acfefb0b02 | note | Produce Record - C
6cce2771-a336-5900-9553-502611bcb880 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property - Skid Resistance
dee301eb-914d-593f-b00f-3b2d910c04e8 | note | Controlling Documents - NZTA T/10
0aaec6f5-0f8b-561a-9d09-d8b5ca64b51d | note | Acceptance Criteria - Meet Skid performance Requirement
395d58e7-cce2-5a29-859e-46bb92da7be3 | note | Method - Aggregate Perfomance Method TNZ T/10 section 12.3
27e29e97-2425-5870-9216-0f8ef4acca35 | note | Frequency - Each Site
67cbb82f-cc05-56fe-adc2-ac5ca210efa2 | note | Responsible Person - Surfacing Project Manager
6196aab0-ae2d-5e3e-a51f-b49cc8b80864 | note | Verifying Document - IANZ Report's
eb9e9eda-259f-52b9-b7af-270c5d74b7fe | note | Conduct - C
b2277d89-012e-5b01-88ac-05775440d7a0 | note | Produce Record - C
a195d98a-2e0c-53bc-84fa-f65879f88adb | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
0f2390e0-edc3-5839-b53b-5d67da6791d5 | note | Controlling Documents - NZTA P/17, M/6
ed418a14-e1e6-5c7f-8830-c022d76d2b8e | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
193b8e5b-3606-5e8d-8a3a-2564361eabf7 | note | Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
c2a40b9e-8ee1-5c5b-8650-c64fd19fbb42 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
90231086-e4f5-55f5-acfa-9aebe293e1eb | note | Responsible Person - Surfacing Project Manager
430e0387-b0fa-5aa5-b446-88ebb4bc9b68 | note | Verifying Document - IANZ Report's
faf1f892-3641-5b98-a84b-0ada62feeb70 | note | Conduct - C
55b39962-548a-5e12-90d2-889f38bceb09 | note | Produce Record - C
17fd44b2-17aa-5266-8bee-9fe72a572e61 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
6c9c7364-9608-5e5e-94bc-93f3a674db35 | note | Controlling Documents - NZTA P/17, M/6
f244c457-582a-5c37-a78e-b2649dbc578c | note | Acceptance Criteria - As per Table 3 NZTA M/6
e53a1c60-08da-5cd6-a0b3-3d39bec7d3fb | note | Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
068d4e7e-743e-5e47-a8d8-65a7919e445c | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
5968212a-b3e8-5042-84c3-5f8ff3837a0a | note | Responsible Person - Surfacing Project Manager
ec3304a9-5e71-569f-9dd4-03a5c5745f36 | note | Verifying Document - IANZ Report's
1d5dc456-28b9-506d-a571-a3919254ab64 | note | Conduct - C
45cee48d-331c-5d10-b61c-4e4af4dce718 | note | Produce Record - C
a06ce9cb-479f-53c2-86c5-3aa51f21c1d6 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
9b724a64-1b5f-5872-aa10-9fa2e153b561 | note | Controlling Documents - NZTA P/17, M/6
1bc7a6a9-2fe1-5fcf-bdd6-365a5b86c9ea | note | Acceptance Criteria - Min. 98%
cd928d99-2b53-5973-884a-e102563f889a | note | Method - Sample Test - Broken Faces NZS 4407 Test 3.14
6cd1d34e-4940-5a38-9810-f819f41688b3 | note | Frequency - Per Stockpile <100m3 - 1 Sample, 100-500m3 - 2 Samples, >500m3 - 3 Samples
9ffe063d-5d88-51ae-bf07-382e5d1946ad | note | Responsible Person - Surfacing Project Manager
e2bf9d0d-377e-5cc6-8c8d-31005972260b | note | Verifying Document - IANZ Report's
c80c726b-1345-5c58-b027-1741788b526a | note | Conduct - C
c3c416e0-f1b7-5cf5-a887-55e142a4c76d | note | Produce Record - C
c5e80e5d-81ab-54a7-af1b-11dfc77897ef | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Chipseal Designs
c6d965dd-10b1-50c6-8fc8-f0b8753cfdce | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
2b72a7a7-6be2-5cae-9dfa-97fa20d654e9 | note | Acceptance Criteria - Client Approval
b2786d5e-290c-5a3b-ba07-1d42d283058c | note | Method - Review
e2456134-186c-5ed3-b12a-4f565d5e2fa2 | note | Frequency - Annual
b588fa65-4efc-5dc8-ba8d-549cbdf4033b | note | Responsible Person - Surfacing Project Manager
5407b7a1-e57c-5477-9ac4-2c35bf9b55f8 | note | Verifying Document - EBOP NOC Design Report Acceptance
4dae3c57-1a35-54fd-a5ef-9a5889db0fb4 | note | Conduct - C
5519d192-758f-5cf3-b3f9-11e7bc9e7f81 | note | Produce Record - C
5fc36aef-f2b5-557a-878a-8f7e79781a5d | note | Approval - N
| signoff | HOLD POINT
| section | 6. Chip Sealing - 6.2. Construction
| checkpoint | Ensure limits of site are marked
5b774056-93b4-528b-8377-dfd64485fb76 | note | Controlling Documents - EBOP NOC Design Report
7be7d4be-ab84-5ad3-80e1-9672546b9d0b | note | Acceptance Criteria - Visual Inspection
43ac4598-3e81-5140-bfa3-1381d709c113 | note | Method - Visual
c393e38a-bcee-5d86-8109-8498b99d6145 | note | Frequency - Prior to start sealing each site
d24682a9-4d08-5551-9c4e-c858ebeec71b | note | Responsible Person - Surfacing Supervisor
16a088f1-7a0a-58f8-805b-c108653f4cd2 | note | Verifying Document - Chip Sealing Quality and Site Record
9997a453-7be0-51a4-910c-3c459c19ccfa | note | Conduct - C
5de13b03-f736-58b6-86f7-9d453bede8f5 | note | Produce Record - C
f826f813-dc48-5a40-95c6-2e110b805dcc | note | Approval - C
3c0575ec-9aca-56d7-822c-6e210e9381a4 | note | Witness Point - Y
| checkpoint | Sweep surface clean of deleterious material
9fdaac7b-7708-526a-a927-57867d69d4ee | note | Controlling Documents - P/17
29b58954-2ee4-5bb3-b25e-13b8c43b1969 | note | Acceptance Criteria - Visual Inspection
e5cef753-39f4-523c-a097-c1ca82f246ba | note | Method - Visual
56bba6f2-3ced-5ec9-8a88-10d0b689a82a | note | Frequency - Each site, prior to start of sealing
08f5bcfd-cca2-510d-9c9f-08c53eb37841 | note | Responsible Person - Surfacing Supervisor
cfca2208-f29c-5875-9748-d7a746e8b848 | note | Verifying Document - Chip Sealing Quality and Site Record
63c1f2cf-d6ec-5c04-883e-09f44194752d | note | Conduct - C
4947d6e7-0c62-5f23-80cb-911505578679 | note | Produce Record - C
45c9bde9-13d8-5a33-98a4-386a5e6770b7 | note | Approval - C
ac615a1b-3c42-5ca0-810b-7a3d42d88590 | note | Witness Point - Y
| checkpoint | Record ATP's on site
8123e58d-0edc-51d8-9d97-cd664af614a3 | note | Controlling Documents - N/A
bf11ae36-338b-551f-ad79-e6075ed04c78 | note | Acceptance Criteria - Visual Inspection
596b2994-3638-5de4-9625-12a3056bacde | note | Method - Visual
764a92a8-f817-53c8-9c88-99f2cee76e73 | note | Frequency - Each site, prior to start of sealing
67f55058-f5c1-5523-8ede-632d9638270f | note | Responsible Person - Surfacing Supervisor
c7453b92-6d61-5407-aa52-8fb9be68cf4a | note | Verifying Document - Chip Sealing Quality and Site Record
4f432c45-fac9-55a1-8632-afa365a53523 | note | Conduct - C
f4b03cea-805f-51c7-9890-aeb2aa777375 | note | Produce Record - C
66a2b450-6e06-50be-bf4d-3acd49f33fac | note | Approval - C
f597a4ec-369d-5a89-a1b6-e90e36b2bb8b | note | Witness Point - Y
| checkpoint | Confirm correct treatment(s) and chip
e2e21476-3ad2-564e-b24f-c660bc096011 | note | Controlling Documents - EBOP NOC Design Report
5fcb5916-96bc-5af9-9b0d-68ca2432d362 | note | Acceptance Criteria - Details/chip correct
e64e5f36-5718-5470-a636-1e6a32ba6683 | note | Method - Visual
c9f76c53-7e05-5f69-949a-37971fa00a9c | note | Frequency - Each Site
d2d4ce2f-0bd5-53c8-ba7c-f17b8bb4e14e | note | Responsible Person - Surfacing Supervisor
4d909594-6dc5-5904-976d-0e2d5b4ccb2b | note | Verifying Document - Chip Sealing Quality and Site Record
b4a8ffc3-75f9-5eef-9cc9-296c9c4981dc | note | Conduct - C
006f66b1-cf1a-50ef-8221-3ff8f4272340 | note | Produce Record - C
51fbf086-3570-5520-83b7-075f961dee0a | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Cutback Bitumen Blend
fef5dac7-762a-5806-8fc9-0a743221916c | note | Controlling Documents - RNZ 9803_0513
ba0b60f3-b1bd-5660-887c-68b263d57e87 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
28d17d0a-a7c2-5fd8-99e7-e685fee7b41f | note | Method - Sample and test
57456b3e-557d-5720-879e-21c18b2cab36 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
4c8e95ad-2ec8-599f-b96a-216f6e0c1d2e | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
2a589efb-a5b6-55c6-838f-5fc2f3a3f6a7 | note | Verifying Document - IANZ Report's
b5a95e9e-7b34-5cc2-8ce7-ec5366030387 | note | Conduct - C
6c0abba5-b435-5021-869d-a283457e8ca2 | note | Produce Record - C
1a8b62b3-3109-546f-9664-1b0a5545df4e | note | Approval - C
51e7d591-e816-5494-8724-2aba875f0b5c | note | Witness Point - Y
| checkpoint | Bitumen Application Rate
e47df641-ddc9-5228-9c94-15c4efe6b4f6 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
ddecfd05-ae94-5b75-bdb3-e47482ec4d3f | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
f41cfd42-a104-5e32-98d7-507615d647fa | note | Method - Test, Review
81739e81-f3c9-5525-a301-514913808027 | note | Frequency - Per Sprayer, Per Site
d343ed88-9767-5cef-b2db-2ed8666043a2 | note | Responsible Person - Surfacing Supervisor
af0185b5-ce6f-523b-b489-de8012565509 | note | Verifying Document - E/2 Certificate. Spray Sheets
3ae739f1-b509-59de-9b79-e621427a0e5d | note | Conduct - C
2de9bc02-9838-5782-b34d-56feb599d9d9 | note | Produce Record - C
155a0576-507a-5807-8535-d5803de0c9e5 | note | Approval - C
c69f1c3c-2230-5e2d-8a8d-f384a57508be | note | Witness Point - Y
| checkpoint | Chip Application Rates
6d78cae6-b926-5c03-aa97-14ff2eb8c97e | note | Controlling Documents - Chipsealing in NewZealand
78545a7a-721e-5e4c-8f09-25dc89839668 | note | Acceptance Criteria - As per Chipping Guide
f75af9b9-ef93-54f0-95ec-f07f9d4850ee | note | Method - Visual
9393fd44-8072-5982-907f-de6e55997396 | note | Frequency - Each Site
c5fcc65e-7103-5e96-8da2-68d73eb0bfe2 | note | Responsible Person - Surfacing Supervisor
952606a3-a468-52d1-84ca-5dfa7cb3bc08 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
215e8acb-41fa-5de4-806a-45cc112d21d3 | note | Conduct - C
16b346d9-783b-529c-8228-ecd163e6acb2 | note | Produce Record - C
c63a6826-d444-5912-83b9-88188a35e2ae | note | Approval - C
911b9321-dd8a-5665-9af2-20938a528008 | note | Witness Point - Y
| checkpoint | Rolling
38e0f8ec-7421-59ca-b14e-0c416a3fbc73 | note | Controlling Documents - Chipsealing in NewZealand
5d44e809-3e8e-545c-a656-d828277254e7 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
cb38250a-88e0-56cd-b249-c07ed0814468 | note | Method - Visual
34502e9b-e06d-5e0b-8159-79245b4f35b1 | note | Frequency - Each Site
c4f1f0e3-0eb1-57a6-884b-67f0d16ef7c5 | note | Responsible Person - Surfacing Supervisor
d49e9c07-0ea1-5e6c-8ec7-88e6255f3206 | note | Verifying Document - Chip Sealing Quality and Site Record
2231e702-60a4-5146-ae9b-6ab5b93e2ad4 | note | Conduct - C
487151b0-f47e-5740-ac8f-20a69de38a84 | note | Produce Record - C
a918a5dc-0c6a-5143-9c8e-f21fba080e85 | note | Approval - C
f8632623-93fd-5669-a7c6-b9601b6ad8e2 | note | Witness Point - Y
| checkpoint | Cleanup
ad574819-e879-5c37-8af2-da6c63c16ea5 | note | Controlling Documents - Chipsealing in NewZealand
1b0cf053-f846-58ba-9aab-58c132779276 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
2f1e21c4-e0d4-50bf-b7c9-30b2547f1a8e | note | Method - Visual
e65f10fe-5f42-57bd-b71a-f38a9d75c53a | note | Frequency - Each Site
116962c4-4200-53f9-8d8e-47c65031632c | note | Responsible Person - Surfacing Supervisor
8253da48-3a86-5aeb-8132-7e193890c268 | note | Verifying Document - Chip Sealing Quality and Site Record
7c28be5d-cab2-5036-9cb0-f8f202ebdec7 | note | Conduct - C
772adade-d351-5820-ac88-3315365d9c5c | note | Produce Record - C
79fda24c-e73d-5bdb-a315-4df0f7d8d05f | note | Approval - C
133cbb6a-becc-5b13-b789-1ce370e2631a | note | Witness Point - Y
| checkpoint | Post Sweeping
9a2aea55-b738-56c5-b0bb-5b7cf901a4af | note | Controlling Documents - Chipsealing in NewZealand
6f0de3c3-ccc6-5caf-9ba1-3ac3f23a07ab | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
ff91aa66-33d8-5523-8763-bbb190eaa095 | note | Method - Visual
b9685670-cbb4-573a-808e-bc63b2df88f7 | note | Frequency - Each Site
0abc7b5a-cd7a-53a6-92a9-ec083f924189 | note | Responsible Person - Surfacing Supervisor
1e0fe49a-1007-57b4-a1a8-ffa64b0c4e6c | note | Verifying Document - Site Record
46750517-33f2-53b5-a809-f6c38b1d3fb6 | note | Conduct - C
6429ad6c-b500-5eb1-b7ca-1aa70009daa4 | note | Produce Record - C
4ce82371-aa69-5dbb-a4fe-145ecd86f9b3 | note | Approval - C
a2c475df-2bde-57e9-bb06-f0115644b7eb | note | Witness Point - Y
| checkpoint | Linemarking and RRPM Reinstated
c39eccdf-61c4-539a-93ae-9b0e2c5bd042 | note | Controlling Documents - MOTSAM
1a9dab43-61b2-5e1c-a7ac-28addf44aae1 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
3c2319b7-0073-5194-a93c-ef66dcb6b4cf | note | Method - Visual
5d4faf23-03b5-5ce1-8600-9d566f19f39a | note | Frequency - Each Site
178ad9a7-6edb-5e8d-84b5-6aa9160212c2 | note | Responsible Person - Surfacing Supervisor
f251cb57-4943-50e2-811d-ddecdda50989 | note | Verifying Document - Site Record
446dee75-ec0d-5c41-b642-27e7eefd87bd | note | Conduct - C
6847764d-3d24-5236-8986-9488c95c5e1c | note | Produce Record - C
9223cbe9-d85f-53bb-b94f-d709ca6f0805 | note | Approval - C
74e9778e-8066-5241-a212-0a76ca2594f7 | note | Witness Point - Y
| section | 6. Chip Sealing - 6.3. Post Construction
| checkpoint | Post Construction Walkover
c3662a68-ac17-5e7d-b850-9af8a42e95cf | note | Acceptance Criteria - Formal Agreement
bcaba44c-389e-5853-af50-13e74b2b9d62 | note | Method - Visual Inspection
d202333f-fb72-5a4c-ae8a-057d3a02daed | note | Frequency - Post seal sweep
7fac248c-7772-5ed8-936c-114d625c2d0a | note | Responsible Person - Quality Controller, Supervisor and Engineer
aa0c3046-d774-50e3-b780-44db45acf5ce | note | Verifying Document - Meeting Minutes
26f9e926-654d-5293-9b1a-17bc2a82bdb3 | note | Conduct - C
0d2220a3-27f5-50a0-aa9e-356de6571bad | note | Witness - C, S and E
d1899132-d20c-5f0b-926b-71a218147463 | note | Produce Record - C
4d794c88-ad06-5336-9ac6-0854349bf41e | note | Approval - E
| signoff | HOLD POINT
| checkpoint | Resurfacing Construction Completion report
3cc5c3ea-d367-5aaf-a333-1e1efc03a4de | note | Controlling Documents - NOC; MS 6.1.3
fd6716f1-e124-5c8a-9f59-42515594f64f | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
e0e980dc-8124-513b-8c58-8d73c471efa8 | note | Method - Record
b9460a8b-3684-52aa-a7ae-0d3706843eae | note | Frequency - Within 2 months of completing the annual resurfacing programme
5f903fd8-a1e3-5d7e-a830-26e7e81f9bd7 | note | Responsible Person - Surfacing Manager
41f8e6c9-ee67-5056-8ea2-571a52f87733 | note | Verifying Document - Construction Completion Report
ac1e41e2-4adb-5f5c-95ae-d978ff364219 | note | Conduct - C
3c1bbea7-a5fe-517a-a9b4-e0a783953818 | note | Produce Record - C
c2d51fc0-dcb4-583e-a884-18759d2d8e1d | note | Approval - C
| signoff | HOLD POINT
| checkpoint | Chipseal Post-Verification Testing and Report
ac5e1801-7cbb-5dba-a595-660319769b3e | note | Controlling Documents - NOC; MS 6.1.3
007e0ddc-e3ba-5976-9681-165d9847400f | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
ef4eec82-453c-50cc-9921-90f8d2fad73d | note | Method - Record
c02d51f9-c468-537b-8436-133660a976f7 | note | Frequency - Each Site
2a799a79-8570-5bc8-8771-620f2f321976 | note | Responsible Person - Surfacing Manager
229ce6c9-0417-5b94-b9e7-49d4b184f03b | note | Verifying Document - Chipseal Post-Verification Testing and Report
5bf3d902-be38-5240-b6cb-bc88a32c1bfe | note | Conduct - C
07ccfb34-b9c4-56a7-9543-356a5ac77eb4 | note | Produce Record - C
cd4de66d-bb76-54dc-861d-8d6f54c0ce47 | note | Approval - C
| signoff | HOLD POINT
| section | 7. Close Out
| checkpoint | Pavement Rehabilitation Construction Completion Report
7dc3aaf9-7dfa-5583-bb00-3217d78ef29f | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
5c28d6e6-4c42-5140-a72d-3e4c9ed782e0 | note | Acceptance Criteria - Engineer Approval
9bf5a1e9-b3fa-5a1f-a5e6-a90797b42a09 | note | Method - Visual Inspection
f68c4fcf-a68c-55b8-802e-a97cc663ba9f | note | Frequency - ≤2 months of 1st Coat Seal
c008ef23-e56b-5d5c-869b-6a42f74bab62 | note | Responsible Person - Quality Controller/ Contract Manager
df847338-6b5b-5c25-9cf0-4151fe86ea82 | note | Verifying Document - Signed Report
63fce4e2-2c30-55d7-a844-41de376e4e44 | note | Conduct - C
4363de39-1289-5a51-82be-0130ecd07a13 | note | Witness - C, S and E
76be5e78-ec48-5aee-b814-3c49a8060c3d | note | Produce Record - C
189080a8-49bf-5e74-91ca-9c22344b0499 | note | Approval - E
| signoff | HOLD POINT
| checklist | ITP - Pavement Rehabilitation, Cement modified generic |  | ITP - Pavement Rehabilitation, Cement modified generic | 8211b0d7-711a-493e-b32c-54fe32ca3a1b
| section | 1. Procurement
| checkpoint | Geometric Design
23daf0e6-5980-5234-9c9c-e471610e8e9a | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design
56af718b-440b-5c41-85d2-884c7440787b | note | TNZ State Highway Geometric Design Manual
fa641f6c-6362-5cc6-823f-eb59ebfd66b0 | note | Acceptance Criteria - Principal Approval
d95124bd-9d48-5201-8fdf-5011d2cbb303 | note | Method - Contractor and Principal peer review
b3eeb8cf-387b-5f22-8707-fcb656a939d4 | note | Frequency - per design revision
6bc00443-b0aa-5a2d-afea-449317440a93 | note | Conduct - C or S
f1423ef5-5298-5a6f-af48-1b96745c247f | note | Produce Record - C
e6111f50-18a0-5e34-8596-97bfaca1efcc | note | Approval - E
| checkpoint | Pavement Treatment Design
a920dc16-3ea3-52b0-8d82-52dd8b9de056 | note | Controlling Documents - Austroads Guide to Pavement Technology
1fdbd713-156d-50a6-a3c8-08239e9bc5b3 | note | New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
5a860fcb-e3af-5c7f-ad91-c739ad7f898d | note | Acceptance Criteria - Principal Approval
f2b4b5ed-9b19-5325-adf7-c440f35b058f | note | Method - Contractor and Principal peer review
b5cb49b3-de51-5354-abd5-b74f3b36ffab | note | Frequency - per design
35f7a04c-7dcd-59aa-a459-62d081b6ff0d | note | Conduct - C or S
a79f40cd-d51f-5fcc-a4f6-fd7d3008c8c1 | note | Produce Record - C
5146ce22-11a1-5633-a0a0-6e6e4d621cc0 | note | Approval - E
| checkpoint | Aggregate Sampling
cc42f583-805f-54b1-82ce-1834c1637c5f | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
262b03f9-deb7-5536-b79e-ecd4989670d3 | note | Verifying Document - Sampling Worksheet
15b95cb7-3c4c-5bb0-b692-a051f677c60e | note | Conduct - C or S
ee10aec3-237a-5d0e-b87e-ce1cd7de3925 | note | Approval - S
| checkpoint | Source Property Test
741e3e05-8b7f-5157-9436-5a6d316cb133 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
9071d0b4-ec10-5091-b408-730b2c17afca | note | Acceptance Criteria - Soaked CBR ≥ 40
3bf37e92-d2d2-5e39-884b-e67fa51dfb55 | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
7e8e8f7f-a947-5fa3-a07d-cbc691a76d23 | note | Responsible Person - Supervisor
915f2b94-f5d9-5278-a8ef-5a3b21644dc1 | note | Verifying Document - Test Report
05646849-d0c7-544e-acf0-ab070d5e55ff | note | Conduct - Sp or C or S
f9cb9837-dd44-5c75-9485-435e71cc041f | note | Produce Record - Sp or S
8da8546d-90d7-57a3-8f31-4997c600fe9e | note | Approval - E
| checkpoint | Production Property Test
1958a4d8-35d9-5af9-a1fc-0781a369f8f3 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
9c3fb33d-e573-55e1-a2fb-d0a3c6f5c97a | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
2265c70c-1907-5182-92ee-8983671864cb | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
8583d81a-38e8-5d93-8d82-8d86f11c36cd | note | Responsible Person - Supervisor
88901877-21d4-54d1-8a75-0d47e2aa1142 | note | Verifying Document - Test Report
64f73317-7d6f-511a-81c0-3ba2a24b2416 | note | Conduct - Sp or C or S
2dde12bc-23fc-519c-935c-935586f70537 | note | Produce Record - Sp or S
b40476d8-2e6a-5dd7-a77b-28a042dbc6d4 | note | Approval - E
| checkpoint | Aggregate Sampling
122345f9-1685-5096-a8a4-25156a318ac0 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
75fce1c9-bfb6-553a-8b3c-0846cd327710 | note | Verifying Document - Sampling Worksheet
| checkpoint | Source Property Test
64e1a29c-0ffb-521d-8455-025ed95a09fd | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
7dc27a84-986e-5f90-8a19-e747c66b4614 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
126d844a-a739-52d5-8846-2788ff4767de | note | Method - Crushing Resistance Test (NZS 4407:1991, Test 3.10)
940a5dda-136a-5298-9821-408a312603f0 | note | Frequency - One test for every 10,000m³ of source material
62a265aa-9506-532f-881d-a64f599090ac | note | Responsible Person - Quality Controller
56437e86-4c65-53c3-9de3-5be34547f238 | note | Verifying Document - Test Report
83e4977f-9473-5bf1-b840-4a1e39a8c861 | note | Conduct - Sp or C or S
d2fb076a-d350-578a-82df-2f88e8b6561c | note | Produce Record - Sp or S
4bac2861-5ee3-5df7-9a5f-13b55bac3d14 | note | Approval - E
| checkpoint | Source Property Test
c7ecd514-76a5-5ac1-9014-aeaa03a136f4 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
9ee9b218-f425-5271-8c1f-7e7eb17dff7f | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
59f64ea1-0290-5cb3-8bff-125617cb7aaa | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
25c289ef-c65d-55f2-a79e-835185ea6cc3 | note | Frequency - One test for every 10,000m³ of source material
f3a9f57f-3e47-5da8-b02c-6a2a10972ab7 | note | Responsible Person - Quality Controller
a2ab7b59-7cfb-5d1e-abd9-537fecb5a7c0 | note | Verifying Document - Test Report
cb4ca2e2-4a95-5af9-a20a-ea7d818ffc53 | note | Conduct - Sp or C or S
d4849851-4474-5cb8-87d6-7058126c981d | note | Produce Record - Sp or S
709b0886-f0f4-568e-a844-136c617adaf1 | note | Approval - E
| checkpoint | Source Property Test
50973de9-53af-5738-909a-adda36e73e2e | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006,
493ec83d-85a5-5d13-845d-f27c44114f90 | note | NZS 4402: 1986 Test 4.1.3,
7b8df431-d13c-5675-bd3a-b084c9a5d27e | note | NZS 4407: 1991 Test 3.15
13f1ba93-73b0-5a90-a503-fafecb5a7cd4 | note | (California Bearing Ratio Test)
4280800b-8b56-5b01-a03f-80e76bae7e4a | note | Acceptance Criteria - Soaked CBR ≥ 80%
8939421c-090e-5def-ac92-cdd6d8ba19f0 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
81feafd9-c53e-5280-a7d4-7390bf3087a6 | note | Frequency - One test for every 10,000m³ of source material
f422e47b-9c9a-59ff-b141-967ccaaab0ab | note | Responsible Person - Quality Controller
1072c4d9-cde6-56af-9f1b-0fecad219d8a | note | Verifying Document - Test Report
d0fb3d0b-7b24-5072-b0d2-f32bc233dd92 | note | Conduct - Sp or C or S
2c5f2197-a679-5024-9d87-ac220155f93a | note | Produce Record - Sp or S
d4c6817f-f4e7-546c-8e27-660ebf54e50f | note | Approval - E
| checkpoint | Production Property Test
ab66f585-ed41-5351-b893-cdb24f4b6c4e | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006
3f812ab1-1058-5dd2-b53e-38594eee3813 | note | NZS 4407: 1991 Test 3.6 or
909a4000-367c-5199-8cf9-2f979ad5eb57 | note | Clay Index (4.2.1.2) - TNZ M/4: 2006,
8886a70b-4c16-5116-bc11-7c3e1cd4b65a | note | NZS 4407: 1991, Test 3.5 or
ed46665f-1933-5f95-a92e-8af632534130 | note | Plasticity Index (4.2.1.3) - TNZ M/4: 2006,
0c99d82c-9629-5b2f-af13-c4c48b1cb786 | note | NZS 4407: 1991 Test 3.4
58c76dd7-8df5-535c-9df6-38152e0e7dcd | note | Acceptance Criteria - Sand Equivalent ≥40; or
e949d827-41c4-577d-8d08-0045c57f8730 | note | Clay Index ≤3; or
b507b2a2-a614-5af0-a200-538d8d2f2d3b | note | Plasticity Index ≤5
5c291ad3-f6e3-5682-9c63-91c40dcfc815 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or
dda5df13-766d-5812-bd07-60a1a5cd5e81 | note | Clay Index Test
b7466020-d7b9-58d1-8498-3dbfb7211bc5 | note | (NZS:4407: 1991, 3.5); or
5b6fe145-52a2-5068-8d27-35a2888fab5f | note | Plasticity Index Test
6d3b344f-d4ac-5999-8261-d336055ab19f | note | (NZS 4407:1991, 3.4)
53bb0088-9a37-59bd-a830-446202009b2c | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
fa9b19d1-181b-5ae8-be98-1799103d6c8e | note | Responsible Person - Quality Controller
8fd0e4ee-a1d3-5721-a169-d79e8e9d5097 | note | Verifying Document - Test Report
f2f8d449-2c41-58f3-9b4b-1d5e3302328a | note | Conduct - Sp or C or S
c649d521-b56f-513e-95f3-073d2b9b0040 | note | Produce Record - Sp or S
d8ec158c-2a8f-5bc2-a3a5-dfe0cf1ce3fd | note | Approval - E
| checkpoint | Production Property Test
88687629-76d9-51a9-8410-96dc53f69eca | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
28f25aa5-9db1-583f-b56c-bacad667f934 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
f1ff14af-81be-56f4-8677-26b4b80eda63 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
2430f651-4961-56ee-9432-566ea899ddb9 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
a4fc1129-d2d9-57d6-b67f-1855893afd05 | note | Responsible Person - Quality Controller
f22ae790-0751-5e9d-af35-f5e929e5ac40 | note | Verifying Document - Test Report
a84f4c7a-79a8-53f8-ae50-b3087597a71c | note | Conduct - Sp or C or S
aef67428-bd89-52e8-b3f5-cf231c8456e0 | note | Produce Record - Sp or S
56ca0436-c0c2-5110-989b-5e3c46182159 | note | Approval - E
| checkpoint | Production Property Test
5c722765-77f1-58f5-8942-da986b8b94f2 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
fdcc847d-7d9d-5676-bbdc-aeaf4834ebcb | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
94de280f-1a93-5813-a62e-b3d85ec3abaf | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
1b7b05ee-d383-5e00-8380-7098e03182d6 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
30706776-cb3d-5e02-ae23-054fba1cd24c | note | Responsible Person - Quality Controller
c3cc79b6-a908-5250-8d85-0ca6c02a484f | note | Verifying Document - Test Report
f3f5502f-372b-5d34-86e0-91dfdf2065c2 | note | Conduct - Sp or C or S
8f802276-5bb0-518d-b5e0-978d4cc19956 | note | Produce Record - Sp or S
7bff03b8-a026-5964-bdd2-b7fa24a1e4a5 | note | Approval - E
| checkpoint | Stabilising Agent Selection
70dcd3d5-a82a-52d2-9c78-a71d9c69be65 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
b64d9add-7bd3-5e62-b9d6-a61b39928f4d | note | Acceptance Criteria - GP
61ec4fa7-4a56-51cc-84f5-d20b2b002139 | note | Method - Visual inspection of supplier docket
c8491ba8-b4d1-5d8f-8b46-ddc0c431348c | note | Frequency - per truck load
3a328fd8-2536-5ac4-8961-7c0d8fd0bdf9 | note | Responsible Person - Quality Controller
051f15a6-1d8b-5827-b8fb-96b71f0add4e | note | Verifying Document - Supplier Docket Supplier Cert
afd8d568-6c62-5291-af3c-0a570a4fa102 | note | Conduct - Sp or S
e5cf148a-8a34-51dc-a10d-ba5495661f0c | note | Produce Record - Sp or S
ae3fdd51-48fa-57b9-9cde-7249e12a7ed9 | note | Approval - C
| checkpoint | Water draw for stabilising
89870684-1914-5840-8254-97d8c53b9b2b | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
f47bba05-2e23-50f3-8a39-19d8ac536086 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
e9f38b0b-6a95-5f71-a2d5-6d40209d6b7c | note | Method - Visual inspection of hydrant use form
9f9080b3-7d90-506c-92a5-f85a6e5b561c | note | Frequency - per truck load
54cd115a-0fac-5740-96a7-9f3cc87a758a | note | Responsible Person - Quality Controller
fe7f8ae7-bb3d-59ac-9629-5c39dfafa185 | note | Verifying Document - Hydrant use form
49e97a82-41b9-5ddc-979f-276a634a122d | note | Conduct - Sp or S
e3d35f23-5f9f-5681-b790-431f3d1e6530 | note | Produce Record - Sp or S
e412bb73-ca25-5599-a637-04bc6d084ba7 | note | Approval - C
| section | 2. Pre-Implementation
| checkpoint | Work Pack complete and held on site
e05b42c2-5cfa-5f5e-aafa-ece248b48d33 | note | Controlling Documents - ..\Work Pack
204aaeb7-a365-5fc6-a99d-f89320b270a2 | note | Conduct - C
292d5208-7898-550e-a3c4-90b7e30cb791 | note | Produce Record - C
0f747e60-2ff7-5699-a8d8-7e98771deffb | note | Approval - C
| checkpoint | Communication Plan implemented
c9162a58-e9c6-56f4-abd0-1e185cbfb11b | note | Controlling Documents - ..\4.5 CSCMP
27bccb62-836b-57dd-bc4c-9195c484700d | note | Conduct - C
10364ed0-155a-5d2f-9d42-8e26320bb78c | note | Produce Record - C
0abf1e41-0f2a-5c7e-9ad6-840c612b4f5b | note | Approval - C
| checkpoint | Are any consents /approvals required, including for taking water.
1501e1a3-6b5e-5481-a7de-865d129355cd | note | Controlling Documents - Hydrant Use form
999a7bc8-c0a1-58b2-9fea-458e9ae5c0e5 | note | Acceptance Criteria - Forms available for applicable days
a66c2c73-0fee-56fa-8058-33a74c60d3b2 | note | Method - Visual inspection and recording
ac267f59-0224-5f3b-8d33-a180b8aec30f | note | Frequency - Daily as required
fee9a705-bd95-577e-9c3a-a7f2a244bb52 | note | Responsible Person - Supervisor
ab15f582-1e52-5345-ba97-b48c50f7dea6 | note | Verifying Document - Hydrant Use Form
398ad660-ab3b-5991-a878-f611a359a411 | note | Conduct - S
47713c6a-a882-5592-b795-8068ec657ce9 | note | Produce Record - S
| checkpoint | Quality Control forms on site
10207b03-85e4-5b8d-82d2-45af3ee643d0 | note | Controlling Documents - RQP, ITP, Scala Penetrometer Test Records, Material test sheets etc.
44e03621-f775-5a87-b6cb-483bf2ca96c1 | note | Acceptance Criteria - Visual Confirmation
59ed82a6-1d7f-5549-80e1-db622f842a0c | note | Witness - C
| checkpoint | Person(s) on site with authority to stop work if quality of final outcome is compromised for any reason
a8f581dd-094d-50dc-a13a-621d1e55f325 | note | Controlling Documents - QMP
49427b1c-327b-5770-b69e-ed12a3acb1cb | note | Acceptance Criteria - At least one nominated staff member on site at all times
1f5682ce-ea59-5114-8d16-e48878674b03 | note | Responsible Person - Site Supervisor, Quality Controller, Engineer
5ae8886e-3ccd-5fb4-9fce-4cd76c7af966 | note | Verifying Document - Pre-start sheets, timesheets
78eaa47e-7ee3-5a70-9b62-10e1fd10f15e | note | Conduct - C or S
0cab0a76-2909-53ef-9f89-85314295f204 | note | Produce Record - S
| checkpoint | Records Management (i.e. it is known what documented records are to be kept)
d6349ef0-eaa4-501b-a3b9-4ebd728d447f | note | Controlling Documents - ITP and QMP state what quality documentation is required
d12f3dad-a085-5717-8d87-f27989d51f1f | note | Acceptance Criteria - Filled in and Signed ITP
e5b5eadb-2348-50a5-a663-1112be63afaa | note | Method - Visual inspection, recording and approval
eede3cfe-3dac-5cce-aa38-c872d2c29a4f | note | Frequency - As per hold points in collaboration with the programme
26e3d35f-ac6c-5f6f-afa0-6d31eb8ea90d | note | Responsible Person - Quality Controller
d34ae252-136c-5952-b048-b18529f31384 | note | Verifying Document - ITP
f38230d3-08ef-5375-b540-3900efde45fa | note | Conduct - C
c3a55091-3351-5532-8d1c-c29413c81df1 | note | Produce Record - C
c34ed24f-18ef-5b34-b048-36e7b1df3df0 | note | Approval - E
| section | 2. Temporary Works (including Traffic Management, Environmental and Health and Safety Controls)
| checkpoint | Traffic Management Approved / Implemented (copy in Job Pack on-site)
9e38439d-6f9c-5158-ade0-16358d36a8f0 | note | Controlling Documents - Site Specific TMP, COPTTM, Higgins TTM SOP, SCR Form
684334fd-4279-53b4-90df-78b917522215 | note | Acceptance Criteria - Passing SCR audits
dc9631f0-bb79-51bd-82a0-867a8587074d | note | Method - Visual inspection and recording
3f81d287-1670-550d-93d6-961e7d25c351 | note | Responsible Person - STMS
7b7d1bc9-35e9-54bc-95e5-e3551d898087 | note | Verifying Document - Site Specific TMP, SCR
1015ef44-6cc5-5311-973a-a34c2a201bd1 | note | Conduct - C
29b69568-c344-55a0-9764-0366014459eb | note | Witness - C
9f25d3d6-2ff4-531b-b007-51bf9b672ed9 | note | Produce Record - C
91d613ae-2949-5197-b99b-25b5bee5d9f4 | note | Approval - C
| checkpoint | Environmental controls in place?
2b6a2655-308a-59b8-99ae-9eafb79ea950 | note | Controlling Documents - HSE Audit, JSEA
b8c5bb13-fed1-5518-b6ee-b2dfa4c4157f | note | Responsible Person - Site Supervisor
b8b0170c-2cc4-58bc-9f49-65d57f0bef9a | note | Verifying Document - HSE Audit, JSEA
ebc3bd11-c0c5-5425-9be6-cd9fb352e0d7 | note | Conduct - C
7f849acf-26ab-57a0-b2b9-3e4cc574ad19 | note | Witness - C
ca049235-b36c-5428-be9d-87cd844aad7b | note | Produce Record - C
c0d844d5-b683-597c-8912-b87717d97223 | note | Approval - C
| checkpoint | Health and Safety controls in place (e.g. Isolate work area)
a3cb0aca-5d23-5ca4-905a-a049592b13e1 | note | Controlling Documents - HSE Audit, JSEA
47a70285-2685-5680-8464-350c32b17544 | note | Responsible Person - Site Supervisor
abf19f6f-c5d6-5fdd-ba6e-245e8bb435bc | note | Verifying Document - HSE Audit, JSEA
49a02dd7-2f83-5b92-b489-5a2cd80c76e7 | note | Conduct - C
6f739ad9-df4f-59ac-aa0b-ca77303f49be | note | Witness - C
648c17b1-e0b1-5f50-9ebc-208039ed0689 | note | Produce Record - C
3b090e12-8960-5066-b9fe-a8a1301bf665 | note | Approval - C
| checkpoint | Standard Operating Procedures / JSEAs available on site
9ed2c9d1-7483-5cf4-866e-15c51258ee19 | note | Controlling Documents - HSE Audit
e0d394c2-e007-54c8-bd12-c918489d166a | note | Responsible Person - Site Supervisor
1f18c8dc-1d10-5add-8b4c-8b284b40bc60 | note | Verifying Document - HSE Audit
525300b5-5235-52e0-a2d9-13fef275ad6b | note | Conduct - C
91dd910f-0efe-534a-84aa-e1ec5282e272 | note | Witness - C
3d04c9bc-aeb2-5f44-9ad3-f34326920176 | note | Produce Record - C
7457f46e-bfe4-5244-8e1c-2a9888a818f4 | note | Approval - C
| checkpoint | Any service covers or utilities identified and protected to Service Authorities expectations
0b3fc37b-d54c-591f-b12b-30e8ae307929 | note | Controlling Documents - PTW Process, B4UDIG
7749fa8d-80f0-53a0-8ee2-9f425bb66469 | note | Acceptance Criteria - Work always undertaken under live PTW
f5f440c2-fee1-5bf3-8fc4-c8859625ff64 | note | Method - Visual inspection and recording
bc8836f6-b568-5175-9457-f19c4a0b3724 | note | Frequency - Weekly
074a43e6-bf57-5264-81f8-d93d922569b7 | note | Responsible Person - Permit Issuer
c39337f3-ea31-5f44-bdd9-329bb9b12b28 | note | Verifying Document - PTW
fe1bbbc8-bf5a-5840-b007-b308d4bad88e | note | Conduct - C
0103728a-7b1b-5cd9-bf04-b10cbd7802de | note | Witness - C
8beac278-9ac3-53e6-a1e4-ced8b629f090 | note | Produce Record - C
ac4b57d2-19c1-5155-919f-06e11c56333f | note | Approval - C
| section | 3. Construction - Drainage
| checkpoint | Drainage identification and placement
92ad4f2a-0011-5648-9ec2-34d42773f256 | note | Controlling Documents - Review design with Client
e2ff12b2-1779-5af4-bd11-d9cee8a90dbd | note | Acceptance Criteria - Visual agreement with Client
17c2f1c7-a5d0-5820-b1f9-b3ebeecd390a | note | Method - Visual inspection and recording
7c78b1e7-8d6c-5f92-9e38-c219bda2560b | note | Frequency - As required
d8223deb-1fdc-536b-afad-d9bcdeda23fa | note | Responsible Person - Supervisor/pm
4beaf26b-2ec9-5744-a941-a51f9852cbf5 | note | Verifying Document - Production notes
e9cff1f8-ab7d-57af-a197-f6c66ebf021b | note | Conduct - S
7a9ab55d-cc5c-50fb-b4c7-23c0edf770aa | note | Witness - C
6118e0a5-09f0-5ede-9b3d-9d403521d764 | note | Produce Record - S
dc10a466-9190-5c81-bb10-9fe86e515637 | note | Approval - E
| checkpoint | Excavate trenches and placement of drainage
39369fe8-d955-54c9-b7f4-86430754cb53 | note | Controlling Documents - Higgins SOP - culvert installation
452fd16b-a8cc-55e2-8423-1aabe6ddeee1 | note | Acceptance Criteria - Relative fall > 1%
a5f352a3-e5b3-5283-b443-4a1d668872e1 | note | Method - Digital level
c6cb5d26-6f1e-51f0-ac26-9c61d2ac1c14 | note | Frequency - As required
8fa9b952-e601-5c44-bcb8-f9614db8e9a3 | note | Responsible Person - Quality Controller
64d202ae-5baf-5d6c-aa9d-34b86bb26624 | note | Verifying Document - Drainage QA form
c34b34d4-9f75-56fa-874b-1cb426b1e137 | note | Conduct - S
5ae97c1e-2c2a-5c81-8c93-8c557d305072 | note | Witness - C
5c2182c9-0717-5f09-8213-9076eeb58fad | note | Produce Record - S
164c5086-f464-5234-98d1-6b887d25a1ac | note | Approval - C
| checkpoint | Drainage materials and aggregates
099cdf22-7016-532a-8e7c-bc44b9b25f17 | note | Controlling Documents - B2
fdc56bb0-31d2-5cdc-be6d-768b6779b4d0 | note | Acceptance Criteria - Sieve test
4a06a0d8-255c-5a01-91de-706c250ab8d0 | note | Method - Lab result
2596fdf1-d15c-5a09-873c-cc239a5d09be | note | Responsible Person - Quality Controller
1cea4e39-dc78-55e6-8903-cd0202f3530a | note | Verifying Document - Drainage QA form
8ea5e17a-1bd0-5129-91f6-566c7b189db3 | note | Conduct - S
226b72b9-a912-5e2c-ba45-177f170ea9f8 | note | Witness - C
9109c188-4f4d-59be-9640-14a33ead536a | note | Produce Record - S
c80d4b9e-79ac-526d-8c1b-2c82e1b5be29 | note | Approval - C
| section | 4. Construction - Pre-treatment Digouts
| checkpoint | Pre-treatment Repair Method Selection
8a1a35a1-378a-54c8-a2ca-a806761e0f34 | note | Controlling Documents - Site specifics to be confirmed
c9a650e0-f91c-5d0d-a33f-2dc4e80ba8a2 | note | Acceptance Criteria - Verify scala result against treatment type
b156f592-e24d-57ac-a2ca-f0972a373b29 | note | Method - Scala Penetrometer on Excavation Floor
81b46ba9-6542-5f4b-a93b-693203cf4c6b | note | Frequency - As required
4f297912-40d3-5fd4-998c-e07170f1e974 | note | Responsible Person - Quality Controller
44adbec9-354b-5efd-9cbe-fa7c1584d20b | note | Verifying Document - Scala sheet test result
20d3e81f-5c14-5fc4-bd76-d547d0bc1616 | note | Conduct - S
c10294c4-51ff-5630-9ffa-c4520a164ac5 | note | Witness - C
d28a8317-1f25-5087-a161-5de63271b10d | note | Produce Record - S
3cf9c3d3-35ed-57fc-8eb4-14098275a033 | note | Approval - E
| checkpoint | Excavation floor drainage
27127dd7-c29f-5138-9566-a275ed9648a0 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
cc94d1fa-12c7-5d5d-bf98-4332ccaefd2f | note | Acceptance Criteria - 4-8% toward edge of seal
2a3b0083-7445-5d20-9a76-ebac836e9fcf | note | Method - Digital level
b3f6f136-f5fa-5d7a-894a-520f6e4a4e0e | note | Frequency - As required
e0e7738d-f255-595a-ab7f-4d81f0b5f6e7 | note | Responsible Person - Quality Controller
c98f8997-1827-5e73-a1a3-257cbd24760e | note | Verifying Document - Dig out QA form
0db11486-d249-5d26-8aee-b74a82ccc0eb | note | Conduct - S
9d70d0e0-4629-5c56-99b5-1f71703c305d | note | Witness - C
b0d16d59-3d08-5cd6-ab2a-013f04adbe29 | note | Produce Record - S
5f02a89c-7e8d-5c43-97ab-c33544ed585f | note | Approval - C
| checkpoint | Base Course material hardness
180f434a-9aff-5964-b229-743ff7c2dba4 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
7a536855-2284-5193-b6e1-03c878065422 | note | Acceptance Criteria - ≥45 Clegg
f12946ad-8cb6-5d48-98ac-30851462df47 | note | Method - Clegg Hammer
0cc96726-49bf-5488-a91b-54258ee7bf7a | note | Frequency - 2 per patch
72ceba3e-f5cc-537e-9c82-2ecf48f3b7d3 | note | Responsible Person - Quality Controller
2b6153cd-2fe0-5b99-8759-e5e9f876c1c8 | note | Verifying Document - Clegg hammer form
93a2e25b-7ed0-5512-a5f2-f31dea5351e4 | note | Conduct - S
8b9b3bb3-6468-5727-b3de-0cfce259edd6 | note | Witness - C
3ea046a5-b547-5faf-a59d-41c3e8480836 | note | Produce Record - S
3d4ae4f6-9124-5ff1-bdce-8890d5b66061 | note | Approval - C
| section | 5. Construction - Granular make up and In-situ Modification
| checkpoint | Plant and Machinery Selection
eab2ab0a-74de-5a6d-b3d4-e33bb72c3e42 | note | Controlling Documents - Plant and Equipment (6.0.0) - TNZ B/5: 2008
57af197f-3957-5877-8559-97601e011807 | note | Acceptance Criteria - Cement Spreading Truck, Direct Injection Stabilising Mill, Vibratory Single Drum Roller and either; 1 Smooth Double Drum and 1 PTR or 1 Combination Roller
e1cf4264-6d9b-5844-866c-2957e35b9dbb | note | Method - Visual Inspection
089ce533-9409-51df-a2df-e4c02fc36310 | note | Frequency - Pre-establishment
a301eddd-af12-5cfd-aaf8-aad66c36473c | note | Responsible Person - Quality Controller
e34cb9bf-61b0-556b-9c1c-e0e3bdea64c7 | note | Verifying Document - Daily Site Record
21f6b842-740c-509a-8bce-3a3b5b5876f7 | note | Conduct - S
044cc412-7beb-5112-898b-5ab132021117 | note | Produce Record - S
abae606a-0313-57e0-8618-1f441ad66914 | note | Approval - E
| checkpoint | Weather including temperature
fe1a2f8b-3c0c-582f-bb72-ce8ef8b0534c | note | Controlling Documents - Weather Limitations (7.1.1) - TNZ B/5: 2008
3de2d282-22ed-5e0a-bd29-f434236b85d3 | note | Acceptance Criteria - Ambient air temp ≥5˚ C, Wind speed ≤25km/h, Rainfall ≤0mm
548ebe26-1330-5d58-ad39-cf8d514c9245 | note | Method - Visual Inspection, Met Service
7432174a-36f5-5fe6-b701-f619c5318f7a | note | Frequency - Throughout process
df98fbaa-77d2-5bb7-b598-54f24b25e73d | note | Responsible Person - Quality Controller
0c540aac-1097-535d-bb07-a847897d1d85 | note | Verifying Document - Daily Site Record, Metservice
7b126a26-091c-5774-9425-08dbed24a3bc | note | Conduct - S
299b2034-fffd-5aa1-a126-824e754c0d91 | note | Produce Record - S
1cd235eb-a784-5b3c-9d59-c6c81d181df4 | note | Approval - E
| checkpoint | Spreading of Cement
779ce055-d1b1-5bfc-88d7-89b33adbdeab | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
92a0c94a-cf72-5e6b-825a-4cc08fe4cee9 | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
d1387c95-fbef-59a1-a5ff-87ccbaedac56 | note | Method - Mat test (1m² canvas) and Average Usage Test
50207a19-65aa-5a36-b159-18968e8957e6 | note | Frequency - per 400m² and upon emptying the spreader
03865fe2-724c-5d89-9c4c-9aed8fa13cc5 | note | Responsible Person - Quality Controller
7097a712-c10e-5199-ac65-cc485a0d37cf | note | Verifying Document - Mat Test Form and truck dockets
077a42ee-8a68-5d87-82ac-8974d62d462d | note | Conduct - S or Sp
57d16403-8ff0-580d-a90d-7a36cd33afa3 | note | Produce Record - S
7205f251-7da2-5eb1-8af6-f60dd463dccf | note | Approval - E
| checkpoint | Addition of Water
09563d34-bbe0-5548-b2c9-94771d72c9f6 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
c25e7440-70c5-545e-9e43-4421c8974582 | note | Acceptance Criteria - 90-100% OWC
c478b4af-4c45-5aac-8f71-ddee1b9f711c | note | Method - Nuclear Densometer Testing prior to Stabilisation
2b554c7c-0228-5bfc-91ce-d4265c868ee8 | note | Frequency - ≥1 per 1000m² lot
5ca1ae5c-d5c5-5d91-afaa-b36e8c80c9f9 | note | Responsible Person - Quality Controller
bf6c18d4-3448-54dd-85a0-eb22d6c5032c | note | Verifying Document - NDM Record
5f2185e1-d77e-59d0-8fe3-dcfddcbac7c6 | note | Conduct - S
c4072f41-7961-5821-b842-1d1aee1fde71 | note | Produce Record - S
ce58f37e-13fc-5476-8150-069c4331e8f9 | note | Approval - C
| checkpoint | Cut Depth
ae4f0923-b2ec-530d-8e7d-029565896dd4 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
896b8101-29e5-5ecf-b81e-d891d36950af | note | Acceptance Criteria - -5mm and +15mm of design stab depth
da6934c4-da65-5e54-b2cf-7bb83d99b208 | note | Method - Physical Measure and Visual Record
012d7c0d-127b-5bc1-ad9a-8f55425675b2 | note | Frequency - ≥1 per 200m of cut length
29196fd5-8eee-5b86-9cca-521a02901476 | note | Responsible Person - Quality Controller
e036ffff-f3eb-5e46-a315-787ef0d0680f | note | Verifying Document - Photographs and Daily Site Record
5b1bc5f7-1fcd-5905-9f7e-7fea69dfffbe | note | Conduct - S
c733de5f-fbb8-5e68-a017-75af32a06b6b | note | Produce Record - S
4f3f6d8d-bd46-5051-8a0d-50e4fcf70a0c | note | Approval - C
| checkpoint | Longitudinal Joints
60198ac2-ce10-5714-9f08-c711a3012320 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
3ba46e61-853d-5325-b887-65aaffd640c7 | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
0a7a86a4-be48-5420-889e-9a52191aa7ec | note | Method - Visual Record
5eba05c5-83f0-52de-b5aa-bc2c317d7cfd | note | Frequency - per successive cut
8aa1a230-a6fd-5242-ad3d-592735fc6f27 | note | Responsible Person - Quality Controller
8331d570-d05f-54c8-92c7-eba2f1c530ec | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
12defcd1-fc53-546f-92a7-1ea54c7d5328 | note | Conduct - S
85328c64-b73e-51f6-a704-f0d5ee993b1c | note | Produce Record - S
7938acba-9e06-5a0d-90a5-f7f2f696a0c8 | note | Approval - C
| checkpoint | Continuity of Layer
99fe71c5-3150-53c5-b996-c38c5d2acdc9 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
f4e6bb8d-6a66-5841-9bd5-1e31c8173199 | note | Acceptance Criteria - Longitudinal overlap 1m
0ad48dac-008f-5de0-95e7-5eb76475bdeb | note | Method - Visual Record
4e4867ab-7c1c-5cec-a33c-182d795ff6dd | note | Frequency - per successive cut
7c983f5d-1550-58f9-8fdb-eef7d808e4d9 | note | Responsible Person - Quality Controller
a192c250-4b7f-5b99-82e6-f6822cfa63fa | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
0db0f717-0751-550e-b76c-32afceeb8aba | note | Conduct - S
07151af7-0f92-5a24-b607-f13636129cbc | note | Produce Record - S
db78d226-ea73-58d4-abd8-8accdd107da7 | note | Approval - C
| checkpoint | Stabilised Material Particle Size
a2df3fcb-ed3e-50f5-9b16-010ef735c615 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
74dc9588-afe5-5314-990b-ef4a45edb073 | note | Acceptance Criteria - No excessive breakdown of stabilised material
0b2300ac-1dd0-5de0-9cef-4e738fe0eab7 | note | Method - Visual Record
ce4c8a17-89ca-5d14-a59d-694debd353f3 | note | Frequency - within 20m per successive cut
b89493ed-e111-5642-b7e4-2f89dfa18101 | note | Responsible Person - Quality Controller
5d11bfdd-0278-5343-a3c7-680d44e278b3 | note | Verifying Document - Photographs
20feea77-15ae-5798-871e-88421907933e | note | Conduct - S or C
f15b7d56-f7f2-599e-9a3e-9ba3d0199cda | note | Produce Record - S or C
52bb278b-7ff4-53c7-a962-5ba2c591e836 | note | Approval - C
| checkpoint | Establish Compaction Target
59c72fa2-a4d9-5be1-bacc-d3db55dcea84 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
67122a60-5f6c-5f98-bd22-18055ebf7c41 | note | Acceptance Criteria - Formal Agreement
50cf8cac-cf2a-5e9e-a517-1e2cd8ea299e | note | Method - Plateau Density Testing
0170797d-f42b-553e-842c-cf406f58a47d | note | Frequency - 1 time, or additional tests when material changes visually (Recommend a minimum of 1-2 tests per section)
c0938476-acc2-5240-9c0d-140453eb1620 | note | Responsible Person - Quality Controller
0e12526c-3d69-5471-86f7-dff4ee66d58f | note | Verifying Document - NDM Record
435cd426-fbcf-507c-a429-c74ff7a1cc5d | note | Conduct - S or C
4a1e8751-03f5-539f-a497-bee86dd3cdbd | note | Produce Record - S or C
30534eff-03dd-548f-a98b-b3aa7f7042eb | note | Approval - C
| checkpoint | Compaction Acceptance
a50d0450-166b-58ac-a030-815e8efe67c2 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
9dc387a9-27d0-5831-b345-d577b5e268f2 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
e954345a-8557-5f02-ab7c-c4d57e157429 | note | Method - Nuclear Densometer Testing
d7b4283a-3c1b-5d4f-b089-82f6bceaf1e1 | note | Frequency - ≥ 5 tests per 1000m² lot
cc4a0219-758e-5e9d-9dcd-367a3163e6dc | note | Responsible Person - Quality Controller
7630e42d-75a0-59a8-bcd2-014d1b254d70 | note | Verifying Document - NDM Record
1b4871d2-c753-5317-bc8c-086bb4523b16 | note | Conduct - S or C
0d4e501e-6f11-5bee-a956-95c87e0003e8 | note | Produce Record - S or C
aa628863-92d7-5a12-98e9-f95ffc2fafdd | note | Approval - C
| checkpoint | Control Testing
167f584f-f910-5138-9c90-8d15f8772fee | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
899cb87d-a328-5d26-8c86-4313f1795f54 | note | Acceptance Criteria - Nil
7e0f2986-87db-5cf6-8892-8ce87ac950b7 | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
95d4658b-35d4-53ca-a811-2114df48c274 | note | Frequency - when agreed
c4e2260b-53a9-54d0-9162-ddd6f1c12954 | note | Responsible Person - Quality Controller
b23f9564-d41c-51e1-9e57-2043c64ea46e | note | Verifying Document - Test Report
6ebc6c2d-3f51-52e6-9a36-86c4ca0b2d37 | note | Conduct - S or C
962b85e0-2750-5ede-a36b-6f6ad7900b0a | note | Produce Record - S or C
af6638e7-a950-5a94-b490-a52cbbfbcbe1 | note | Approval - E
| checkpoint | Surface Smoothness
546d0d2f-0530-51a4-beeb-50f370dae915 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
ff4f1ab2-f023-597f-9b8d-694d118aac68 | note | Acceptance Criteria - ± 10mm deviation
e43d4e7d-4d5b-5ea6-93be-b7afb622d5a3 | note | Method - 3m Straight Edge
9eb8dfe0-a2fe-5811-b1a5-35675fee7576 | note | Frequency - during construction and prior to seal
e216fb85-c163-593f-be07-7c640fd1c07c | note | Responsible Person - Supervisor
4f061c65-c08f-5f5f-a762-569a6759dd3d | note | Verifying Document - Photographs
e44b67db-2eed-5547-9b3d-e21b0e1d9f93 | note | Conduct - S
3076c3db-c553-5744-af7d-b013b6f986d7 | note | Produce Record - S
85532d8b-1bb7-56d6-aa46-2c996bf2cbe5 | note | Approval - E
| checkpoint | Surface Shape
b8eb2a25-ec3e-5ddf-ad6e-6435ed9b77ef | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
014db4a7-a51b-5bed-8532-aedfd585f92f | note | Acceptance Criteria - Between -5mm and +15mm
a57ff17b-a15a-5a44-8d8d-579c83226f75 | note | Method - String lines or Survey As Built
30c65329-5d26-5242-b08f-ad1882727cc8 | note | Frequency - during construction and prior to seal
2aa48e48-4b8d-544d-a7cd-7aa31dd5fa97 | note | Responsible Person - Supervisor
6c9619ec-2d7b-59e6-8b86-49611e96b944 | note | Verifying Document - String Sheet/Survey As Builts
b5804a9c-15aa-5f70-b377-c395255bf883 | note | Conduct - S
353ec70e-d1f0-5276-89e4-a3fb27b6e15b | note | Produce Record - S
34bcb6d6-872e-545a-bc8e-16b7aab427df | note | Approval - E
| checkpoint | Cross Fall
62ee53ac-0029-5e5b-ab65-0a1f99c39399 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
1070836a-ae26-5c21-93f1-d265a7fc116a | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
0d72304a-9ee1-5f37-bd51-c53761bed7aa | note | Method - 3m straight edge or Survey As Built
5a5738d8-30c3-5df0-acb8-78c1074efa0a | note | Frequency - during construction and prior to seal
b45c6bd9-2dba-542e-9f2c-0e7a9639beb1 | note | Responsible Person - Supervisor
d09aaa62-3430-5c1c-9bde-b7567d1ec67b | note | Verifying Document - Cross Fall Records/Survey As Builts
06f43bba-4bc9-5f9c-b23c-3183eed35804 | note | Conduct - S
5ac5588c-755b-5871-bfee-9e6291d42482 | note | Witness - C
e0ce1ed5-65e6-5c81-9d83-9fdee24a0b1a | note | Produce Record - S
49ac7de1-13c6-54cb-8134-9f3726bb2377 | note | Approval - E
| checkpoint | Surface Finish
eff60613-9167-529d-a613-03983050e10f | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
b9766024-69a7-5a58-936f-144c08b48407 | note | Acceptance Criteria - Tightly bound matrix post sweep
38f9b670-8a9f-5d2b-8836-78e5fa10302c | note | Method - Visual inspection
812e13ec-e6ca-5d73-b223-b3dbb5a4f08d | note | Frequency - prior to seal
0196b742-fd0f-5bd1-8392-5179e61e66fe | note | Responsible Person - Supervisor
f78259a1-4160-5fda-bcc4-7c1c8a7013fd | note | Verifying Document - Pre-seal inspection sheet
8a4a0c99-b590-5d44-b643-af207fb76415 | note | Conduct - C
83fd7b34-8604-54a3-ae99-8e498534ca3f | note | Witness - C and E
320b2915-4ae3-5f5f-8e72-5ba157129770 | note | Produce Record - C or S
119fc0d3-4b7b-5310-873c-edd7e9d90550 | note | Approval - E
| checkpoint | Pre-sealing Requirements
197aed84-7954-5531-9685-e78192cad3c9 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008,
69db532f-c4bd-5295-851a-44987e0a3dbf | note | Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
06c49834-f875-5296-a012-531496eb5243 | note | Acceptance Criteria - ≤80%, however 65% is ideal
40e875b1-b314-5766-8728-fccccc6f5fc1 | note | Method - Nuclear Densometer Testing
7d9ba89f-347d-5d3d-96d4-c795d722e0ed | note | Frequency - if required, ≥5 tests per 1000m² lot
57c3aaf3-cd64-5ad7-8f0c-62d221c375d2 | note | Responsible Person - Quality Controller
d839ca46-d145-5a93-bc98-1df334dcb349 | note | Verifying Document - NDM Record
1b864631-4fc6-5d88-a91d-e74b4809af62 | note | Conduct - C
f832235d-5478-57b6-b265-495d78f5b400 | note | Witness - E
5da84be2-2f4b-5491-ae1f-735ffd91125f | note | Produce Record - S
d713e3db-2de1-55f5-8872-43835a4d09f4 | note | Approval - E
| section | 6.1. Procurement (Chip Seal Resurfacing)
| checkpoint | Binder - Penetration Grade
c8eed71a-04c0-5c7e-b2c1-7cf96643c0a8 | note | Controlling Documents - TNZ M/1
8b32eef4-525b-5e29-8698-7a54c27dd84c | note | Acceptance Criteria - Table 1
1dbe47a3-9dd7-5525-88ea-f7ec0f30f814 | note | Method - Property Test
491a2e94-cbbe-58e3-9800-7e43c1277dc7 | note | Frequency - Annual
a70cf99c-1704-5f6b-962d-b415b788fb39 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
7d3205c7-1ba0-5794-87ba-2954db422b9a | note | Verifying Document - IANZ Report's
43eefaa3-44c2-580d-a238-371dcb86c9ca | note | Conduct - C
1d16de17-d09d-55eb-ba05-24d083320936 | note | Produce Record - C
471a056d-3154-5102-93d2-fa4b9e84d22a | note | Approval - N
| checkpoint | Binder - Polymer Modified Emulsion
d47d414a-719c-5d14-8fce-c757ce61556e | note | Controlling Documents - Higgins Internal Specification
4050a639-ea42-5805-9d38-17ca36a19c49 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
86724cf2-714e-5b0a-a46d-75fa88c35e62 | note | Method - Property Test
75deb3fd-eabc-538e-b6ff-2e91f0c05eaa | note | Frequency - 1/100,000 litres supplied
e32d5363-9d36-5dd5-beae-a895ed711b82 | note | Conduct - C
4c6f031e-234e-561b-84f6-a2a99ee5acb8 | note | Produce Record - C
95daeb04-309e-55b6-be37-3ad344fe940f | note | Approval - N
| checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
ca704e10-3256-55fd-a0d3-b8bf2faa48ce | note | Controlling Documents - TNZ M6
3e340514-90be-5242-964c-7650c992078f | note | RNZ 9805:2009
816ed67b-2238-5115-b780-80240594da7f | note | Acceptance Criteria - <10% fines under 230kN minimum
ade7d123-d0a3-58df-a1ac-c717ef1a8e0a | note | Method - Sample Test - Crushing Resistance
56751622-de55-5171-a7c8-695924ce7d41 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
30f7f63b-5c73-56f3-8a42-50f17e6a1793 | note | Responsible Person - Surfacing Project Manager
d96724e2-e701-5dda-9651-fb1e7de29ead | note | Conduct - C
536e30cd-cad5-5cf8-a00e-c7b280ccee1f | note | Produce Record - C
9e5dc714-bb35-589b-86ee-1cb23484d961 | note | Approval - N
| checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
dec2efe7-fd96-5319-bafb-517c217c89af | note | Acceptance Criteria - AA or BA
78c5f70b-fda6-58e3-ac4a-f87c6dca8a24 | note | Method - Weathering Quality Index
ea1b14ee-4fd5-53ac-af16-ef6e9264f85b | note | Conduct - C
6a03b210-7c88-5d96-8a4e-d1aba496c76a | note | Produce Record - C
cdab389e-a653-5aaa-975b-d3be8a0aef10 | note | Approval - N
| checkpoint | Production Property - Skid Resistance
34d12fa7-aa14-518e-8819-b3d3a466b735 | note | Controlling Documents - NZTA T/10
053971d2-37b7-5684-b962-b22c502c40f9 | note | Acceptance Criteria - Meet Skid performance Requirement
9625f79f-1c27-523d-8c07-934f88e2b5bf | note | Method - Aggregate Performance Method
fa0d76ae-e06d-554d-8a85-37f234738fd8 | note | Frequency - Each Site
324646de-dc38-5498-9555-115b5fcf6bf7 | note | Conduct - C
0cc32584-1397-5572-86c2-674037d02610 | note | Produce Record - C
7c5273f6-9e36-5a19-95a8-0a5569265cee | note | Approval - N
| checkpoint | Production Property - Cleanness Value
d2320f4b-87da-5b8b-83cf-bec5ca3146ad | note | Controlling Documents - NZTA P/17, M/6
35012be5-f7d0-5e3c-90c5-3ade81b4c06d | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
517bea58-fad9-579d-b2bf-984a8464dba0 | note | Method - Sample Test - Cleanness Value
7c99254c-3a5b-5279-95f5-0c845d5dc77b | note | Frequency - Per Stockpile
b4d53dd2-8ded-5048-befe-640c32f1299f | note | <100m3 - 1 Sample
bc79fa54-e407-5596-896f-890344f7a7e1 | note | 100-500m3 - 2 Samples
866f5428-fdf2-5630-be19-5007b58d75ea | note | >500m3 3 Samples
32584941-042b-54f6-b8cd-d0fef9ee7014 | note | Conduct - C
8e798841-f432-5769-ba44-2d9c9f064baa | note | Produce Record - C
25f9f1b1-e998-57f0-a639-de914d31f6ea | note | Approval - N
| checkpoint | Production Property - Particle Size/Shape
66e71881-5beb-5896-8da7-a42542699d63 | note | Acceptance Criteria - As per Table 2 and 3 NZTA M/6
0158a40d-45cf-5122-80f6-504dbd98b917 | note | Method - Sample Test - Particle Size/Shape
7eff8023-9792-58dc-9479-37b7b2ec4f9b | note | Conduct - C
bbac334c-843f-50fa-b634-a306e7ca701d | note | Produce Record - C
40181668-e860-5177-b4f9-0fa3132f1dee | note | Approval - N
| checkpoint | Production Property - Broken Faces
135aacde-7288-5fb4-8779-67014447a48f | note | Acceptance Criteria - 0.98
5f97faf3-5183-54c2-a630-949019eb5127 | note | Method - Sample Test - Broken Faces
1dfa7caf-2c3f-5324-8550-4d5107f5faea | note | Conduct - C
54ffe832-65e3-5517-9b29-6707e57dba32 | note | Produce Record - C
77ef3cc9-553b-534f-a932-b0ba7ed06496 | note | Approval - N
| checkpoint | Chip Seal Designs
ff0bae9c-ef1f-5a10-a86b-d4f6b02f8d21 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
5ce4fd5e-701a-5192-bad0-8c35b76ae05f | note | Acceptance Criteria - Client Approval
245744b7-6976-54c8-938e-a963aa6dac65 | note | Method - Review
15844307-8e27-58e4-8101-58756d30ee98 | note | Frequency - Annual
9f097b21-0cec-54c5-99fe-a11d9288eb02 | note | Verifying Document - EBOP NOC Design Report Acceptance
c081694e-f17c-5780-90fb-1b874e78d8f9 | note | Conduct - C
efb7bbb0-35e1-5464-82fd-79fbf3d4cb38 | note | Produce Record - C
5425a4a8-7315-58e5-bca9-1927a91cde89 | note | Approval - N
| section | 6.2. Construction (Chip Seal Resurfacing)
| checkpoint | Start spraying Temp >10°C
2fa505af-4779-5d55-96c2-2e6e73ec59a9 | note | Controlling Documents - NZTA P/17
59563562-b5ea-554d-ae80-409c7fd83bbb | note | Acceptance Criteria - Start >10°C
a0c6384e-49a7-5fb9-a295-1bbe9fa629c5 | note | Frequency - Per site
080ba78e-261f-54d9-9345-c3a7b9206422 | note | Responsible Person - Site Foreperson / Site QA
445fdd50-dce2-5df7-9265-d65cd3f29c6b | note | Verifying Document - Spray Sheet
22428573-b6d8-5ab5-b875-b08fd59861ca | note | Conduct - C
140cfdf6-3b98-5a22-99f7-855a430ee918 | note | Produce Record - C
9a77ff0c-652d-57b3-96b4-e8876d283d16 | note | Approval - C
| checkpoint | Binder application variation
d105ca1e-cf9d-57ae-b2b9-ed8553de1a2d | note | Controlling Documents - NZTA P/17
f08b6058-54ef-5cb8-a43c-8c413fbf04fd | note | Acceptance Criteria - +/- 4% (spray rate)
ef832bd6-f965-5e99-9d50-f19352fb737f | note | Frequency - Per site
a02837cf-455d-53a7-a3c5-42303c2860b1 | note | Responsible Person - Site Foreperson / Site QA
63009873-6549-5852-b58c-8bb135c8c8aa | note | Verifying Document - Spray Sheet
88191725-43b1-544e-b21d-db3f03c02c84 | note | Conduct - S
034c5910-8567-5bab-baa4-818ca8b454a9 | note | Produce Record - S
286e6eb4-30d6-5222-80b9-5c636b6ff88a | note | Approval - C
| checkpoint | Sealing chip application
6700002c-2098-58c7-a4e2-b6c19ad91c55 | note | Controlling Documents - NZTA P/17
55588f24-2a28-5b33-b1e8-96a408ca7d7e | note | Acceptance Criteria - Full and even coverage of sprayed area
7cb22e35-9334-5fae-b6c0-eff75d2b6d19 | note | Frequency - Per site
337808f1-35aa-5525-b385-fa7e7f831e35 | note | Responsible Person - Site Foreperson / Site QA
b64c6fd4-2343-5c6a-a37a-5638901fb005 | note | Verifying Document - Post-seal Inspection Form
821dffd3-f1a5-573b-afec-20f8b8748fb2 | note | Conduct - C
10a66b31-9e4e-5e9b-8dc5-47c0dd58cdcc | note | Produce Record - C
69ec8cfc-f905-56d5-a1fa-1a45ac69c635 | note | Approval - C
| checkpoint | PTR Rolling pattern
0d25254b-2933-5cc1-9c30-aa5ddaf7d603 | note | Controlling Documents - NZTA P/17
269496eb-274d-5d54-998c-143f0b4738b0 | note | Acceptance Criteria - Initial rolling completed along with traffic-rolling under controlled TTM
aa0556f6-0546-5ec5-bbee-1383522d6738 | note | Frequency - Per Site
6e42871e-160d-5abe-ad14-ff974b248b89 | note | Responsible Person - Site Foreperson
9601a552-cd9f-546f-9e31-acd2e4e068bb | note | Verifying Document - Post-seal Inspection Form
abfb9eac-70d7-588b-9b39-18dfa073ca63 | note | Conduct - C
2bd3f990-6655-583c-b2e7-76c0d976f5d0 | note | Produce Record - C
8a8ac96d-2f3b-533d-91c5-80cf74278563 | note | Approval - C
| checkpoint | Trafficking
7fc276ad-d89b-5ffb-8d79-37da199daa9b | note | Controlling Documents - Chapter 11 - Chipsealing in NZ
4726e498-ee3e-52b8-b148-f62a8b2073fc | note | Acceptance Criteria - Initial rolling completed along with traffic-rolling under controlled TTM
b8333da8-97db-583b-8372-d2c3a40d4d50 | note | Frequency - Per Site
40530a06-d7a5-5b1a-94b0-00141e854b4a | note | Responsible Person - Site Foreperson / STMS
56550f31-c87f-53e0-9d2f-c15d7624ce59 | note | Verifying Document - Post-seal Inspection Form
a9627f44-329e-5a9f-ae60-9e83547de829 | note | Conduct - C
6ded0161-a737-58c1-b77a-3216d2f4c090 | note | Produce Record - C
77d0d536-7f45-5fed-94c6-2006ae590d04 | note | Approval - C
| checkpoint | Tagging for line marking
bfca921e-605c-544a-bd55-dfa36a323548 | note | Controlling Documents - Chapter 11 - Chipsealing in NZ
61190d37-2f41-5c60-8bed-fde40afbee0c | note | Acceptance Criteria - Pre-seal Visual check
13b9fcbd-e0e0-5930-a50b-3480f5569cb3 | note | Frequency - Per site
b328be30-5170-572a-b791-5ae4bf60faff | note | Responsible Person - Site Foreperson
b78aabd7-eeb3-541e-8160-3dc2c5683744 | note | Verifying Document - Post-seal Inspection Form
04e5f64f-714f-512c-b730-f53024f25cdf | note | Conduct - C
c5f89d5a-3c39-570b-9cf3-7e920c5fb317 | note | Produce Record - C
e4832b06-c321-5fab-8ed2-f2d31506c05c | note | Approval - C
| checkpoint | Post-Sealing Surfacing Condition
c3800a60-de6f-56f3-bb22-ad0ef18522e0 | note | Controlling Documents - QMP
b60367fe-b9ed-51b6-bc15-db4163c7fb9a | note | Acceptance Criteria - Visual check
097ba107-598c-5c11-b6b8-5a03519e7837 | note | Frequency - Per site
28d20919-3c26-54b6-850c-8f66d65623f0 | note | Responsible Person - Site Foreperson
a90e434a-f6da-59a0-86ef-d38bbae8ff90 | note | Verifying Document - Post-seal Inspection Form & Photograph
09ac524c-e8cb-52c1-8741-8b4819508904 | note | Conduct - C
aea65367-4aef-5b67-a5e0-79febad4c6f7 | note | Produce Record - C
7ed315dc-188c-50d2-b412-e5ac4ef7b1e5 | note | Approval - C
| checkpoint | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
8215621b-05e4-5fc6-99a7-8b6e1bee4c3a | note | Acceptance Criteria - Current E/2 Certificate
300bad08-8984-5084-aaa5-a8159bbee143 | note | #ERROR!
23392ed1-f49f-5344-bab8-5511d82b0a2f | note | Method - Test, Review
36681c60-edc1-5b99-bf0c-5e626bf1c0c4 | note | Frequency - Per Sprayer, Per Site
9af839b8-3ccf-53a7-a7db-c8b958c8c2e2 | note | Responsible Person - Surfacing Supervisor
ae3c51c6-ab48-5f0e-95d5-ddafe97c2406 | note | Verifying Document - E/2 Certificate. Spray Sheets
c9c0955d-0618-5c76-bae9-145d1bad296e | note | Conduct - C
744f8d33-60f5-5e7f-9428-71ef481b239d | note | Produce Record - C
45293c68-563f-5521-b6fc-0c6cb5ca9105 | note | Approval - C
| checkpoint | Line Marking and RRPM Reinstated
9b4fbdde-4677-5221-8653-bf0b9929cbb3 | note | Controlling Documents - MOTSAM
5212daae-2420-51d1-beec-c9625589449a | note | Acceptance Criteria - Visual check
b1e20833-cf5c-551d-8847-0fac01d61988 | note | Frequency - Per site
39fd9953-9c0b-5d43-b981-c5728089cabb | note | Responsible Person - Project Manager
6d7bd652-11ae-542c-ad25-4a1eb95d2824 | note | Verifying Document - Photograph
fab56455-5ebc-579e-b5f1-ee419db197db | note | Conduct - C
d479d0c6-2942-5341-8d4d-81db53b5dc55 | note | Produce Record - C
843ddc5e-3482-5885-a42a-6b816960f732 | note | Approval - C
| checkpoint | Matches previous Line Marking - within 48 hours of sealing
6ff9acf3-9712-5465-9c97-a21e6ef3b079 | note | Controlling Documents - MOTSAM
79a5bee6-ca28-53dc-930d-aee3f6722bec | note | Acceptance Criteria - Visual check
b97db8b8-cef3-5950-9b31-298333dc8f5b | note | Frequency - Per site
ba3a1b18-c274-520a-8333-c818c921abc0 | note | Responsible Person - Project Manager
a93f5f76-2492-5cdc-a4a4-64abc9514334 | note | Verifying Document - Photograph
ac6593fe-9d6a-53ed-9c21-5d16e84e259c | note | Conduct - C
f7cd3393-72dd-54bb-b8ab-2dd604044d50 | note | Produce Record - C
5356bef3-38f8-5020-888e-cb6497fc24e2 | note | Approval - C
| checkpoint | Spray Sheet/s Checked & Supplied for Claiming
ae80ccc8-933f-54f6-845e-b133b155f106 | note | Controlling Documents - QMP
b64237ed-6b17-5240-820f-52895d44bd4b | note | Acceptance Criteria - Spray sheet data verified against design/programme
a2e2324f-f4d9-58a6-be6f-3837c5115f44 | note | Frequency - Per site
7cf4c11c-4781-537f-8f04-d1b612934392 | note | Responsible Person - Project Manager
7280791d-9cb9-58d6-b698-42d0f708b179 | note | Verifying Document - Spray Sheet/s
ca667949-3d43-5056-9586-1900b4856adc | note | Conduct - C
b9171473-1722-571d-904d-b21e9f55f3d2 | note | Produce Record - C
baaa4c2c-7ecd-5784-9545-cef1d300f735 | note | Approval - C
| checkpoint | Collect & Upload RAMM data
07b7d154-fbaf-55d2-8bf7-9107f05503d8 | note | Controlling Documents - Comply with Waka Kotahi format
cc8bea09-bb78-52b1-a576-9d09c8451111 | note | Acceptance Criteria - Correct data supplied
ede5cfc5-db37-5216-9f4f-275b9985c42c | note | Frequency - Per site
a4aa5746-bef5-53e9-8300-0867e3c8f8ff | note | Responsible Person - Renewals Manager
f5b3d78d-47c3-56b1-8c7d-1ce210bee59e | note | Verifying Document - Spray Sheet/s & Photographs
6ed7bbf9-7090-514b-8b4d-e4058bd157d1 | note | Conduct - C
243153e0-b41c-5b6e-9426-955953f66c0f | note | Produce Record - C
2fc5adce-3237-5129-b44f-128b01265c21 | note | Approval - C
| checkpoint | Removal of TTM
7c90afe4-6220-53e6-a1f0-1c019dba9531 | note | Controlling Documents - TMP
151e0f6d-d8c7-5e1a-869e-d4ae00b83378 | note | Acceptance Criteria - Comply with TMP
90da0291-aea1-5fcb-b795-72afb818be1f | note | Frequency - Each Site
f15a57e4-ea39-51c2-8134-9b035dc2b022 | note | Responsible Person - STMS/ Surfacing Supervisor
bd0cdb52-79fb-5d86-8727-1e98177f90f2 | note | Verifying Document - STMS Record / Daily Report
1ad55394-4e80-5127-87b9-c9d765fa3338 | note | Conduct - C
2f7f9327-27d0-5260-b0ad-b07390f9694d | note | Produce Record - C
d75df27e-3856-5c91-92ea-0f18abd8859f | note | Approval - C
| section | 7. Close Out
| checkpoint | Pavement Rehabilitation Construction Completion Report
45f1c205-3c10-5c20-b1ce-11a6b542b125 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
19c4adbf-662b-532c-beb6-c2f2c6d3e246 | note | Acceptance Criteria - Engineer Approval
6cbb20d2-690f-59dc-acf0-5b0a8cd7c4dd | note | Method - Visual Inspection
7b3091c2-b175-5051-8bf9-dd77a494fe58 | note | Frequency - ≤2 months of 1st Coat Seal
f8200d5b-fc9d-5157-8994-105b938c4ad6 | note | Responsible Person - Quality Controller/ Contract Manager
d2372fe6-504a-5e66-83c2-836cc932f406 | note | Verifying Document - Signed Report
7e3ae063-462a-5fe0-b2dd-5e1ca8c44edc | note | Conduct - C
786cd607-960f-59a2-9e2e-dc82abdb6b70 | note | Witness - C, S and E
c9b57d5f-8d8b-523a-b4b5-8a6eeb38fb6d | note | Produce Record - C
60523ceb-af9a-50de-9d3e-a4a127ef21eb | note | Approval - E
| checklist | ITP - Resurfacing | itp | ITP - Resurfacing | 8fefdcf2-f1dd-45f2-a008-3e617d011fd2
| section | 1.0 Pre-Work
| checkpoint | Approved JMF for Strengthening Repairs Mix (if required)
2206b41c-d0e3-553e-a630-d6f970d2b090 | note | H
376ea47a-b31a-5fa8-ad3e-d10a526d0a89 | note | Reference or Specification - Design Report
ca0a57dd-4c42-5fc3-a9c2-f07521ea10ea | note | Method/Test Required - Confirm approved JMF dates in Design Report
affa38d7-153f-56a2-8d04-5d2f8bd0af4d | note | How Often? Each site
842e26ca-67b8-59a8-95b8-2b6e9df84603 | note | Records Required - Copy of Approved Design Report
0f470ee3-ee75-5ef7-b460-551189a9dbd8 | note | Responsibility - Project Manager
| checkpoint | Approved JMF for Pre-Level Mix (if required)
96355c61-9d41-5472-a535-0005854ab9a1 | note | H
c40e764d-def6-5acf-b2b8-963bc51a4ae4 | note | Reference or Specification - Design Report
6e85b06f-52d3-5c56-ac67-b7c17209f38e | note | Method/Test Required - Confirm approved JMF dates in Design Report
21f584f4-01dd-566a-b895-65266d264889 | note | How Often? Each site
db5f468e-029c-5c6e-aec9-51528f5f569f | note | Records Required - Copy of Approved Design Report
822e5804-7374-589e-9ada-189150ddbd5a | note | Responsibility - Project Manager
| checkpoint | Approved JMF for Wearing Course Mix
3cb3f29a-301b-59dd-8f5b-a83acb8b9d7f | note | H
37cae36c-3d77-5f29-9a22-46c06f30fd27 | note | Reference or Specification - Design Report
e969011c-623a-5a46-941f-129450142506 | note | Method/Test Required - Confirm approved JMF dates in Design Report
226c5367-56c0-5fdb-aacb-638c65428efd | note | How Often? Each site
893a48db-69df-5bdb-8788-19059311f227 | note | Records Required - Copy of Approved Design Report
56c43060-a36c-53e0-8e23-3119ec87d7e2 | note | Responsibility - Project Manager
| checkpoint | Approved Design Report
337d13d1-d82a-57b4-9d8d-4dcc857e5903 | note | H
88172857-3e01-5547-b97d-1988c273f1e6 | note | Reference or Specification - Design Report
0af9a51f-c16c-58d8-a2f3-8bb1c224bc29 | note | Method/Test Required - Confirm document on-site
a2eac3fe-6560-56f5-b12a-961c09abea0e | note | How Often? Each site
3acad867-a6d7-53fb-9fe0-738334dd6d45 | note | Records Required - Copy of Approved Design Report
3ca6d6f7-1a8a-5667-a654-b327f77e73b0 | note | Responsibility - Project Manager
| checkpoint | Treatment of affected Service Covers (to be raised or protected)
67e37a52-c6fc-51ba-a888-6eb26913bfba | note | H
11d6c3c1-fb01-5737-af82-78978d9f560b | note | Reference or Specification - Job sheet
5c2ccb51-8db2-5733-bae8-0dc05d8ba209 | note | Method/Test Required - Confirm plan in place
7e1aa2c1-12b1-5b13-abe2-e706fda56ce0 | note | How Often? Each site
60fcfb27-b059-5773-866c-e648735118b5 | note | Records Required - Job Sheet record
d7896c0d-8321-5929-9447-aecd888fcf55 | note | Responsibility - Project Manager
| checkpoint | Stakeholder Management Requirements met
dbe01c22-49bc-5150-8cc3-74b0f8b1be94 | note | H
f23968fb-20a7-561e-aad7-b575448bf38c | note | Reference or Specification - CSCMP
7f50c371-8440-50d5-b999-ae1e9b596eab | note | Method/Test Required - Confirm requirements followed
d41a5033-cab4-5b9a-bec7-7ac9dd6a514c | note | How Often? Each site
36ed58f0-6e52-5be8-adc3-f0becc045e38 | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
570f2568-ffad-599a-9026-5ab71d11a205 | note | Responsibility - Project Manager
| checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
1d396e89-637f-5f37-ae3b-86d94d1ce65e | note | H
1dc8bef1-4243-5f01-8e73-26ca484937cd | note | Reference or Specification - QMP
5de9d5dc-65a3-5aa5-92ee-79c187d72dfc | note | Method/Test Required - Brief all team members on day’s work plan
0714015a-017b-5c1b-82a0-78e2021869a7 | note | How Often? Each site
77bb0492-2ca5-561c-b149-8fde1ed90ec6 | note | Records Required - Daily diary
619c6412-7701-584b-bc60-760ef4800fde | note | Responsibility - Project Manager
| checkpoint | Confirm if any environmental protection is required
4caccc3e-6f93-57f6-a54b-c9e815740036 | note | H
a96cfb35-dfad-5835-a3ae-077115b1dbdd | note | Reference or Specification - ESMP
232082d8-79bd-5182-8e57-a65e1de83c30 | note | Method/Test Required - Record decision
05bc419f-e496-561d-b25a-117c2274d19c | note | How Often? Each site
6d9e03f6-a623-5e6c-81a1-7344fee09d74 | note | Records Required - Job Sheet record
885965ed-d865-5f22-b770-5dcc0ef3f6e7 | note | Responsibility - Project Manager
| section | 2.0 Site set up
| checkpoint | Ambient Conditions - Pavement Surface Temp ≥ 5ºC (Intermediate or structural layers) and ≥ 10ºC (wearing course) and forecast to rise
3e2796e5-422e-5762-af05-6a3e4224fa6e | note | H
49c2d762-8095-5bbe-8aee-ba5bcb8ef9a3 | note | Reference or Specification - NZTA M10: 2020 9.5.2
8a690283-280b-5227-89e1-9d19674c4f19 | note | Method/Test Required - Temperature Gun Check
23c1fc4a-7b25-5f26-b810-234b36cb4a43 | note | How Often? Each site
bdf321f7-a28d-5ac6-b8ea-0b63fcf95a3d | note | Records Required - Job Sheet record
9d2a9abb-dcf3-5967-b863-d0a7c7347f1c | note | Responsibility - Site Supervisor
| checkpoint | Job start, identify risks and controls, communicated to team
af7890d6-9a05-58e4-96d9-2fd31e8fb76c | note | H
302bafc9-bc63-51c4-833d-de1e1100443c | note | Reference or Specification - HSMP
52631a86-5df0-5538-b0cd-4f145e7296c0 | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
ece4b107-8480-531e-9f4e-66ff3cb4008e | note | How Often? Each site
58d2ed09-4af9-5c2e-b36a-9e6a9bc34bc2 | note | Records Required - Hazard ID form
0eb44db5-32c9-5abf-bf1c-6159cca9bec9 | note | Responsibility - Site Supervisor
| checkpoint | Establish traffic management to plan
a83d7f61-4e3c-5a5a-8ca4-e7405cc93d57 | note | H
8e1d9c0c-ec3d-53cc-ba43-b0b4128e82c9 | note | Reference or Specification - TMP
4fc4688f-5a07-5b07-a7b3-b14954401a68 | note | Method/Test Required - Site audit post set up
f13b3bf9-9bf1-513a-8d5d-a9634bf6f92a | note | How Often? Each site
299ec372-2c30-5fcf-80e9-06d8f2938e78 | note | Records Required - TTM diary
7cf8ebca-68da-5ea0-8e05-eeb6e481a3a3 | note | Responsibility - STMS
| checkpoint | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
9e045253-daf4-5393-9d69-ca1e881ea60d | note | H
2f782b51-4387-56a2-81d2-4030e637b2e1 | note | Reference or Specification - Design Report
c0bf009d-675c-5fe7-ab38-cfca0399d0f1 | note | Method/Test Required - Record as-built site dimensions
94ec6e8a-0381-5dd2-92c5-6059714e2669 | note | How Often? Each site
fe8bcc43-1558-57d7-9ee3-63e30b1d6f40 | note | Records Required - Job Sheet record
8f04b532-7516-5058-bf0a-a9fb9213a96e | note | Responsibility - Site Supervisor
| checkpoint | Identification of Services; Service Plans on Site; Shallow Services Marked
cf865470-54d5-5b59-9a60-a185a5135c33 | note | H
f11c8385-35e1-5894-96c7-fd1c6f2f0398 | note | Reference or Specification - SOP
74128de0-4028-5665-9a08-d68f1fe4a0da | note | Method/Test Required - Confirm document on-site / Visual check
1ac45e59-34b6-575e-87de-236f9b36458e | note | How Often? Each site
1b232b6c-bf5f-5277-aa39-f7638bb3548a | note | Records Required - Job Sheet record
ab5d4c6b-4e8a-5c94-9c60-027ce7fdfc80 | note | Responsibility - Site Supervisor
| checkpoint | Record & photograph environmental protection measures installed
502f07b8-a3d7-50ee-9896-b7e97f61e67c | note | I
ba235174-5971-537d-903d-de33798a3686 | note | Reference or Specification - ESMP
52d1e394-0e42-54e6-8d9c-7d7e2613d912 | note | Method/Test Required - Record temporary measures
4e4d1109-4f70-57b4-8408-9d7489d0a770 | note | How Often? Each site
80b7f4fd-8153-5f3b-9e55-88c0156220b5 | note | Records Required - Job Sheet record & photograph
d0b0ab46-ed5f-5a47-adf6-2e2a1ef32f25 | note | Responsibility - Site Supervisor / Site QA
| section | 3.0 Milling (If Required)
| checkpoint | Milling undertaken to correct depth - +/- 5mm nominal thickness
2e880ef4-359d-5c81-a506-21dc2572ce83 | note | I
34b5999e-cff3-58d9-84fb-9315cd4494b5 | note | Reference or Specification - Design Report
8c46f4f7-de4f-5670-a4d0-bd728965b655 | note | Method/Test Required - Dip checks
1e7dd2e2-4759-5d36-bc82-831d10eff52a | note | How Often? Per site
c43c7f65-02fb-502b-8daf-caa76657e593 | note | Records Required - Job Sheet record
87bf2549-baf9-5936-9e71-ae9bc5d8c79d | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Exposed Basecourse waterproofed / levelled
47e4f073-1d8a-5a48-896b-f99d83e1221a | note | I
d0d7e596-53fa-5725-b845-3dfb2a19d942 | note | Reference or Specification - QMP
85577660-9190-52b7-b280-8d60a8a67486 | note | Method/Test Required - Acceptable / Unacceptable
245b86ec-1216-59a5-a9f4-42956a6d3108 | note | How Often? Per site
cea254db-eb83-5816-accb-7489074d9534 | note | Records Required - Job Sheet record
31cc612a-ab04-534f-a7fc-8e3a5dc7b2fe | note | Responsibility - Site Supervisor
| section | 4.0 Membrane (If Required)
| checkpoint | Application as per Design Requirements (Chip size / binder application rate)
5cd7db54-be27-58fd-985b-e3e8de595a98 | note | I
acabcd08-5bec-5ac3-b764-6bbc5dce2785 | note | Reference or Specification - Design Report
a5d748da-5e81-5ae5-bcee-e594acfe8138 | note | Method/Test Required - Spray Sheet/s
44a57b29-dcef-587b-9f93-62cfe8aa6fa1 | note | How Often? Per site
3a5f35c9-517a-534f-8867-12b8f1fb9e2b | note | Records Required - Job Sheet record
dd8fd798-cf90-53a2-845b-8ebb1b79fa74 | note | Responsibility - Site Supervisor / Site QA
| section | 5.0 Strengthening Repairs (If Required)
| checkpoint | Delivery temperature - +/- 30 degrees from recommended mixing temperature
4f1b387b-2c2a-5ab0-9fb9-7736328830e1 | note | T
df2b56e4-3c07-56f6-a530-97e4c3cfa593 | note | Reference or Specification - NZTA M10: 2020 Notes
23dd68ad-6f7d-5673-8079-24cbbc077520 | note | Method/Test Required - Temperature Gun Check - Acceptable/Unacceptable
5747e0c8-8c85-5e31-a31c-e00bedc48d73 | note | How Often? Per load
fd0c5e6e-a48e-5f80-95f7-352dabd2fd76 | note | Records Required - Job Sheet record
4b151498-be03-5f8f-b5d7-66f75766dca2 | note | Responsibility - Site Supervisor
| checkpoint | Structural Asphalt Layer Thickness - Each Layer >55mm with ±10mm nominal thickness
00f1f4c5-af96-5780-bf18-a7b1a6523c77 | note | T
b0874908-b094-5557-b6ab-25ba77e88504 | note | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
c1b170b9-7105-5cbb-acfa-637b61c29f7b | note | Method/Test Required - Dip checks during paving process / Cores
003fe724-9273-54d6-8314-6a6512f9b488 | note | How Often? One test per patch & / or One test per 300m2
44faa9c8-2906-563e-8ba5-ba96e516d243 | note | Records Required - Job Sheet record & photograph
69cbea48-73cd-5440-856e-fe2467ad374b | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids
a4674e5a-649b-593d-a267-1eb9e54a7220 | note | T
0f095c28-bea1-576c-a490-855faaf628f9 | note | Reference or Specification - Paving SOP
f68e6b0a-aef0-5cca-a9a5-576685e01088 | note | Method/Test Required - NDM for Quality Control Only
6063fc31-2178-55b2-9a73-81178eba9bf4 | note | How Often? One test per patch & / or One test per 50m2
ec7b7780-ba1c-5d14-8260-0fc4072a7af4 | note | Records Required - Job Sheet record & photograph
c5e6a4d1-5949-5934-94d3-bff99966f25c | note | Responsibility - Site Supervisor / Site QA
| section | 6.0 Pre-Levelling (If Required)
| checkpoint | Delivery Temperature - +10 / -30 degrees from recommended mixing temperature
672ec022-fce7-5afa-9831-82a7c242fd06 | note | T
12ba052c-619c-5646-aaa0-c35c71ecd8a1 | note | Reference or Specification - NZTA M10: 2020 Notes
9b014056-08e5-5463-ba1e-416797ff503d | note | Method/Test Required - Temperature Gun Check
4091019c-6afd-59e5-93b4-1e2c86875c39 | note | How Often? Per load
94118284-5c3f-514c-b346-e286df3f46a4 | note | Records Required - Job Sheet record
8137f2dd-ccbd-5e26-812c-f9cba3c9f12d | note | Responsibility - Site Supervisor
| checkpoint | -5mm / +5mm below bottom of the nominal thickness of wearing course specified in Design Report
928c3c7e-4eae-55da-aa64-5b92a8792ca5 | note | T
f0e7a9bd-1933-5177-841d-6bb59984b8fb | note | Reference or Specification - Design Report
22128586-f4f1-5b16-b996-6ca403661c19 | note | Method/Test Required - Dip checks during paving process / Cores
85331183-7935-585d-85c5-ad76a014ba92 | note | How Often? Every 15m
8098af5e-9bca-5ba5-b42b-3f0c3e98ff45 | note | Records Required - Stringline Sheet record & photograph
e9c7d65f-3c3f-5295-a0bb-13c9709d5a09 | note | Responsibility - Site Supervisor / Site QA
| section | 7.0 Wearing Course
| checkpoint | Delivery temperature - +10 / -30 degrees from recommended mixing temperature
f2c8cad6-3b11-5355-abf1-eaabf3be129e | note | T
74528bde-d000-5bc4-b3f4-cbb4f81c7966 | note | Reference or Specification - NZTA M10: 2020 Notes
eefa4d76-20c0-5b2e-baa7-8af7b9405906 | note | Method/Test Required - Temperature Gun Check
8c78f34d-12ea-5fb7-863a-05039e26bcc5 | note | How Often? Per load
9436f9da-b4c9-5879-ac9a-f6832f63d918 | note | Records Required - Job Sheet record
1ea33632-98e8-5e4e-a8f6-6342114af7a0 | note | Responsibility - Site Supervisor
| checkpoint | -5mm / +10mm nominal thickness specified in Design Report; If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report
ffae70f6-4274-5a9e-b0c6-3ca4eefc68bb | note | T
75addc95-21ab-5a6f-b030-9364070fbc9f | note | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 or NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
30df4787-ecb4-5bba-b80b-b2776eb7c3a4 | note | Method/Test Required - Dip checks during paving process / Stringline Sheet
297852b2-2851-5062-92b7-b270cce1c520 | note | How Often? Every 15m
c509acdc-d1b0-505c-b358-acfedff96e7b | note | Records Required - Stringline Sheet record & photograph
d96acfb8-5d1a-51f4-9829-81aba96a6aee | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids (1)
33a13f5f-64f8-51b7-984a-961f4c315a67 | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset (1)
d85edd41-2f8e-59b6-b2e7-859f96de1faa | note | T
4296959a-719a-547c-b106-1c20c884e949 | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
c12a5f19-dbc8-55d7-b35a-b5adbe28a982 | note | Method/Test Required - 150mm Diameter Cores where: 1. >30 tonnes 2. >=35mm lift thickness
cf181920-7fc6-53ff-baff-28e316c4c247 | note | 100mm Diameter Cores where: 1. >30 tonnes, 2. >=35mm and <40mm lift thickness
ed6175e8-0e83-5841-b68d-cdd1d6e95482 | note | NDM (only where accepted by the Engineer in writing along with the testing plan.)
eb46026e-0818-58bf-b6bb-fd12ce115123 | note | How Often? Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
62932d39-86e6-59ba-8418-ed7b577712e4 | note | Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
eac9a6bd-05ce-59ca-bdbb-6c871a0d1f95 | note | NDM (only where accepted by then Engineer as per agreed testing plan.)
26d40d6b-06a1-5578-9f71-e914a099cbd6 | note | Records Required - IANZ Accredited Laboratory
be2c3dba-e541-56f4-8b5f-b25e70309031 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids
009bba04-96c4-5fc4-9475-19eaf87cd4e4 | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset
5370ce52-89c5-5e64-93fa-09afcd96eb5a | note | T
88970b0f-bcd9-58d7-9f58-851ffe570f09 | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
183be702-4efb-584e-bd43-72eadfa82434 | note | Method/Test Required - NDM for Quality Control Only
52aef13e-ef53-5a60-86e4-b8dd66ea678c | note | How Often? Every 20m alternating wheel tracks
417727c4-9209-5782-883b-681ddf1e28de | note | Records Required - Job sheet Record
a1f2ab54-179b-50be-99b8-0b9c3f762107 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Post construction surface condition
565b6726-9be0-500a-a24f-d3f491f20fd0 | note | I
e61f501d-0afa-5053-a3cd-ffbec443a0b5 | note | Reference or Specification - Design
213a0b7b-ac84-5849-8e55-e84edfcad32d | note | Method/Test Required - Acceptable / Unacceptable
bdb03da0-7169-59ee-8fea-a1ff2b4be169 | note | How Often? Per site
75915582-9cca-56f6-87f0-c07bbfbef0dc | note | Records Required - Job Sheet record
5ff1a08a-3721-5e11-bef1-1d0bac918a10 | note | Responsibility - Site Supervisor
| checkpoint | Supervisor to provide an update regarding site completion per shift
6c359ad0-682d-5f35-b414-f0599a455190 | note | H
3b4a1da4-d8d9-59e5-bbd5-116c5eb078cc | note | Reference or Specification - Design
af896fa1-d940-5018-8294-8da248bd7bdb | note | Method/Test Required - Acceptable / Unacceptable
50f10cf0-2dbb-599a-bf8e-1e59b7cb0ae8 | note | How Often? Per site
b2c004cc-a7c5-5d13-a46c-8be516128c85 | note | Records Required - Email
59015451-7907-5b7f-b65c-e94e0e5fb7a6 | note | Responsibility - Site Supervisor
| section | 8.0 Post-Construction
| checkpoint | Linemarking and RRPM Reinstated - Matches previous linemarking - within 48 hours of sealing
c89e92d0-d50e-58b4-be3f-1d0610947037 | note | H
41aeef3c-677f-5dfa-a1d1-14de1b332e69 | note | Reference or Specification - MOTSAM
f9915846-9e2c-5994-8b94-ba0b40c1cd52 | note | Method/Test Required - Visual check
a4e58d1c-f153-5ee5-9076-06c3782b81cd | note | How Often? Per site
bd3a188f-3a0e-51f0-a0c7-12701c3ad56e | note | Records Required - Job Sheet record & photograph
94c724c2-c0c6-551d-8f09-a9325f4050e2 | note | Responsibility - Project Manager
| checkpoint | As-Built records – structural patches
22f58c3e-7cd4-5a5d-90ab-5767f2fab9df | note | H
d2c1f388-7a52-54c3-8146-9708721367e8 | note | Reference or Specification - Design
3799eeaf-2730-57f0-8c1f-dda585bb657b | note | Method/Test Required - Record as-built patch dimensions & RPs
a548255d-3195-5935-8881-56342f74a1f2 | note | How Often? Per site
96766b65-794f-525a-961f-04f9b9a6df2a | note | Records Required - Job Sheet record & photograph
cba2ec15-858c-5340-97b2-b17c9f002d1d | note | Responsibility - Project Manager / Site QA
| checkpoint | Collect RAMM data
df8d213e-d829-511e-9c3a-f8d340b6714c | note | H
c8be74f2-a3ca-52c3-bb82-bd005960196f | note | Reference or Specification - Comply with Waka Kotahi format
a58015ca-dd26-5d9a-99b7-027bc2bbbff0 | note | Method/Test Required - Correct data supplied
81e2e29f-5d1f-5456-85cd-e33227ee1129 | note | How Often? Per site
16f2adc5-8ceb-591b-adf4-43282de224ae | note | Records Required - Job Sheet record + As-Builts + photographs
3d79e30c-1fc5-5922-9db9-58e4e3e39e8d | note | Responsibility - Project Manager / Site QA
| checkpoint | Compaction as per sample test results
0d6495c4-715b-5bb9-a144-aefe9cd059a0 | note | H
6351a0b0-c1e4-5c7d-b80e-e06b99da1efe | note | Reference or Specification - JMF Design Compaction
786c4aa5-b663-5e21-8b06-7007da440370 | note | Method/Test Required - Mean ≥95% ; Minimum ≥92%
b3a83b80-9d1a-5c78-92e2-2854252f7fbe | note | How Often? Every 20m alternating wheel tracks
ee2764a8-2625-501a-a8d3-0b90a7f69fec | note | Records Required - Post-Verification Testing and Report from IANZ Accredited Lab
aae94182-9bd7-50b8-86f6-68873ddb6545 | note | Responsibility - Project Manager
| section | 9.0 Out Of Season Paving
| checkpoint | Out of Season Paving
b3555ee3-2077-5614-8835-4ac4fe242217 | note | H
4ffa7979-a375-50bd-a9fe-f03a693eebdf | note | Reference or Specification - Winter Surfacing Site Note
b920417d-bbaa-5c7b-ac1b-c4134bfa6c56 | note | Method/Test Required - Waka Kotahi Approval
d36a6ada-a389-5ca3-8aa9-6f3bfca8aca8 | note | How Often? Per Applicable Site
59eb161a-9f0e-5866-9640-d71e169a9f3e | note | Records Required - Copy of Waka Kotahi Approval on-site
dd6cf1ff-c6f3-5bc8-a5cb-d63c85367e93 | note | Responsibility - Project Manager / Site Supervisor
| checkpoint | Dispatching Temperature compliance
10aad9ca-5331-5b98-8110-cff467939dcd | note | T
46ff0729-c533-59d8-b0fb-d3fe9a385088 | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
76179902-2af7-512b-9e0b-9da04cf40d2a | note | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
0bdaca13-3d60-5f3b-8e6d-a07d29939dc6 | note | How Often? Per Load
9cc5c9cc-ff49-50fd-be4b-8a00722a28ea | note | Records Required - Job Sheet record
16038e4e-18d6-569b-babf-419114c39f29 | note | Responsibility - Asphalt Plant Manager
| checkpoint | Arrival and Compaction Temperature: 110-170°C - To be recorded when mix is tipped into the paver.
d863dc72-21d0-514c-ab28-e7082ac98e33 | note | Manager to be notified if temperature falls below:
049c442a-7624-511d-8a2c-c1500d2f09bf | note | SMA9.5 134°C
de93256b-b27e-53ed-a512-cf11f04be34c | note | SMA12.5 134°C
940dc724-6fee-5535-b4c5-a35481a9a04b | note | SMA11 134°C
aaf25a0b-d59a-50fc-b54f-bcde1c269a0a | note | AC20 145°C
d7974f37-7ec7-5132-b6c7-4433aad6961f | note | AC14 142°C
626dff8c-7a0d-5840-adab-b71184554720 | note | If temperature falls below 110°C mix will not be used
aca99e1e-1e26-5896-84a0-e1aaf528fef3 | note | T
d78f4110-0d6c-5e0b-8162-f13b9bde811a | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
d6f2ec19-7497-55bc-96a5-632c60e057c1 | note | Method/Test Required - Temperature Gun, Acceptable / Unacceptable
580bef94-b676-5c32-adad-58d8b53b557e | note | How Often? Per Load
065b8d56-34d7-52bc-8c02-5b70ab39b3ba | note | Records Required - Job Sheet record
5fb255e2-3645-56e5-9eef-24a21ac35f8f | note | Responsibility - Site Supervisor / Site QA
| checklist | ITP - Resurfacing Physical Works | itp | ITP - Resurfacing Physical Works | da62f677-d6d6-48fd-82cb-6c70537311d5
| section | 1.0 Pre-Works (Off Site)
| checkpoint | Stakeholder Management Requirements met
cdbfdb4a-d24b-5cc3-8174-8645ac4ad163 | note | H
50bbdd45-eb78-5ecd-9322-c3ecb496aada | note | Reference or Specification: CSCMP
4cbff717-c5be-51df-9575-55723a8e9dda | note | Method/Test required: Confirm requirements followed
117f8001-ab2d-503a-ada2-95cdeae542ff | note | How Often? Each site
658aa158-24ea-5c2d-be74-af1631414747 | note | Records Required: Copy of stakeholder notification / Photographs of VMS Boards
7673e013-0850-5f5a-8ed8-a647f703e3a4 | note | Responsibility: Project Manager / Renewals Manager
| checkpoint | Confirm if any environmental protection is required
b34c7fb8-cc8c-5849-95e5-b77c64e097af | note | I
243a7e07-82bc-51ee-b441-9836c4bdd7a5 | note | Reference or Specification: ESMP
f2ce81e5-7384-5a65-8ece-1b72fa3927af | note | Method/Test required: Record decision
54597b4e-0af4-5023-8478-1d719181dcb3 | note | How Often? Each site
99a2a15b-7adb-5cba-83b5-f40e4784b1c9 | note | Records Required: Pre-seal Inspection Form
5964959e-b1b9-562c-bca0-d2f79ffc7f18 | note | Responsibility: Project Manager
| checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
a3d6c656-a3f4-523b-864a-b3d7637204e1 | note | H
22c408f8-fa9c-5281-b96f-7be6f7735ac4 | note | Reference or Specification: QMP
5f838ea5-5868-5503-b93f-a3119836a32f | note | Method/Test required: Brief all team members on day’s work plan
02a584c4-70f4-5fef-b7b6-ac01101cc0f3 | note | How Often? Each site
fd7aba74-aa34-59e2-9ad9-d2b2cacb86c2 | note | Records Required: Pre-seal Inspection Form
2062912c-f538-5849-8cf8-6e3e44b6b716 | note | Responsibility: Project Manager
| section | 2.0 Pre-Construction (On Site)
| checkpoint | Job start, identify risks and controls, communicated to team
e6d149ae-f116-5a8d-9e78-15db3a3b2288 | note | H
b4acb78c-9aa1-58a7-8b67-61c1319dc563 | note | Reference or Specification: HSMP
99d9085f-1b63-5fbd-bf97-bdf1bed99ca5 | note | Method/Test required: Record all risks and controls on Hazard ID following Team discussion
9797f6bd-1c62-5f2d-b301-75cde1afe59b | note | How Often? Each site
52341539-4f26-5a34-832f-fd5fff39beaf | note | Records Required: Hazard ID form
61b3a9a4-0522-50d6-bc14-fa40c40d3189 | note | Responsibility: Site Foreperson
| checkpoint | Establish traffic management to plan
0f493a92-8a60-5824-b6b3-95f27a427d7e | note | H
ac58de1f-2941-551b-ae2a-3e0a1151ca54 | note | Reference or Specification: TMP
9725cd06-6c03-541b-86c4-d0d2b41bc5c1 | note | Method/Test required: Site audit post set up
9a78cc7f-8c51-5c58-886b-f51a55ee1bc7 | note | How Often? Each site
97fcc26d-98c1-54cf-91e8-c6e601165184 | note | Records Required: TTM Diary
4f4b72e3-2ec4-528a-a13d-e9e90159ecbf | note | Responsibility: STMS
| checkpoint | Confirm site is on approved programme
534d5581-1913-5a69-9da3-7fe548a43035 | note | H
dc75f533-266c-5ee6-a6e6-10052ac2dc48 | note | Reference or Specification: Approved Programme
83127d40-9123-5301-a8f9-0ed1755e6f11 | note | Method/Test required: Record as-built site dimensions
2c210442-a7dd-5cb4-9bcc-40f6e1e9dcd8 | note | How Often? Each Site
e9c1b3f2-dcc3-5bb8-95bc-f8a09f5a5822 | note | Records Required: Pre-seal Inspection Form
decec038-6802-5740-b436-0af349833260 | note | Responsibility: Site Foreperson
| checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
3c1afa8e-5218-5ac8-934e-c2a032a5ad3d | note | H
d098261c-50e2-5a67-8e17-e51c2c195be4 | note | Reference or Specification: Approved Programme
064a72f6-bee8-5307-9880-a054b15c482f | note | Method/Test required: Record as-built site dimensions
ad445598-39c2-5533-943a-c4909417c17c | note | How Often? Each Site
bc436c36-69a2-5cbd-8a74-e814d0c8012e | note | Records Required: Pre-seal Inspection Form
a7b79433-be25-5bb1-a1ad-da253c304e60 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Stockpiled sealing chip is clean and suitable for sealing
d17b3bbd-7393-589a-9ae8-ebd751d472d9 | note | H
2dbdb2d4-2b72-5638-971d-e7ce55f4703a | note | Reference or Specification: QMP
77da869d-0497-5ef2-89cf-4e11ad3e148d | note | Method/Test required: Acceptable/Unacceptable
f00fee48-495f-5153-b90c-9669e4845b23 | note | How Often? Each Stockpile
64403bb0-86a8-5b25-83b6-a81005d02c20 | note | Records Required: Pre-seal Inspection Form & Photograph
e97de4b1-7f3a-593c-b6fd-8abcb164d37a | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
50664fb8-d6b6-53ad-9393-f74ae7577333 | note | H
97066233-9ffb-5ef0-969d-2db61c6b930e | note | Reference or Specification: QMP
5ce4fa85-b74c-506b-ade1-13f622078eb9 | note | Method/Test required: Acceptable/Unacceptable
52a2f23b-2019-55d6-81e5-bd9ddf18cbae | note | How Often? Each Stockpile
cf069fea-3338-50aa-8fde-254814f3358b | note | Records Required: Pre-seal Inspection Form
39c54daf-cd50-5b77-b750-78d68b0faeca | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Record & photograph environmental protection measures installed
8ed2474a-a321-5fdd-b715-723d4b301806 | note | I
744bf317-6a11-59c3-91d2-b8b1170cc984 | note | Reference or Specification: ESMP
56cdcb7c-bb2c-5b48-8158-39e87167f631 | note | Method/Test required: Record temporary measures
32764105-bfec-5960-b815-a344880e096f | note | How Often? Each site
5750ea02-81d1-585a-b088-6416e9f5edd4 | note | Records Required: Pre-seal Inspection Form & Photograph
dca434d7-b224-5495-bf5b-162973e83d9b | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Binder application rate
26ac55df-5697-5d02-bfa2-5ed7e99b60cc | note | T
24060e91-7b06-51a9-a74b-debd2e15610f | note | Reference or Specification: Seal Design / Spraying Instructions
82677a5b-81fb-543d-b6ba-ea25a2bf907a | note | Method/Test required: Confirm seal design requirements from programme
b2f97d7e-aee7-5ce8-b256-d3760c534722 | note | How Often? Per site
e7d153e3-e851-585c-9800-88fddecefe2a | note | Records Required: Spray Sheet
d3fdf202-f295-53a6-b940-ffe441038793 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Pre-Sealing surface condition
a8f808df-b9af-5562-9a3a-a2beebebf2b1 | note | I
1ae7ae28-d524-5cd8-825b-7246fccb79c5 | note | Reference or Specification: QMP
7540d5cf-5a7e-5668-acea-522c9a1db232 | note | Method/Test required: Acceptable/Unacceptable
db0c2e38-988c-5a0b-9f3f-6580d26423af | note | How Often? Per Site
4e17fdc0-9327-574a-aea7-0654d908bbdf | note | Records Required: Pre-seal Inspection Form & Photograph
255848e4-7bbc-5e42-9ea3-ec56fa7cf681 | note | Responsibility: Site Foreperson / Site QA
| section | 3.0 Construction
| checkpoint | Start spraying Temp >10°C
01336111-0af4-57a7-bed0-cf5b2ce88e20 | note | T
f1bc9e01-dbda-5a06-ae80-6597e1c375d3 | note | Reference or Specification: NZTA P/17
c9dc2a97-1487-5c6b-9a5a-6ff1ee44caaa | note | Method/Test required: Start >10°C
20626384-7370-586f-b3f6-90fd5bf8e45e | note | How Often? Per site
bd9af927-6c24-526d-a043-f65d7e8e05a8 | note | Records Required: Spray Sheet
01c53d0e-982a-544e-92cd-17e56ea9e4bd | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Binder application variation
d5f15e87-0a9d-5122-a9d6-121603950276 | note | T
2525a921-6bc0-5cc1-a280-ee9323867de4 | note | Reference or Specification: NZTA P/17
22f3f8f5-49a8-5044-9b66-15b74be23d38 | note | Method/Test required: +/- 4% (spray rate) ; '+/- 50l (tank dip)
aee9410e-dce0-5d13-abbc-3caee6c1931f | note | How Often? Per site
32a5eec4-d4e1-5254-bc3b-2e66dd1caf72 | note | Records Required: Spray Sheet
cc206622-80a3-51e1-bae3-8eb2a6065078 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Sealing chip application
c811bbff-d316-5660-a2fd-f37a40f0f48a | note | I
1d1a1683-53b3-5445-9517-8d65c1f0f190 | note | Reference or Specification: NZTA P/17
39aecca8-8070-545d-ab43-a8f661baa761 | note | Method/Test required: Full and even coverage of sprayed area
b404cf64-dbcb-5226-8ce1-9e50baff72c8 | note | How Often? Per site
5e2a5aef-edce-5410-aece-7d16d486ca7a | note | Records Required: Post-seal Inspection Form
1db84468-050f-5370-907c-70f1c7392024 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | PTR Rolling pattern
255c3fb6-536b-52ee-b8cb-fce74f5287c3 | note | I
21086bce-46fe-525a-8f81-ecde439379fe | note | Reference or Specification: NZTA P/17
5db6abbb-e11c-5992-b5e5-c9e31d8bc35d | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
6d5a234d-009e-5a25-b63a-0ac7840752ec | note | How Often? Per Site
543a7248-17d0-5815-a691-62bf51d1cc4c | note | Records Required: Post-seal Inspection Form
ba3f9ae0-9877-5b27-937e-36518fcad1c0 | note | Responsibility: Site Foreperson
| checkpoint | Traffickating
c2ff3134-1a8d-5126-bf6e-7ac62a8485ae | note | I
0ad0d532-4b20-5448-a4d7-04c01a3f09c2 | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
41778075-be09-5bd5-92e0-2cfe587e87f3 | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
8f8963a2-654c-5f55-abdc-d73a98756db0 | note | How Often? Per Site
578d1904-8009-54d9-8f8d-7f3848e9a031 | note | Records Required: Post-seal Inspection Form
6ed84a04-c4a1-5377-8d97-91d54d4cd462 | note | Responsibility: Site Foreperson / STMS
| checkpoint | Tagging for line marking
3a740848-78f2-5a3f-944f-e9696e1eb965 | note | I
95b3ecb0-9a83-5def-a6f5-56ca030cc34c | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
ea95e64b-b91e-56ab-abeb-87e4a9e45ab0 | note | Method/Test required: Pre-seal Visual check
6d9492c4-b48a-51ae-8b1f-549b8e7fd44d | note | How Often? Per site
491317cb-f9ca-521d-b85e-003e988ec69f | note | Records Required: Post-seal Inspection Form
bafff7b6-826d-5f95-86dc-77e1ecc665e7 | note | Responsibility: Site Foreperson
| checkpoint | Post-Sealing Surfacing Condition
dd5b1df1-a9d8-5326-b017-7d845c140298 | note | I
9e8d6acf-3143-5a1a-8346-fc18655c90b5 | note | Reference or Specification: QMP
fe662e7a-771c-5aaa-a68e-924be69d139c | note | Method/Test required: Visual check
ce1645f1-ad03-561f-b374-aabcbfe053e2 | note | How Often? Per site
a2d0bceb-fa49-5576-8976-238b851957ea | note | Records Required: Post-seal Inspection Form & Photograph
ce2c78a1-615c-50bd-acb8-03b36d53fc4e | note | Responsibility: Site Foreperson
| section | 4.0 Post-Construction
| checkpoint | Linemarking and RRPM Reinstated, Matches previous linemarking - within 48 hours of sealing
bcce04e9-05a5-5c90-9c44-85bf7b603357 | note | H
53725ac3-5e7c-5d53-bd7d-76d183dd3305 | note | Reference or Specification: MOTSAM
308889cd-5efb-5e7b-9130-434e714cdaa3 | note | Method/Test required: Visual check
0f5785ad-92c1-5362-8424-d6a953d14f6f | note | How Often? Per site
a069e844-ca12-5d8f-91ce-9a5163f47402 | note | Records Required: Photograph
4379108f-f0ea-5f3d-bb1c-012fca74f6c4 | note | Responsibility: Project Manager
| checkpoint | Spray Sheet/s Checked & Supplied for Claiming
658e7f1f-939c-5684-8b83-27ed1965928c | note | H
6249776e-51d9-53d4-8aac-d298f5790102 | note | Reference or Specification: QMP
51ee2afc-24db-5d82-9c9d-ccd97b92d7b1 | note | Method/Test required: Spray sheet data verified against design/programme
dcecb69e-8a12-5eeb-b4f7-274c2c5fbb25 | note | How Often? Per site
99dc1304-c1a9-55b0-9574-1942c4210baa | note | Records Required: Spray Sheet/s
09f63ad2-b8e4-5161-aa9c-327b5528db36 | note | Responsibility: Project Manager
| checkpoint | Collect & Upload RAMM data
8d7e45a9-f108-51cd-99b1-f741ead63676 | note | H
b36ed547-f582-5ba3-90c0-c2a4d8f80729 | note | Reference or Specification: Comply with Waka Kotahi format
2220a9f0-a4f9-5f10-9f95-a9d346648f04 | note | Method/Test required: Correct data supplied
e365a772-6213-54ec-9f7d-e756043dd338 | note | How Often? Per site
af37524f-28de-51b7-a956-5d7a36648d47 | note | Records Required: Spray Sheet/s & Photographs
51c17567-73e0-57fc-afc7-084a52a4d876 | note | Responsibility: Renewals Manager
| section | 5.0 Out Of Season Sealing
| checkpoint | Out of Season Sealing
641b7c62-e616-5ef6-ad60-6fbabffb3ebe | note | H
dd2a6469-f6e4-58ae-b8df-93162484b08a | note | Reference or Specification: Winter Surfacing Site Note
ad196084-e963-5a54-8570-10038bb7e4da | note | Method/Test required: Waka Kotahi Approval
a8a8ec4e-81d6-54a2-ad6f-45b7d30a32d1 | note | How Often? Per Applicable Site
3e49c9a4-ea4a-5d95-8307-1ab0b247421d | note | Records Required: Copy of Waka Kotahi Approval on-site
48bc0663-71f2-5cc5-b7bd-a8e73bbe755a | note | Responsibility: Project Manager / Renewals Manager
| checklist | Production and Testing ITPs |  | Production and Testing ITPs | 7395ac36-901e-4308-acb9-dc025ceb5b8d
| checkpoint | Production and Testing ITPs
| checklist | QMP |  | QMP | 144e53bf-b2f7-41a7-ade5-e8ccd2613d25
| checkpoint | QMP
| checklist | Verified Program |  | Verified Program | 1af391ff-6854-4bc7-9333-1338307d668c
| checkpoint | Verified Program