## Project Structure
Folder Structure |  |  | Checklists
Site QA
| Prelim Activities | To Contain Preliminary Checklist | Preliminary Activities and Materials Approval
| Byford Type D&E Beams | To Contain Viaduct Checklist | Ability to Add Type D Beam casting Checklist
Ability to Add Type E Stage-1 casting Checklist
Ability to Add Type E Stage-2 casting Checklist

## Preliminary activities and Mate
type | name | values
checklist-sectioned | Preliminary Activities and Materials Approval Checklist
section | Preliminary Activities (Approved by Client)
checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint | Permacast Project Quality Management Plan
checkpoint | Inspection & Test Plan
checkpoint | MDR Index
checkpoint | Work Method Statement (WMS) - Prestress
checkpoint | Concrete Repair Methodology
checkpoint | Shop Drawings
checkpoint | Test Panel Prepared and Inspected by Client
checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
section | Concrete
checkpoint | S50 Concrete Mix Design Approved by Client
section | Steel Reinforcement
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
section | Prestressing Tendons
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Ensure that all Coil Numbers are recorded
checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint | Stressing Jack Calibration Certificates
section | Lifting Anchors
checkpoint | Lifting Design Approved by Client
checkpoint | Lifting Devices Approved by Client
checkpoint | Inspection of Delivery for Completeness and Quality
section | Cast-in Items and Ferrules
checkpoint | All Cast in Materials Approved
checkpoint | Inspection of Delivery for Completeness and Quality

## Planks - Casting Checklist
checklist-sectioned | S2M prestressed Planks
section | Pre-Pour Checklist
text | Cast Number
checkpoint | Shop Drawings approved for Works
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked
label | Cleaned
label | Sealed
label | Rubbers in Place
label | Oiled
label | Chamfers in Place
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement size
label | Lap Length
label | Bar Chairs
checkpoint | Detailed inspection of Mould and cage
checkpoint | Cover maintained and within tolerance
checkpoint | All Lifting Inserts are installed in accordance with Drawings
text | Lifters
checkpoint | All Dowels are installed as per drawings
text | Specify Dowel size
label | Dowel in correct position
checkpoint | Prestressing Strands
text | Coil Number Used for this Cast
text | Dia and No. of strands
text | Strands arrangement verified
label | Sag Load all Strands
label | Mutli-Stress as per Pre-stressing Procedures
label | Verify debonding strands
checkpoint | Pre-lifting cage inspection (Client present)
checkpoint | Stressing Records subject to Client Review (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | QA Engineer Check Completed by
checkpoint | Pre-pour cage/mould inspection (Client Present) (HOLD POINT FOR CLIENT TO SIGN OFF)
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Dockets (list all)
checkpoint | Total Concrete Volume
text | Volume (m3)
checkpoint | Mix Design Verified
text | Specify mix used
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance (200+/-40) (Tested 1st truck and subsequently for every 20m3)
text | Slump (list all)
checkpoint | Trucks Tested for strength
text | Test Report Reference Number (list all)
checkpoint | Time Lag Between Trucks not exceeded 20 minutes
checkpoint | Concrete Placed within allowable time from Batching Plant, not exceeding 90 minutes
checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
checkpoint | Required Finish Applied as per Drawings
checkpoint | Retarders applied on Green Cut areas as shown in drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
label | Conversion KN to MPa = Reading / 7.851
label | Stripping strength 37MPa (HOLD POINT FOR CLIENT TO SIGN OFF)
text | Stripping Strength
checkpoint | Lifting Strength Achieved
label | Lifting strength required - 37MPa
text | Specify strength at time of lifting
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Additional Curing
label | Plank covered for 7 days
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | Lifters
text | Dowels
checkpoint | Post-Pour Works Completed (As Required)
text | Strands are Cut Flush and Epoxied
text | Lifters are cleaned
text | Roughened Surfaces are Greencut
text | All Miscellaneous Items are Completed
text | Bottom surface clear from tie wire (Attach Pictures)
checkpoint | Survey Hog of Beams
text | First Reading (Within 2 days of Stripping)
text | Final Reading (7 days prior to scheduled delivery)
section | Any Defect Identified
checkpoint | Punchlist Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Crack Map Completed (if applicable)
checkpoint | Any NCR Required (if applicable)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report
text | 7 Day Strength (List all)
text | 28 Day Strength (List all)
section | Transportation Requirements
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Punchlist signed copy
checkpoint | Delivery Notes
checkpoint | Delivery Docket
section | Final Acceptance
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Client Representative (if applicable)