## Sheet1
Design - Geometric Design | Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual | Principal Approval | Contractor and Principal peer review | per design revision |  |  | C or S |  | C | E | Y |  | Design - Geometric Design | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual | Acceptance Criteria - Principal Approval | Method - Contractor and Principal peer review | Frequency - per design revision | Responsible Person - | Verifying Document - | Conduct - C or S | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Design - Geometric Design
Design - Pavement Treatment Design | Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Principal Approval | Contractor and Principal peer review | per design |  | Pavement Rehabilitation Design Report 2023/24 | C or S |  | C | E | Y |  | Design - Pavement Treatment Design | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Acceptance Criteria - Principal Approval | Method - Contractor and Principal peer review | Frequency - per design | Responsible Person - | Verifying Document - Pavement Rehabilitation Design Report 2023/24 | Conduct - C or S | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
Materials: GAP 65 Pre-treatment Material - Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet | C or S |  |  | S |  |  | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide | Acceptance Criteria - | Method - | Frequency - | Responsible Person - | Verifying Document - Sampling Worksheet | Conduct - C or S | Witness - | Produce Record - | Approval - S | Hold Point Y/N - | Witness Point Y/N - | Acceptance Criteria - Principal Approval
Materials: GAP 65 Pre-treatment Material - Source Property Test | CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Soaked CBR ≥ 40 | Soaked CBR test (NZS:4407:2015:3.15) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: GAP 65 Pre-treatment Material - Source Property Test | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Acceptance Criteria - Soaked CBR ≥ 40 | Method - Soaked CBR test (NZS:4407:2015:3.15) | Frequency - | Responsible Person - Supervisor | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Method - Contractor and Principal peer review
Materials: GAP 65 Pre-treatment Material - Production Property Test | Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Sand Equivalent >35, OR CHAR(LESS)35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Sand Equivalent Test (NZS:4407:2015, 3.6) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: GAP 65 Pre-treatment Material - Production Property Test | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Acceptance Criteria - Sand Equivalent >35, OR CHAR(LESS)35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Method - Sand Equivalent Test (NZS:4407:2015, 3.6) | Frequency - | Responsible Person - Supervisor | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Frequency - per design revision
Materials: M/4 AP40 Basecourse Material - Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet | [6 empty] | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide | Acceptance Criteria - | Method - | Frequency - | Responsible Person - | Verifying Document - Sampling Worksheet | Conduct - | Witness - | Produce Record - | Approval - | Hold Point Y/N - | Witness Point Y/N - | Responsible Person -
Materials: M/4 AP40 Basecourse Material - Source Property Test (1) | Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | less than 10% fines passing 2.36mm sieve size under a load of 130kN | Curshing Resistance Test (NZS 4407:1991, Test 3.10) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Basecourse Material - Source Property Test (1) | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10) | Frequency - One test for every 10,000m³ of source material | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Verifying Document -
Materials: M/4 AP40 Basecourse Material - Source Property Test (2) | Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | AA, AB, AC, BA, BB or CA | Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Basecourse Material - Source Property Test (2) | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | Acceptance Criteria - AA, AB, AC, BA, BB or CA | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | Frequency - One test for every 10,000m³ of source material | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Conduct - C or S
Materials: M/4 AP40 Basecourse Material - Source Property Test (3) | California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Soaked CBR ≥ 80% | California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Basecourse Material - Source Property Test (3) | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Acceptance Criteria - Soaked CBR ≥ 80% | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | Frequency - One test for every 10,000m³ of source material | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Witness -
Materials: M/4 AP40 Basecourse Material - Production Property Test (1) | Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Basecourse Material - Production Property Test (1) | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Produce Record - C
Materials: M/4 AP40 Basecourse Material - Production Property Test (2) | Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Broken Face Test (NZS:4407: 1991, Test 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Basecourse Material - Production Property Test (2) | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Method - Broken Face Test (NZS:4407: 1991, Test 3.4) | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Approval - E
Materials: M/4 AP40 Basecourse Material - Production Property Test (3) | Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Basecourse Material - Production Property Test (3) | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Hold Point Y/N - Y
Materials: Cement - Stabilising Agent Selection | Cement (4.1.2) - TNZ B/5: 2008 | GP | Visual inspection of supplier docket | per truck load | Quality Controller | Supplier Docket Supplier Cert | Sp or S |  | Sp or S | C |  | Y | Materials: Cement - Stabilising Agent Selection | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008 | Acceptance Criteria - GP | Method - Visual inspection of supplier docket | Frequency - per truck load | Responsible Person - Quality Controller | Verifying Document - Supplier Docket Supplier Cert | Conduct - Sp or S | Witness - | Produce Record - Sp or S | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Witness Point Y/N -
Materials: Water - Water draw for stabilising | Water (5.0.0) - TNZ B/5: 2008 | Free from impurities justified by use of municipal water supply | Visual inspection | per truck load | Quality Controller | Hydrant use form | Sp or S |  | Sp or S | C |  | Y | Materials: Water - Water draw for stabilising | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008 | Acceptance Criteria - Free from impurities justified by use of municipal water supply | Method - Visual inspection | Frequency - per truck load | Responsible Person - Quality Controller | Verifying Document - Hydrant use form | Conduct - Sp or S | Witness - | Produce Record - Sp or S | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Design - Pavement Treatment Design
Materials: Geotextile - Geotextile (Strength Class C) A29 or greater | TNZ F7 Specification | Details on Docket | Visual inspection | Per Delivery | Quality Controller | MDS | Sp or S |  | Sp or S | C |  | Y | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater | Controlling Documents - TNZ F7 Specification | Acceptance Criteria - Details on Docket | Method - Visual inspection | Frequency - Per Delivery | Responsible Person - Quality Controller | Verifying Document - MDS | Conduct - Sp or S | Witness - | Produce Record - Sp or S | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent | As per NZTA list of approved materials/suppliers | Details on Docket | Visual inspection | Per Delivery | Quality Controller | MDS | Sp or S |  | Sp or S | C |  | Y | Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent | Controlling Documents - As per NZTA list of approved materials/suppliers | Acceptance Criteria - Details on Docket | Method - Visual inspection | Frequency - Per Delivery | Responsible Person - Quality Controller | Verifying Document - MDS | Conduct - Sp or S | Witness - | Produce Record - Sp or S | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Acceptance Criteria - Principal Approval
Production Testing of stabilised material - OMC/MDD | TNZ B/5 section 7.5 CHAR(AMP) 7.7.1 | To obtain OMC CHAR(AMP) MDD | NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test. | Once on commencement and then each stablilised layer at one test per 5000m2 | Quality Controller | Test report | S or C | C | S or C | C |  | Y | Production Testing of stabilised material - OMC/MDD | Controlling Documents - TNZ B/5 section 7.5 CHAR(AMP) 7.7.1 | Acceptance Criteria - To obtain OMC CHAR(AMP) MDD | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test. | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2 | Responsible Person - Quality Controller | Verifying Document - Test report | Conduct - S or C | Witness - C | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Method - Contractor and Principal peer review
Production Testing of stabilised material - Solid Density | TNZ B/5 section 7.7 | For info. and use in MDD calculation | NZS 4407; test 3.7.1 | Once on commencement and if any materials change | Quality Controller | Test report | S or C | C | S or C | C |  | Y | Production Testing of stabilised material - Solid Density | Controlling Documents - TNZ B/5 section 7.7 | Acceptance Criteria - For info. and use in MDD calculation | Method - NZS 4407; test 3.7.1 | Frequency - Once on commencement and if any materials change | Responsible Person - Quality Controller | Verifying Document - Test report | Conduct - S or C | Witness - C | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Frequency - per design
Project survey setting out | Reference from Project Drawings |  | Survey/Mobile Roads, Marks with Dazzle | Chainages for every different pavement sections | Subcontractor/ Engineer | Construction drawings | S or C | C | S or C | C |  | Y | Project survey setting out | Controlling Documents - Reference from Project Drawings | Acceptance Criteria - | Method - Survey/Mobile Roads, Marks with Dazzle | Frequency - Chainages for every different pavement sections | Responsible Person - Subcontractor/ Engineer | Verifying Document - Construction drawings | Conduct - S or C | Witness - C | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Responsible Person -
Pre-treatment Repair Method Selection | Site specifics to be confirmed | Confirm scala acceptance criteria based on treatment type | Scala Penetrometer on Excavation Floor | As required | Quality Controller | Agreed treatment plan | S | C | S | E |  | Y | Pre-treatment Repair Method Selection | Controlling Documents - Site specifics to be confirmed | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type | Method - Scala Penetrometer on Excavation Floor | Frequency - As required | Responsible Person - Quality Controller | Verifying Document - Agreed treatment plan | Conduct - S | Witness - C | Produce Record - S | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Verifying Document - Pavement Rehabilitation Design Report 2023/24
Digout of Patches to repair | Higgins SOP 0128 - Digout Repair | 250mm deep unless specified | Visual inspection | As required | Quality Controller | Dig out site records/ Asbuilt | S | C | S | C |  | Y | Digout of Patches to repair | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - 250mm deep unless specified | Method - Visual inspection | Frequency - As required | Responsible Person - Quality Controller | Verifying Document - Dig out site records/ Asbuilt | Conduct - S | Witness - C | Produce Record - S | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Conduct - C or S
Subgrade material hardness Check base of excavation | Higgins SOP 0128 - Digout Repair | Scala > 3 blows per 100mm or Proof roll CHAR(LESS)5mm | Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful | As required depending on size of digout | Quality Controller | Test report | S/C | C | S/C | E |  | Y | Subgrade material hardness Check base of excavation | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - Scala > 3 blows per 100mm or Proof roll CHAR(LESS)5mm | Method - Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful | Frequency - As required depending on size of digout | Responsible Person - Quality Controller | Verifying Document - Test report | Conduct - S/C | Witness - C | Produce Record - S/C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Witness -
Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd) | TNZ F7 Specification | Meet TNZ F7 Spec. | Visual inspection | Per Delivery | Quality Controller | Certificate of conformance | Sp or S |  | C | C |  | Y | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd) | Controlling Documents - TNZ F7 Specification | Acceptance Criteria - Meet TNZ F7 Spec. | Method - Visual inspection | Frequency - Per Delivery | Responsible Person - Quality Controller | Verifying Document - Certificate of conformance | Conduct - Sp or S | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Produce Record - C
Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer (if rqd) | As per NZTA list of approved materials/suppliers | On the list of approved materials/suppliers | Visual inspection | Per Delivery | Quality Controller | Certificate of conformance | Sp or S |  | C | C |  | Y | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer (if rqd) | Controlling Documents - As per NZTA list of approved materials/suppliers | Acceptance Criteria - On the list of approved materials/suppliers | Method - Visual inspection | Frequency - Per Delivery | Responsible Person - Quality Controller | Verifying Document - Certificate of conformance | Conduct - Sp or S | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Approval - E
Place and compact GAP65 in digout area | Higgins SOP 0128 - Digout Repair | Clegg value > 45 | Clegg Test | Min. 2 per digout | Quality Controller | Test report | S/C | C | S/C | E |  | Y | Place and compact GAP65 in digout area | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - Clegg value > 45 | Method - Clegg Test | Frequency - Min. 2 per digout | Responsible Person - Quality Controller | Verifying Document - Test report | Conduct - S/C | Witness - C | Produce Record - S/C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Hold Point Y/N - Y
Place M/4 AP40 Basecourse Material | TNZ B/5 (section 7) | Evenly spread, no segregation, placed near optimium moisture content | Visual Inspection | On completion of placement | Quality Controller | Photographs and Daily Site Record | S or C |  | S or C | C |  | Y | Place M/4 AP40 Basecourse Material | Controlling Documents - TNZ B/5 (section 7) | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content | Method - Visual Inspection | Frequency - On completion of placement | Responsible Person - Quality Controller | Verifying Document - Photographs and Daily Site Record | Conduct - S or C | Witness - | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Witness Point Y/N -
Spreading of Cement | Spreading of Cement (7.3) - TNZ B/5: 2008 | Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate | Mat test (1m² canvas) and Average Usage Test | per 400m² and upon emptying the spreader | Quality Controller | Mat Test Form and truck dockets | S or Sp | C | S | E |  | Y | Spreading of Cement | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008 | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate | Method - Mat test (1m² canvas) and Average Usage Test | Frequency - per 400m² and upon emptying the spreader | Responsible Person - Quality Controller | Verifying Document - Mat Test Form and truck dockets | Conduct - S or Sp | Witness - C | Produce Record - S | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
Addition of Water | Addition of Water (7.5) - TNZ B/5: 2008 | 90-100% OWC | Nuclear Densometer Testing prior to Stabilisation | ≥1 per 1000m² lot | Quality Controller | NDM Record | S or C |  | S | S or C |  | Y | Addition of Water | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008 | Acceptance Criteria - 90-100% OWC | Method - Nuclear Densometer Testing prior to Stabilisation | Frequency - ≥1 per 1000m² lot | Responsible Person - Quality Controller | Verifying Document - NDM Record | Conduct - S or C | Witness - | Produce Record - S | Approval - S or C | Hold Point Y/N - | Witness Point Y/N - Y | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
Cut Depth | Control of cut depth (7.6.1) - TNZ B/5: 2008 | -5mm and +15mm of design stab depth | Physical Measure and Visual Record | ≥1 per 200m of cut length | Quality Controller | Photographs and Daily Site Record | S or C |  | S | S or C |  | Y | Cut Depth | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008 | Acceptance Criteria - -5mm and +15mm of design stab depth | Method - Physical Measure and Visual Record | Frequency - ≥1 per 200m of cut length | Responsible Person - Quality Controller | Verifying Document - Photographs and Daily Site Record | Conduct - S or C | Witness - | Produce Record - S | Approval - S or C | Hold Point Y/N - | Witness Point Y/N - Y | Acceptance Criteria -
Longitudinal Joints | Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008 | The minimum of 100mm or half the layer thickness | Visual Record | per sucessive cut | Quality Controller | Photographs, Daily Site Record and Stabilising Plan | S or C |  | S | S or C |  | Y | Longitudinal Joints | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008 | Acceptance Criteria - The minimum of 100mm or half the layer thickness | Method - Visual Record | Frequency - per sucessive cut | Responsible Person - Quality Controller | Verifying Document - Photographs, Daily Site Record and Stabilising Plan | Conduct - S or C | Witness - | Produce Record - S | Approval - S or C | Hold Point Y/N - | Witness Point Y/N - Y | Method -
Continuity of Layer | Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008 | Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents | Visual Record | per sucessive cut | Quality Controller | Photographs, Daily Site Record and Stabilising Plan | S or C |  | S | S or C |  | Y | Continuity of Layer | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008 | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents | Method - Visual Record | Frequency - per sucessive cut | Responsible Person - Quality Controller | Verifying Document - Photographs, Daily Site Record and Stabilising Plan | Conduct - S or C | Witness - | Produce Record - S | Approval - S or C | Hold Point Y/N - | Witness Point Y/N - Y | Frequency -
Stabilised Material Particle Size | Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008 | No excessive breakdown of stabilised material | Visual Record | within 20m of each section and then regularly based on material variability | Quality Controller | Photographs | S or C |  | S or C | C |  | Y | Stabilised Material Particle Size | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008 | Acceptance Criteria - No excessive breakdown of stabilised material | Method - Visual Record | Frequency - within 20m of each section and then regularly based on material variability | Responsible Person - Quality Controller | Verifying Document - Photographs | Conduct - S or C | Witness - | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Responsible Person -
Establish Compaction Methodology - type of plant, number and speed of passes | Compaction (7.7) - TNZ B/5: 2008 | To establish type of plant, number and speed of passes to achieve MDD | Plateau Density Testing | 1 time, or additional tests when material changes visually | Supervisor | Test record | S or C |  | S or C | C |  | Y | Establish Compaction Methodology - type of plant, number and speed of passes | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008 | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD | Method - Plateau Density Testing | Frequency - 1 time, or additional tests when material changes visually | Responsible Person - Supervisor | Verifying Document - Test record | Conduct - S or C | Witness - | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Verifying Document - Sampling Worksheet
Establish Compaction Target | Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | To provide MDD for NDM testing | Plateau Density Testing | Minimum once per Lot. A lot shall not exceed 1000 m2. | Quality Controller | Test Record | S or C |  | S or C | E |  | Y | Establish Compaction Target | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | Acceptance Criteria - To provide MDD for NDM testing | Method - Plateau Density Testing | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2. | Responsible Person - Quality Controller | Verifying Document - Test Record | Conduct - S or C | Witness - | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Conduct - C or S
Degree of Compaction MDD to obtain target for NDM testing (1) | Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | To provide MDD for NDM testing | Laboratory MDD at OMC NZS 4402 test 4.1.3. | Minimum once per Lot. A lot shall not exceed 5000 m2. | Quality Controller | Test Record | S or C |  | S or C | C |  | Y | Degree of Compaction MDD to obtain target for NDM testing (1) | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | Acceptance Criteria - To provide MDD for NDM testing | Method - Laboratory MDD at OMC NZS 4402 test 4.1.3. | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2. | Responsible Person - Quality Controller | Verifying Document - Test Record | Conduct - S or C | Witness - | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Witness -
Degree of Compaction MDD to obtain target for NDM testing (2) | Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test | Plateau Density Testing Lab. MDD | At commencement of construction and whenever materials change | Quality Controller Engineer | Notice to Contractor/ Notice to Engineer | S or C |  | S or C | E |  | Y | Degree of Compaction MDD to obtain target for NDM testing (2) | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test | Method - Plateau Density Testing Lab. MDD | Frequency - At commencement of construction and whenever materials change | Responsible Person - Quality Controller Engineer | Verifying Document - Notice to Contractor/ Notice to Engineer | Conduct - S or C | Witness - | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Produce Record -
Compaction Acceptance | Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005 | Mean value ≥ 98% and Minimum Value ≥ 95% | Nuclear Densometer Testing | ≥ 5 tests per 1000m² lot | Quality Controller | NDM Record | S or C |  | S or C | E | Y |  | Compaction Acceptance | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005 | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95% | Method - Nuclear Densometer Testing | Frequency - ≥ 5 tests per 1000m² lot | Responsible Person - Quality Controller | Verifying Document - NDM Record | Conduct - S or C | Witness - | Produce Record - S or C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Approval - S
Control Testing (if required) | Control testing during and after construction (7.7.2) - TNZ B/5: 2008 | Nil | Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | when agreed with the Engineer | Quality Controller | Test Report | S or C |  | S or C | E |  | Y | Control Testing (if required) | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008 | Acceptance Criteria - Nil | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | Frequency - when agreed with the Engineer | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - S or C | Witness - | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Hold Point Y/N -
Surface Smoothness | Surface shape (7.8) - TNZ B/5: 2008 | ± 10mm deviation along a 3m straight edge, No water ponding | 3m Straight Edge | during construction and prior to seal | Supervisor | Photographs | S or C | C and E | S or C | E |  | Y | Surface Smoothness | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008 | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding | Method - 3m Straight Edge | Frequency - during construction and prior to seal | Responsible Person - Supervisor | Verifying Document - Photographs | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Witness Point Y/N -
Surface Shape | Surface shape (7.8) - TNZ B/5: 2008 | Between -5mm and +15mm | String lines or Survey Asbuilt | during construction and prior to seal | Supervisor | String Sheet/Survey Asbuilts | S or C | C and E | S or C | E |  | Y | Surface Shape | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008 | Acceptance Criteria - Between -5mm and +15mm | Method - String lines or Survey Asbuilt | Frequency - during construction and prior to seal | Responsible Person - Supervisor | Verifying Document - String Sheet/Survey Asbuilts | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Materials: GAP 65 Pre-treatment Material - Source Property Test
Cross Fall | Crossfall (7.9) - TNZ B/5: 2008 | 0.5% ≤ X ≤ -0.5% | 3m straight edge or Survey Asbuilt | during construction and prior to seal | Supervisor | Cross Fall Records/Survey Asbuilts | S or C | C and E | S or C | E |  | Y | Cross Fall | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008 | Acceptance Criteria - 0.5% ≤ X ≤ -0.5% | Method - 3m straight edge or Survey Asbuilt | Frequency - during construction and prior to seal | Responsible Person - Supervisor | Verifying Document - Cross Fall Records/Survey Asbuilts | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
Surface Finish | Surface finish (7.10) - TNZ B/5: 2008 | Tightly bound matrix post sweep | Visual inpsection | prior to seal | Supervisor | Pre-seal inspection sheet | S or C | C and E | S or C | E |  | Y | Surface Finish | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008 | Acceptance Criteria - Tightly bound matrix post sweep | Method - Visual inpsection | Frequency - prior to seal | Responsible Person - Supervisor | Verifying Document - Pre-seal inspection sheet | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Acceptance Criteria - Soaked CBR ≥ 40
Degree of Saturation, DOS | Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005 | ≤80%, however 65% is ideal | Nuclear Densometer Testing | ≥5 tests per 1000m² lot | Quality Controller | NDM Record | S or C | C and E | S or C | E |  | Y | Degree of Saturation, DOS | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005 | Acceptance Criteria - ≤80%, however 65% is ideal | Method - Nuclear Densometer Testing | Frequency - ≥5 tests per 1000m² lot | Responsible Person - Quality Controller | Verifying Document - NDM Record | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Method - Soaked CBR test (NZS:4407:2015:3.15)
Roughness (NAASRA) | NZTA Maintainence specification section 6.1.2 | For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km | NZTA Maintainence specification section 6.1.2 | Average of three replica runs for each lane reported at 20m intervals. | Quality Controller | Test Records | S or C | C and E | S or C | E | Y |  | Roughness (NAASRA) | Controlling Documents - NZTA Maintainence specification section 6.1.2 | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km | Method - NZTA Maintainence specification section 6.1.2 | Frequency - Average of three replica runs for each lane reported at 20m intervals. | Responsible Person - Quality Controller | Verifying Document - Test Records | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Frequency -
Binder - Penetration Grade | TNZ M/1 | Table 1 | Property Test | Annual | Bitumen Supplier/ Surfacing Project Manager | IANZ Report's | C |  | C | C |  | Y | Binder - Penetration Grade | Controlling Documents - TNZ M/1 | Acceptance Criteria - Table 1 | Method - Property Test | Frequency - Annual | Responsible Person - Bitumen Supplier/ Surfacing Project Manager | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Responsible Person - Supervisor
Binder - Polymer Modified Emulsion | Higgins Internal Specification | % PMB Required, PH, Residue by Evaporation, Viscosity | Property Test | 1/100,000 litres supplied | Bitumen Supplier/ Surfacing Project Manager | IANZ Report's | C |  | C | C |  | Y | Binder - Polymer Modified Emulsion | Controlling Documents - Higgins Internal Specification | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity | Method - Property Test | Frequency - 1/100,000 litres supplied | Responsible Person - Bitumen Supplier/ Surfacing Project Manager | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Verifying Document - Test Report
Source Property -Coarse Aggregate - Crushing Resistance | TNZ M6, RNZ 9805:2009 | CHAR(LESS)10% fines under 230kN minimum | Sample Test - Crushing Resistance NZS 4407 Test 3.10 | 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Surfacing Project Manager | IANZ Report's | C |  | C | E | Y |  | Source Property -Coarse Aggregate - Crushing Resistance | Controlling Documents - TNZ M6, RNZ 9805:2009 | Acceptance Criteria - CHAR(LESS)10% fines under 230kN minimum | Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10 | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Conduct - Sp or C or S
Source Property -Coarse Aggregate - Weathering Resistance | TNZ M6, RNZ 9805:2009 | AA or BA | Weathering Quality Index NZS 4407 Test 3.10 | 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Surfacing Project Manager | IANZ Report's | C |  | C | E | Y |  | Source Property -Coarse Aggregate - Weathering Resistance | Controlling Documents - TNZ M6, RNZ 9805:2009 | Acceptance Criteria - AA or BA | Method - Weathering Quality Index NZS 4407 Test 3.10 | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Witness -
Source Property - Skid Resistance | NZTA T/10 | Meet Skid performance Requirement | Aggregate Perfomance Method TNZ T/10 section 12.3 | Each Site | Surfacing Project Manager | IANZ Report's | C |  | C | E | Y |  | Source Property - Skid Resistance | Controlling Documents - NZTA T/10 | Acceptance Criteria - Meet Skid performance Requirement | Method - Aggregate Perfomance Method TNZ T/10 section 12.3 | Frequency - Each Site | Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Produce Record - Sp or S
Production Property - Cleaness Value | NZTA P/17, M/6 | G2 - 89 min, G3 - 87 min, G4 - 85 min | Sample Test - Cleaness Value NZS 4407 Test 3.9 | Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Surfacing Project Manager | IANZ Report's | C |  | C | E | Y |  | Production Property - Cleaness Value | Controlling Documents - NZTA P/17, M/6 | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min | Method - Sample Test - Cleaness Value NZS 4407 Test 3.9 | Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Approval - E
Production Property - Particle Size/Shape | NZTA P/17, M/6 | As per Table 3 NZTA M/6 | Sample Test - Particle Size/Shape NZS 4407 Test 3.13 | Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Surfacing Project Manager | IANZ Report's | C |  | C | E | Y |  | Production Property - Particle Size/Shape | Controlling Documents - NZTA P/17, M/6 | Acceptance Criteria - As per Table 3 NZTA M/6 | Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13 | Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Hold Point Y/N - Y
Production Property - Broken Faces | NZTA P/17, M/6 | Min. 98% | Sample Test - Broken Faces NZS 4407 Test 3.14 | Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Surfacing Project Manager | IANZ Report's | C |  | C | E | Y |  | Production Property - Broken Faces | Controlling Documents - NZTA P/17, M/6 | Acceptance Criteria - Min. 98% | Method - Sample Test - Broken Faces NZS 4407 Test 3.14 | Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Witness Point Y/N -
Chipseal Designs | EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17 | Client Approval | Review | Annual | Surfacing Project Manager | EBOP NOC Design Report Acceptance | C |  | C | E | Y |  | Chipseal Designs | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17 | Acceptance Criteria - Client Approval | Method - Review | Frequency - Annual | Responsible Person - Surfacing Project Manager | Verifying Document - EBOP NOC Design Report Acceptance | Conduct - C | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Materials: GAP 65 Pre-treatment Material - Production Property Test
Ensure limits of site are marked | EBOP NOC Design Report | Visual Inspection | Visual | Prior to start sealing each site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C |  | Y | Ensure limits of site are marked | Controlling Documents - EBOP NOC Design Report | Acceptance Criteria - Visual Inspection | Method - Visual | Frequency - Prior to start sealing each site | Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
Sweep surface clean of deleterious material | P/17 | Visual Inspection | Visual | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C |  | Y | Sweep surface clean of deleterious material | Controlling Documents - P/17 | Acceptance Criteria - Visual Inspection | Method - Visual | Frequency - Each site, prior to start of sealing | Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Acceptance Criteria - Sand Equivalent >35, OR CHAR(LESS)35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
Record ATP's on site | N/A | Visual Inspection | Visual | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C |  | Y | Record ATP's on site | Controlling Documents - N/A | Acceptance Criteria - Visual Inspection | Method - Visual | Frequency - Each site, prior to start of sealing | Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
Confirm correct treatment(s) and chip | EBOP NOC Design Report | Details/chip correct | Visual | Each Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | Y |  | Confirm correct treatment(s) and chip | Controlling Documents - EBOP NOC Design Report | Acceptance Criteria - Details/chip correct | Method - Visual | Frequency - Each Site | Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - Y | Witness Point Y/N - | Frequency -
Cutback Bitumen Blend | RNZ 9803_0513 | +/- 2PPH Cutter, +ve for Adhesion agent presence | Sample and test | 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed | Surfacing Project Manager, Surfacing Supervisor | IANZ Report's | C |  | C | C |  | Y | Cutback Bitumen Blend | Controlling Documents - RNZ 9803_0513 | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence | Method - Sample and test | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed | Responsible Person - Surfacing Project Manager, Surfacing Supervisor | Verifying Document - IANZ Report's | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Responsible Person - Supervisor
Bitumen Application Rate | E/2 Certificate, Seal Design / Spray Instruction | Current E/2 Certificate +/- 4% per Spray Run | Test, Review | Per Sprayer, Per Site | Surfacing Supervisor | E/2 Certificate. Spray Sheets | C |  | C | C |  | Y | Bitumen Application Rate | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run | Method - Test, Review | Frequency - Per Sprayer, Per Site | Responsible Person - Surfacing Supervisor | Verifying Document - E/2 Certificate. Spray Sheets | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Verifying Document - Test Report
Chip Application Rates | Chipsealing in NewZealand | As per Chipping Guide | Visual | Each Site | Surfacing Supervisor | Chip application check sheet. Chip Sealing Quality and Site Record | C |  | C | C |  | Y | Chip Application Rates | Controlling Documents - Chipsealing in NewZealand | Acceptance Criteria - As per Chipping Guide | Method - Visual | Frequency - Each Site | Responsible Person - Surfacing Supervisor | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Conduct - Sp or C or S
Rolling | Chipsealing in NewZealand | Mimimum as per CS in NZ - Bit volume / 3600 | Visual | Each Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C |  | Y | Rolling | Controlling Documents - Chipsealing in NewZealand | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600 | Method - Visual | Frequency - Each Site | Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Witness -
Cleanup | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Each Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C |  | Y | Cleanup | Controlling Documents - Chipsealing in NewZealand | Acceptance Criteria - Site including adjacent surfaces free of loose chip | Method - Visual | Frequency - Each Site | Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Produce Record - Sp or S
Post Sweeping | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Each Site | Surfacing Supervisor | Site Record | C |  | C | C |  | Y | Post Sweeping | Controlling Documents - Chipsealing in NewZealand | Acceptance Criteria - Site including adjacent surfaces free of loose chip | Method - Visual | Frequency - Each Site | Responsible Person - Surfacing Supervisor | Verifying Document - Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Approval - E
Linemarking and RRPM Reinstated | MOTSAM | Matches previous linemarking - within 48hours of sealing | Visual | Each Site | Surfacing Supervisor | Site Record | C |  | C | C |  | Y | Linemarking and RRPM Reinstated | Controlling Documents - MOTSAM | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing | Method - Visual | Frequency - Each Site | Responsible Person - Surfacing Supervisor | Verifying Document - Site Record | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Hold Point Y/N - Y
Post Construction Walkover |  | Formal Agreement | Visual Inspection | Post seal sweep | Quality Controller, Supervisor and Engineer | Meeting Minutes | C | C, S and E | C | E | Y |  | Post Construction Walkover | Controlling Documents - | Acceptance Criteria - Formal Agreement | Method - Visual Inspection | Frequency - Post seal sweep | Responsible Person - Quality Controller, Supervisor and Engineer | Verifying Document - Meeting Minutes | Conduct - C | Witness - C, S and E | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Witness Point Y/N -
Resurfacing Construction Completion report | NOC; MS 6.1.3 | Comply with Requirement of NOC MS 6.1.3 | Record | Within 2 months of completing the annual resurfacing programme | Surfacing Manager | Construction Completion Report | C |  | C | C | Y |  | Resurfacing Construction Completion report | Controlling Documents - NOC; MS 6.1.3 | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3 | Method - Record | Frequency - Within 2 months of completing the annual resurfacing programme | Responsible Person - Surfacing Manager | Verifying Document - Construction Completion Report | Conduct - C | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - Y | Witness Point Y/N - | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
Pavement Rehabilitation Construction Completion Report | Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification | Engineer Approval | Visual Inspection | ≤2 months of 1st Coat Seal | Quality Controller/ Contract Manager | Signed Report | C | C, S and E | C | E | Y |  | Pavement Rehabilitation Construction Completion Report | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification | Acceptance Criteria - Engineer Approval | Method - Visual Inspection | Frequency - ≤2 months of 1st Coat Seal | Responsible Person - Quality Controller/ Contract Manager | Verifying Document - Signed Report | Conduct - C | Witness - C, S and E | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
Acceptance Criteria -
Method -
Frequency -
Responsible Person -
Verifying Document - Sampling Worksheet
Conduct -
Witness -
Produce Record -
Approval -
Hold Point Y/N -
Witness Point Y/N -
Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
Frequency - One test for every 10,000m³ of source material
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
Acceptance Criteria - AA, AB, AC, BA, BB or CA
Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
Frequency - One test for every 10,000m³ of source material
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
Acceptance Criteria - Soaked CBR ≥ 80%
Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
Frequency - One test for every 10,000m³ of source material
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: Cement - Stabilising Agent Selection
Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
Acceptance Criteria - GP
Method - Visual inspection of supplier docket
Frequency - per truck load
Responsible Person - Quality Controller
Verifying Document - Supplier Docket Supplier Cert
Conduct - Sp or S
Witness -
Produce Record - Sp or S
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Materials: Water - Water draw for stabilising
Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
Acceptance Criteria - Free from impurities justified by use of municipal water supply
Method - Visual inspection
Frequency - per truck load
Responsible Person - Quality Controller
Verifying Document - Hydrant use form
Conduct - Sp or S
Witness -
Produce Record - Sp or S
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
Controlling Documents - TNZ F7 Specification
Acceptance Criteria - Details on Docket
Method - Visual inspection
Frequency - Per Delivery
Responsible Person - Quality Controller
Verifying Document - MDS
Conduct - Sp or S
Witness -
Produce Record - Sp or S
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent
Controlling Documents - As per NZTA list of approved materials/suppliers
Acceptance Criteria - Details on Docket
Method - Visual inspection
Frequency - Per Delivery
Responsible Person - Quality Controller
Verifying Document - MDS
Conduct - Sp or S
Witness -
Produce Record - Sp or S
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Production Testing of stabilised material - OMC/MDD
Controlling Documents - TNZ B/5 section 7.5 CHAR(AMP) 7.7.1
Acceptance Criteria - To obtain OMC CHAR(AMP) MDD
Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
Responsible Person - Quality Controller
Verifying Document - Test report
Conduct - S or C
Witness - C
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Production Testing of stabilised material - Solid Density
Controlling Documents - TNZ B/5 section 7.7
Acceptance Criteria - For info. and use in MDD calculation
Method - NZS 4407; test 3.7.1
Frequency - Once on commencement and if any materials change
Responsible Person - Quality Controller
Verifying Document - Test report
Conduct - S or C
Witness - C
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Project survey setting out
Controlling Documents - Reference from Project Drawings
Acceptance Criteria -
Method - Survey/Mobile Roads, Marks with Dazzle
Frequency - Chainages for every different pavement sections
Responsible Person - Subcontractor/ Engineer
Verifying Document - Construction drawings
Conduct - S or C
Witness - C
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Pre-treatment Repair Method Selection
Controlling Documents - Site specifics to be confirmed
Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
Method - Scala Penetrometer on Excavation Floor
Frequency - As required
Responsible Person - Quality Controller
Verifying Document - Agreed treatment plan
Conduct - S
Witness - C
Produce Record - S
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Digout of Patches to repair
Controlling Documents - Higgins SOP 0128 - Digout Repair
Acceptance Criteria - 250mm deep unless specified
Method - Visual inspection
Frequency - As required
Responsible Person - Quality Controller
Verifying Document - Dig out site records/ Asbuilt
Conduct - S
Witness - C
Produce Record - S
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Subgrade material hardness Check base of excavation
Controlling Documents - Higgins SOP 0128 - Digout Repair
Acceptance Criteria - Scala > 3 blows per 100mm or Proof roll CHAR(LESS)5mm
Method - Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful
Frequency - As required depending on size of digout
Responsible Person - Quality Controller
Verifying Document - Test report
Conduct - S/C
Witness - C
Produce Record - S/C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
Controlling Documents - TNZ F7 Specification
Acceptance Criteria - Meet TNZ F7 Spec.
Method - Visual inspection
Frequency - Per Delivery
Responsible Person - Quality Controller
Verifying Document - Certificate of conformance
Conduct - Sp or S
Witness -
Produce Record - C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer (if rqd)
Controlling Documents - As per NZTA list of approved materials/suppliers
Acceptance Criteria - On the list of approved materials/suppliers
Method - Visual inspection
Frequency - Per Delivery
Responsible Person - Quality Controller
Verifying Document - Certificate of conformance
Conduct - Sp or S
Witness -
Produce Record - C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Place and compact GAP65 in digout area
Controlling Documents - Higgins SOP 0128 - Digout Repair
Acceptance Criteria - Clegg value > 45
Method - Clegg Test
Frequency - Min. 2 per digout
Responsible Person - Quality Controller
Verifying Document - Test report
Conduct - S/C
Witness - C
Produce Record - S/C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Place M/4 AP40 Basecourse Material
Controlling Documents - TNZ B/5 (section 7)
Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
Method - Visual Inspection
Frequency - On completion of placement
Responsible Person - Quality Controller
Verifying Document - Photographs and Daily Site Record
Conduct - S or C
Witness -
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Spreading of Cement
Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
Method - Mat test (1m² canvas) and Average Usage Test
Frequency - per 400m² and upon emptying the spreader
Responsible Person - Quality Controller
Verifying Document - Mat Test Form and truck dockets
Conduct - S or Sp
Witness - C
Produce Record - S
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Addition of Water
Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
Acceptance Criteria - 90-100% OWC
Method - Nuclear Densometer Testing prior to Stabilisation
Frequency - ≥1 per 1000m² lot
Responsible Person - Quality Controller
Verifying Document - NDM Record
Conduct - S or C
Witness -
Produce Record - S
Approval - S or C
Hold Point Y/N -
Witness Point Y/N - Y
Cut Depth
Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
Acceptance Criteria - -5mm and +15mm of design stab depth
Method - Physical Measure and Visual Record
Frequency - ≥1 per 200m of cut length
Responsible Person - Quality Controller
Verifying Document - Photographs and Daily Site Record
Conduct - S or C
Witness -
Produce Record - S
Approval - S or C
Hold Point Y/N -
Witness Point Y/N - Y
Longitudinal Joints
Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
Acceptance Criteria - The minimum of 100mm or half the layer thickness
Method - Visual Record
Frequency - per sucessive cut
Responsible Person - Quality Controller
Verifying Document - Photographs, Daily Site Record and Stabilising Plan
Conduct - S or C
Witness -
Produce Record - S
Approval - S or C
Hold Point Y/N -
Witness Point Y/N - Y
Continuity of Layer
Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
Method - Visual Record
Frequency - per sucessive cut
Responsible Person - Quality Controller
Verifying Document - Photographs, Daily Site Record and Stabilising Plan
Conduct - S or C
Witness -
Produce Record - S
Approval - S or C
Hold Point Y/N -
Witness Point Y/N - Y
Stabilised Material Particle Size
Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
Acceptance Criteria - No excessive breakdown of stabilised material
Method - Visual Record
Frequency - within 20m of each section and then regularly based on material variability
Responsible Person - Quality Controller
Verifying Document - Photographs
Conduct - S or C
Witness -
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Establish Compaction Methodology - type of plant, number and speed of passes
Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
Method - Plateau Density Testing
Frequency - 1 time, or additional tests when material changes visually
Responsible Person - Supervisor
Verifying Document - Test record
Conduct - S or C
Witness -
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Establish Compaction Target
Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
Acceptance Criteria - To provide MDD for NDM testing
Method - Plateau Density Testing
Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
Responsible Person - Quality Controller
Verifying Document - Test Record
Conduct - S or C
Witness -
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Degree of Compaction MDD to obtain target for NDM testing (1)
Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
Acceptance Criteria - To provide MDD for NDM testing
Method - Laboratory MDD at OMC NZS 4402 test 4.1.3.
Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
Responsible Person - Quality Controller
Verifying Document - Test Record
Conduct - S or C
Witness -
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Degree of Compaction MDD to obtain target for NDM testing (2)
Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
Method - Plateau Density Testing Lab. MDD
Frequency - At commencement of construction and whenever materials change
Responsible Person - Quality Controller Engineer
Verifying Document - Notice to Contractor/ Notice to Engineer
Conduct - S or C
Witness -
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Compaction Acceptance
Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
Method - Nuclear Densometer Testing
Frequency - ≥ 5 tests per 1000m² lot
Responsible Person - Quality Controller
Verifying Document - NDM Record
Conduct - S or C
Witness -
Produce Record - S or C
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Control Testing (if required)
Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
Acceptance Criteria - Nil
Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
Frequency - when agreed with the Engineer
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - S or C
Witness -
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Surface Smoothness
Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
Method - 3m Straight Edge
Frequency - during construction and prior to seal
Responsible Person - Supervisor
Verifying Document - Photographs
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Surface Shape
Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
Acceptance Criteria - Between -5mm and +15mm
Method - String lines or Survey Asbuilt
Frequency - during construction and prior to seal
Responsible Person - Supervisor
Verifying Document - String Sheet/Survey Asbuilts
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Cross Fall
Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
Method - 3m straight edge or Survey Asbuilt
Frequency - during construction and prior to seal
Responsible Person - Supervisor
Verifying Document - Cross Fall Records/Survey Asbuilts
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Surface Finish
Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
Acceptance Criteria - Tightly bound matrix post sweep
Method - Visual inpsection
Frequency - prior to seal
Responsible Person - Supervisor
Verifying Document - Pre-seal inspection sheet
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Degree of Saturation, DOS
Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
Acceptance Criteria - ≤80%, however 65% is ideal
Method - Nuclear Densometer Testing
Frequency - ≥5 tests per 1000m² lot
Responsible Person - Quality Controller
Verifying Document - NDM Record
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Roughness (NAASRA)
Controlling Documents - NZTA Maintainence specification section 6.1.2
Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
Method - NZTA Maintainence specification section 6.1.2
Frequency - Average of three replica runs for each lane reported at 20m intervals.
Responsible Person - Quality Controller
Verifying Document - Test Records
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -