## Project Structure
Folder Structure |  |  | Checklists
Pre-Con Inspection |  |  | Pre-Con Inspection
Site QA
LOWER GROUND
| FCU-LG-G8 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-LG-G9 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-LG-G1-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-LG-G1-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
LOWER GROUND
| FCU-LG-G8 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-LG-G9 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-LG-G1-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-LG-G1-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
|  | FINAL SIGN OFF | ITP-115 - Mechanical - Final Sign Off
GROUND FLOOR
| FCU-GL-03 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-08 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-09 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-G1-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-G1-3 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-G1-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-G6-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-G6-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-G5 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-GL-G4 | ROUGH IN | ITP-115 - Mechanical - Rough-In
GROUND FLOOR
| FCU-GL-03 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-08 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-09 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-G1-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-G1-3 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-G1-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-G6-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-G6-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-G5 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-GL-G4 | FIT OFF | ITP-115 - Mechanical - Fit-Off
|  | FINAL SIGN OFF | ITP-115 - Mechanical - Final Sign Off
LEVEL ONE
| FCU-L1-1.5 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-1.4 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-1.3 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-1.2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-1.1.1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-1.1.2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-G6-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-G6-3 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-G5 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-G4 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-1.6 | ROUGH IN | ITP-115 - Mechanical - Rough-In
LEVEL ONE
| FCU-L1-1.5 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-1.4 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-1.3 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-1.2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-1.1.1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-1.1.2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-G6-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-G6-3 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-G5 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-G4 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-1.6 | FIT OFF | ITP-115 - Mechanical - Fit-Off
|  | FINAL SIGN OFF | ITP-115 - Mechanical - Final Sign Off
LEVEL TWO
| FCU-L2-2.7-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.1-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.1-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.3-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.2-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.2-3 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.4-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.4-3 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.5-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L2-2.5-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L1-1.6 | ROUGH IN | ITP-115 - Mechanical - Rough-In
LEVEL TWO
| FCU-L2-2.7-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.1-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.1-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.3-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.2-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.2-3 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.4-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.4-3 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.5-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L2-2.5-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L1-1.6 | FIT OFF | ITP-115 - Mechanical - Fit-Off
|  | FINAL SIGN OFF | ITP-115 - Mechanical - Final Sign Off
LEVEL THREE
| FCU-L3-3.1-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.1-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.2-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.2-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.3-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.3-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.4-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.5-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.5-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-3.6 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-L3-2.4-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
LEVEL THREE
| FCU-L3-3.1-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.1-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.2-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.2-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.3-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.3-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.4-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.5-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.5-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-3.6 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-L3-2.4-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
|  | FINAL SIGN OFF | ITP-115 - Mechanical - Final Sign Off
MEZZANINE FLOOR
| FCU-MEZZ-3.1-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-MEZZ-3.1-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU--MEZZ-3.1-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-MEZZ-3.6-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-MEZZ-3.6-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-MEZZ-3.5-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-MEZZ-3.5-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-MEZZ-3.4-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| FCU-MEZZ-3.6-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-1 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-2 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-3 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-4 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-5 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-6 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-7 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-8 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-9 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-10 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-11 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-12 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-13 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-14 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-15 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-16 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-17 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-18 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-19 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-20 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-21 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-22 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-23 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-24 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-25 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-26 | ROUGH IN | ITP-115 - Mechanical - Rough-In
| CU-RF-27 | ROUGH IN | ITP-115 - Mechanical - Rough-In
MEZZANINE FLOOR
| FCU-MEZZ-3.1-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-MEZZ-3.1-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU--MEZZ-3.1-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-MEZZ-3.6-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-MEZZ-3.6-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-MEZZ-3.5-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-MEZZ-3.5-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-MEZZ-3.4-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| FCU-MEZZ-3.6-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-1 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-2 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-3 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-4 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-5 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-6 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-7 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-8 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-9 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-10 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-11 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-12 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-13 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-14 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-15 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-16 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-17 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-18 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-19 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-20 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-21 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-22 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-23 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-24 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-25 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-26 | FIT OFF | ITP-115 - Mechanical - Fit-Off
| CU-RF-27 | FIT OFF | ITP-115 - Mechanical - Fit-Off
|  | FINAL SIGN OFF | ITP-115 - Mechanical - Final Sign Off

## Checklists
type | name | values
checklist-flat | Pre-Con Inspection
checkpoint | Sub Review
checkpoint | Safety Induction
checkpoint | Drawings Approved
checkpoint | Site Inspection
checklist-flat | ITP-115 - Mechanical - Rough-In
checkpoint | Check Materials
checkpoint | Install FCUs
checkpoint | Install Fans
checkpoint | Install Pipework
checkpoint | Install Cabling, Controls, etc.
checkpoint | Install Flexible Ducts
checkpoint | Install Drains and test
checkpoint | Fire Boxes/Collars/Dampers Installed. Attach photos
checkpoint | Install Rigid Duct and seal
checkpoint | Install Louvre Box
checkpoint | Access Panels Marked
checkpoint | Pressure Testing
checkpoint | Confirm Model No
checkpoint | Confirm Serial No.
checklist-flat | ITP-115 - Mechanical - Fit-Off
checkpoint | Check Pressure
checkpoint | Install Condensers
checkpoint | Terminate Drain
checkpoint | Terminate Power and Controller
checkpoint | Install Grilles
checkpoint | Pressure test
checkpoint | Vacuum system
checkpoint | Access To Equipment Checked
checkpoint | Commission
checkpoint | Confirm Model No
checkpoint | Confirm Serial No.
checklist-flat | ITP-115 - Mechanical - Final Sign Off
checkpoint | Subcontractor Sign-Off (attach signature)
checkpoint | Head Contractor Sign-Off (attach signature)
checkpoint | Client Sign-Off (attach signature)