## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | QA - Cable Tray
section | Details
checkpoint | Unistrutt Filed & Painted
checkpoint | Hangers Spaced as Specified
checkpoint | Correct Size Ladder Installed
checkpoint | Divider strip installed as required
checkpoint | Ladder Joined Correctly
checkpoint | Hangers Sceismicly Restrained as per Design
checkpoint | Ladder Fastened to Hangers
checkpoint | Correct Anchors used fixing to Ceiling / Walls
checkpoint | Cable Ladder Bonded
checkpoint | Photos
checklist | QA - Inground Services
section | Ducts and Conduits
checkpoint | Correct size installed
checkpoint | Start and finish locations correct as per plan
checkpoint | Separation from other services
checkpoint | Clean inside and in good condition
section | Electrical Pits
checkpoint | Set out correct
checkpoint | Correct size installed
checkpoint | Duct entry holes sealed / water proofed
checkpoint | Pits installed to correct height and level
checkpoint | Clean inside and in good condition
section | Light Pole Foundations
checkpoint | Set out correct
checkpoint | Ducting in correct position - centre of cage
checkpoint | Correct Cage Installed
checkpoint | Cage installed to correct height / level
checkpoint | Ground Plant pole installed to correct height / level
section | Photos
checkpoint | Photos
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Fire Rated or Acoustic
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Intumescent Pad In Place
section | Cabling
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Equipment cables installed correctly
checkpoint | Circuits clearly labelled
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | Cable Ladder
checkpoint | Minimum 25% spare capacity left on cable tray
section | QA - Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Seismic Bracing
checkpoint | For Lighting
checkpoint | Cable Tray
checkpoint | Switchboard
section | Conduits
checkpoint | Correct size installed
checkpoint | Location as per plan
checkpoint | All conduits glued & watertight
checkpoint | Clean inside and in good condition
checkpoint | Stainless screws used
section | Photos
checkpoint | Photos
checklist | QA - Second Fix
section | Power Outlets
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
checkpoint | Correctly installed with stainless screws & 90 / 45 angle
section | Photos
checkpoint | Photos
checklist | Switchboard
section | Details
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
checkpoint | Photos