## Master List Templates
Id | Type | Name | Values | Prompting Name
14abefd1-26c1-5712-b570-bbb1ba8010f0 | checklist | Add Documentation |  | Add Documentation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
863362b8-5317-5d7a-a715-e486bd987d08 | checkpoint | Please upload all documements and press PASS.
bdb9e136-1502-5650-ac01-bebab5559d1b | checklist | Carpet Installation |  | Carpet Installation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
121829f8-3c35-5850-b263-9de4043e175d | checkpoint | Substrate clean and approved for installation?
77c38787-909a-5917-b9bf-8d268ea65908 | checkpoint | Are sills, door frames & tiles flush with carpet?
3d26b873-349f-5bc2-98ae-c5f73d6855f0 | checkpoint | Doors to be removed?
e706ae95-1e82-50b0-a884-1c1b14492175 | checkpoint | Confirm plan matches site and joins ok?
66f4dbe1-2e43-50e3-82ee-a893f3b8a782 | checkpoint | Confirm the underlay type from job sheet?
16de04f7-14c5-5446-9f0e-33051c557c12 | checkpoint | Take photo of carpet joins?
d0d6cd78-bc19-5bc5-af09-c892b6a6d12e | checkpoint | Area dust free and all rubbish removed?
cf15ad2f-0517-55f7-9cf8-6fd9bc004a58 | checkpoint | No damage to joinery, skirtings or walls?
ddfc8926-e396-574a-811d-857efbe76348 | checkpoint | Has the floor been protected?
69a54c12-7b63-5187-9a7d-808ed5c1a6c9 | checkpoint | Installation complete with no damage?
93c03ca9-28c3-5947-9572-6c21d1fb0fbd | signoff | Please signoff / request sign off
c755ba6d-cc14-48b7-b857-ac5c6c2947c9 | checklist | Carpet Tiles Installation |  | QA Carpet Tile Installation :
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3e5897ea-15f3-46bf-b8f4-09ec59218523 | checkpoint | Carpet tile range and colour check and confirmed
ca7af71d-548d-4271-82d5-f91e1eb21437 | checkpoint | Area / Location to receive carpet tiles
0b919c41-9165-5e29-816f-07ff4a87f876 | textbox
3532ecac-75ae-4ea3-854d-dc05161964e5 | checkpoint | Floor prep required ?
91ba2909-8cb2-5a4b-aedb-b40d54d1bd25 | textbox
169e1a52-41ac-4c26-9a53-294cfc40585c | checkpoint | Installation direction confirmed ?
1d613fa5-4aa9-4b5d-92b7-441fd2b3f438 | checkpoint | Setting out lines square ?
02ce727b-a5dd-4c24-8eda-32c3a18156aa | checkpoint | Are all edges free from fraying ?
6192cd56-5fa2-495f-919d-a7d392832aa1 | checkpoint | Are all edges cut neat and straight?
7ae6fe07-6a0a-41ca-bec2-53b8e2010ba7 | checkpoint | Carpet tile adhesive used
7af8d0dc-ff0e-56dd-ba5a-1931b6cc8f31 | note | x1 Pictures
d2dae3fd-f1bc-4394-85d7-b6acded2717d | checkpoint | Completed Carpet Tile installation
9a74155b-f21a-5bf5-8025-8359e41031ef | note | x4 Pictures
c062a656-2501-4b33-9ade-fb586f853bfd | checkpoint | Check and clean any excess adhesive in joints, on wall, or skirting
139fcae5-bae5-43c3-bfca-24d9c03d6d2e | checkpoint | Transition between other floor covering level and flush
1606949e-9f0a-4713-83ac-d9e56454bdf1 | checkpoint | Phase completed with no damage ?
5608e008-a164-4b9c-acc1-422397f875d0 | signoff | Please signoff / request sign off
e70eab55-1d2c-5ae6-8faa-b1cda6c49bc7 | checklist | CDC Floor Prep |  | CDC Floor Prep
dbb9cb9e-39fa-5f2a-bef9-73e770a37c31 | checkpoint | Survey floor for flatness?
23aef3ef-ffe6-5802-9139-121278dac909 | checkpoint | Moisture test done prior to installation?
b9ca189c-9140-5bd9-91ae-3ad7ca1ee80b | checkpoint | At-risk surfaces protected?
c4e5a6ce-fc37-5d27-94da-c9e7c1017149 | checkpoint | Apply 1st Coat - Planiseal MR Moisture barrier
b370c798-9a12-522d-8b91-3c104e8658f9 | checkpoint | Apply 2st Coat Planiseal MR Moisture barrier with Broadcast Sand
a0b642b9-e265-5fd9-a3bb-5675f6d6a8a2 | checkpoint | All areas dammed up to prevent leaks?
b65289cb-5ed6-571c-a749-ecfe42b3c6c5 | checkpoint | Apply Mapei Ultraplan Eco Leveller
937c9c1e-9911-5c6a-8c35-542266abc217 | checkpoint | Area clear of rubbish and debris?
e052e593-13ec-58f1-82ed-ec7959c5cb8f | checkpoint | No damage to other surfaces?
f8d3f9fc-1698-5013-8bcc-c0f7ddf14804 | checkpoint | Levels checked and ready for installation?
bb85de61-faca-5628-a714-0d6e5d468cb6 | checkpoint | Preparation complete with no damage?
aa141209-1d99-55f3-bdcc-537b31f25223 | signoff | Please signoff / request sign off
dbd6cef7-bb1a-510b-bea3-23cdad29ad20 | checklist | CDC Floor Vinyl |  | CDC Floor Vinyl
52d71412-8bfa-5b7b-8ab4-dc1a5d9e16d3 | checkpoint | DT059 Capping strip set at 150mm
926bc2f6-0fed-5a51-99ca-824d27ee50c4 | checkpoint | Plastic cove to base of skirting
88008a9c-8a6f-5ab4-a960-a297d22c1ac0 | checkpoint | Correct adhesive for Vinyl - Uzin KE2000S Glue
1d01a4c7-814a-598c-9871-12e134ba9e90 | checkpoint | Install Tarkett IQ Granit SD Sheeting to Data Halls (Pic of label + install)
c46db8cc-3bb0-563f-9b6c-479fe067f36d | checkpoint | Install Tarkett IQ Granit Standard to Circulation areas (Pic of label + install)
1da513eb-b9ec-57ac-971c-628881fc97ce | checkpoint | All butterfly corners done with templet, images required?
4883d0c2-69ee-5704-b842-9b355754bc74 | checkpoint | No excess glue on vinyl surface?
26de048e-3fa5-52bc-a6cb-5fa5a6809242 | checkpoint | All joints been welded?
ddfc8926-e396-574a-811d-857efbe76348 | checkpoint | Has the floor been protected?
47d7914b-77af-50a7-8dc6-d7aaf9b8d7bd | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
94234bd3-4e38-5791-96e1-59e273f124e4 | signoff | Please signoff / request sign off
67f3a7ce-644f-5ca7-a2aa-72821f09c254 | checklist | Concrete Moisture Test - On slab method |  | Concrete Moisture Test - On slab method
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
d5022283-1819-56e7-ada7-db9aaaf8dac3 | checkpoint-no-value | General Details
c40e01b4-d2c3-5b90-a434-314e3b45abdb | note | According to the NZS AS 1884:2013, the acceptable level of concrete moisture content is less than 4.4%
ddf22931-e58c-5527-bf1a-2226624a32ba | date | Date of test
14dfe0c1-281b-5783-b79f-ffda5d7d0a9f | textbox | Project name
462026c8-238d-5e03-8ce6-9c5390b5e136 | checkpoint-no-value | Hygrometer device used for test
96b17690-9aec-57a3-96e3-9a157d41e53c | tickbox | Photo of Hygrometer device uploaded?
149906b5-90e3-5e9b-ad91-2fb3e6b0136d | checkpoint-no-value | Test 1
712f819b-c17e-569a-a42f-1d0a507a99e7 | textbox | Area/Location of test and result
f0e9bdf4-4a96-5834-ab90-e66968d0f9f2 | button | Result | PASS, FAIL
12f2501c-4e3e-5d1d-8c10-d7cb896dc86f | checkpoint-no-value | Test 2
c3d97e0a-2b5e-5128-af0e-efdbd3864fb3 | textbox | Area/Location of test and result
f1fcf52b-b07c-5838-bc68-4464eb10a096 | button | Result | PASS, FAIL
f4e2a2e2-c3bd-5ffd-9572-ac37a3fef314 | checkpoint-no-value | Test 3
208232e1-68aa-5aa5-9f53-20200178969f | textbox | Area/Location of test and result
6827edc9-af60-53cd-89c8-f295e9a64703 | button | Result | PASS, FAIL
3e5fcd55-a736-59f5-ba09-2a1c2dfedb56 | checkpoint-no-value | Test 4
da86241e-87ef-58b7-a4b1-6a45a2b39c84 | textbox | Area/Location of test and result
e82ae221-1502-52c6-aac0-5ae1fe725eb0 | button | Result | PASS, FAIL
4b27ac9e-dcfa-5be5-906a-dd0f34d38b38 | checkpoint-no-value | Test 5
44e5b2b9-d2da-5d8c-9e8f-df8e5c7c7e22 | textbox | Area/Location of test and result
3a327208-0093-5da1-880f-cc2d774e2f00 | button | Result | PASS, FAIL
348a193a-c958-5f37-a445-e3c92d111543 | checkpoint-no-value | Test 6
7f5578e5-2b00-5ee4-81ba-52b522305ddb | textbox | Area/Location of test and result
c2c276d2-ef47-53fd-afae-72a3c5e80261 | button | Result | PASS, FAIL
c732f92c-b1f2-5f0e-a579-73f83db74f52 | checkpoint-no-value | Test 7
fcfa9c22-1f3b-5e17-9c9a-ce8acfc4e246 | textbox | Area/Location of test and result
5b5dca08-2215-5e74-9ed0-69e0d55c21d7 | button | Result | PASS, FAIL
18deba49-84cc-562c-a17b-f84962926eb2 | checkpoint-no-value | Test 8
12715022-47cf-507a-bb91-d26636a67dfd | textbox | Area/Location of test and result
2b339373-6602-5bc7-bd21-a5e924de7bb0 | button | Result | PASS, FAIL
4458ab4f-b068-548a-a956-c870a1e3006c | checkpoint-no-value | Test 9
5004b0f4-213d-5e26-a3af-0e9764487938 | textbox | Area/Location of test and result
9a2ca82b-c0fc-53fa-a39d-d8af6d66a77f | button | Result | PASS, FAIL
671622f5-d85a-53f7-8ab1-400edca53203 | checkpoint-no-value | Test 10
ebf3f132-ac5d-541a-a725-10bec8b3d266 | textbox | Area/Location of test and result
4f4a61ad-84da-59e4-a3d0-61339dce9275 | button | Result | PASS, FAIL
1a79c1b0-81fa-5eff-883c-dce0270ea67b | checkpoint-no-value | Remarks from examinee
a03ca273-703e-55ce-a0fa-dfafd521dc6d | textbox | Remarks/conclusion
8c218aff-e1c1-57e0-8a5f-f6ca5135236e | signoff | Click here to signoff
b739ebf3-2a0a-487f-96bf-0df2eea25748 | checklist | Dayworks Checklist |  | Dayworks Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c9874600-3f1e-4789-90fd-b3c92474a351 | checkpoint | Job details
b24c4113-9610-57c4-b5bd-f220e5b8c81d | textbox | Job Number
1e64838d-de49-57cd-a1de-bc9bc49a560f | textbox | Client
8698df71-9832-503b-8f1c-2e0292a77a6d | textbox | Project
0d7a347a-64e5-5dc2-8d9c-bb14cdb91fa7 | textbox | Area
cc484d20-d5da-413a-9542-dc4d4f26fce5 | checkpoint | Dayworks details
6c573f64-14d2-5b1e-ac7f-0c6e1fb4d540 | date | Date
98ddf7c2-20a8-57de-88c4-c3cf0d4ed952 | textbox | Grinding
f071ca1e-dc6d-54d1-9dd0-7285072ef36f | textbox | Start
892cdc61-c268-5b97-8247-c15d98f1a475 | textbox | End
87b62626-8515-535a-bcfd-f3143f6896ce | textbox | Hours
db84204b-0755-5853-9b95-c769e0b6673b | textbox | Men
e561682f-2acd-5b62-aa2f-c9365db0c53d | textbox | Total hours
3987d398-e27e-5fb4-a06a-069f23de2ded | textbox | Screed Compound
b672c2b9-e6dc-5daf-85da-959bccb10fe8 | textbox | QTY Bags
c20b95f3-665c-5014-a70e-31947436a1fb | textbox | Note
a4724775-20d9-443b-a41d-416116fb410f | signoff | SIGNATURE
bf256cb6-a7fb-5728-b66a-cb256aecd829 | checklist | Floor Prep |  | Floor Prep
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
dbb9cb9e-39fa-5f2a-bef9-73e770a37c31 | checkpoint | Survey floor for flatness?
23aef3ef-ffe6-5802-9139-121278dac909 | checkpoint | Moisture test done prior to installation?
b9ca189c-9140-5bd9-91ae-3ad7ca1ee80b | checkpoint | At-risk surfaces protected?
cf071370-4eb1-59d6-b7d9-15a9895b3171 | checkpoint | Moisture barrier required? If yes Pictures required
a0b642b9-e265-5fd9-a3bb-5675f6d6a8a2 | checkpoint | All areas dammed up to prevent leaks?
937c9c1e-9911-5c6a-8c35-542266abc217 | checkpoint | Area clear of rubbish and debris?
e052e593-13ec-58f1-82ed-ec7959c5cb8f | checkpoint | No damage to other surfaces?
f8d3f9fc-1698-5013-8bcc-c0f7ddf14804 | checkpoint | Levels checked and ready for installation?
bb85de61-faca-5628-a714-0d6e5d468cb6 | checkpoint | Preparation complete with no damage?
aa141209-1d99-55f3-bdcc-537b31f25223 | signoff | Please signoff / request sign off
89aaef07-7816-54ef-b1f4-c0cd1930ff24 | checklist | Floor Prep Wet Room |  | Floor Prep Wet Room
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint-no-value | Details
7c4f752a-38b6-5edb-9bc6-125364b54dab | date | Date
812dc702-2d3c-5943-aef1-49bedb070ade | checkpoint | Surveyed floor for flatness?
96d5ff67-6ba1-5066-ab32-8fbf9a7005f5 | checkpoint | Clean Grind Subfloor
592cc1e9-d50e-5d0f-8a0b-c76a19c35e82 | checkpoint | Apply First coat - 1 K Turbo moisture barrier North to South
040a2598-f76b-5128-b7b4-45d718b1eb6f | checkpoint | Apply Second coat - 1 K Turbo moisture barrier East to West
bca03bc9-31ed-5be3-ad3e-1b2638f25be4 | checkpoint | Prime floor Eco Prim Grip Plus
f365b81a-46d7-5b41-9d23-b93867445f40 | checkpoint | Adjust falls with Novarapid if required and prime floor again with Eco prim Grip Plus
94938dec-7e47-5978-bc72-6446961060c8 | checkpoint | Prime wall with Eco prim T Plus
6c9c2691-419b-51eb-abc6-3c64e32e494d | checkpoint | Apply 2nd coat of Aquadefense
e32ef342-02de-5bf6-b70f-3fe713cd3d3f | checkpoint | Apply mapeband and 1st coat of Aquadefense
ba339ee1-7374-51e8-b0aa-fed4f9cc8fa8 | checkpoint | Skim floor with Planiprep SC
6cdf3ab6-7469-59f2-846f-b5969e19e1fb | checkpoint | Skim Wall with Planiprep SC
995a7947-7758-5038-bfab-5379fbfd2782 | checkpoint | Disk floor and wall ready for Vinyl
66607121-153f-5e33-910e-bf82a515eaf2 | checklist | Floor Vinyl / LVT / Marmoleum |  | Floor Vinyl / LVT / Marmoleum
121829f8-3c35-5850-b263-9de4043e175d | checkpoint | Substrate clean and approved for installation?
23aef3ef-ffe6-5802-9139-121278dac909 | checkpoint | Moisture test done prior to installation?
47d5dd33-13ec-5193-b759-65da09fe84cb | checkpoint | Specify glue to use e.g 68T, UZ2000 or Marmoleum glue.
3d26b873-349f-5bc2-98ae-c5f73d6855f0 | checkpoint | Doors to be removed?
7589e395-957a-59aa-af5c-21371fd083da | checkpoint | All capping installed?
1da513eb-b9ec-57ac-971c-628881fc97ce | checkpoint | All butterfly corners done with templet, images required?
7b08e172-5d45-5fd0-ae60-1ccb618b2ac4 | checkpoint | All areas welded?
4883d0c2-69ee-5704-b842-9b355754bc74 | checkpoint | No excess glue on vinyl surface?
52b5a535-3c44-54bb-a29b-1532a9c7a937 | checkpoint | All transition trims installed?
d0d6cd78-bc19-5bc5-af09-c892b6a6d12e | checkpoint | Area dust free and all rubbish removed?
ddfc8926-e396-574a-811d-857efbe76348 | checkpoint | Has the floor been protected?
47d7914b-77af-50a7-8dc6-d7aaf9b8d7bd | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
da4b0364-0969-514d-8ce5-415d1da2a629 | signoff | Please signoff / request sign off by Site Manager
0673025c-0e15-5226-9ca7-aff526d2fa27 | checklist | GB Add Documentation |  | GB Add Documentation
863362b8-5317-5d7a-a715-e486bd987d08 | checkpoint | Please upload all documements and press PASS.
9ea51d7f-46d6-5481-aaad-3f5d731de3ce | checklist | GB Carpet Installation |  | GB Carpet Installation
121829f8-3c35-5850-b263-9de4043e175d | checkpoint | Substrate clean and approved for installation?
cd5385cf-973b-5595-8d5f-5655f738cc3c | note | x 2 Picture
77c38787-909a-5917-b9bf-8d268ea65908 | checkpoint | Are sills, door frames & tiles flush with carpet?
27f338f3-af5d-57fb-8f62-49aa08285903 | note | x 2 Pictures min
27ae565b-3d47-5fe4-87a9-a27767772d40 | checkpoint | Doors to be removed? Take pictures before and after (proof no damage)
a36e6497-56f9-511c-be09-f994457a32cf | note | x 2 Pictures min
e706ae95-1e82-50b0-a884-1c1b14492175 | checkpoint | Confirm plan matches site and joins ok?
fbada2da-57c0-5be2-bc3b-3f5cafc53a63 | checkpoint | Review job sheet confirm all detail matches e.g. colour of carpet, underlay required?
16de04f7-14c5-5446-9f0e-33051c557c12 | checkpoint | Take photo of carpet joins?
ed607150-812e-5619-b32c-bc3d20426ca4 | note | x 2 Pictures min
5d3e0ad6-c296-5c26-ada8-9eb201187db8 | checkpoint | No damage to skirtings or walls?
78f90f27-5585-5d0b-a320-08bc3c5b1c46 | note | x 4 Pictures min
31ab1ec2-12e8-509b-91f8-76281901e710 | checkpoint | Doors replaced and area left clean of offcuts and rubbish? Take pictures before and after (proof no damage)
4eddf662-05a6-58f7-a19c-ee93e951278d | note | x 2 Pictures min
b629fa6e-1c35-5fd5-916b-474ff16fe701 | checkpoint | Walked all areas, pins tapped down, stairs tight, no carpet lifting, all ok?
a24b1a42-6ff8-5bf2-87ea-1906e9c5e7f9 | note | x 2 Pictures min
ff7d7645-40ea-566e-93b2-e119cc47cd64 | signoff | Please signoff / request sign off
1c97f82c-5d16-539a-ab41-230541f90612 | checklist | GB Laminate |  | GB Laminate
115dee43-c8b4-584e-9733-6db625838a2d | checkpoint | Area clear of rubbish and tradespeople?
18a40e1b-d420-53a4-848d-5b9fd28e62ef | note | x1 Picture
9dccbd25-5dc8-572f-be60-e9ade39b93ee | checkpoint | Survey floor, More than 3 bags and 3 hours grinding? If yes, notify the office with images & scope and wait for approval.
2d946654-bf1c-55c3-bef6-01edbdf4cb1b | note | x1 Picture
141cad72-c9b7-5163-8f05-ba15514a475b | checkpoint | Direction of planks shown on plan?
c79af078-ec3f-525c-8ad5-2eb61af2c461 | checkpoint | Review job sheet confirm all detail matches e.g. colour of planks, underlay.
b9ca189c-9140-5bd9-91ae-3ad7ca1ee80b | checkpoint | At-risk surfaces protected?
156f6cd4-5e2e-5162-934f-a86c6b6ad0d8 | note | x1 Picture
69a54c12-7b63-5187-9a7d-808ed5c1a6c9 | checkpoint | Installation complete with no damage?
43642242-59fa-5c9b-aeda-fd560f090771 | note | x4 Picture
b1cac97d-7eb2-5de8-a036-e631f988136e | checkpoint | Walked area and checked for gapping, bouncing, expansion etc?
118f46d0-53a2-5229-8538-0ddee126a027 | checkpoint | Opened boxes left on site and unopened returned?
d47b5e69-b72f-569c-939b-fa0083f43e39 | checklist | GB Timber Installation |  | GB Timber Installation
23aef3ef-ffe6-5802-9139-121278dac909 | checkpoint | Moisture test done prior to installation?
a35f8e99-a430-5c6b-afac-343ef863f6c8 | note | x1 Picture
1ed1c56f-b514-5ae9-bade-d2de5fe49bff | checkpoint | Floor prep assessed and deviation less than 3mm over 3m?
0a99de2b-7c3c-5b17-8de1-92ae869cc23e | checkpoint | Review job sheet confirm all detail matches e.g. colour of timber etc
100fe00a-e5d2-5c7f-9a7e-0b103a9aedd8 | checkpoint | Timber direction confirmed on plan?
d9149828-f02a-5f35-bd8e-205122a892c1 | checkpoint | Bags and hours grinding signed off by Jay before starting?
b1bc2c5a-181b-54bd-88fa-2f09b953ba72 | checkpoint | Timber weighted down after installation?
e5c18ad1-5f6a-5350-b6c4-a810465c3e5c | note | x 2 Picture
52b5a535-3c44-54bb-a29b-1532a9c7a937 | checkpoint | All transition trims installed?
80c9d5f8-90f8-55fc-b838-9358cb2967e1 | note | x 1 Picture min
d0d6cd78-bc19-5bc5-af09-c892b6a6d12e | checkpoint | Area dust free and all rubbish removed?
31e16a4e-adad-5b08-901e-93d41a3e69ac | note | x 2 Picture
69a54c12-7b63-5187-9a7d-808ed5c1a6c9 | checkpoint | Installation complete with no damage?
6b4dfa2b-4770-5e10-80b4-00c790aa6ac6 | note | x 2 Pictures min
d60ae3a0-ecab-5c1f-89f7-3deca8f9c464 | checkpoint | Walked area, all ok no gapping or damage?
d1a3a52e-748a-5863-8b1c-28ba21d8ffa5 | note | x 2 Pictures min
34b8ced6-3c9a-5093-85c8-fb83fb54607e | checkpoint | Jay advised of all left over materials?
4059dad4-1167-5343-a038-8b7b053c425d | signoff | Please signoff / request sign off
8792d8be-2860-59d3-bbe3-42650e6219db | checklist | GB Vinyl Plank |  | GB Vinyl Plank
dbb9cb9e-39fa-5f2a-bef9-73e770a37c31 | checkpoint | Survey floor for flatness?
937c9c1e-9911-5c6a-8c35-542266abc217 | checkpoint | Area clear of rubbish and debris?
bc0900f4-c135-520e-86c2-81669b85873a | checkpoint | Planks have been on site and are acclimated?
141cad72-c9b7-5163-8f05-ba15514a475b | checkpoint | Direction of planks shown on plan?
7f4c8c6d-f3f5-59cf-9009-84a9571c1744 | checkpoint | More than standard prep required? If yes, notify Jay with images and scope, wait for approval
23aef3ef-ffe6-5802-9139-121278dac909 | checkpoint | Moisture test done prior to installation?
7f727ba6-ad83-5f8c-b326-df38d076c58f | note | x 2 Picture
4057cdca-30c3-5879-a49f-19b7fd4972eb | checkpoint | Windows with direct sunlight blocked
0482f83f-0175-5360-8071-33982a0e6355 | note | x 2 Picture
77c6f5de-7f03-5dab-8b16-705cbe047466 | checkpoint | 68T used 1.5m from splashzone (sink etc)
b9ca189c-9140-5bd9-91ae-3ad7ca1ee80b | checkpoint | At-risk surfaces protected?
e9cc9646-dd38-50c3-98cf-0c72755a42bf | note | x 2 Picture
69a54c12-7b63-5187-9a7d-808ed5c1a6c9 | checkpoint | Installation complete with no damage?
8848a6c4-3d00-502c-bbea-dcebbe6b127e | note | x 2 Pictures min
fa667a63-143d-5cb4-8033-2af6bbe7faf9 | checkpoint | Walked all areas, checked for gapping, lifting, excess glue on boards and skirtings and all ok?
118f46d0-53a2-5229-8538-0ddee126a027 | checkpoint | Opened boxes left on site and unopened returned?
23d7a866-e47d-54ad-9ced-f335890d30d4 | checklist | Incident Report |  | Incident Report
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
4590ccd5-cae6-54cc-86c7-e31689ad1427 | checkpoint-no-value | Project name or location
4144a973-eacb-570e-9f02-08ff3f96392b | textbox
9372b717-d3f1-5e2c-943e-7ee91fc43842 | checkpoint-no-value | Date & Time of Incident
69481eeb-2214-509c-8bf9-a3a1dd6fbb13 | textbox | Date & Time
abf70ff8-5fe9-5404-ae57-1335411405fb | checkpoint-no-value | Reported by
26872896-33b8-5204-b423-01e1caa6177e | textbox | Name & Surname
4d127f3f-663f-5391-a9e8-9d579bc9812d | checkpoint-no-value | Reported to
7f1583e7-c437-5909-89c8-da5342eda19c | textbox | Name & Surname
e5aab8c5-3bbb-56d2-9b74-f2cb2f112d30 | checkpoint-no-value | Incident Type
332bcbd7-4854-5d0b-b51b-f7991ef76d24 | textbox
6c81a22a-4a93-54a5-bf5a-4d55ba59552f | note | Add Picture
c36ac797-1572-5376-b083-db966fbc09b8 | checkpoint-no-value | Details of incident (Injuries)
821dc724-5c63-5b7b-81e1-4c897a8a8b94 | checkpoint-no-value | Person involved
c55eb6e2-65e6-553d-a6a0-41dd9588b7fb | textbox | Name & Surname
3f50c281-edfd-5e5f-89f5-80b2ed215215 | textbox | Contact details
67d6d3b5-3be1-5ee0-a523-fb1d50092222 | checkpoint-no-value | Details of witness
bf50962a-5bd5-544d-986c-46f95093c60b | textbox | Name & Surname
8f58a340-87ae-5cd7-b344-90eaf12008fa | textbox | Contact details
5337ea5e-7fc5-5fde-9a18-b7750729c8ef | checkpoint-no-value | Manager Remarks - Actions and Follow up
c96eb7ae-b800-56e2-a0a7-5334baf32cfe | textbox
490807e5-5021-5d85-aa78-f8b5bea67f8c | signoff | Review and signoff by Supervisor / Manager
40c41e6e-0df1-460b-bb00-d4f5b255d1e1 | checklist | NZ Living - Balcony |  | NZ Living - Balcony
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7ce3de8b-ebfb-49c8-abbf-cbf5607eec15 | checkpoint | Details
3b66c41c-5832-58af-b30d-aab645656b94 | textbox | Block Number
2a2c7c17-e211-5282-a8a1-1ddd9c192777 | textbox | Level Number
bb56e98e-7d19-5fa2-b1d5-e93cebdb9d01 | textbox | Unit Number
f097b912-f1dc-4300-b21b-1fef39f3ab3d | checkpoint | Clean Grind - 30 DISK
259c8eb9-6c3b-59c3-95e2-5979aaf689e5 | note | x 1 Picture
f90a54ae-fe66-44fe-ae1e-96c13ea700cc | checkpoint | Dremel tool in corners and below ranch slider
a81d49a5-c168-5aac-97be-6447ced9f159 | note | x 1 Picture
1fc5ca35-8d7c-4e24-8f0f-e82ebbb2e561 | checkpoint | Polish Grind - 80 DISK
28c00610-8bc0-580e-b15e-e12e33a12bbb | note | x 1 Picture
c213c337-a37e-4162-ac3f-a82e7c29b575 | checklist | NZ Living - Bathroom per unit |  | NZ Living - Bathroom per unit
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ab05fcbb-1748-47e3-90b8-663aced12aa0 | checkpoint | Details
62c4610d-546b-585f-8d64-9c81583e0754 | textbox | Block Number
17fe428e-02a3-53eb-847a-5cea3f9a665e | textbox | Level Number
67503979-e505-5611-b446-1f2a9fed8b97 | textbox | Unit Number
34f359bc-c678-4db5-a02b-7b820bb78df7 | checkpoint | Clean Grind
b71261fa-66d5-54cf-9442-b44abfbd6d43 | note | x 1 Picture
51f08809-5d6b-49bf-9e21-ac16205653f5 | checkpoint | MAPEI AQUA DEFENCE 1st Coat
17b9648e-ff44-547d-9549-0865cd103a94 | note | x 1 Picture
305989d0-a2d5-4cd6-af4c-c69fda218039 | checkpoint | MAPEI AQUA DEFENCE 2nd Coat
69dc96c5-49fe-5c3b-a659-db695343b86b | note | x 1 Picture
cc28aa46-f819-4e47-bc81-269b791d0d43 | checkpoint | Mapei band easi 400x400 waterproof membrane
68a86f11-03af-5084-b331-bd4339feeb46 | note | x 1 Picture
b82ed121-16e5-4a53-b617-45c5e238a3d2 | checkpoint | Apply Mapei Eco prim-T primer
17d3bc52-d6c4-5fd7-ba07-532d4eb532a4 | note | x 1 Picture
445969d4-6478-43e6-aac0-0856032789b0 | checkpoint | Apply smoothing screed compound
cfd1b85b-aacc-5b1e-8831-74929dc9ee9a | note | x 1 Picture
6465b791-ab83-42d4-9acf-0a8fcc011dc1 | checkpoint | 2mm Rubber underlay 1st floor and up only
ec704735-8bbf-4949-a04f-0e30f374a9b5 | checklist | NZ Living - Carpet |  | NZ Living - Carpet
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
22b8558b-d24b-4f87-96c0-1425124b0867 | checkpoint | Details
110fb50b-77c3-55a7-9a1b-a18168dbae8d | textbox | Block Number
713dd5e4-7298-511d-92d2-1821d2a70a59 | textbox | Level Number
1c9aa9ea-2105-5e9c-9d08-20139ba03453 | textbox | Unit Number
4303f131-278b-5ef8-89ee-87c46b2d719b | textbox | Range and colour fitted
57123ab1-6a6c-5633-bf40-30a3191ae492 | note | x 1 Picture
4e386b45-18dd-4fd3-bf69-e88705b7a254 | checkpoint | Underlay install
20fdefdb-12f3-599a-98aa-35acc713423c | note | x 1 Picture
964db42b-e47b-4f06-8a8a-e99a2391bb0e | checkpoint | Door transition trim between vinyl and carpet
80230ffc-8bb3-5fcf-b4a2-c764f8583e27 | note | x 1 Picture
9895d920-20e4-49fb-be08-3e384e5ff0b4 | checkpoint | Assure grippers are pushed down with bolster!
c39b79f5-3f49-5326-8e57-a27f3bf57b62 | note | x 1 Picture
07fa7299-d18b-49ec-8cb9-63da78649569 | checkpoint | Completed carpet install
e7c72250-d848-5b13-8fb4-2983b7e62fd3 | note | x 4 Pictures
a60ce3bb-924d-4201-a939-9ebc9fa553c8 | checklist | NZ Living - First floors and up units |  | NZ Living - First floors and up units
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3e7892ab-e67b-4652-811e-da7440c22f55 | checkpoint | Details
6fb61526-62f6-569c-af18-8ecc704d6c13 | textbox | Block Number
85365474-8916-57d4-bbad-b14755783f16 | textbox | Level Number
89bce13e-fbe1-51b6-a817-014fa2ba1ba2 | textbox | Unit Number
dac7de8b-001f-4b89-8983-12cc3e350f67 | checkpoint | Clean Grind subfloor
375b1547-2f5c-5cee-b550-9d3a96dd475c | note | x 1 Picture
004b2fbd-6ca3-4b5e-bc5d-5c8ebf28c3fe | checkpoint | Fine finish screed preparation
a3680f3e-520f-5687-9112-f8dcec0d5476 | note | x 1 Picture
a904a498-7457-405b-a9d7-de24b186d978 | checkpoint | Ramp at ranch sliders
d91a104c-d4dd-59e1-aca3-6c1273c90170 | note | x 1 Picture
ce60c6ac-c924-4c97-8bdd-8aa5b23844d2 | checkpoint | Polyvac prior vinyl
57421dfe-1a8b-53e7-a6d7-70e2eff4ba1c | note | x 1 Picture
b8b13317-cb27-48d7-a1fd-96dca8c94efb | checkpoint | Undercut bathroom door frame for LVT
1ede50d0-025b-5cf4-b87c-1021a017acb2 | note | x 1 Picture
9dd4dc33-0e44-4003-bd4e-704e8e1bbef9 | checkpoint | Bathroom vinyl adhesive 68T
355b04bd-89b2-5f1a-bb58-9d142e8abf03 | note | x 1 Picture
b7b93896-11c1-4462-9fac-5145f3977edd | checkpoint | Completed vinyl plank install to bathroom
9a8106ef-e130-5b7a-8088-dffb3bfab866 | note | x 1 Picture
981badb4-3c25-419b-9a4a-ea91179f88f4 | checkpoint | Fit regupol underlay prior vinyl with KE2000 (Sub supply)
bcefa41d-f009-5450-a543-98d530e380bf | note | x 1 Picture
03c528e1-5765-4972-9f42-31fcfa2a2c8d | checkpoint | LVT neatly but up against skirting
81f4f70f-0765-5fbf-8d99-824ae2cb5dec | note | x 1 Picture
5f6eec5c-80ea-4047-86b8-f693b2d79a65 | checkpoint | Vinyl plank completed installation pictures
029549b8-b3b0-51fd-ab16-831277f65782 | note | x 2 Pictures
64c32e05-f04b-4ef2-8b9e-8fee99c9fdc6 | checkpoint | Received and installed drain waste
ea2f1541-a238-56d7-8e5c-621fe3862031 | note | x 1 Picture
5ae53c51-f74c-4b0b-bc92-1bce42b0640d | checklist | NZ Living - Ground floor units |  | NZ Living - Ground floor units
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
48f8aec8-fc05-49c1-aba5-8187ebcb93da | checkpoint | Details
89f450d3-8cfd-58f5-ae7c-a7bf59fc51de | textbox | Block Number
4ef5ae9a-53db-529f-a5ed-d84b9f970025 | textbox | Level Number
7d60b79e-0042-5143-ac99-efacd5711d90 | textbox | Unit Number
2d1c327b-7d1d-4fc6-84bc-961cb24b96c5 | checkpoint | Moisture check
4f4621d1-d2b0-5a3b-a91f-daf29e0d07f1 | note | x 2 Pictures
42c0fdfd-d555-4289-8c32-697a29674910 | checkpoint | Clean Grind subfloor
4644957c-12a8-5d9f-9f08-ec6d2260e839 | note | x 1 Picture
237594b2-ede1-4b8d-b254-19bcc55fd3bb | checkpoint | Fine finish screed preparation
fa63d555-f08a-535e-b9c2-51bc42e8c212 | note | x 1 Picture
bb8e3122-a053-4485-bada-41fd0ab508a1 | checkpoint | Ramp at ranch sliders
b718fbd0-5099-5ff2-b478-6456e0a6b11b | note | x 1 Picture
be244f02-fe81-4634-8ffc-26e33c9db0b1 | checkpoint | Polyvac prior vinyl
857fa70e-f7b8-5818-b66f-f2d28cca5080 | note | x 1 Picture
3ad04569-0997-4a2c-971f-08e10230d495 | checkpoint | Undercut bathroom door frame for LVT
d4d94bd7-bc00-583a-8c69-65d68b7f0226 | note | x 1 Picture
2ff1608a-74f3-41d2-aeee-f08ba27b8596 | checkpoint | Bathroom vinyl adhesive 68T
f7915530-9b84-537f-a5a8-b087ac2c9f05 | note | x 1 Picture
c42dfadf-3415-4f3c-9fd5-e743552cd225 | checkpoint | Completed vinyl plank install to bathroom
c2852327-6e67-50c9-86ec-8f620e652d92 | note | x 1 Picture
d6936fa0-a258-48fd-95a4-e14dd1111984 | checkpoint | LVT neatly but up against skirting
19d42c2c-eed3-5879-bf12-3078158318bf | note | x 1 Picture
96b02104-2423-47d7-a1f4-59be0702e326 | checkpoint | Vinyl plank completed installation pictures
e9b94e1c-8b5e-5658-8d61-c0559aec995e | note | x 2 Pictures
6afc60a5-0458-4ee2-b41e-bba0ec3e6084 | checkpoint | Received and installed drain waste
b41842a1-dfe1-565e-bb88-88b4b6153e88 | note | x 1 Picture
86edd4f1-e8e6-4701-a026-2d827693e3f8 | checklist | NZ Living - Staircase |  | NZ Living - Staircase
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
12c171aa-a421-471f-aac9-6577a71a53d8 | checkpoint | Details
b8834cfd-0d0a-5c6f-9556-2009c224453b | textbox | Block Number
0555051f-e1e4-4ff2-bbda-2338d6ab98b6 | checkpoint | Staircase Number
151e9679-931b-4f70-9348-b67fa475bae4 | checkpoint | Sand and prep
c2fe2d1e-093a-4f7d-a5db-a1e37218f6de | checkpoint | Prep fill next to staircase on ground slab dirt trap
574a19d3-f5ef-546d-9f96-6f435f4dc65a | note | x 1 Picture
5a96285a-9d35-52f5-b411-eef97aeb6244 | textbox | Screed bag count
f5045963-8405-4eb2-ab45-31864c710a2f | signoff | Client Signature
49a990d7-e417-4f89-800e-dedef0796771 | checkpoint | Fit approved nosing and insert
ddbb2961-fa47-52d1-93d6-5349acec9a63 | note | x 4 Pictures
8ed85664-7dde-41c3-bb81-0d3669ef41ad | checkpoint | Fit vinyl sheeting adhesive 68T
d190fb1b-aa51-5a7f-af7a-987e9aa4619d | note | x 1 Picture
4fd48300-befa-4689-b672-46e3166722e4 | checkpoint | Completed vinyl installation
4c749be7-18f6-527e-9081-e8cfb65315aa | note | x 4 Pictures
c73da582-d311-584c-8c33-e71f11ac43e0 | checklist | Project Stock Control |  | Project Stock Control
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
d5022283-1819-56e7-ada7-db9aaaf8dac3 | checkpoint-no-value | General Details
f4296876-bf31-527b-9544-50e63324f3a6 | textbox | Project name
2faeb6c9-de03-52a1-9b5f-f22eb504c032 | textbox | Job number
9bcb2867-8067-53b0-812d-32d9b03c6f98 | textbox | Product Manufacturer
6bc69c41-4f6a-5470-b1bd-1111d5ac17ae | textbox | Product Range
894164a3-4b4c-5b7c-ab89-2447a10e3402 | textbox | Product colour(s)
3bcbafe0-a70a-5183-9d2e-9b41dddbf0c7 | checkpoint | Quantity Received from suppliers
ab01efc2-335f-5757-bce4-2e6695102e89 | textbox | Boxes
c0a5cf00-ecf7-5cb6-931f-a05cc3de1b8f | textbox | Square Metre Per/Box
2f7039b9-4d4b-533f-bfbe-8021acdcc4e5 | textbox | Square Metre Per/Roll
254338e1-9f5a-5fb1-8e62-bd28e2ab9737 | checkpoint-no-value | Stock issued out to installer - 1
74e0ab65-d1bb-59d9-abda-a2f7721b9fce | textbox | Colour/Range
072074ca-c9ae-51a0-90f4-2d05eabe8c51 | date | Date
a5f2ca50-3563-5a89-a5bf-5ef829af3bf6 | textbox | Quantity
3a980a47-afaa-5e50-9ff9-d52b4f4ea62e | textbox | Balance left
0333e5d1-846a-5eed-94af-cc03fa28f0ce | signoff | SIGN HERE
6275ce62-dbec-55bc-918b-eb6c4bb18c82 | checkpoint-no-value | Stock issued out to installer - 2
95ec445e-dc8d-5061-8c8c-cc52bdfe00da | textbox | Colour/Range
cc610b6f-0002-5374-af9c-b4b8a5ae6ae0 | date | Date
612545fa-b2f3-54ff-8073-a11cfe7eac24 | textbox | Quantity
33241603-cde1-5a68-b9f2-8a38f2dc48de | textbox | Balance left
79db8317-f63a-5ef6-9369-f08ac7c08b8e | signoff | SIGN HERE
92491d40-08a2-5f42-84cb-b5d3c5635b40 | checkpoint-no-value | Stock issued out to installer - 3
21e2f9ca-484d-51b8-8131-3733cda4a99c | textbox | Colour/Range
53c0366a-cd3b-5ece-9057-e22862cc6bd2 | date | Date
e774cc48-5977-5303-8d1d-ea2a7bfcf892 | textbox | Quantity
f4147c8d-9ab5-5cf0-af7e-d9610bfaeffb | textbox | Balance left
48eeafa3-8a3e-5d63-a104-10d3d422c8a7 | signoff | SIGN HERE
b03bff71-3da1-5310-b2a3-833b79160174 | checkpoint-no-value | Stock issued out to installer - 4
8760df6b-d301-5428-ba2a-d17c99742643 | textbox | Colour/Range
72a9dbca-0fc1-52bf-ae64-08e84214347c | date | Date
30a7be37-a74a-55a5-8151-8c90f9835279 | textbox | Quantity
788264e1-917b-5ee3-bcdc-cf728c68fef0 | textbox | Balance left
cdc4fb50-95be-520f-ae9f-6a01cf857830 | signoff | SIGN HERE
7eed414b-57a5-543d-8bd3-cc111e219ec5 | checkpoint-no-value | Stock issued out to installer - 5
fcb07b5b-2ae7-5da6-8296-6324019e3e59 | textbox | Colour/Range
bcc5e07c-c92c-5eaa-a1e1-0db62f781efc | date | Date
78c0bddb-5ce4-5f21-8fef-58a7384db2c2 | textbox | Quantity
7765ce0a-03c7-50cf-8867-900ecbac77b8 | textbox | Balance left
127591ea-0edd-50d8-ad32-067b00301fe5 | signoff | SIGN HERE
b965de41-d3d5-533b-a7a9-a9c07a9e4599 | checkpoint-no-value | Julius Remarks
412256a0-699c-5a93-be0f-a6d667cb8bad | textbox | Remarks
af1cb1cc-67c5-518d-925d-e393844cd3e6 | checkpoint | Any material returned upon completion?
a261d881-b680-52c9-8ca4-f172c973e2e0 | textbox
42c21dbd-9bff-5051-bd1f-f936237b2320 | checkpoint | Signoff
e41842dd-f42c-530c-9e35-56a1388e253f | signoff | Review and signoff by Manager upon completion of project
32776feb-87fb-527d-9c88-94ab6fb2bfe8 | checklist | Timber Installation |  | Timber Installation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
23aef3ef-ffe6-5802-9139-121278dac909 | checkpoint | Moisture test done prior to installation?
1ed1c56f-b514-5ae9-bade-d2de5fe49bff | checkpoint | Floor prep assessed and deviation less than 3mm over 3m?
be551b5e-a321-5e60-96dc-4fa152f2d546 | checkpoint | V2 notch trowel used for underlay to substrate?
e4179a0d-886e-5de3-a20c-6646de5aee72 | checkpoint | Underlay installed and rolled?
5bb8f8dc-47f0-5155-961f-4c714ba8e299 | checkpoint | 5mm notch trowel used for installation of timber?
9f6c8dda-641b-5b59-9e92-ea734c0160a5 | checkpoint | Timber direction been approved?
17fe55bd-d3bb-5cea-9c0d-6b2e09ff33d5 | checkpoint | Undercut doors and joinery?
050b7ca3-62c2-5d6f-ba2e-e9545466f5df | checkpoint | Expansion gaps as per installation manual?
f344c09d-df6b-5dcd-865a-e15b67f4138e | checkpoint | Timber weighted down during installation?
52b5a535-3c44-54bb-a29b-1532a9c7a937 | checkpoint | All transition trims installed?
d0d6cd78-bc19-5bc5-af09-c892b6a6d12e | checkpoint | Area dust free and all rubbish removed?
cf15ad2f-0517-55f7-9cf8-6fd9bc004a58 | checkpoint | No damage to joinery, skirtings or walls?
ddfc8926-e396-574a-811d-857efbe76348 | checkpoint | Has the floor been protected?
69a54c12-7b63-5187-9a7d-808ed5c1a6c9 | checkpoint | Installation complete with no damage?
93c03ca9-28c3-5947-9572-6c21d1fb0fbd | signoff | Please signoff / request sign off
46943479-fc13-5ec2-8a35-cf51ac3dc926 | checklist | Toolbox Talk - Site-Specific |  | Toolbox Talk - Site-Specific
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
d5022283-1819-56e7-ada7-db9aaaf8dac3 | checkpoint-no-value | General Details
e8b22717-3746-5b67-85d1-4d5a66e99b8d | textbox | Project name or location
c44fcb72-ef9b-5826-ae97-018a406405f2 | date | Conducted on Date
5fa35a35-ab82-530c-93d5-eab7a431ee08 | textbox | Who is running this meeting?
f6e50065-335b-5792-ba67-89a17703ffed | checkpoint-no-value | Toolbox Topic
7c59a214-cd6a-5932-9e59-efa0dc8868a2 | textbox | Description
d31fa13c-6650-5b8b-8f7e-b3c0f5dd342e | textbox | Actions
834fbd45-53e4-50ca-ae96-397432c46bb2 | checkpoint-no-value | Issues raised from site?
4eb33881-f857-5380-92f6-90e71e95bd1a | textbox | Description
88a62530-f668-5693-948c-75f883c5e157 | textbox | Actions
6e0d3ffa-4e0f-575c-85e9-5ed5a8b38ddf | checkpoint-no-value | Employee raised issues?
26081100-cbce-5617-9dc9-020017180893 | textbox | Description
48e876d8-f427-5b89-acb6-c80c355a4371 | textbox | Actions
6d88e701-a549-5ab6-a9b5-f33240b9eb49 | checkpoint-no-value | Incident or Injuries
159c4d5e-ed73-53a2-8c6d-787af98d5fe4 | button | Any Incident or Injuries to report | Yes, No
41d3f0a5-4d72-50a3-995a-edd4d477f923 | textbox | Description
949ebb50-c9d0-5ac2-9614-4bbc22c2a62e | textbox | Actions
65bd108a-d3b2-5f95-b13f-db5cec6f22da | checkpoint-no-value | Hazards
61facd37-3d53-573a-bccb-ece106fe098d | button | Any Hazards to report (Dangerous activity or condition) | Yes, No
266f98cd-4e14-5841-847d-554587e0c20b | textbox | Description
7f94b49c-dce3-523c-b637-da01c6ee94d2 | textbox | Reported to
f829565d-f251-5c0d-b2a6-1143e091a8a8 | checkpoint-no-value | Risks
9f3dd917-6244-512a-8e31-052bc7c067c1 | button | Any Risk to report (Possibility of something bad happening) | Yes, No
8f08b828-7308-5c28-b918-e54284ea64cd | textbox | Description
5af006b9-361d-5e07-a3c9-3ba22ec47e39 | textbox | Reported to
63f8fb5e-dcbd-590d-9e8d-b3a50d1fe0ae | checkpoint | PPE - Personal Protective Equipment - Correct and in good condition ?
aed05275-254d-5edb-98bb-8d4bec48b80e | tickbox | Inspected
2622054e-3999-56d4-8c06-8299d0798ea0 | checkpoint | Positive safe-action observations
33250962-a2fa-5ca8-9c10-1c30404d9a2b | textbox | Observations
3fbac0af-4e74-580e-9d7a-124d76e23a66 | checkpoint | Attendance Record
cb6b1745-1f03-52c6-8efc-7e452836db2f | signoff | Each attendee to click here to signoff
8aa74929-eb63-5e88-98af-5b1bd55ca68e | checkpoint | Supervisor / Manager remarks and signoff
36037859-0a40-5cdc-bfb4-646498cbb6a9 | textbox | Manager's remarks
41a1b71e-1db3-53eb-b8d4-9b45aaac272a | signoff | Review and signoff by Supervisor / Manager
ac1642b6-f1a4-48f5-bc7c-39f73808cfa9 | checklist | Vehicle Inspection |  | Vehicle Inspection
ea515c1e-08fe-4772-88d1-9ecec7869177 | section | Details
39e3f7f8-3c6a-4210-923a-ddccd0162865 | checkpoint | Date - Capture text
ca54b560-e669-43a1-83f0-37254419104a | checkpoint | Driver - Capture text
02f65968-31de-4485-8484-60d0be3bfd6e | checkpoint | Current Odometer reading - Capture text and photo
1ac7ffc2-3503-4e79-b26e-29a1935ba882 | checkpoint | RUC Current KM - Capture text and photo
3566f9f1-349d-4791-b1de-2f687115c26e | checkpoint | WOF Due date - Capture text and photo
a0c3c649-a955-4743-acae-2a142a1cafb2 | checkpoint | Last Service date - Capture text and photo
8b445e72-f416-4905-9312-899c05bdf2fe | checkpoint | Last Service Km - Capture text and photo
b661eca7-c917-46db-b8d1-70d77203ffd0 | checkpoint | Mirrors Clean and no visiable damages
f86ba463-3e02-4c00-92c1-be3a650b47cd | checkpoint | Tyres have adequate Thread - min 2mm
7293250b-6eae-472b-ba58-6e2b61b9234c | checkpoint | Check Oil and Water
21e0e442-78d7-460d-adb8-48d3db2951c8 | checkpoint | Headlights and Indicators working?
edc59fcd-b8fa-4335-9c6a-f4c4cc1d5368 | checkpoint | Break and Tail lights Working?
827b814b-b1c3-4930-bbe9-d7210386e20a | checkpoint | Windcsreen no cracks and chips?
700033f7-5e62-4c06-9e08-49b44acf5d87 | checkpoint | Body of vehicle need repairs? - Take Pic all 4 sides
5ffdaa45-d2d9-4b74-bb6e-b9f24358238f | checkpoint | Vechicle clean? - Take 3 Pictures of inside.
ce606c3b-ce87-4785-85ac-962ec5545db9 | checkpoint | Medical kit in vehicle?
fd563dbe-17da-5584-afd3-f2dcdb1abcf1 | checklist | Wall Vinyl / Cove / Splashback |  | Wall Vinyl / Cove / Splashback
121829f8-3c35-5850-b263-9de4043e175d | checkpoint | Substrate clean and approved for installation?
47d7914b-77af-50a7-8dc6-d7aaf9b8d7bd | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
2db911cd-d7a7-5b64-a5e1-eeaf258d76e1 | checkpoint | Cove height confirmed, and capping installed?
7b08e172-5d45-5fd0-ae60-1ccb618b2ac4 | checkpoint | All areas welded?
4883d0c2-69ee-5704-b842-9b355754bc74 | checkpoint | No excess glue on vinyl surface?
52b5a535-3c44-54bb-a29b-1532a9c7a937 | checkpoint | All transition trims installed?
d0d6cd78-bc19-5bc5-af09-c892b6a6d12e | checkpoint | Area dust free and all rubbish removed?
fb259b44-9062-4472-993e-808d940f9683 | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
4abaf8ce-85a2-5552-bdef-a2e5ff19c534 | signoff | Please signoff / request sign off by Site Manager