## Contract Start Up
|  |  |  | Process Control Plan |  | FHIMS-QA-6000 | Approved |  | Signature
|  |  |  | Contract Name: | Richmond South Low-Level Reservoir |  | FH Engineer
|  |  |  | Procedure: | Compliance Record |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: | [7 empty] | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Pre-construction sign-offs | H | Is there a Safe Work Method Statement for this task? | Prior to commencement | Document Review, Submission | Relevant parties to review, Note Method statement in the Comments | Sign off this task | Project/Quality Manager
2 | Design | H | Review relevent design / task characteristics and identify hold points | Prior to commencement | Document Review | All design requirements are met | Sign off this task | Project/Quality Manager
2.1 | Design | H | Is a temporary works design required for this task? | Prior to commencement | Document Review, Submission | Temporary Works design completed and attached | TW design, Sign off this task | Project/Quality Manager
3 | Technical Reports | H | If relevant attach technical reports | Prior to commencement | Document Review | All related reports attached | Sign off this task | Project/Quality Manager
4 | Materials | W | If required provide required laboratory testing reports, material designs and attach i.e. grading curves, concrete design, steel certs etc. | Prior to commencement | Document Review, submission | All related reports are attached | Laboratory test results, Sign off this task | Project/Quality Manager | Design Engineer
5 | Field Compliance | W | Complete any field testing and Checksheets required by permanent design or temporary works design | During construction | Testing | All related reports are attached | Field Test, Sign off this task | Project/Quality Manager | Design Engineer
6 | Photo Records | H | Attach photo records | As completed | Document Review | All related photos are attached | Photo records, Sign off this task | Project/Quality Manager
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: