## Subsoil Drainage
|  |  |  | Process Control Plan |  | FHIMS-QA-6010 | Approved |  | Signature
|  |  |  | Contract Name: | Richmond South Low-Level Reservoir |  | FH Engineer
|  |  |  | Procedure: | Subsoil Drainage |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7010 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | H | Obtain Permits | As required | Document Review | Digging & Excavation Permit, (incl. marking out & potholing existing services), Confined Space Permit if rquired. Notify Worksafe NZ if required. | Permit attached or permit number noted | Site Engineer
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
3 | Survey Setout | W | Setout and mark all known services along the line of the Sub-soil Drain. | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
4 | Material Compliance (1) | H | Ensure Subsoil Drainage pipe is TNZ F2 Grade and 110mm diameter Nexus Hiway grade slotted high density polyethelene smooth bore corrugated plastic pipe | Upon delivery to site | Ensure delivery docket matches materials delivered | 110mm diameter Nexus Hiway TNZ F/2 Grade pipe | Delivery docket | Site Engineer
4 | Material Compliance (2) | H | Ensure drainage material surrounding subsoil pipe conforms to TNZ F/2 and meets the grading limits setout in the NTLDM |  | Visual inspection | TNZ F/2 & NTLDM | Delivery docket | Site Engineer
4 | Material Compliance (3) | H | Ensure Geotextile Filter Fabric is A29 Bidim, Strength Class C & Filtration Class 1 or equvilant approved by Engineer | Upon delivery to site | Ensure delivery docket matches materials delivered | Ensure geotextile is approved for use | Delivery docket | Site Engineer
5 | Trenching (1) | H | Inspect trench profile and ensure it allows minimum 100mm bedding, side support and surround. | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet | Photo / FHIMS-CS-4001 | Site Engineer
5 | Trenching (2) | H | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | 10m intervals | Visual inspection and measurement | Ensure trench line and levels match the design drawings | Photo / FHIMS-CS-4001 | Site Engineer
5 | Trenching (3) | H | Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works. | As required | Visual Inspection | Design Engineer to instruct action and record on dip sheet and as built drawing | Photo / FHIMS-CS-4001 | Site Engineer | Design Engineer
6 | Bedding, pipe installation and Backfill (1) | H | Upon completion of trenching A29 Bidim or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material | 10m intervals | Visual inspection | Ensure material covers the trench and is pinned in place | Photo / FHIMS-CS-4001 | Site Engineer
6 | Bedding, pipe installation and Backfill (2) | W | Ensure 100mm thick conforming TNZ F/2 bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo / FHIMS-CS-4001 | Site Engineer
6 | Bedding, pipe installation and Backfill (3) | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
6 | Bedding, pipe installation and Backfill (4) | H | As built Survey the Pipe before backfill | 10m intervals | Document review | Consistency with Subsoil Details | As-built receipt | Site Engineer
6 | Bedding, pipe installation and Backfill (5) | W | Backfill by tipping conforming TNZ F/2 into the trench | - | Visual inspection | Ensure good coverage | Photos | Site Engineer
6 | Bedding, pipe installation and Backfill (6) | W | Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place |  | Visual inspection |  |  | Site Engineer
7 | Catchpit Connection (1) | W | Ensure minimum entry point 150mm above soffit of outlet stormwater pipe | As required | Visual inspection | Consistency with Subsoil Details | Photo / FHIMS-CS-4001 | Site Engineer
7 | Catchpit Connection (2) | W | Perforate Catchpit and epoxy grout pipe from inside to completely seal connection. | As required | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
8 | Outlet to any open areas | W | If a subsoil drain outlets to a swale drain/grassed area ensure that a concrete plinth is construction and a marker post is installed - survey to pick up immediately | As required | Survey |  | Survey receipt | Site Engineer
9 | Survey As Built | H | Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process | At completion of sub soil drainage line | Survey |  | Survey receipt | Site Engineer
10 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
11 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into M-Files | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: