## Gabion Retaining Wall
|  |  |  | Process Control Plan |  | FHIMS-QA-6013 | Approved |  | Signature
|  |  |  | Contract Name: | Richmond South Low-Level Reservoir |  | FH Engineer
|  |  |  | Procedure: | Gabion Retaining Wall |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7013 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | H | Obtain Permits | As required | Document Review | Digging & Excavation Permit, (incl. marking out & potholing existing services). Notify Worksafe NZ if required. | Permit attached or permit number noted | Site Engineer
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
3 | Survey Setout | W | Set out base of wall to 1m offset. Setout and mark all known services along the line of the Retaining Wall. | Prior to commencement | Survey | Consistency with Construction Drawing. Designer to confirm extent of MSE Wall | Survey receipt | Site Engineer | Design Engineer
4 | Gabion Baskets | W | All baskets are to be ordered in accordance with the specifications & drawings | Prior to commencement | Review | Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately | Delivery Dockets | Site Engineer
5 | Gabion Rock and Backfill Material Compliance Testing | H | Material to meet specifications and approved by engineer | Each material used | Review | Compliance with requirements and approved by engineer | Delivery Dockets | Site Engineer | Design Engineer
6 | Compaction Trial | W | Carry out compaction trial minimum of 3x superimposed layers to determine peak achievable compaction (NDM) | Backfill material | Review |  | Lab test results | Site Engineer | Design Engineer
7 | Geotextiles & Geogrid | H | All geotextile & geogrid are to be ordered in accordance with the specifications & drawings | As required | Review | Geotextile: Strength Class C, Filtration Class 1. Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life | Delivery Dockets | Site Engineer
8 | Excavate Base of Wall (1) | H | Excavate footprint of the wall area to the correct line and level and ensure area safe to work in. | As required | Survey |  | Survey Receipt | Site Engineer
8 | Excavate Base of Wall (2) | H | Base of excavation to be checked by Geotech engineer / Design Engineer | As required | Visual |  | FHIMS-CS-4100 | Site Engineer | Design Engineer
8 | Excavate Base of Wall (3) | H | Compact subgrade and test the base to ensure it meets 50kPa. | Prior to construction of wall | Scala | 2-3 blows/100mm. If CBR is less than 2.5 or 50kPa undercut may be required. Seek engineer guidance for undercut depth | FHIMS-LA-4403 | Site Engineer | Design Engineer
9 | Subsoil Drainage | H | If subsoil drainage is required for this wall construction then follow the FHIMS-QA-6010 ITP for Subsoil Drainage | Prior to construction of wall | Document Review |  | FHIMS-QA-6010 | Site Engineer | Design Engineer
10 | Construct Leveling Pad | W | Leveling pad to be 300mm compacted aggregate, can include 75mm concrete topping without reinforcing steel | Prior to gabion placement | Visual |  | Photos | Site Engineer
11 | Construct Wall (1) | W | Erect the first level of baskets as per Manufacturers specs along the front face of layers to ensure correct line and level. | As required | Visual |  | Photos | Site Engineer
11 | Construct Wall (2) | W | Tie the 1st layer of baskets together using Manufacturers specs for tying baskets | As required | Visual |  | Photos | Site Engineer
11 | Construct Wall (3) | W | Install geotextile filter fabric, strength class C, filtration class 1 | As required | Visual | Geotextile: Strength Class C, Filtration Class 1. | Photos | Site Engineer | Design Engineer
11 | Construct Wall (4) | W | Place first 100mm layer of filter material | As required | Visual | NZTA F/2 | Photos | Site Engineer
11 | Construct Wall (5) | H | Install subsoil drainage as per FHIMS-QA-6010 ITP for Subsoil Drainage | Prior to construction of wall | Document Review |  | FHIMS-QA-6010 | Site Engineer | Design Engineer
11 | Construct Wall (6) | W | Install 1st layer geogrid and attach to gabbion basket | As required | Visual | Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life | Photos | Site Engineer
11 | Construct Wall (7) | W | Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square. Tip Gabion material slowly into the baskets to fill the voids as much as possible | Every basket | Visual |  | Photos | Site Engineer
11 | Construct Wall (8) | W | Backfill 1st layer in accordance with the specifications & drawings | 2x sets of NDMs for each 1m high by 3m wide by 20m long layer | Lab Testing | 95% of Standard or 92% Vibrating Hammer | FHIMS-CS-4020 | Site Engineer
11 | Construct Wall (9) | W | Tie 2nd layer of Gabion to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again | Every basket | Visual |  | Photos | Site Engineer
11 | Construct Wall (10) | W | Install 2nd layer geogrid and attach to gabbion basket. | As required | Visual | Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life | Photos | Site Engineer
11 | Construct Wall (11) | W | Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square. Tip Gabion material slowly into the baskets to fill the voids as much as possible | Every basket | Visual |  | Photos | Site Engineer
11 | Construct Wall (12) | W | Backfill 2nd layer in accordance with the specifications & drawings | 2x sets of NDMs for each 1m high by 3m wide by 20m long layer | Lab Testing | 95% of Standard or 92% Vibrating Hammer | FHIMS-CS-4020 | Site Engineer
11 | Construct Wall (13) | W | Tie 3rd layer of Gabion to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again | Every basket | Visual |  |  | Site Engineer
11 | Construct Wall (14) | W | Install 3rd layer geogrid and attach to gabbion basket. | As required | Visual | Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life | Photos | Site Engineer
11 | Construct Wall (15) | W | Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square | Every basket | Visual |  | Photos | Site Engineer
11 | Construct Wall (16) | W | Tip Gabion material slowly into the baskets to fill the voids as much as possible | Every basket | Visual |  |  | Site Engineer
11 | Construct Wall (17) | W | Backfill 3rd layer in accordance with the specifications & drawings | 2x sets of NDMs for each 1m high by 3m wide by 20m long layer | Lab Testing | 95% of Standard or 92% Vibrating Hammer | FHIMS-CS-4020 | Site Engineer
12 | Survey As Built | H | Ensure all works comply with design prior to carrying on with next construction process | At completion of sub soil drainage line and each gabion layer | Survey |  | Survey receipt | Site Engineer
13 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
14 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into CONQA | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: