## Steel Fabrication & Painting
|  |  |  | Inpesction Test Plan |  | FHIMS-QA-6038 | Approved |  | Signature
|  |  |  | Contract Name: | Richmond South Low-Level Reservoir |  | FH Engineer
|  |  |  | Procedure: | Steel Fabrication & Painting |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7038 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | Shop Drawings | H | Shop Drawings have been created by the Subcontractor and approved by the Design Engineer before any fabrication commences | Prior to commencement | Document Review | Shop Drawings |  | Site Engineer | Design Engineer
3 | Material Compliance | H | Subcontractor to supply all material compliance certificates for materials used in construction |  | Document Review |  | Subcontractor QA | Site Engineer
4 | Welding (1) | H | Welders Qualifications to be supplied | Prior to commencement | Document Review |  | Subcontractor QA | Site Engineer
4 | Welding (2) | H | All welding procedures and testing of welds to be reviewed & approved by Design Engineer before commencing construction | Prior to commencement | Document Review |  | Subcontractor QA | Site Engineer | Design Engineer
5 | Fabrication (1) | W | Cutting of Steel - checking the steel grade, dimension inspections and ensuring there are no snags on the edges | During Construction | Visual Inspection |  | Subcontractor QA | Site Engineer
5 | Fabrication (2) | W | Drilling of hole layout - checking dimensions & de-burr inspections | During Construction | Visual Inspection |  | Subcontractor QA | Site Engineer
5 | Fabrication (3) | W | Weld stiffeners - Non destruction testing carried out, fillet welds checked and tested | During Construction | Visual & Measured Inspection |  | Subcontractor QA | Site Engineer
5 | Fabrication (4) | W | Stud Layout & Welding - Ensure correct specification & correct positioning | During Construction | Visual & Measured Inspection |  | Subcontractor QA | Site Engineer
6 | Surface Protection (Painting) (1) | W | Surface Preparation - final check for sharp edges, weld splatter and that all holes have been de-burred | At Completion of Construction | Visual Inspection |  | Subcontractor QA | Site Engineer
6 | Surface Protection (Painting) (2) | W | Abrasive Blasting & Seal Coating | At Completion of Construction | Visual Inspection |  | Subcontractor QA | Site Engineer
6 | Surface Protection (Painting) (3) | W | Post Primer Inspection - check that it meets the coating specification | At Completion of Construction | Visual Inspection |  | Subcontractor QA | Site Engineer | Design Engineer
7 | Delivery to Construction Site (1) | H | Ensure that the laydown are is prepared for the arrival of all of the steel components. A TMP is in place and the STMS is briefed as to when deliveries are scheduled to arrive | Prior to delivery | Visual Inspection |  | Subcontractor QA | Site Engineer
7 | Delivery to Construction Site (2) | H | Permit to Lift (Lift Study) carried out and lifting crew is prepared for the deliveries | Prior to delivery | Document Review | Permit to Lift (Lift Study) | Permit | Site Engineer
7 | Delivery to Construction Site (3) | H | All delivery dockets to be supplied and collected as materials arrive onsite to ensure the correct materials have been supplied | During Delivery | Document Review |  | Delivery Dockets | Site Engineer
8 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into CONQA | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
9 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings | Ensure all Asbuilts uploaded into CONQA | Asbuilt Drawing | Site Engineer
10 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into CONQA | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: