## Precast Concrete
|  |  |  | Inpesction Test Plan |  | FHIMS-QA-6049 | Approved |  | Signature
|  |  |  | Contract Name: | Richmond South Low-Level Reservoir |  | FH Engineer
|  |  |  | Procedure: | Precast Concrete |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7049 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | H | Obtain Permits | As required | Document Review | Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Design (1) | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | Design (2) |  | Produce Shop Drawings and Submit for approval | Prior to Commencement | Document Review | Drawing Register | Check Drawing Register | Site Engineer | Design Engineer
3 | Survey Setout | H | Formwork / Mould to be setout to be inspected by Site Engineer prior to concrete being poured | Prior to commencement | Visual Inspection / Measure | Consistency with Construction Drawing | FHIMS-CS-4008 | Site Engineer
4 | Material Compliance (1) | H | Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete | Prior to commencement | Document review |  | Design Engineer Approval | Site Engineer | Design Engineer
4 | Material Compliance (2) | H | All concrete delivered to site shall be produced strictly in accordance with the approved mix design | Prior to pouring concrete | Concrete Delivery Dockets |  | Concrete Delivery Dockets | Site Engineer
4 | Material Compliance (3) | H | Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings | Prior to ordering steel | Document review | AS/NZS4671&NZS3109 | Detail Sheets and Mill Certificates | Site Engineer
4 | Material Compliance (4) | H | Any welding or mechanical splicing to be approved in writing by the Design Engineer | Prior to welding or splicing | Document review |  | Mark Up As Built Drawings | Site Engineer
4 | Material Compliance (5) | H | Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer | Prior to cutting or bending on site | Document review |  | Mark Up As Built Drawings | Site Engineer
5 | Reinforcing (1) | W | Reinforcing steel shall be handled, placed and fixed as per NZS 3109 | Daily Visual Inspection | Document review | Concrete Inspection Record | FHIMS-CS-4008 | Site Engineer
5 | Reinforcing (2) | H | Check Finished Reinforcing cage to ensure correct spacing, grade, diameter and number of bars | Prior to concrete pour | Visual inspection | Concrete Inspection Record | FHIMS-CS-4008 | Site Engineer | Design Engineer
5 | Reinforcing (3) | H | Check for any cast in items and ensure they are fixed correctly | Prior to concrete pour | Visual inspection | Concrete Inspection Record | FHIMS-CS-4008 | Site Engineer | Design Engineer
6 | Pre-tensioning (1) | H | Review Strand stressing / extension calculations comply with Specifications | Prior to concrete pour | Document Review |  | FHIMS-CS-4008 | Site Engineer | Design Engineer
6 | Pre-tensioning (2) | H | Check Strand Size and type complies with Specifications | Prior to concrete pour | Visual Inspection |  | FHIMS-CS-4008 | Site Engineer | Design Engineer
6 | Pre-tensioning (3) | H | Check Debound lengths, and compliance with strand schedule | Prior to concrete pour | Visual Inspection |  | FHIMS-CS-4008 | Site Engineer | Design Engineer
6 | Pre-tensioning (4) | H | Check Actual Strand Stress/Extension with theoretical value. | Prior to concrete pour | Visual Inspection |  | FHIMS-CS-4008 | Site Engineer | Design Engineer
7 | Concreting (1) | H | The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection |  | FHIMS-CS-4008 | Site Engineer | Design Engineer
7 | Concreting (2) | H | Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets | Prior to concrete pour | Test Results | NZS 3104 | FHIMS-CS-4090 | Site Engineer
7 | Concreting (3) | H | Concrete surfaces shall be F4 or better for formed surfaces and U2 or better for unformed surfaces, Bridge decks U5 (broom) finish | At completion of pour | Visual inspection | Concrete Inspection Record | FHIMS-CS-4008 | Site Engineer
8 | Striking of formwork and curing of Units | W | Striping of Beams shall only commence when Concrete has reached release strength and minimum 12 hours of curing | At completion of pour | Visual inspection | Concrete Inspection Record | FHIMS-CS-4008 | Site Engineer
9 | Beam Hog | M | To be Measured prior to site delivery. Deck slab thickness to be adjusted if required. | Prior to Precast Unit Delivery | Visual Inspection |  | FHIMS-CS-4008 | Site Engineer
10 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
11 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into M-Files | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: