## Lot Register
Richmond South Reservoir
Lot No | Activity | ITP TYPE | ITP #
Work Area
1.X.X | ENABLING WORKS
1.1.X | Crane Pads
1.1.1 | Northern Crane Pad | Compliance Record | FHIMS-QA-6000 | Temporary Works
1.1.2 | Southern Crane Pad | Compliance Record | FHIMS-QA-6000 | Temporary Works
1.1.3 | Internal Crane Pad | Compliance Record | FHIMS-QA-6000 | Temporary Works
1.1.4 | Subgrade Earthworks | Compliance Record | FHIMS-QA-6000 | Earthworks
2.X.X | MSE WALL
2.1.X | Gabion Wall & Geogrid
2.1.1 | Layer 1 | MSE wall | FHIMS-QA-6013 | Base leveling pad, geotextile, geogrid layer 1, gabion layer 1, subsoil, filter material, backfill
2.1.2 | Layer 2 | MSE wall | FHIMS-QA-6013 | Geogrid, gabion, backfill
2.1.3 | Layer 3 | MSE wall | FHIMS-QA-6013 | Geogrid, gabion, backfill
2.1.4 | Handrail | Mechanical Installation | FHIMS-QA-6038 | Footing & handrail
3.X.X | PREACAST
3.1.X | Precast Concrete
3.1.1 | Walls | Precast Concrete | FHIMS-QA-6049
3.1.2 | Pilasters | Precast Concrete | FHIMS-QA-6049
3.1.3 | Capital | Precast Concrete | FHIMS-QA-6049
3.1.4 | End Beams | Precast Concrete | FHIMS-QA-6049
3.1.5 | T Beams | Precast Concrete | FHIMS-QA-6049
4.X.X | THREE WATERS
4.1.X | Scour Pipeline
4.1.1 | DN250 (Res → Scour Manhole → Stilling Well) | Drainage Installation | FHIMS-QA-6007 | PE Pipeline, Water Stops
4.2.X | Overflow Line
4.2.1 | DN450 (Res → Stilling Well) | Drainage Installation | FHIMS-QA-6007 | PE Pipeline, Water Stops
4.3.X | Inlet/Outlet Pipeline
4.3.1 | SS lines (Res → Valve Chamber ) | Drainage Installation | FHIMS-QA-6007 | Pipework from Battery Limit to stainless steel pipework, excludes valve chamber & flow meter
4.3.2 | SS lin (Valve Chamber → Flow Chamber → Rising Main) | Drainage Installation | FHIMS-QA-6007 | Components within valve chamber chamber
4.4.X | Subsoil & leak detection
4.4.1 | Subsoil Installation | Subsoil Drainage | FHIMS-QA-6010 | Pipework from Battery Limit to stainless steel pipework, excludes valve chamber & flow meter
4.4.2 | Leak detection | Subsoil Drainage | FHIMS-QA-6010 | Components within valve chamber
4.5.X | Valve and Flow Chamber
4.5.1 | Chamber fitout | Mechanical Installation | FHIMS-QA-6038 | Pipework from Battery Limit to stainless steel pipework, excludes valve chamber & flow meter
5.X.X | VALVE CHAMBER STRUCTURE
5.1.X | Concrete
5.1.1 | Chamber Floor | Insitu Concrete | FHIMS-QA-6006 | Site Concrete, Reo placement, Concrete placement
5.1.2 | Chamber Walls | Insitu Concrete | FHIMS-QA-6006 | Site Concrete, Reo placement, Concrete placement
6.X.X | SUBSTRUCTURE (FLOOR)
6.1.X | Concrete
6.1.1 | Wall Foundation | Insitu Concrete | FHIMS-QA-6006 | Site Concrete, Formwork, Reo placement, Concrete placement
6.1.2 | Column Foundation | Insitu Concrete | FHIMS-QA-6006 | Site Concrete, Waterbar, Formwork, Reo placement, Concrete placement
6.1.3 | Floor Slab | Insitu Concrete | FHIMS-QA-6006 | Gravel raft, Site concrete, Subsoil?, Waterbar,Hydrophilic, Reo placement, Concrete placement
6.1.4 | Floor Stitch | Insitu Concrete | FHIMS-QA-6006 | Site Concrete, Hydrophilic, Reo placement, Concrete placement
6.1.5 | Concrete Nib | Insitu Concrete | FHIMS-QA-6006 | Formwork, Reo placement, Concrete placement
6.1.6 | Wall Footing | Insitu Concrete | FHIMS-QA-6006 | External
7.X.X | WALLS
7.1.X | North/West Section
7.1.1 | Pilaster - P2x1 - Precast | Precast Installation | FHIMS-QA-6040 | FHIMS-QA-6049 Precast Concrete
7.1.2 | Wall Panels - W1x3, W2x1, W3x1 - Precast | Precast Installation | FHIMS-QA-6040
7.1.3 | Insitu Joins x6 | Precast Installation | FHIMS-QA-6040
7.2.X | South/West Section
7.2.1 | Pilaster - P1x1 - Precast | Precast Installation | FHIMS-QA-6040
7.2.2 | Wall Panels - W1x5 - Precast | Precast Installation | FHIMS-QA-6040
7.2.3 | Insitu Joins x6 | Precast Installation | FHIMS-QA-6040
7.3.X | South/East Section
7.3.1 | Pilaster - P2x1 - Precast | Precast Installation | FHIMS-QA-6040
7.3.2 | Wall Panels - W1x4, W4x1 - Precast | Precast Installation | FHIMS-QA-6040
7.3.3 | Insitu Joins x6 | Precast Installation | FHIMS-QA-6040
7.4.X | South/East Section
7.4.1 | Pilaster - P1x1 -Precast | Precast Installation | FHIMS-QA-6040
7.4.2 | Wall Panels - W1x5 - Precast | Precast Installation | FHIMS-QA-6040
7.4.3 | Insitu Joins x6 | Precast Installation | FHIMS-QA-6040
7.5.X | Column
7.5.1 | Column - Insitu | Insitu Concrete | FHIMS-QA-6006
7.5.2 | Capital - Precast | Precast Installation | FHIMS-QA-6040
7.6.X | Post-Tensioning
7.6.1 | Post Tensioning | Compliance Record | FHIMS-QA-6000
7.7.X | End Beams
7.7.1 | End Beams x12 | Precast Installation | FHIMS-QA-6040
8.X.X | ROOF
8.1.X | Tee Beams
8.1.1 | Tee Beams x47 - Precast | Precast Installation | FHIMS-QA-6040
8.2.X | Insitu Capital
8.2.1 | Insitu Capital | Precast Installation | FHIMS-QA-6040
8.3.X | Topping Slab
8.3.1 | Pour 1 | Insitu Concrete | FHIMS-QA-6006
8.3.2 | Pour 2 | Insitu Concrete | FHIMS-QA-6006
8.4.X | Openings
8.4.1 | Construction Access Nib | Insitu Concrete | FHIMS-QA-6006
8.4.2 | Access Hatch Nib | Insitu Concrete | FHIMS-QA-6006
9.X.X | M&E FITOUT
9.1.X | Steel Fabrication
9.1.1 | Air Vents | Mechanical Installation | FHIMS-QA-6038
9.1.2 | External Staircase | Mechanical Installation | FHIMS-QA-6038
9.1.3 | Internal Ladder | Mechanical Installation | FHIMS-QA-6038
9.1.4 | Hatches | Mechanical Installation | FHIMS-QA-6038
9.1.5 | Valve Chamber Lid & Stairs | Mechanical Installation | FHIMS-QA-6038
10.X.X | PAVEMENT
10.1.X | Pavement
10.1.1 | Subgrade | Compliance Record | FHIMS-QA-6000
10.1.2 | Kerb & Channel | Compliance Record | FHIMS-QA-6000
10.1.3 | Pavement Construction - sub-base, basecourse & surfacing | Compliance Record | FHIMS-QA-6000
11.X.X | LANDSCAPING
11.1.X | Planting
11.1.1 | Planting Tress & Shrubs | Compliance Record | FHIMS-QA-6000
11.2.X | Fencing
11.2.1 | Farm Fencing | Mechanical Installation | FHIMS-QA-6038
11.2.2 | Security Fencing & Gate | Compliance Record | FHIMS-QA-6000
11.3.X | Structural
11.3.1 | Access Stairway & Landscape Wall | Compliance Record | FHIMS-QA-6000
12.X.X | COMMISSIONING
12.1.X | Electrical
12.1.1 | Electrical fitout (by others) | Compliance Record | FHIMS-QA-6000
12.2.X | Leak Testing
12.2.1 | Roof Leak Test | Compliance Record | FHIMS-QA-6000
12.2.2 | Reservoir Leak Test | Compliance Record | FHIMS-QA-6000
12.3.X | Disinfection
12.3.1 | Clean, Disinfect, Neutralise & Final Fill | Compliance Record | FHIMS-QA-6000

## ITP Register
ITP | Status | Date | Comment
Compliance Record
MSE Wall
Mechanical Installation
Drainage Install
Subsoil Drainage
Insitu Concrete
Subgrade Construction
Precast Installation

## Checksheets
Checksheet | Status | Date | Comment
E37 - Environmental Inspection Checklist
FHIMS-CS-4100 Subgrade Approval
FHIMS-CS-4002
FHIMS-CS-4029 Concrete Pump
FHIMS-CS-4008 Concrete Inspection Record
FHIMS-CS-4090 Concrete Testing Record
FHIMS-CS-4001 Subsoil Dipsheet