## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | FHIMS-QA-6000-ITP-Compliance Record | itp |  |  |  |  | FHIMS-QA-6000-ITP-Compliance Record
section | Compliance Record
checkpoint | 1 - Pre-construction sign-offs
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Is there a Safe Work Method Statement for this task?
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review, Submission
label | CONFORMANCE CRITERIA - Relevant parties to review, Note Method statement in the Comments
label | RECORDS - Sign off this task
holdpoint | HOLD POINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Review relevent design / task characteristics and identify hold points
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - All design requirements are met
label | RECORDS - Sign off this task
holdpoint | HOLD POINT
checkpoint | 2.1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Is a temporary works design required for this task?
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review, Submission
label | CONFORMANCE CRITERIA - Temporary Works design completed and attached
label | RECORDS - TW design, Sign off this task
holdpoint | HOLD POINT
checkpoint | 3 - Technical Reports
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If relevant attach technical reports
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - All related reports attached
label | RECORDS - Sign off this task
holdpoint | HOLD POINT
checkpoint | 4 - Materials
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - If required provide required laboratory testing reports, material designs and attach i.e. grading curves, concrete design, steel certs etc.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review, submission
label | CONFORMANCE CRITERIA - All related reports are attached
label | RECORDS - Laboratory test results, Sign off this task
checkpoint | 5 - Field Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Complete any field testing and Checksheets required by permanent design or temporary works design
label | FREQUENCY - During construction
label | INSPECTION - Testing
label | CONFORMANCE CRITERIA - All related reports are attached
label | RECORDS - Field Test, Sign off this task
checkpoint | 6 - Photo Records
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Attach photo records
label | FREQUENCY - As completed
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - All related photos are attached
label | RECORDS - Photo records, Sign off this task
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | QA checked By Quality Manager:
textbox | Accepted By Design Engineer:
date | Date:
signoff | Sign ITP
checklist | FHIMS-QA-6006-ITP-Insitu Concrete | itp |  |  |  |  | FHIMS-QA-6006-ITP-Insitu Concrete
section | Insitu Concrete
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
holdpoint | HOLD POINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Set out design features as per Issued For Construction drawings (Cast in items, Ducting, Penetrations)
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Engineer approval
label | RECORDS - Design Engineer Approval
holdpoint | HOLD POINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | FREQUENCY - Prior to pouring concrete
label | INSPECTION - Concrete Delivery Dockets
label | RECORDS - Concrete Delivery Dockets
holdpoint | HOLD POINT
checkpoint | 5 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
label | FREQUENCY - Prior to ordering steel
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - AS/NZS4671&NZS3109
label | RECORDS - Detail Sheets and Mill Certificates
holdpoint | HOLD POINT
checkpoint | 5 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any welding or mechanical splicing to be approved in writing by the Design Engineer
label | FREQUENCY - Prior to welding or splicing
label | INSPECTION - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | HOLD POINT
checkpoint | 5 - Material Compliance (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
label | FREQUENCY - Prior to cutting or bending on site
label | INSPECTION - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | HOLD POINT
checkpoint | 6 - Foundation Acceptance by Engineer's Rep
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Approval given by engineer's Rep and Signed off Subgrade Approval Checksheet
label | FREQUENCY - Prior to commencement
label | INSPECTION - Inspection by Engineer
label | CONFORMANCE CRITERIA - Inspection and Acceptance of Structure Foundations
label | RECORDS - FHIMS - CS-4100
holdpoint | HOLD POINT
checkpoint | 7 - Blinding Concrete
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Once blinding concrete layer has been completed the Engineer's Rep to inspect and give approval for the rest of the works to commence
label | FREQUENCY - Prior to commencement
label | INSPECTION - Inspection by Engineer
label | CONFORMANCE CRITERIA - Engineer approval
label | RECORDS - Sign off this document
holdpoint | HOLD POINT
checkpoint | 8 - Temporary Works (Formwork) (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Formwork to be constructed to design and set to correct line and level as set out by the surveyor
label | FREQUENCY - Daily Visual Inspection
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
checkpoint | 8 - Temporary Works (Formwork) (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 9 - Reinforcing (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Reinforcing steel shall be handled, placed and fixed as per NZS 3109
label | FREQUENCY - Daily Visual Inspection
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
checkpoint | 9 - Reinforcing (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check for any cast in items and ensure they are fixed correctly
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 10 - Concrete Pumping Operations
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure the Permit to Concrete Pump Checksheet has been completed before concrete pumping commences
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Permit to Pump Checkseet
label | RECORDS - FHIMS-CS-4029
checkpoint | 11 - Concreting (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The MSQA Engineer shall be advised at least 48 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual inspection
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 11 - Concreting (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken i.e. Slump test
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Test Results
label | CONFORMANCE CRITERIA - NZS 3112, Concrete Inspection Record
label | RECORDS - FHIMS-CS-4090
holdpoint | HOLD POINT
checkpoint | 11 - Concreting (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete surface finishes shall be
label | ○ Concealed Form Surfaces: F1
label | ○ Exposed Formed Surfaces: F4
label | ○ Exposed Uniformed Surfaces: U2
label | ○ Concealed Uniformed Surfaces: U1
label | FREQUENCY - At completion of pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 12 - Remove formwork
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Remove formwork as per the approved work method
label | FREQUENCY - At completion of pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
checkpoint | 13 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | CONFORMANCE CRITERIA - Ensure all Asbuilts uploaded into CONQA
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | 14 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | QA checked By Quality Manager:
textbox | Accepted By Design Engineer:
date | Date:
signoff | Sign ITP
checklist | FHIMS-QA-6007-ITP-Drainage Installation | itp |  |  |  |  | FHIMS-QA-6007-ITP-Drainage Installation
section | Drainage Installation
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Digging & Excavation Permit, (incl. marking out & potholing existing services), Confined Space Permit if rquired. Notify Worksafe NZ if required.
label | RECORDS - Permit attached or permit number noted
holdpoint | HOLD POINT
checkpoint | 2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Sub-Contract and Supplier Agreements are signed, TMP is approved all Sub-Contractors and Suppliers are inducted to site
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Signed Subcontract and Supplier Agreements, TMP approved
label | RECORDS - Subbie/Supplier Agreements, Approved TMP, Induction register
holdpoint | HOLD POINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 5 - Locate existing services by hand digging or hydrovac
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure all services conflicting with the line of trench has been exposed by hand digging or hydrovac
label | FREQUENCY - Prior to commencement
label | INSPECTION - Potholing
label | CONFORMANCE CRITERIA - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | RECORDS - As-built Drawings Doc. Review
holdpoint | HOLD POINT
checkpoint | 6 - Trenching and Excavation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Inspect trench profile and ensure it is correct to lines and levels to design
label | FREQUENCY - Daily
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - Line and level is correct
label | RECORDS - FHIMS-CS-4025
checkpoint | 6 - Trenching and Excavation (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure trench width is sufficient to provide enough space on either side of the pipe for compaction
label | FREQUENCY - Daily
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - 300mm either side of the pipe
label | RECORDS - FHIMS-CS-4025
checkpoint | 7 - Foundation Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Test formation level on completion of excavation to check if undercut required
label | FREQUENCY - One test per 15m linear metres
label | INSPECTION - Scala Penetrometer, Visual Inspection by designer
label | CONFORMANCE CRITERIA - If CBR is less than 2.5 or 50kPa undercut may be required. Seek engineer guidance for undercut depth
label | RECORDS - FHIMS-LA-4003, FHIMS-CS-4025
holdpoint | HOLD POINT
checkpoint | 7 - Foundation Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If water is in the trench backfill with Drainage 40/20 material ensuring Bidium cloth is pinned to the bottom of the trench. 40/20 material to extend to the mid point on the pipe or to the water table (whichever is highest).
label | FREQUENCY - Visual
label | INSPECTION - Compaction
label | CONFORMANCE CRITERIA - Ensure material is whacked every 150mm lift
label | RECORDS - FHIMS-CS-4025
holdpoint | HOLD POINT
checkpoint | 8 - Undercut BackFill Material Compliance Testing (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Material to meet specifications dependant on material type selected
label | FREQUENCY - Each material used
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Compliance with requirements from Specifications
label | RECORDS - Lab Test Report
holdpoint | HOLD POINT
checkpoint | 8 - Undercut BackFill Material Compliance Testing (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Geotextile or Geogrid that is used in the undercut is to be documented on FHIMS-CS-4025
label | FREQUENCY - Each material used
label | INSPECTION - Certification
label | RECORDS - FHIMS-CS-4025
checkpoint | 8 - Undercut BackFill Material Compliance Testing (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Backfill Construction Material
label | FREQUENCY - 1 test per 15m
label | INSPECTION - Lab Testing
label | RECORDS - FHIMS-CS-4025
holdpoint | HOLD POINT
checkpoint | 9 - Pipe Bedding Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Material to meet specifications dependant on material type selected
label | FREQUENCY - Each material used
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Compliance with requirements from Specifications
label | RECORDS - Lab Test Report
holdpoint | HOLD POINT
checkpoint | 9 - Pipe Bedding Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Backfill Construction Material
label | FREQUENCY - 1 test per 15m
label | INSPECTION - Lab Testing
label | RECORDS - FHIMS-CS-4025
holdpoint | HOLD POINT
checkpoint | 10 - Bedding (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Bedding - Ensure correct thickness of bedding is placed and compacted
label | FREQUENCY - Daily
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - 100mm thick bedding for <450mm dia pipe
label | RECORDS - FHIMS-CS-4025
checkpoint | 10 - Bedding (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure bedding material is compacted
label | FREQUENCY - Prior to laying pipe
label | INSPECTION - Testing
label | RECORDS - Lab test results
checkpoint | 11 - Pipes and Precast Units
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | FREQUENCY - Each delivery to site
label | INSPECTION - Certification
label | CONFORMANCE CRITERIA - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
label | RECORDS - Delivery Dockets
holdpoint | HOLD POINT
checkpoint | 12 - Cast Insitu Drainage Components
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If any cast insitu component i.e. Headwalls is to be completed on a separate ITP - FHIMS-QA-6006 Insitu Concrete
label | FREQUENCY - Every Cast Insitu Component
label | INSPECTION - Document Review
label | RECORDS - FHIMS-QA-6006
holdpoint | HOLD POINT
checkpoint | 13 - Pipe Laying (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
label | FREQUENCY - Daily
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - Invert level <= 5mm and grade <= 3mm from design levels
label | RECORDS - FHIMS-CS-4025
checkpoint | 13 - Pipe Laying (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - No defects/ gaps / pipes are aligned correctly
label | RECORDS - Photos
checkpoint | 13 - Pipe Laying (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - As-built survey of pipes installed
label | FREQUENCY - Once line is completed between 2 structures
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Invert level <= 5mm and grade <= 3mm from design levels
label | RECORDS - Survey Receipt
checkpoint | 14 - Design Engineer Pre backfill Inspection (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
label | FREQUENCY - Daily
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Compliance with the Specification
label | RECORDS - FHIMS-CS-4025
checkpoint | 14 - Design Engineer Pre backfill Inspection (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 5mm
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Vertical tolerance +/- 5mm
label | RECORDS - FHIMS-CS-4025
checkpoint | 14 - Design Engineer Pre backfill Inspection (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
label | FREQUENCY - Prior to backfilling
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Vertical tolerance +/- 5mm
label | RECORDS - FHIMS-CS-4025
checkpoint | 15 - Pipe Backfill Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Material to meet specifications dependant on material type selected
label | FREQUENCY - Each material used
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Compliance with requirements from Specifications
label | RECORDS - FHIMS-CS-4025
holdpoint | HOLD POINT
checkpoint | 15 - Pipe Backfill Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Backfill Construction Material
label | FREQUENCY - 1 NDM test per 15m
label | INSPECTION - Lab Testing
label | RECORDS - Lab Test Report
holdpoint | HOLD POINT
checkpoint | 16 - Backfilling
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade. Remainder of backfill to be done with excavated material.
label | FREQUENCY - 1 test per 20 m length of trench per 300mm lift
label | INSPECTION - Testing
label | RECORDS - Lab test results
checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall) (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Base of structure to be tested. Scala's to be minimum of 3 blows per 100mm
label | FREQUENCY - 1 test per structure
label | INSPECTION - Testing
label | CONFORMANCE CRITERIA - Scala minimum 3 blows/100mm
label | RECORDS - FHIMS-LA-4003
checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall) (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Structures to be installed to the design survey location and level
label | FREQUENCY - During structure construction
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - As Built Survey
label | RECORDS - FHIMS-CS-4006 and Survey receipt
checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall) (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All joints are to be sealed including rungs and lids
label | FREQUENCY - During structure construction
label | INSPECTION - Visual/Inspection
label | CONFORMANCE CRITERIA - Pipe joint to structure shall be encased in 200mm (min.) thick 20MPa concrete
label | RECORDS - FHIMS-CS-4006
checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall) (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Arrange as-built survey of the structure and all invert levels
label | FREQUENCY - Once installed
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - As Built Survey
label | RECORDS - Survey Receipt
checkpoint | 18 - Post Backfill Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - On completion of backfilling all lines to be inspected
label | FREQUENCY - One per line
label | INSPECTION - Internal Visual Inspection with camera (compliant with Confined Spaces working)
label | CONFORMANCE CRITERIA - Lines must be straight, free from dirt and obstructions, with no ponding.
label | RECORDS - FHIMS-CS-4025
holdpoint | HOLD POINT
checkpoint | 19 - CCTV
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - For pipes <900mm a CCTV inspection must be completed. Pipes >900mm must be visually inspected
label | FREQUENCY - At completion of the works
label | INSPECTION - Visual Inspection/ CCTV inspection
label | CONFORMANCE CRITERIA - No Defects
label | RECORDS - Inspection Report CCTV DVD
holdpoint | HOLD POINT
checkpoint | 20 - Testing of Manholes & Pipelines
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If called for in the specifications then test results for water tightness in the structures and low pressure air testing of the pipelines is to be carried out - test sheets to be filling in where required
label | FREQUENCY - One per line/structure
label | INSPECTION - Measurement
label | CONFORMANCE CRITERIA - Drainage Structure Water Tightness Test Record & Low Pressure Air Test Record
label | RECORDS - FHIMS-CS-4073 & FHIMS-CS-4074
holdpoint | HOLD POINT
checkpoint | 21 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure all drainage lines comply with design prior to carrying on with next construction process
label | FREQUENCY - At completion of drainage line
label | INSPECTION - Measurement
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 22 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | CONFORMANCE CRITERIA - Ensure all Asbuilts uploaded into CONQA
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | 23 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | QA checked By Quality Manager:
textbox | Accepted By Design Engineer:
date | Date:
signoff | Sign ITP
checklist | FHIMS-QA-6010-ITP-Subsoil Drainage | itp |  |  |  |  | FHIMS-QA-6010-ITP-Subsoil Drainage
section | Subsoil Drainage
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Digging & Excavation Permit, (incl. marking out & potholing existing services), Confined Space Permit if rquired. Notify Worksafe NZ if required.
label | RECORDS - Permit attached or permit number noted
holdpoint | HOLD POINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Setout and mark all known services along the line of the Sub-soil Drain.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - Survey receipt
checkpoint | 4 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 110mm diameter Nexus Hiway grade slotted high density polyethelene smooth bore corrugated plastic pipe
label | FREQUENCY - Upon delivery to site
label | INSPECTION - Ensure delivery docket matches materials delivered
label | CONFORMANCE CRITERIA - 110mm diameter Nexus Hiway TNZ F/2 Grade pipe
label | RECORDS - Delivery docket
holdpoint | HOLD POINT
checkpoint | 4 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure drainage material surrounding subsoil pipe conforms to TNZ F/2 and meets the grading limits setout in the NTLDM
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - TNZ F/2 & NTLDM
label | RECORDS - Delivery docket
holdpoint | HOLD POINT
checkpoint | 4 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure Geotextile Filter Fabric is A29 Bidim, Strength Class C & Filtration Class 1 or equvilant approved by Engineer
label | FREQUENCY - Upon delivery to site
label | INSPECTION - Ensure delivery docket matches materials delivered
label | CONFORMANCE CRITERIA - Ensure geotextile is approved for use
label | RECORDS - Delivery docket
holdpoint | HOLD POINT
checkpoint | 5 - Trenching (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Inspect trench profile and ensure it allows minimum 100mm bedding, side support and surround.
label | FREQUENCY - 10m intervals
label | INSPECTION - Visual inspection and measurement
label | CONFORMANCE CRITERIA - Record levels of base of trench on dip sheet
label | RECORDS - Photo / FHIMS-CS-4001
holdpoint | HOLD POINT
checkpoint | 5 - Trenching (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | FREQUENCY - 10m intervals
label | INSPECTION - Visual inspection and measurement
label | CONFORMANCE CRITERIA - Ensure trench line and levels match the design drawings
label | RECORDS - Photo / FHIMS-CS-4001
holdpoint | HOLD POINT
checkpoint | 5 - Trenching (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | FREQUENCY - As required
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Design Engineer to instruct action and record on dip sheet and as built drawing
label | RECORDS - Photo / FHIMS-CS-4001
holdpoint | HOLD POINT
checkpoint | 6 - Bedding, pipe installation and Backfill (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Upon completion of trenching A29 Bidim or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | FREQUENCY - 10m intervals
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Ensure material covers the trench and is pinned in place
label | RECORDS - Photo / FHIMS-CS-4001
holdpoint | HOLD POINT
checkpoint | 6 - Bedding, pipe installation and Backfill (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure 100mm thick conforming TNZ F/2 bedding is placed in base of trench.
label | FREQUENCY - 10m intervals
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Record levels of top of bedding on dip sheet
label | RECORDS - Photo / FHIMS-CS-4001
checkpoint | 6 - Bedding, pipe installation and Backfill (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | FREQUENCY - 10m intervals
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Consistency with Subsoil Details
label | RECORDS - Photos
checkpoint | 6 - Bedding, pipe installation and Backfill (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - As built Survey the Pipe before backfill
label | FREQUENCY - 10m intervals
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Consistency with Subsoil Details
label | RECORDS - As-built receipt
holdpoint | HOLD POINT
checkpoint | 6 - Bedding, pipe installation and Backfill (5)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Backfill by tipping conforming TNZ F/2 into the trench
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Ensure good coverage
label | RECORDS - Photos
checkpoint | 6 - Bedding, pipe installation and Backfill (6)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | INSPECTION - Visual inspection
checkpoint | 7 - Catchpit Connection (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
label | FREQUENCY - As required
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Consistency with Subsoil Details
label | RECORDS - Photo / FHIMS-CS-4001
checkpoint | 7 - Catchpit Connection (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
label | FREQUENCY - As required
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Consistency with Subsoil Details
label | RECORDS - Photos
checkpoint | 8 - Outlet to any open areas
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - If a subsoil drain outlets to a swale drain/grassed area ensure that a concrete plinth is construction and a marker post is installed - survey to pick up immediately
label | FREQUENCY - As required
label | INSPECTION - Survey
label | RECORDS - Survey receipt
checkpoint | 9 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
label | FREQUENCY - At completion of sub soil drainage line
label | INSPECTION - Survey
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 10 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | 11 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into M-Files
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | QA checked By Quality Manager:
textbox | Accepted By Design Engineer:
date | Date:
signoff | Sign ITP
checklist | FHIMS-QA-6013-ITP-Gabion Retaining Wall | itp |  |  |  |  | FHIMS-QA-6013-ITP-Gabion Retaining Wall
section | Gabion Retaining Wall
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Digging & Excavation Permit, (incl. marking out & potholing existing services). Notify Worksafe NZ if required.
label | RECORDS - Permit attached or permit number noted
holdpoint | HOLD POINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Set out base of wall to 1m offset.
label | ○ Setout and mark all known services along the line of the Retaining Wall.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing. Designer to confirm extent of MSE Wall
label | RECORDS - Survey receipt
checkpoint | 4 - Gabion Baskets
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All baskets are to be ordered in accordance with the specifications & drawings
label | FREQUENCY - Prior to commencement
label | INSPECTION - Review
label | CONFORMANCE CRITERIA - Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately
label | RECORDS - Delivery Dockets
checkpoint | 5 - Gabion Rock and Backfill Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Material to meet specifications and approved by engineer
label | FREQUENCY - Each material used
label | INSPECTION - Review
label | CONFORMANCE CRITERIA - Compliance with requirements and approved by engineer
label | RECORDS - Delivery Dockets
holdpoint | HOLD POINT
checkpoint | 6 - Compaction Trial
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Carry out compaction trial minimum of 3x superimposed layers to determine peak achievable compaction (NDM)
label | FREQUENCY - Backfill material
label | INSPECTION - Review
label | RECORDS - Lab test results
checkpoint | 7 - Geotextiles & Geogrid
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All geotextile & geogrid are to be ordered in accordance with the specifications & drawings
label | FREQUENCY - As required
label | INSPECTION - Review
label | CONFORMANCE CRITERIA - Geotextile: Strength Class C, Filtration Class 1. Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life
label | RECORDS - Delivery Dockets
holdpoint | HOLD POINT
checkpoint | 8 - Excavate Base of Wall (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
label | FREQUENCY - As required
label | INSPECTION - Survey
label | RECORDS - Survey Receipt
holdpoint | HOLD POINT
checkpoint | 8 - Excavate Base of Wall (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Base of excavation to be checked by Geotech engineer / Design Engineer
label | FREQUENCY - As required
label | INSPECTION - Visual
label | RECORDS - FHIMS-CS-4100
holdpoint | HOLD POINT
checkpoint | 8 - Excavate Base of Wall (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Compact subgrade and test the base to ensure it meets 50kPa.
label | FREQUENCY - Prior to construction of wall
label | INSPECTION - Scala
label | CONFORMANCE CRITERIA - 2-3 blows/100mm. If CBR is less than 2.5 or 50kPa undercut may be required. Seek engineer guidance for undercut depth
label | RECORDS - FHIMS-LA-4403
holdpoint | HOLD POINT
checkpoint | 9 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If subsoil drainage is required for this wall construction then follow the FHIMS-QA-6010 ITP for Subsoil Drainage
label | FREQUENCY - Prior to construction of wall
label | INSPECTION - Document Review
label | RECORDS - FHIMS-QA-6010
holdpoint | HOLD POINT
checkpoint | 10 - Construct Leveling Pad
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Leveling pad to be 300mm compacted aggregate, can include 75mm concrete topping without reinforcing steel
label | FREQUENCY - Prior to gabion placement
label | INSPECTION - Visual
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Erect the first level of baskets as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | FREQUENCY - As required
label | INSPECTION - Visual
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Tie the 1st layer of baskets together using Manufacturers specs for tying baskets
label | FREQUENCY - As required
label | INSPECTION - Visual
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Install geotextile filter fabric, strength class C, filtration class 1
label | FREQUENCY - As required
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Geotextile: Strength Class C, Filtration Class 1.
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Place first 100mm layer of filter material
label | FREQUENCY - As required
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - NZTA F/2
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Install subsoil drainage as per FHIMS-QA-6010 ITP for Subsoil Drainage
label | FREQUENCY - Prior to construction of wall
label | INSPECTION - Document Review
label | RECORDS - FHIMS-QA-6010
holdpoint | HOLD POINT
checkpoint | 11 - Construct Wall (6)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Install 1st layer geogrid and attach to gabbion basket
label | FREQUENCY - As required
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (7)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square. Tip Gabion material slowly into the baskets to fill the voids as much as possible
label | FREQUENCY - Every basket
label | INSPECTION - Visual
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (8)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Backfill 1st layer in accordance with the specifications & drawings
label | FREQUENCY - 2x sets of NDMs for each 1m high by 3m wide by 20m long layer
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - 95% of Standard or 92% Vibrating Hammer
label | RECORDS - FHIMS-CS-4020
checkpoint | 11 - Construct Wall (9)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Tie 2nd layer of Gabion to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again
label | FREQUENCY - Every basket
label | INSPECTION - Visual
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (10)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Install 2nd layer geogrid and attach to gabbion basket.
label | FREQUENCY - As required
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (11)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square. Tip Gabion material slowly into the baskets to fill the voids as much as possible
label | FREQUENCY - Every basket
label | INSPECTION - Visual
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (12)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Backfill 2nd layer in accordance with the specifications & drawings
label | FREQUENCY - 2x sets of NDMs for each 1m high by 3m wide by 20m long layer
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - 95% of Standard or 92% Vibrating Hammer
label | RECORDS - FHIMS-CS-4020
checkpoint | 11 - Construct Wall (13)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Tie 3rd layer of Gabion to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again
label | FREQUENCY - Every basket
label | INSPECTION - Visual
checkpoint | 11 - Construct Wall (14)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Install 3rd layer geogrid and attach to gabbion basket.
label | FREQUENCY - As required
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (15)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square
label | FREQUENCY - Every basket
label | INSPECTION - Visual
label | RECORDS - Photos
checkpoint | 11 - Construct Wall (16)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Tip Gabion material slowly into the baskets to fill the voids as much as possible
label | FREQUENCY - Every basket
label | INSPECTION - Visual
checkpoint | 11 - Construct Wall (17)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Backfill 3rd layer in accordance with the specifications & drawings
label | FREQUENCY - 2x sets of NDMs for each 1m high by 3m wide by 20m long layer
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - 95% of Standard or 92% Vibrating Hammer
label | RECORDS - FHIMS-CS-4020
checkpoint | 12 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure all works comply with design prior to carrying on with next construction process
label | FREQUENCY - At completion of sub soil drainage line and each gabion layer
label | INSPECTION - Survey
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 13 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | 14 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | QA checked By Quality Manager:
textbox | Accepted By Design Engineer:
date | Date:
signoff | Sign ITP
checklist | FHIMS-QA-6038-ITP-Steel Fabrication & Painting | itp |  |  |  |  | FHIMS-QA-6038-ITP-Steel Fabrication & Painting
section | Steel Fabrication & Painting
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 2 - Shop Drawings
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Shop Drawings have been created by the Subcontractor and approved by the Design Engineer before any fabrication commences
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Shop Drawings
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Subcontractor to supply all material compliance certificates for materials used in construction
label | INSPECTION - Document Review
label | RECORDS - Subcontractor QA
holdpoint | HOLD POINT
checkpoint | 4 - Welding (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Welders Qualifications to be supplied
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Subcontractor QA
holdpoint | HOLD POINT
checkpoint | 4 - Welding (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All welding procedures and testing of welds to be reviewed & approved by Design Engineer before commencing construction
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Subcontractor QA
holdpoint | HOLD POINT
checkpoint | 5 - Fabrication (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Cutting of Steel - checking the steel grade, dimension inspections and ensuring there are no snags on the edges
label | FREQUENCY - During Construction
label | INSPECTION - Visual Inspection
label | RECORDS - Subcontractor QA
checkpoint | 5 - Fabrication (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Drilling of hole layout - checking dimensions & de-burr inspections
label | FREQUENCY - During Construction
label | INSPECTION - Visual Inspection
label | RECORDS - Subcontractor QA
checkpoint | 5 - Fabrication (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Weld stiffeners - Non destruction testing carried out, fillet welds checked and tested
label | FREQUENCY - During Construction
label | INSPECTION - Visual & Measured Inspection
label | RECORDS - Subcontractor QA
checkpoint | 5 - Fabrication (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Stud Layout & Welding - Ensure correct specification & correct positioning
label | FREQUENCY - During Construction
label | INSPECTION - Visual & Measured Inspection
label | RECORDS - Subcontractor QA
checkpoint | 6 - Surface Protection (Painting) (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Surface Preparation - final check for sharp edges, weld splatter and that all holes have been de-burred
label | FREQUENCY - At Completion of Construction
label | INSPECTION - Visual Inspection
label | RECORDS - Subcontractor QA
checkpoint | 6 - Surface Protection (Painting) (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Abrasive Blasting & Seal Coating
label | FREQUENCY - At Completion of Construction
label | INSPECTION - Visual Inspection
label | RECORDS - Subcontractor QA
checkpoint | 6 - Surface Protection (Painting) (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Post Primer Inspection - check that it meets the coating specification
label | FREQUENCY - At Completion of Construction
label | INSPECTION - Visual Inspection
label | RECORDS - Subcontractor QA
checkpoint | 7 - Delivery to Construction Site (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that the laydown are is prepared for the arrival of all of the steel components. A TMP is in place and the STMS is briefed as to when deliveries are scheduled to arrive
label | FREQUENCY - Prior to delivery
label | INSPECTION - Visual Inspection
label | RECORDS - Subcontractor QA
holdpoint | HOLD POINT
checkpoint | 7 - Delivery to Construction Site (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Permit to Lift (Lift Study) carried out and lifting crew is prepared for the deliveries
label | FREQUENCY - Prior to delivery
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Permit to Lift (Lift Study)
label | RECORDS - Permit
holdpoint | HOLD POINT
checkpoint | 7 - Delivery to Construction Site (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All delivery dockets to be supplied and collected as materials arrive onsite to ensure the correct materials have been supplied
label | FREQUENCY - During Delivery
label | INSPECTION - Document Review
label | RECORDS - Delivery Dockets
holdpoint | HOLD POINT
checkpoint | 8 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 9 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | CONFORMANCE CRITERIA - Ensure all Asbuilts uploaded into CONQA
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | 10 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | QA checked By Quality Manager:
textbox | Accepted By Design Engineer:
date | Date:
signoff | Sign ITP
checklist | FHIMS-QA-6040-ITP-Precast Installation | itp |  |  |  |  | FHIMS-QA-6040-ITP-Precast Installation
section | Precast Installation
checkpoint | 1 - Permits (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
holdpoint | HOLD POINT
checkpoint | 1 - Permits (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Permit to Lift &/or Lift Study to be carried out
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Approval given by Construction Manager
label | RECORDS - Permit to Lift
holdpoint | HOLD POINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 4 - Precast Installation (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - No Precast Components are to be installed until FHIMS-QA-6049 has been completed and signed off for that item
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Process Control Plan, Checksheets & any other associated documentation is provided
label | RECORDS - FHIMS-QA-6049
holdpoint | HOLD POINT
checkpoint | 4 - Precast Installation (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Delivery Dockets are collected and signed before precast materials are removed from the truck
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Delivery Dockets
holdpoint | HOLD POINT
checkpoint | 4 - Precast Installation (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial to be done by the manufacturer onsite & an OFI to be completed
label | FREQUENCY - Prior to unloading
label | INSPECTION - Visual
label | RECORDS - Delivery Dockets
holdpoint | HOLD POINT
checkpoint | 4 - Precast Installation (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that other components are installed correctly (bearings etc.) and are approval given from Designer team before precast components are lifted into their final positions
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
holdpoint | HOLD POINT
checkpoint | 4 - Precast Installation (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the risk control plan
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - RCP
holdpoint | HOLD POINT
checkpoint | 5 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | 6 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | QA checked By Quality Manager:
textbox | Accepted By Design Engineer:
date | Date:
signoff | Sign ITP
checklist | FHIMS-QA-6049-ITP-Precast Concrete | itp |  |  |  |  | FHIMS-QA-6049-ITP-Precast Concrete
section | Precast Concrete
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
holdpoint | HOLD POINT
checkpoint | 2 - Design (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 2 - Design (2)
label | DETAIL - Produce Shop Drawings and Submit for approval
label | FREQUENCY - Prior to Commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Drawing Register
label | RECORDS - Check Drawing Register
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Formwork / Mould to be setout to be inspected by Site Engineer prior to concrete being poured
label | FREQUENCY - Prior to commencement
label | INSPECTION - Visual Inspection / Measure
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 4 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document review
label | RECORDS - Design Engineer Approval
holdpoint | HOLD POINT
checkpoint | 4 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | FREQUENCY - Prior to pouring concrete
label | INSPECTION - Concrete Delivery Dockets
label | RECORDS - Concrete Delivery Dockets
holdpoint | HOLD POINT
checkpoint | 4 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
label | FREQUENCY - Prior to ordering steel
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - AS/NZS4671&NZS3109
label | RECORDS - Detail Sheets and Mill Certificates
holdpoint | HOLD POINT
checkpoint | 4 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any welding or mechanical splicing to be approved in writing by the Design Engineer
label | FREQUENCY - Prior to welding or splicing
label | INSPECTION - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | HOLD POINT
checkpoint | 4 - Material Compliance (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
label | FREQUENCY - Prior to cutting or bending on site
label | INSPECTION - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | HOLD POINT
checkpoint | 5 - Reinforcing (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Reinforcing steel shall be handled, placed and fixed as per NZS 3109
label | FREQUENCY - Daily Visual Inspection
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
checkpoint | 5 - Reinforcing (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check Finished Reinforcing cage to ensure correct spacing, grade, diameter and number of bars
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 5 - Reinforcing (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check for any cast in items and ensure they are fixed correctly
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 6 - Pre-tensioning (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Review Strand stressing / extension calculations comply with Specifications
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Document Review
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 6 - Pre-tensioning (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check Strand Size and type complies with Specifications
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual Inspection
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 6 - Pre-tensioning (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check Debound lengths, and compliance with strand schedule
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual Inspection
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 6 - Pre-tensioning (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check Actual Strand Stress/Extension with theoretical value.
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual Inspection
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 7 - Concreting (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Visual inspection
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 7 - Concreting (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets
label | FREQUENCY - Prior to concrete pour
label | INSPECTION - Test Results
label | CONFORMANCE CRITERIA - NZS 3104
label | RECORDS - FHIMS-CS-4090
holdpoint | HOLD POINT
checkpoint | 7 - Concreting (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete surfaces shall be F4 or better for formed surfaces and U2 or better for unformed surfaces, Bridge decks U5 (broom) finish
label | FREQUENCY - At completion of pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
holdpoint | HOLD POINT
checkpoint | 8 - Striking of formwork and curing of Units
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Striping of Beams shall only commence when Concrete has reached release strength and minimum 12 hours of curing
label | FREQUENCY - At completion of pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
checkpoint | 9 - Beam Hog
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - To be Measured prior to site delivery. Deck slab thickness to be adjusted if required.
label | FREQUENCY - Prior to Precast Unit Delivery
label | INSPECTION - Visual Inspection
label | RECORDS - FHIMS-CS-4008
checkpoint | 10 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | 11 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into M-Files
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | QA checked By Quality Manager:
textbox | Accepted By Design Engineer:
date | Date:
signoff | Sign ITP