## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
c16e26e7-5dc6-4c0c-8fa1-ac1f05cf038e | checklist | Generic - ITP - ACO Drain |  | Generic - ITP - ACO Drain
8d4265ea-2d86-4ac5-8aa1-18c1aec1fc78 | section | Site Set Out
c1a1f7b2-1817-4780-8685-5de3197a3fa5 | checkpoint | 1 - Site Set out
ff5bbdca-ff3e-53f5-9001-e3349dcdfb40 | note | VERIFICATION ACTIVITY: Surveyor
d124904c-d4a6-5087-8391-237c93beba82 | note | METHODS OR REFERENCE: Surveyor
4d7a6196-a3c9-5302-92dc-eeeaf7a9ab31 | note | FREQUENCY: Everysite
14867c09-0cb4-593c-87f7-84c24b434310 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
3002204c-acf5-5cc6-befd-f37bd7c4e92a | note | ○ Alternatively like for like
665b964f-0304-5d9d-a5de-e6aa531871d1 | note | HOLD POINT: Mandatory HOLD POINT -
010f1b57-ecdf-56a1-9f85-9748e50144c4 | note | RECORDS: Survey Receipt
a20e5e60-e692-5ad3-9470-f6533317796c | note | ONSITE RESPONSIBILITY: Site Engineer
5fb8dfb3-1bfe-4587-aafa-5548b6d46db9 | signoff | AUTHORITY HOLDPOINT
75af41bf-9f99-4467-99e3-c26fe5f6b226 | section | Materials
9f39c956-6e17-4dfe-90b0-e51ea90d65fe | checkpoint | 2 - Aco Drain K300
215cccdc-f07e-59d2-bd86-71e938944972 | note | VERIFICATION ACTIVITY: QA FORM
5269ea8e-416e-515a-8fd5-18c27c070f23 | note | METHODS OR REFERENCE: TDM Technical Standards
7711f668-6b5c-57dc-8d88-203cabf87a33 | note | FREQUENCY: Every site
96ad1475-9211-5b71-9b21-d970b9cf722c | note | ACCEPTANCE CRITERIA: All the block and the grate should be inspected before installation.
002a8e4b-795f-57f3-822e-c97dc130035b | note | HOLD POINT: Inprocess Inspection
f01c4cb3-147b-5a6e-834e-92d6b300c2f2 | note | RECORDS: Dockets
393cbe39-79af-56ad-9606-b26ba10410f1 | note | ONSITE RESPONSIBILITY: Site Engineer
39b7a761-b589-46fd-9bbf-b5afd728d844 | section | Construction
cb08a9d7-1a2b-4a36-b618-3f9f75af9b24 | checkpoint | 3 - Prep and Level Check
256cc425-12f5-52a7-9f80-e3b101516a63 | note | VERIFICATION ACTIVITY: QA FORM
53c69049-a33d-5650-bc35-ee416a20384e | note | METHODS OR REFERENCE: TDM Technical Standards
df9ba017-1dc7-5b74-9cb3-67e4437e4930 | note | FREQUENCY: Each block
76cf880d-c2c0-5741-bcb9-69ffe197f37a | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
f89a9492-5fd7-509f-b1f3-5df1eb5ced25 | note | ○ Base course - 100mm min. thickness GAP40
aa176d9d-8ba1-58e4-be66-c3795b2c8032 | note | ○ Clegg CIV > 12
ec425b9b-cf01-55fa-80e4-9fe6fe2856fd | note | ○ water flow check
8ddbeb48-b705-5565-af8f-a6f67c7e6177 | note | HOLD POINT: Inprocess Inspection - Engnieer to check
0c22bdda-c0b3-5092-b36c-62b0ac740e67 | note | RECORDS: Depth check photos, fall check photos
633416e6-a645-545e-8966-0823c63f9b56 | note | ONSITE RESPONSIBILITY: Site Engineer
1135e31a-25be-4a23-9bc6-4141c8f4cace | checkpoint | 4 - Lay Kerb Drain
0b93d776-23d2-5bf2-9cda-8d6d1a12aa17 | note | VERIFICATION ACTIVITY: QA FORM
ed0c3d0c-ef25-5af3-a0b6-b2202416e512 | note | METHODS OR REFERENCE: TDM Technical Standards
f0a994a4-c660-5c6b-b348-2fd737187d95 | note | FREQUENCY: Each Block
ea4c5a08-5983-5d67-bc60-e03f8a7f6fff | note | ACCEPTANCE CRITERIA: Boxing to be done along the aco drain
f3c7ccf4-8619-5681-9c54-c383c8e5467b | note | ○ Surfacing - Concrete 150mm and 25 MPa @ 28 days.
d15a40d8-1b70-5582-a1ad-a5270dd8b483 | note | ○ Side Haunching for 150mm thickness
875f16c5-3c66-5f91-a147-95821dd9f6fd | note | ○ Vibrator to be used to avoid voids
7b4bfc45-be08-5acb-98c5-02cb5eee1c3b | note | ○ Finished level of concrete to match with the grate
8ab11bc0-7492-5824-ad55-f37e2a2d57b7 | note | HOLD POINT: Inprocess Inspection - Engnieer to check
68d3605b-7173-5ee8-a34f-bb2f00f00ac8 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
29a21b32-05a4-5a97-8921-02cf8520d7e3 | note | ONSITE RESPONSIBILITY: Site Engineer
19ddc850-5949-41d3-9459-02caabe7e530 | section | Asbuilts
a0b55c73-b567-4bfb-b593-5b64584a5ad4 | checkpoint | 5 - As built information
dd73c842-3c63-5e7a-845f-42bbccfd893f | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
e784b473-f7b0-52e3-8db2-8b93ecd610ed | note | METHODS OR REFERENCE:
d994ca37-d983-5465-80c2-2b3fa7702289 | note | FREQUENCY: Every Site
8ccf5f9b-d367-581b-be93-715e95b1f096 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
a505571a-d69a-5c62-98ee-467fc9ddaab7 | note | HOLD POINT: In Process Inspection
3165be87-a215-5bbb-852a-629618ae209a | note | RECORDS: Asbuilt records
15603495-cff1-510f-ac45-d0db544d4f56 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
6244bed8-2b88-4dcc-8fcc-de41cad06c75 | section | ITP APPROVAL
b5889270-4edf-4517-bd60-bda490804026 | checkpoint | ITP Approval
2da5bdb0-464e-57ae-8741-05b5c0a30147 | textbox | Prepared by:
7f753368-e69d-55c3-847e-e1ef109db75f | textbox | Approving Delegate: