## Sheet1
ae225fb3-9ad9-4149-ae2b-9de7a66c2e8a | checklist | SWP - QA - Fibertite Overlay Install Checklist | SWP - QA - Fibertite Overlay Install Checklist | Notes
69a03ed2-c42f-4ead-ab0e-953c9bb300e1 | section | Prestart
51740d88-776b-4771-a821-d0572776de18 | checkpoint | Area accessible
0562f0ef-d611-48f2-9733-705ffa41f8a1 | checkpoint | Edge protection and safety installed
711ba1bd-5f6a-4a04-b5f0-7385f2e7b202 | checkpoint | Substrate complete and ready for SWP
a55c359d-069e-4a3a-a565-8d434543fba7 | section | Substrate
4623f929-7fc6-4c30-b150-7ef32fe815e5 | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
b163d177-93ef-4f01-bd5d-b9267bba42d4 | checkpoint | Cut back existing roof edge at gutter
3cf478aa-cf4c-48f5-8797-5258317b11ed | checkpoint | Remove ridge as we go
08e5f3bc-955d-4504-82a7-c8ddac54db03 | section | VCL-Vapour Control Layer
5ee316aa-81fc-446c-9728-404ca5166cd1 | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
2af9f685-74d7-4b48-a5a0-2cc5e0eb6143 | checkpoint | All areas covered and lapped a minimum of 100mm
80dbeb04-342d-4dfc-a24a-c98858134eee | checkpoint | All holes/penetrations patched and made watertight
1459d4f1-ff49-441f-9c7b-b5bc12358d69 | section | Roof Pan Infills
0fc7f1c0-2038-468e-824f-32f5896070b6 | checkpoint | Surface is dry before installing PIR infills |  | Change check point
9320b599-6c0a-4a92-b208-e5526c1f11b5 | checkpoint | Infills to be a minimum 5mm above ridges on roof
ca17e849-2d06-4ccf-8cd7-fdccab81f773 | checkpoint | Every pan has been infilled
a2d66e97-6f34-4cf6-8484-b83358d9b5a6 | section | 80mm PIR |  | Change heading
685d1725-3ea5-490f-9e87-afe8780eebb9 | checkpoint | Substrate/surface dry & clean prior to being installed
30d619b3-5b62-4871-90d8-116beefb04db | checkpoint | Installed in brick pattern
4e4d6655-4e2d-4f35-912d-eb18e5ac8abf | checkpoint | Correct screws with load washer
113e6fb4-f3c1-427e-8d71-1927d098a48e | checkpoint | Installed as per wind uplift fixing plan
| checkpoint | Install PIR laminated plywood at gutter edge as per fixing plan |  | Change check point
5483c944-e22a-41e2-a410-38b74f8043be | checkpoint | Install zincalume flashing |  | Change check point
9711814b-0d44-48f8-a1e4-0a24a1ba148b | section | Fibertite
a03e76c0-a094-4221-818d-7c4ad2eaa2bc | checkpoint | Correct Glue being used for substrate
| checkpoint | Prime substrate where required |  | New checkpoint
9d2e1a3c-1612-4712-884b-2c09554d028f | checkpoint | Fibertite fully glued to substrate
84141ba0-a738-4541-935f-bd4e786fea00 | checkpoint | Broom/rolling of fibertite
730b38fa-2675-4675-a39a-3d98985fbb41 | checkpoint | Wipe/clean laps with acetone prior to welding
| checkpoint | Test weld with welding machine |  | New checkpoint
| checkpoint | Probe of seam with QA hook |  | New checkpoint
6edfa285-3c29-4430-849f-72e8d77421f1 | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
2c3ca352-240e-4f21-9886-e393ec2ce7c0 | checkpoint | Clamps / rings / baskets installed |  | remove
82f6e9e4-7b90-486f-a1d1-61f38bd0e398 | checkpoint | Flooded / ILD checked |  | remove
| section | Sumps |  | New section
d2777793-20c0-4c49-9f5d-d4ee59e07dae | checkpoint | Sealant installed to dropper flange under membrane |  | New checkpoint
0f0e094b-0581-41cc-b054-dbf839f5f155 | checkpoint | Membrane dressed in to outlets |  | New checkpoint
adc384b3-c321-43a9-a4b6-d378122fcaf3 | checkpoint | Clamp/rings/basket installed |  | New checkpoint
e68febee-624c-4dbc-aba4-9499331398b9 | checkpoint | Flood test |  | New checkpoint
117c08bc-8ec1-446e-86ac-ac79bcc5d7cd | checkpoint | Fibertite fully welded to flashing and QA'd with hook |  | New checkpoint
5be381d0-60b0-475d-91b4-ea9346bd9d0c | section | Smart bar installed |  | New section
| Check point | Smart bar installed as per fixing design |  | New checkpoint
| Check point | Wipe/clean laps with acetone prior to welding |  | New checkpoint
| Check point | Probe of seam with QA hook |  | New checkpoint
5be381d0-60b0-475d-91b4-ea9346bd9d0c | section | Pressure bar installed |  | New section
a47f6505-3ea5-419b-8071-2257b8718766 | checkpoint | Installed correctly according to specifications ( right way around ) |  | New checkpoint
e46ab990-28c4-4974-ac99-905a6c753aef | checkpoint | Fixings done according to specifications and details |  | New checkpoint
57f86877-4794-4dde-b88f-1cb8c1429a3b | checkpoint | Prime of Substrate where required |  | New checkpoint
971083d1-bac8-42d1-9cca-a57bc13c0d4c | checkpoint | Sealant installed |  | New checkpoint
fbe7cb25-cd4b-4229-a6b2-c8030cf7b05f | section | Over flashings |  | New section
1e7b43b8-4101-4f85-8da9-bd69eee594af | checkpoint | Over flashings has a separation barrier |  | New checkpoint
2c0716cb-ab90-4b5d-b9b4-1c647edc7f51 | checkpoint | Fixings done according to specifications and details |  | New checkpoint
f8dafa97-f460-4c97-b8ec-fb97811eec34 | checkpoint | Prime of Substrate where required |  | New checkpoint
a8f73413-0c3c-49e5-90b0-75e4e7476287 | checkpoint | Sealant installed |  | New checkpoint
1fe182bc-cb97-4599-85fb-5e9834ad1ea8 | section | Review and sign off |  | New section
f5b2e402-e4a3-4f6b-8ded-05860cd6a73e | checkpoint | Area left clean and tidy |  | New checkpoint
be0ff889-1683-497d-b443-d10256dcab9a | checkpoint | All installation work completed, checked and reviewed as per specifications |  | New checkpoint
84bf2986-9f0b-4fc0-a03b-cec9d51ae25d | checkpoint | Client/main contractor sign off |  | New checkpoint
ad255f4d-d2e4-4ee1-a00e-9ce89c5561ae | checkpoint | All installation work completed, checked and reviewed as per specifications |  | New checkpoint
44e3f277-e2db-468c-b926-6e835477ec7e | signoff | Client/main contractor sign off |  | New checkpoint