## Master List Templates
Id | Type | Name | Values | Prompting Name
95ac2946-a5ff-4921-9542-de380bfe7b01 | checklist | Add Daily Cassette Log |  | Daily Cassette Log -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
2429362a-7360-4e48-b037-9bc798594a84 | checkpoint-no-value | Date:
e5ab19af-90b5-4328-9a8b-ee0707087643 | textbox
1eda46e1-bc31-44de-a728-b1b2daa2a00f | checkpoint-no-value | Cassette Number:
8e11a44b-51f7-4a8f-9494-ec9e467452ec | textbox
a9865b08-ef1b-4676-92fe-5d5dc48b14ab | checkpoint-no-value | Record any delays:
22cd20b8-86af-49a9-97d4-39d5b860ca1a | textbox
535e955d-759c-4d47-bb8d-df47da150f3a | checkpoint-no-value | Wind/Weather Conditions:
5114a122-dcf7-44a7-be38-8623182196af | textbox
ff116188-34a6-4484-8575-6996b8d6a91a | checkpoint-no-value | Comments/Issues/Observations:
a6aebd36-6433-4aca-b8f4-ef6216c059cf | textbox
8c4914dd-74d4-4a55-bda6-a6040c08eab7 | checklist | Add Dayworks Checklist |  | Dayworks -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
672f7ac1-ee66-4860-80e7-e8ad8a72c774 | checkpoint | Day Work Details
d27d8079-cce6-47f2-bc8f-5447bd0b63c3 | textbox | NTSC / SI #:
d63889f7-ee5a-4b1a-8284-614d5f938189 | textbox | Labours (HR)
926bb36c-59db-4b70-828c-6bc1bf2ce049 | textbox | Work Description:
693bbb1a-ade5-4140-a549-223cae16f4cb | textbox | Materials:
6d1abe7d-16c2-45ff-b354-7f74775359b8 | textbox | SWP Representative. Prepared By:
7e548609-67fa-4b3f-91fa-027d546e556f | textbox | Client Representative. Confirmed By:
acdcd675-97c3-4d51-9f49-4908499e6c30 | signoff | Request Signature Signoff
c2549456-1224-46ad-929e-321839ac1cdd | checklist | Add Defect Checklist |  | Defect -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
816bf434-035d-4c1e-8ae5-8db7a6827e04 | checkpoint | Defect details recorded
9b18e909-7530-4d08-ad54-acb417409980 | textbox | Explanation of defect:
3af60290-922d-4e09-aeb9-b795186cbbd5 | textbox | Area:
da7b5fcc-182d-4ccf-ade5-02dfaae6dedb | textbox | Party responsible for damages:
f37cdc9e-47d2-43c7-b8ce-36034d624bbc | textbox | Efforts required for repair:
16d78d9b-0a7d-4e07-bb38-68e664e6d30e | textbox | Man hours required for repair:
691822a3-eb41-4ca2-a294-1ace94dd5379 | signoff | Request Approval from Main Contractor
d75e4435-3f1c-4efd-88fd-3c14f024ff23 | checkpoint | Defect Fixed
be38c8bf-dda3-42f5-9c67-65126f0a8e3e | signoff | Request Defect signoff
1d099947-2b08-4cdd-8671-b5e81d25ab28 | checklist | Add Delay Checklist |  | Delay Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
702465d2-0fe4-44ab-b649-0cb753f4929f | checkpoint-no-value | Delay details.
ae5b692f-ee75-4a3d-90e7-43a6b2bca49e | textbox | Date:
8e11a44b-51f7-4a8f-9494-ec9e467452ec | textbox | Description:
22cd20b8-86af-49a9-97d4-39d5b860ca1a | textbox | Area/Grids:
e5ab19af-90b5-4328-9a8b-ee0707087643 | textbox | Wind/Weather Conditions:
a4fa5854-c40e-4098-aa98-12e1105fde3d | checklist | Add Final Inspection Checklist |  | Final inspection
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8e041c66-1944-4e3b-93a7-852cb585f573 | checkpoint | Final inspection
5c48b2f9-7155-5010-a625-9c61273b1f4a | textbox | Date
cd590b2d-dfd9-5926-aa7f-cbbffee96ba3 | textbox | Area/elevation/grids
f185db39-ef5a-566f-a627-b84ed061402b | textbox | Description
bc73c8d4-7e08-5fa4-a4f2-97028cc937d1 | note | Attach Photos
4f1005cb-4ee4-4c32-a03c-38127ff3cee5 | signoff | Request Signature Signoff
5fa9fe1b-6373-4ce1-9f0d-5b3d1ac548d0 | checklist | Add Flood Testing Checklist |  | Flood Test Area:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e0ea2272-9dcf-4c81-a369-f62123247e35 | checkpoint | Is area fully finished, QA’d and ready to be tested
99440e2a-5ce2-4dd5-a79a-0c6c6a75e82c | checkpoint-no-value | Flood test details
dc968f8f-9cf1-485a-a65f-e4087427ee32 | textbox | Date:
b0fb2bc4-3c3c-47bb-93fe-add4a651804d | textbox | Area tested:
befd486d-6456-4e39-ba95-1395566ebfda | textbox | Duration:
3fff6840-5866-4f4c-96c8-494f7e9efd79 | button | Have you checked regularly for leaks | Yes, No, N/A
050fef10-15f2-4590-ba62-2a0b1b1b0a29 | button | Is there rain in the forecast | Yes, No, N/A
b9de0cd4-9c7a-42cb-89ee-535d7ebdcd00 | button | Have all leaks been repaired | Yes, No, N/A
e4d1c39c-4b0a-49ea-85eb-1e822921871d | checkpoint | Flood test complete
5d04628a-e7a1-4bd7-b9ee-92a88ef12e94 | button | Have the plugs been removed from the drains | Yes, No, N/A
b74c91b9-0371-4641-ad5b-1c9d76ee0c77 | button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
73725ecd-b091-4667-93a7-7847c8438080 | signoff | Sign Off
e1f68669-3868-404e-accc-d916463043f3 | checklist | Add Variation Checklist |  | Variation Details -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
01f920e2-53fa-4a29-a5f7-b7e0a75de6ef | checkpoint | Variation Details Approved
28d26279-c304-4689-8317-1deb797dc8fe | textbox | Reference/Drawing/Instruction Number
2247155b-6de8-434c-a1e1-058d724a6a62 | textbox | Variation Area
ae7fc046-dca9-4fab-98f8-374caeb044ec | textbox | Materials & labour breakdown
3bd163d1-6cff-4d16-9f0a-0e98dc9d3169 | signoff | Request Variation Acknowledgement
0d626ac2-dc64-42f9-8151-b6d29b2bacd5 | checkpoint | Variation Completed
577bc738-456d-4241-b02e-850a66d781d6 | signoff | Request Variation Signoff
42fc4a4e-84bd-58ad-9a45-f2488184e204 | checklist | Fibertite Roof Overlay with PIR board |  | Fibertite Roof Overlay with PIR board
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
c0e9bd74-e7d8-5ee9-bae7-2272d9eaa5db | checkpoint | Area Accessible
0c87dabb-bb9c-53eb-a34b-a5354f8a9350 | checkpoint | Edge Protection in place
972a70d5-b3c3-5494-84a9-2f8250951f7c | checkpoint | Substrate ready for SWP
691ae12f-acc2-5904-80b8-90c3607eed06 | section | Substrate
4bbe7c4d-d166-5058-ac30-35970395face | checkpoint | Clean and wash down roof
743d695f-4269-5205-a9f2-153b9020999a | checkpoint | Mechanically fix existing roof pans to each purlin (1 fixing per pan 20mm class 4 steel tek)
f6c73b31-8ee0-5429-901f-6a6496757e86 | checkpoint | Skylights covered with plywood (by others)
aed7152d-8ab9-5172-b870-cb0253cef682 | checkpoint | Removal of ridge/old tray flashings
5b030369-a815-5423-9d64-e52a59fc1d21 | section | Roof pan infills
756b061c-3488-5273-b29f-3f96c74f542e | checkpoint | Install trough infills (50mm PIR fillets)
5b609b25-2801-5de5-8547-7157a8e9cf08 | checkpoint | Butted together in every pan
74992dd5-bd56-548b-8e51-da93d8ef1aa4 | section | VCL
cd888f55-8a1b-5d0c-8288-428e428a4d4b | checkpoint | Surface/substrate dry and clean
466eec61-37c9-5794-8df0-601bdb2e43f0 | checkpoint | All areas covered and lapped a minimum 100mm
c76f2066-dce6-5a14-95e0-1f0480ff3e3e | checkpoint | All holes/penetrations patched and made watertight
56f3e634-b514-5240-8e08-cf3d021c39c4 | section | PIR Board
2477f1f4-2b6d-52de-a113-bf8fefbfbd00 | checkpoint | Substrate/surface dry & clean prior to being installed
d233c62e-d7fc-5559-a846-b8b60d11e882 | checkpoint | Boards tightly butted
c4e5c927-5e99-54f6-8c5b-29d460431864 | checkpoint | Correct Screws and load washer used
01d8a1da-0f1b-5d52-9816-77051de620b4 | checkpoint | Installed as per wind uplift fixing plan
b3098a4e-2d2d-5531-8d33-62cd3a06eec9 | section | Fibertite
4085aa83-c9b3-5afa-832b-39ce23bc81a9 | checkpoint | Correct Glue being used
d9f1de24-05fd-57db-81fd-a4868a881abf | checkpoint | Fibertite glued to surface of PIR
88678fa1-ad90-58bd-955c-52a39204d991 | checkpoint | Broom/rolling of Fibertite
cca6ba74-d669-5290-b383-3559ec5abb5b | checkpoint | Wipe/clean laps with acetone prior to welding
50a1283a-c71c-5ace-abc3-dc5d8f3efa22 | checkpoint | All laps, details, penos fully welded off and QA'd with probe
3dd8790a-fc1a-5fd4-b101-b2e26dba5385 | checkpoint | Clamps / rings / baskets installed
6096719d-32c8-566a-b182-0f3c3a3accfb | section | Fiberclad Flashings
d28888df-f527-5879-a21e-8f8c497bcab4 | checkpoint | Installed correctly
dfb0890f-baaa-5bc1-bd5a-09802dd7616a | checkpoint | Fixed according to supplier recommendations
e068753a-292a-57cf-8a55-8dd8f44c9027 | checkpoint | Cleaned and wipe prior to welding
ce092601-e1a9-57ea-b3f5-1dfd266dda22 | checkpoint | Fibertite fully welded to flashing and QA'd with probe
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
7522b949-ffcc-5857-970f-1d5304735f76 | checkpoint | All installation works complete, checked and reviewed
b2a64aa1-bf30-568f-bbdc-39eae2319671 | checkpoint | Client sign off
b153f164-796e-4f4e-8620-90d7fb88cc39 | checklist | FiberTite to concrete checklist |  | FiberTite to concrete checklist
9ebe2621-da73-4ff5-9aa7-7b80ad239fbb | section | Pre start
8fed1918-07a4-428f-b6ae-d0bf2bdb996b | checkpoint | Area accessible
621190a6-32fb-4dcb-a810-4dcca4ef4f02 | checkpoint | Edge protection and safety installed
def8a313-cbe0-4360-ace0-23d7cdfbc3c6 | checkpoint | Visual inspection of substrate ready for SWP
e68b87dc-1a6c-4824-85b1-c2abc4b70616 | checkpoint | QA document received from previous trade from main contractor
6de8284b-4bdc-4710-a0d8-8a911eb47305 | checkpoint | Large holes filled with grout by others
c06add2e-055b-452f-a826-18559e6a8f0b | checkpoint | All lumps and sharp concrete bits ground/hammered down
282108d7-65b7-4c19-b914-05d0c74692a3 | section | Concrete substrate
01520c55-7be0-414c-a6b0-41fe7821bd03 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
a82272f8-c4d5-418e-a5e7-1f194e9a9615 | section | FiberTite
051fcda3-16d8-4f49-9218-1088a43dd5a1 | checkpoint | Prime substrate where required
39524385-3de4-4a6d-af9c-328c8b133737 | checkpoint | Adhesive installed to substrate
c71eea11-e1b6-482f-9f8a-17868f99cef3 | checkpoint | Laying of membrane into adhesive
dfd345a8-be85-4d95-9eec-eb7cd88a08dd | checkpoint | Broom/rolling of membrane
ebd9ca1a-0af4-4963-b29b-90d05e5cea33 | checkpoint | Wipe and clean laps prior to welding
b666d821-089f-47a3-b965-f8efee8c4761 | checkpoint | Test weld with welding machine
8fb5da68-658a-459d-aef9-21bbc1e5932a | checkpoint | Probe of seam with QA hook
3628e6c6-dfc9-44b9-a6d9-840535251846 | section | Sumps
2db72287-72da-495c-b01e-2a9a11434351 | checkpoint | Sealant installed to dropper flange under membrane
1934d81a-33b4-4630-af34-8b8553eba61b | checkpoint | Membrane dressed in to outlets
bfa99aa7-566b-476c-bbe5-b656f14008b9 | checkpoint | Clamp/rings/basket installed
0a0e9f8f-0459-4e54-b918-f2cb8e107616 | checkpoint | Flood test
0716bf58-8f45-400c-a90d-8106f7192e49 | section | ILD report
564a02b4-1638-46f9-bc28-cdafe5fcda06 | checkpoint | ILD report
177aa82c-1a90-416d-a7f9-4643ab1ea3c9 | section | Fiberclad flashing
5b13a66d-7fd4-4826-95c9-b25fb7973e67 | checkpoint | Installed correctly according to specifications ( right way around )
9f1acd2c-62d1-4bd9-9676-ea7cd5a46d97 | checkpoint | Fixing and welding done according to specifications and details
3ac60552-0ae1-4793-a7cb-90f460e5cbd9 | checkpoint | Probe of seam with QA hook
620269c1-2346-44e6-b929-e8621ebb40ce | section | Pressure bar installed
2af6c291-f3b4-449d-b954-681432420764 | checkpoint | Installed correctly according to specifications ( right way around )
b20e7ecb-fff8-4b27-89d0-f379445b61e7 | checkpoint | Fixings done according to specifications and details
8fa7c096-c7f2-4568-8f5f-81eba97670d9 | checkpoint | Prime of Substrate where required
d74629b6-315f-4108-a3c5-0bc013b1ac6d | checkpoint | Sealant installed
93e3f8a4-16f5-447e-bdbf-48963a7706dc | section | Over flashings
afb6b298-d096-48d9-b9c7-653b33cb79b0 | checkpoint | Over flashings has a separation barrier
0e09356e-0aea-4b0b-bbab-a57a7366fe1a | checkpoint | Fixings done according to specifications and details
c8fb20db-2dbc-403d-9542-f72ecd414fd5 | checkpoint | Primer of Substrate
6ed3e255-9491-4519-b182-34a4dbd20728 | checkpoint | Sealant installed
e0764b1a-1530-4ba9-9874-7e074b4b991c | section | Review and sign off
0a8d1372-97b6-46f9-b9c3-4cd1f9f19ca7 | checkpoint | Area left clean and tidy
df1a5ea9-eafe-49b8-b236-5110391ff1b9 | checkpoint | All installation work completed, checked and reviewed as per specifications
0bc3e555-729d-4655-bb50-97a75e014d50 | signoff | Client/main contractor sign off
caa721c8-6d50-46e7-b898-b046b0c7a4bd | checklist | FiberTite to plywood checklist |  | FiberTite to plywood checklist
00313603-82ac-4882-a52c-7d1314c0fad8 | section | Pre start
5ab9ec82-2956-41d9-a3bf-009004e1d27b | checkpoint | Area accessible
bf82f763-37d7-4a5c-bdd6-bfe4f20fbffe | checkpoint | Edge protection and safety installed
8669f0fe-e9b6-4e1c-9989-e60dc00da251 | checkpoint | Visual inspection of substrate ready for SWP
eaa72fb1-fb74-447d-8375-aa5f4fad8997 | checkpoint | QA document received from previous trade from main contractor
b1ef6b23-1df3-4c4c-8c50-9acbeeb6f9d3 | checkpoint | Visual check no screws/nails/fixings popping up
8c858034-0eb5-4d9e-aa61-32d0893d491e | checkpoint | Visual check that joints are flush and even
ec41d241-653f-4000-b3b2-a6e376716d35 | section | Plywood Substrate
11ade12d-26eb-424f-9ba7-4f897b0abfee | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
ecbcfb9b-f794-4543-976e-8b1ee3c14377 | section | ILD Mesh System installed
cd76e72b-f5b4-41eb-9d76-40aecd104bb7 | checkpoint | ILD System installed as per specification
1aa396ee-3473-4f35-b3c8-bf8b725aaddf | checkpoint | ILD test plate installed
de1216ae-cf90-4155-94a9-4cdb148f8fc7 | section | FiberTite
a96e6840-0128-443f-b595-55024883f98e | checkpoint | Prime substrate where required
a6ae10c3-33f6-4e98-8e40-79cf8ce1167f | checkpoint | Adhesive installed to substrate
ba9765bc-884b-419d-8ae0-7c0381650e10 | checkpoint | Laying of membrane into adhesive
0b4b2c17-c113-4baa-89ef-2c2794916c48 | checkpoint | Broom/rolling of membrane
5f3ed1f4-d832-44fa-8493-cdf5b66b754b | checkpoint | Wipe and clean laps prior to welding
a2f78744-e1be-4ecc-a94f-61ef6a0b4e41 | checkpoint | Test weld with welding machine
acb70640-8c61-475e-979a-fd5930dc6ed3 | checkpoint | Probe of seam with QA hook
5e8c22dd-5234-4850-9b70-3efb3da82089 | section | Sumps
ebc1a685-8861-4857-8af6-9a3adc77aa5b | checkpoint | Sealant installed to dropper flange under membrane
1ae2494b-6763-4d4f-b6d5-c6ae429c3464 | checkpoint | Membrane dressed into outlets
abafeef3-a51f-45f6-be12-eb82d6baadc3 | checkpoint | Clamp/rings/basket installed
f0d8549e-c57d-4e95-8f9e-22d3d979970e | checkpoint | Flood test
b1ac06d0-2bd6-4351-a975-c31ab760f525 | section | ILD report
fe822ec4-7f61-4738-b643-1c2ae62c9aef | checkpoint | ILD report
074a1f75-31e5-4cd9-8fbe-34d04da7b075 | section | Fibre clad flashing
22c1d0c0-27cc-4f30-b5c5-1a2d4b1f9189 | checkpoint | Installed correctly according to specifications ( right way around )
e2a8c962-53c0-4a6b-9771-59b8167a40cc | checkpoint | Fixing and welding done according to specifications and details
58be0a37-c9ae-420d-81b0-af4ba905cc46 | checkpoint | Probe of seam with QA hook
8f1eaf3d-8af3-4d7b-b250-c6c4e5cfc129 | section | Pressure bar installed
2568729a-4910-4317-acae-b9bb80457a17 | checkpoint | Installed correctly according to specifications ( right way around )
4119e689-7477-4859-9682-c63ceebb7d22 | checkpoint | Fixings done according to specifications and details
41f1bdee-a1a9-446e-a11e-24544f7c8047 | checkpoint | Prime of Substrate where required
517d406f-752e-4b1b-857a-855c2d1836f8 | checkpoint | Sealant installed
5b00f75c-9bcd-43e9-9aa3-4e6c30ecffa0 | section | Over flashings
c1bea8aa-8410-4862-92bc-72de0081cc7f | checkpoint | Over flashings has a separation barrier
4c4c12a1-e81d-4a11-8076-eee5620e2343 | checkpoint | Fixings done according to specifications and details
6ce56adc-d0da-4522-b309-b6e158e6fa46 | checkpoint | Prime of Substrate where required
664b9daf-135a-49cc-bd5e-b9148f641406 | checkpoint | Sealant installed
1c3cf797-f1ef-410b-9678-d7d5c2b3a7ab | section | Review and sign off
64921976-9a43-47b9-a9e1-39f55527a3a4 | checkpoint | Area left clean and tidy
f4e087ba-f55c-41ce-a6fe-f592ae3eaf37 | checkpoint | All installation work completed, checked and reviewed as per specifications
591171eb-22c2-4ea8-a358-9af336ab9e06 | signoff | Client/main contractor sign off
844a43ff-df57-41ea-8bed-69d17eb30949 | checklist | FiberTite to plywood warm roof checklist |  | FiberTite to plywood warm roof checklist
133cd66b-332f-472a-8c11-7e3306cec15a | section | Pre start
2fa5cda7-fe11-4f3b-8def-7db6205dc7a4 | checkpoint | Area accessible
e0ac4484-8f95-4fe8-ad89-5a06ba657ac1 | checkpoint | Edge protection and safety installed
90ae8537-a3b5-44a4-980f-00adbc594ee7 | checkpoint | Visual inspection of substrate ready for SWP
a434e44b-447b-4fc6-8c6c-e78e5ea6f62b | checkpoint | QA document received from previous trade from main contractor
90ad3e90-5cd3-4f90-87c6-03067cd470ae | checkpoint | Visual check no screws/nails/fixings popping up
34697c9a-dff8-4a1b-830f-bc6361abfefc | checkpoint | Visual check that joints are flush and even
94363565-fb45-4311-8bf4-0d180a323158 | section | Plywood Substrate
d4f4f76d-8887-4b00-bb0c-5d19f3a1d556 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for VCL
e9eba217-b3b3-4b73-8534-cf27b3733ac9 | section | Vapor control layer
5faeeaec-c0c7-4d23-96d0-cf6032b01c81 | checkpoint | Substrate clean, dry, free of debris
b4bd2628-8a2b-42c3-9c86-200989c77c25 | checkpoint | Z flashing installed
30653fd5-9648-442f-8c7e-4bbba3514262 | checkpoint | VCL installed and covered all surface
1578d074-b173-46ec-a157-b5590a4c7459 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
49b9533b-09b2-4b0c-b004-10efbd0ac4a2 | section | Insulation
02c165d0-5ea3-4ca8-b766-d7b75eedaed7 | checkpoint | VCL clean, dry, free of debris prior to install
56cd97dc-94e3-494e-8dc5-aa7ffeb61053 | checkpoint | VCL has been checked for damages and repaired
16b59a26-c227-4db5-ab88-f6932d922578 | checkpoint | Closure flashings installed correctly
c2db62af-fa60-43e1-aa4d-047ea244be10 | checkpoint | Specified insulation board installed
4372fea2-256b-452a-bcc0-84d6269ca292 | checkpoint | Boards tightly butted
9cec61f8-3b74-4852-aa23-d56ec33bcb4d | checkpoint | Fixing plan attached
2744928b-c2fc-4404-a98a-95dca9d03827 | checkpoint | Installed as per fixing plan if no HDP board
44f8ee33-dcea-46d6-aaf6-9626c9ce86ca | section | ILD system installed
e4abafba-3590-4e03-b474-5c1c8cd5c3b3 | checkpoint | ILD System installed as per specs
fa62ca84-8849-4e5c-9297-ad8f87c40659 | checkpoint | ILD test plate installed
bea06c51-8c9f-4778-9832-722fafd6856d | section | HDP board
5edbbf40-2f34-4bc6-8d92-49c9010eeab4 | checkpoint | PIR clean, dry, free of debris prior to install
2083eb4f-94f5-46b3-a18b-1f1644a3a6c8 | checkpoint | Fixing plan attached
c62ca6ee-dbb3-47fa-88d8-db8b15558209 | checkpoint | HDP installed tightly butted in brick pattern
3fde17ef-dbaa-4dec-b70a-c231ad8f750b | checkpoint | Installed as per fixing plan
4e0cd257-5f16-459b-a13c-490155370090 | section | FiberTite
b79b75a9-5a55-4655-bf22-d354ff5e04a5 | checkpoint | Prime substrate where required
04abee32-e505-4c56-a553-938272b186bb | checkpoint | Adhesive installed to substrate
61b91289-e81a-4fcc-b361-15ae3d98c249 | checkpoint | Laying of membrane into adhesive
19ae5b12-3612-4341-a65a-40a91d685809 | checkpoint | Broom/rolling of membrane
e546864a-3d2f-4a79-92a4-a5fbdf75abcf | checkpoint | Wipe and clean laps prior to welding
162247d9-e92c-41d6-a787-2ce253b1e0ce | checkpoint | Test weld with welding machine
7a595469-ed82-40a0-a479-47c96f0d3514 | checkpoint | Probe of seam with QA hook
8fed1978-e9e1-42b8-a4e0-7f0a3869e52a | section | Sumps
c62e0aba-eb24-4bab-8447-8613bf3970de | checkpoint | Sealant installed to dropper flange under membrane
4f98d308-5668-4bfb-98f6-341b7217f59e | checkpoint | Membrane dressed in to outlets
b1026047-5a8c-4d9f-803a-55fe2a722666 | checkpoint | Clamp/rings/basket installed
14656bc1-8a89-44c6-855a-1883572b22e4 | checkpoint | Flood test
8da2cba2-024e-43b7-8b13-c0793a50342c | section | ILD report
4a1679f7-10f7-4a56-8d1b-99e849972a31 | checkpoint | ILD report
187cdd79-ee2e-40ab-92ea-45d7b44210c4 | section | Fibre clad flashing
82e72d85-759c-4784-b3e4-955608724e39 | checkpoint | Installed correctly according to specifications ( right way around )
af84eee2-53be-4e45-b929-2dd090a01ea0 | checkpoint | Fixing and welding done according to specifications and details
2433353d-6623-4e63-8091-5b359e63e31e | checkpoint | Probe of seam with QA hook
835d3f58-6b7a-4cbb-838f-35927ea0c09f | section | Pressure bar installed
f41764e8-7493-4869-9a20-44ebf5d3ad5d | checkpoint | Installed correctly according to specifications ( right way around )
92318ff6-a04d-4255-930b-1270eb220050 | checkpoint | Fixings done according to specifications and details
d61abf8c-6523-4dce-a550-3b9700fcef82 | checkpoint | Prime of Substrate where required
180958c4-6dee-43e1-b6ad-e7dd31efd532 | checkpoint | Sealant installed
2a5ca425-a854-486b-9a39-9f1885a1fe9b | section | Over flashings
f076fa08-71c8-4f9b-b676-15c7fb99770b | checkpoint | Over flashings has a separation barrier
16c8062f-0e9b-4e6c-84f1-3515888c1b53 | checkpoint | Fixings done according to specifications and details
45699fe5-ef79-4f39-9915-ada9fabd9f1e | checkpoint | Prime of Substrate where required
b9c31ac5-3018-4c8c-9d9e-7ef76f23e36b | checkpoint | Sealant installed
15f74147-3602-4358-9b5f-981473f6c417 | section | Review and sign off
f1c7f2c4-2ccc-4a3a-92d1-39c7c856c3b6 | checkpoint | Area left clean and tidy
b5e2fc3a-2d08-4fc4-a093-45c6d20e3900 | checkpoint | All installation work completed, checked and reviewed as per specifications
d65962ab-e55d-408b-9915-2047c12e4635 | signoff | Client/main contractor sign off
d9855c80-b9a6-48e4-8135-ac6cc4c31e02 | checklist | FiberTite warm roof to Base deck checklist |  | FiberTite warm roof to Base deck checklist
74dc71a7-9bda-4073-8c23-44b5824e35ab | section | Pre start
de36d7fa-2818-45e5-b4f2-bf6d9763cf54 | checkpoint | Area accessible
b93baed9-9d4f-4d1a-8a34-059d6e696aa7 | checkpoint | Edge protection and safety installed
42a98d71-1941-46ec-a00b-880b4d40695a | checkpoint | Visual inspection of substrate ready for SWP
df086865-5ab3-44b3-bec8-b11a110ce204 | checkpoint | QA document received from previous trade from main contractor
0dd5dd56-cb92-4492-bb0b-7e966c9cfc1f | section | Metal deck
affb2eac-76ac-42b7-a3b9-f20304335143 | checkpoint | Base deck screwed down in every pan and every purlin
623cad35-bbb8-4e08-bb13-0ab3f7fc86a2 | checkpoint | Base deck laps stitched together at 300mm centres
a21d9fd2-8501-4074-88e8-80126dc704c3 | checkpoint | Correct fixing
ec711c62-cf3d-4eb7-bac6-2b707c7b406a | section | Vapor control layer
41a3f136-efc0-4890-b485-45f4b0157e9e | checkpoint | Substrate clean, dry, free of debris
13c36237-1882-417e-b800-1828d6439cc5 | checkpoint | Z flashing installed
d4be9162-0a03-4a53-8200-f98e86638d3e | checkpoint | VCL installed and covered all surface
dceee2ce-d807-4935-ab36-d9f334c0cfac | checkpoint | VCL lapped with a minimum of 100mm side and end laps
83a5416e-1799-4699-a6f7-3a3d120d91ee | section | Insulation
63052c81-eb2c-4409-b8cd-1de4704a8c38 | checkpoint | VCL clean, dry, free of debris prior to install
3eaff7f8-b538-43f0-aea6-788f7d984d55 | checkpoint | VCL has been cheeked for damages and repaired
0faf0f4f-eab6-44c7-8b36-042d48f4ee99 | checkpoint | Closure flashings installed correctly
11116349-ff98-4a27-83f4-9d5897992ca2 | checkpoint | Specified insulation board installed
244ae483-bc84-4330-8c52-fcc47ed9b194 | checkpoint | Boards tightly butted
1e7c4f33-9c3d-4030-87d5-bcab0c217448 | checkpoint | Fixing plan attached
cc24db4a-ccd5-4b1a-bf6d-9914d6fa0ca6 | checkpoint | Installed as per fixing plan if no HDP board
0cd83069-ba88-4604-97ad-e6384e472761 | section | ILD system installed
fb58216c-fa8c-4194-afd1-1e6ada846960 | checkpoint | ILD System installed as per specs
b2800a83-d0d4-4b20-8dcb-1e54905bb146 | checkpoint | ILD test plate installed
37f889e0-ba75-4202-a22a-156857756841 | section | HDP board
01de1a48-cb7d-4637-bcf6-25aad5b1f86e | checkpoint | PIR clean, dry, free of debris prior to install
fd85bc62-10e7-4402-a39a-ec5697c2277d | checkpoint | Fixing plan attached
6eac79f7-3e3d-49bd-a6c0-7335c1023c25 | checkpoint | HDP installed tightly butted in brick pattern
890797c3-adbc-4ca6-a2cd-6eb7694af3fe | checkpoint | Installed as per fixing plan
51859438-258f-45e0-94a5-8bf47db61286 | section | FiberTite
3ccd9ecb-4c75-477e-914c-a03caaa694e6 | checkpoint | Prime substrate where required
9c0b3302-84ea-4464-9439-da88c6c8fe17 | checkpoint | Adhesive installed to substrate
e140d845-820a-4487-8c3e-e0c632ee17e9 | checkpoint | Laying of membrane into adhesive
906538f9-b55c-4951-8681-1f165d117e05 | checkpoint | Broom/rolling of membrane
88099512-d243-4f57-99a9-6cadf63ceac1 | checkpoint | Wipe and clean laps prior to welding
8fe0e89f-f6c6-43d2-91ba-addcc1caeb7c | checkpoint | Test weld with welding machine
dd9a8fa4-f4ed-4742-95d7-056a0958abb2 | checkpoint | Probe of seam with QA hook
d23b5304-bf82-48f2-aa82-be14f2ab4198 | section | Sumps
be455776-0a71-4fcc-90d7-e99fa3ac5e3b | checkpoint | Sealant installed to dropper flange under membrane
9ae9d59b-ba2c-4172-8146-a42b0d339e5a | checkpoint | Membrane dressed in to outlets
3f41feeb-1218-4d02-ba53-a61ad8b75d18 | checkpoint | Clamp/rings/basket installed
72b890b7-23c3-4ec1-9b3e-2b4139c542cd | checkpoint | Flood test
9941f6ba-6d70-4c50-8e36-9dccf41939e3 | section | ILD report
c5bc3992-a38b-47bc-9821-bd9112d61353 | checkpoint | ILD report
ab57b5f5-78d3-4930-bef6-622da17ec8c5 | section | Fibre clad flashing
0eb5e713-4b5d-42e0-af3f-52be00b32b5f | checkpoint | Installed correctly according to specifications ( right way around )
be508422-a425-4a1d-9a22-202b6e0530fb | checkpoint | Fixing and welding done according to specifications and details
b3bb3808-acad-48c2-b640-5739fe4491a4 | checkpoint | Probe of seam with QA hook
5be381d0-60b0-475d-91b4-ea9346bd9d0c | section | Pressure bar installed
a47f6505-3ea5-419b-8071-2257b8718766 | checkpoint | Installed correctly according to specifications ( right way around )
e46ab990-28c4-4974-ac99-905a6c753aef | checkpoint | Fixings done according to specifications and details
57f86877-4794-4dde-b88f-1cb8c1429a3b | checkpoint | Prime of Substrate where required
971083d1-bac8-42d1-9cca-a57bc13c0d4c | checkpoint | Sealant installed
fbe7cb25-cd4b-4229-a6b2-c8030cf7b05f | section | Over flashings
1e7b43b8-4101-4f85-8da9-bd69eee594af | checkpoint | Over flashings has a separation barrier
2c0716cb-ab90-4b5d-b9b4-1c647edc7f51 | checkpoint | Fixings done according to specifications and details
f8dafa97-f460-4c97-b8ec-fb97811eec34 | checkpoint | Prime of Substrate where required
a8f73413-0c3c-49e5-90b0-75e4e7476287 | checkpoint | Sealant installed
1fe182bc-cb97-4599-85fb-5e9834ad1ea8 | section | Review and sign off
f5b2e402-e4a3-4f6b-8ded-05860cd6a73e | checkpoint | Area left clean and tidy
be0ff889-1683-497d-b443-d10256dcab9a | checkpoint | All installation work completed, checked and reviewed as per specifications
84bf2986-9f0b-4fc0-a03b-cec9d51ae25d | checkpoint | Client/main contractor sign off
ad255f4d-d2e4-4ee1-a00e-9ce89c5561ae | checkpoint | All installation work completed, checked and reviewed as per specifications
44e3f277-e2db-468c-b926-6e835477ec7e | signoff | Client/main contractor sign off
fbcea8a1-c74d-4972-b92f-7243bd33eda9 | checklist | FiberTite warm roof to CLT mechanically fixed and adhered checklist |  | FiberTite warm roof to CLT mechanically fixed and adhered checklist
88a26f50-6376-49d4-be66-211dd5120225 | section | Pre start
5db49482-a4f7-460b-a676-7d39f536e856 | checkpoint | Area accessible
7dc471a6-136b-4fa3-ab06-ebf263a0f57a | checkpoint | Edge protection and safety installed
e0e11a70-7637-4893-950c-8d848b684c53 | checkpoint | Visual inspection of substrate ready for SWP
73c7b3e8-d65a-42e4-b402-f78a273c1b65 | checkpoint | QA document received from previous trade from main contractor
41132fc8-d697-4b6b-bf0b-5a9e4bac7db1 | section | CLT Substrate
b4148ec8-6abb-40f9-887b-96fcca0f580e | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
4afed653-af8b-4b41-a3f3-99f94eb820e6 | checkpoint | Installation of SA primer
d992003a-2e56-439a-bd08-5898c61720cd | section | Vapor control layer
20cf5d4d-6552-4c87-a788-ac8174b34d2a | checkpoint | Substrate clean, dry, free of debris
2755f2c3-faa7-48fb-8e73-a992b168ce4f | checkpoint | Z flashing installed
b6df68b2-3607-4bac-ab47-b6df805ad28e | checkpoint | Install VCL over primer
3648013f-4f12-4877-8528-7e2ffd327bc7 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
f2535f0a-1060-4211-b198-f483f50979b8 | checkpoint | Installation of SA primer
6244eb30-5e68-4fac-88a1-b1f9afd6f492 | section | Insulation
4f1a6b19-7bb9-48f7-b9b2-83be98f4d751 | checkpoint | VCL clean, dry, free of debris prior to install
d66c6d86-9870-46cd-bcc2-35ce989908fa | checkpoint | VCL has been checked for damages and repaired
63c63e94-2e92-4505-baec-cad09b6b0af7 | checkpoint | Closure flashings installed correctly
34c7de4a-0822-4a3f-85b2-966e98eff462 | checkpoint | Install board adhesive in specified pattern
572eeba6-3fa8-4341-8d39-8d49618e8afd | checkpoint | Boards tightly butted
2feedeeb-9ac7-4e4e-8f26-3e525db127a6 | section | Tapered EPS
da31d421-b320-4fcb-bfb1-cd77a454fddd | checkpoint | Insulation boards clean and dry. Free from dirt/debris ready for adhesive
40bff704-c1b6-4bc2-a47b-23eee1cd0da4 | checkpoint | Install board adhesive in specified pattern
29ba92fa-09f6-4af2-98b5-50cebce50638 | checkpoint | EPS board installed into adhesive
75abc055-8462-4753-ae9b-b2f89c46e712 | section | ILD system installed
b367ab3f-f150-418d-86ca-0173f0bb50f8 | checkpoint | ILD System installed as per specs
c433ef0c-61ad-4e11-bf13-ece6dffe9fdb | checkpoint | ILD test plate installed
0dd9b4a8-2d66-4e9a-b9c4-cbb5dbfb382e | section | HDP board
456a73c5-752c-4b4b-9514-8f067de7c8bb | checkpoint | PIR clean, dry, free of debris prior to install
f36191f6-15ab-4c63-93b7-4b98335715d7 | checkpoint | Install board adhesive in specified pattern
92c6be8b-27e2-41e2-995c-97e47a839002 | checkpoint | HDP board installed in brick pattern where possible
2897a156-a4af-4550-8448-dc3e139a16fc | section | FiberTite
bad49f69-dd7d-408c-aefd-26e328afe37f | checkpoint | Prime substrate where required
07842df1-ab2c-4cb9-83ac-a9cb45967c79 | checkpoint | Adhesive installed to substrate
2103e918-3fb1-430b-9f45-00490457dc97 | checkpoint | Laying of membrane into adhesive
7e8aaab7-9b19-4038-87b3-c94babdf6824 | checkpoint | Broom/rolling of membrane
111dc409-ca81-4b80-8a7e-a6c498dfa81c | checkpoint | Wipe and clean laps prior to welding
d2b90419-1372-4202-92c3-6e0cdfafcf16 | checkpoint | Test weld with welding machine
a544cd7a-cc77-42a6-9cf0-1183efd22d09 | checkpoint | Probe of seam with QA hook
6b454415-83ac-4060-8306-40df277bbbc9 | section | Sumps
76a95269-e3e0-4471-ab84-49bf658b6454 | checkpoint | Sealant installed to dropper flange under membrane
d7908ccc-57ef-4012-a122-b3109d05260d | checkpoint | Membrane dressed in to outlets
ba4a860e-5774-4e3f-b5c0-a9d3e3c14f08 | checkpoint | Clamp/rings/basket installed
cc542873-d7ee-4ccd-b57f-278c74a0bc93 | checkpoint | Flood test
c721dfeb-2e51-4bd7-8a19-fe143ba28179 | section | ILD report
5bd6b0dc-9879-488d-a0d5-ded9ee2039f7 | checkpoint | ILD report
a0fe766b-4e57-4fd5-b187-c17f9b147a2b | section | Fiberclad flashing
9624f764-3f72-44e8-bac3-7b6edf87e299 | checkpoint | Installed correctly according to specifications ( right way around )
3d89eda4-a2c5-4844-953c-7b7ad8168689 | checkpoint | Fixing and welding done according to specifications and details
a2b96a41-7948-4aac-ae7a-9d8f4d183bb1 | checkpoint | Probe of seam with QA hook
c344467f-e038-4d50-9fcf-894faf9acfef | section | Pressure bar installed
3981c29c-bf49-4e8b-a06c-ef810f926942 | checkpoint | Installed correctly according to specifications ( right way around )
b91d8027-2bad-487f-ad97-c12bc136ecc3 | checkpoint | Fixings done according to specifications and details
4588f582-9dda-4261-b437-7f8d89a7c1a6 | checkpoint | Prime of Substrate where required
a2881292-b783-4927-9fef-c412d9911272 | checkpoint | Sealant installed
ee70c617-c0e9-46da-b1f7-f0bb2a1aaaf2 | section | Over flashings
9da97450-9843-45d5-a203-cff01d29464a | checkpoint | Over flashings has a separation barrier
681e61d2-9d2b-4ee6-89c8-146367f8d9b6 | checkpoint | Fixings done according to specifications and details
bea43fa4-2976-4d2a-b3bc-c8616b7ceb7e | checkpoint | Primer of Substrate
694f8234-6df2-44ca-b6f2-0e2abbcb0fa7 | checkpoint | Sealant installed
4483bfe2-41ba-4ada-9fdf-cf3b5f3d2515 | section | Review and sign off
841c8db0-43eb-426d-95db-f601de1e0d66 | checkpoint | Area left clean and tidy
8a4b4217-5f2d-4c0d-8b1c-39e55e73f1e7 | checkpoint | All installation work completed, checked and reviewed as per specifications
9d585c92-ebe8-4eaf-8a6f-6de4d87e5bb0 | checkpoint | Client/main contractor sign off
48870fe3-1914-4264-acad-65bf703cd90c | checklist | FiberTite warm roof to concrete fully adhered checklist |  | FiberTite warm roof to concrete fully adhered checklist
234ee8c7-a109-4b1f-a248-57d4cad2ee79 | section | Pre start
251a8f69-6fd7-4a22-a635-ef53c11abf3e | checkpoint | Area accessible
dd636da1-e14d-415c-b056-55795dd94db3 | checkpoint | Edge protection and safety installed
b3ee137c-3ec2-4f85-b883-603195813fbc | checkpoint | Visual inspection of substrate ready for SWP
73d8bf78-75f0-44e2-8715-37d071d0a7c7 | checkpoint | QA document received from previous trade from main contractor
af67550d-291c-49e7-b359-fa322d66f73d | checkpoint | Large holes filled with grout by others
9997390f-90aa-46fc-9f5f-b1aa3cf821b9 | checkpoint | All lumps and sharp concrete bits ground/hammered down
2693bf0f-0635-4713-b079-fc0f93e6f457 | section | Concrete Substrate
76497cc6-9d93-487f-a90b-23678601ef93 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
77c4635b-4be9-4544-ad22-d1639c37144a | checkpoint | installation of SA primer
05e9308e-ba09-47d2-bfd1-4e3d2797e4a9 | section | Vapor control layer
4f239c34-f09b-4625-8073-55205f93f9c7 | checkpoint | Substrate clean, dry, free of debris
0a42305c-b9a1-435c-9c6b-53b13fdb1159 | checkpoint | Z flashing installed
36efa112-66aa-4739-984b-becb6e87a2ce | checkpoint | Install VCL over primer
1496fc19-858a-41c0-895a-f81390061e22 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
fb19c759-8c12-40e5-9362-29fd9aaeb9e7 | checkpoint | Installation of SA primer
b8eec161-2d0c-45d0-bde7-3935d4d1716d | section | Insulation
63e45ef6-1551-4372-9b2d-b76168c68388 | checkpoint | VCL clean, dry, free of debris prior to install
ad3eb8a0-46dc-40de-b074-9cf0686bddf6 | checkpoint | VCL has been checked for damages and repaired
3d6a4871-ab52-4a10-b2fe-aead240e4cc7 | checkpoint | Closure flashings installed correctly
53787caa-8139-436a-a4c2-9b2fd0463be7 | checkpoint | Install board adhesive in specified pattern
0ed11690-1b65-4307-bf5f-780136f0e2be | checkpoint | Specified insulation board installed
f9e24ca6-a75c-43aa-9941-cf1668425913 | checkpoint | Boards tightly butted
0ebefe02-fd6e-4d91-8a8f-d09c19e53a93 | section | ILD system installed
3663f741-5737-411d-97a0-38c5c4b0fa08 | checkpoint | ILD System installed as per specs
06cd2ed0-dc80-4dc0-bbf8-f26c5c035026 | checkpoint | ILD test plate installed
3e29533e-3949-426d-b9d7-d94eb63a57f7 | section | HDP board
53e5aad3-2829-471b-a40b-e11058161e20 | checkpoint | PIR clean, dry, free of debris prior to install
6addceae-a579-42bb-9161-63705da307e5 | checkpoint | install board adhesive in specified pattern
96f5a39e-7ffe-4ed2-b7dc-067313ca71cf | checkpoint | HDP board installed in brick pattern where possible
64e6435a-ffcc-42ed-9145-9c49a560d2b5 | section | FiberTite
4b902ce6-2207-4f85-8603-eb7fe2063a6b | checkpoint | Prime substrate where required
a17b2e10-c679-4f68-823d-4621fcae3eb6 | checkpoint | Adhesive installed to substrate
3efe5af0-b61d-47aa-a25a-4f8c99291f43 | checkpoint | Laying of membrane into adhesive
aa1638ba-8520-46f5-a24b-b3d3bd88331c | checkpoint | Broom/rolling of membrane
d950ca4d-e53e-4f3f-9978-37f422880047 | checkpoint | Wipe and clean laps prior to welding
d76731e2-f822-4fdc-aa8d-ac46bff3b1c5 | checkpoint | Test weld with welding machine
d44487e4-8f11-4bf4-ba68-77e7d92a7008 | checkpoint | Probe of seam with QA hook
60c34037-e9cb-4dbf-bf26-4b189f5529d5 | section | Sumps
b19bf687-7f2b-4341-9f79-e6afa41f591f | checkpoint | Sealant installed to dropper flange under membrane
8fd657a7-0c62-4a89-9862-438edd3a7be2 | checkpoint | Membrane dressed in to outlets
adbc1e8a-eda2-4c0f-bc0a-ebd7b8de9ac1 | checkpoint | Clamp/rings/basket installed
283a5967-010b-46ca-beac-0a43ac75d04e | checkpoint | Flood test
367aec03-9e44-435d-8a82-8db9e1bdc77e | section | ILD report
a0138634-4c84-4f54-be80-f31a6fb91d07 | checkpoint | ILD report
ee2ec622-e7f9-4c3a-a341-d442611c444f | section | Fiberclad flashing
2cc2a029-aece-422c-9903-2748b7bbd9ee | checkpoint | Installed correctly according to specifications ( right way around )
15336044-0988-4a12-b0ea-2753565f6582 | checkpoint | Fixing and welding done according to specifications and details
fcde9f3b-d703-45f1-ab9d-f427c14ca6a7 | checkpoint | Probe of seam with QA hook
a1b848ef-ede5-46bb-b633-a3082045a4d4 | section | Pressure bar installed
528af103-b2c2-4c08-a972-212a8ea5e425 | checkpoint | Installed correctly according to specifications ( right way around )
e23e71d9-b7a0-436b-b48b-98d27adea7b3 | checkpoint | Fixings done according to specifications and details
0d93ac85-57fa-4af4-80ee-cc3619175a23 | checkpoint | Prime of Substrate where required
cb4d98ae-6ccb-46bf-8e19-43a5a3498cd3 | checkpoint | Sealant installed
f5c72c59-6b89-4cdd-bf8f-034292f2152a | section | Over flashings
6d74c3d6-2b78-4d9c-85b2-22674d5eabc4 | checkpoint | Over flashings has a separation barrier
b58e4b13-8d51-49d9-98b6-5b7335b9c287 | checkpoint | Fixings done according to specifications and details
ab1970e5-7228-454d-95eb-7802c153be10 | checkpoint | Primer of Substrate
7cb93422-aee8-4ee9-b6a1-cecd46a0990f | checkpoint | Sealant installed
5835a5d8-eabb-4723-a778-915f47b2c5b4 | section | Review and sign off
75ae54bd-5258-4ddf-8897-b72e4f7e7b4d | checkpoint | Area left clean and tidy
8da00a15-9ece-4b92-8645-a1a8a89071ed | checkpoint | All installation work completed, checked and reviewed as per specifications
3304c18f-09e9-4a28-adb4-b028e3dcbde9 | signoff | Client/main contractor sign off
108396d1-e9a1-4133-b22c-d46b7eefc26b | checklist | Metal cladding checklist |  | Metal cladding checklist
32a0ab1e-777e-401c-a015-d756e3e9d55e | section | Pre start
eb25f47d-ab88-4364-9bc9-e97e9b86b0ea | checkpoint | Area accessible
34cb7b5f-0ba0-4e84-a05b-ed5cf37b0460 | checkpoint | Edge protection and safety installed
d61ef5b0-b49a-40c0-ac1e-7e007c9af6bb | checkpoint | Building wrap installed check plans and specifications and QA / handover received from main contactor
47344df2-469f-4c58-aafa-803c883c88c9 | checkpoint | Battens installed with the correct spacings check plans and specifications QA / handover received from previous trade from main contactor
97d9f9c2-1270-4f4c-a33a-8c72a8aaa7d7 | checkpoint | visual inspection by SWP
7bb60bea-8eb7-4df1-ac84-f5ca178d2a62 | section | Rohm rails Install
fc2d7bde-6a43-497d-83df-527f43786c68 | checkpoint | flashing tape installed check plans and specifications
071690af-f5c1-4c72-8d35-599404137aa2 | checkpoint | Rohm rails installed with the correct spacings check plans and specifications
64f8862c-1f1f-46ca-a66b-4aeda0c01e74 | checkpoint | Rohm rails installed to fixing plan
aef1d140-e779-448d-afbb-521cdb497454 | section | Cladding install
08b626ee-e3d1-4488-bf16-3060a0420fa8 | checkpoint | Cladding installed plump and straight
24907061-3232-421a-bd05-842eab346f43 | checkpoint | Screw pattern according to plan/specs/best practice
c56f4d15-194e-4007-93c6-76d15fa17a90 | checkpoint | Closure foam installed
028900df-fac6-487e-b1d4-7a17c5ad7e27 | checkpoint | Top end turned up
1d24f267-8eb0-4124-8690-c2b0152f9d15 | section | Flashing install
08e77d10-fa58-4c99-8708-e980072f7197 | checkpoint | Sealant installed with 2 continues beads
d062faf1-c7a9-480f-8eab-a1d78900c202 | checkpoint | Clean excess sealant
8eb3f19d-efa8-43fc-8fdc-8e7c7cc858cc | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
380b1209-a77d-4a9b-b5cc-0f6994969f90 | checkpoint | Flashings installed as per drawings and specifications
f5b07d2f-49a5-484f-8a19-38562375a068 | checkpoint | Fixings installed as per drawings and specifications
8cb295a2-af0f-4f5e-9b73-3285614cb853 | section | Review and sign off
8c9fa421-c3ca-40c8-a72f-16ea1e5f823e | checkpoint | Area left clean and tidy
d1fc38f3-2328-403f-a844-af08dd2b7840 | checkpoint | All installation work completed, checked and reviewed as per specifications
43789a3c-4be6-440d-9b1c-97b55e0f3875 | signoff | Client/main contractor sign off
a02895fd-156c-42f0-8289-626e20f24301 | checklist | Metal gutter and downpipe checklist |  | Metal gutter and downpipe checklist
d387e558-474d-47f7-bcb3-bb441e6a8a6d | section | Pre start
059de65c-3d8f-425c-8727-4c2c982dfafd | checkpoint | Area accessible
74b880b0-1bc7-49c5-a480-001ac32e5b00 | checkpoint | Edge protection and safety installed
e8087113-7620-488f-88a9-76f039cdfd28 | checkpoint | Visual inspection of substrate ready for SWP
4e862aae-47b2-4536-a998-f4af9bd23c41 | checkpoint | QA document received from previous trade from main contractor
22627307-4886-44ad-821a-1ce51fc20a9a | section | Gutter install
a1e4f8f8-b1e2-4a4a-9654-8d379259e4cc | checkpoint | Brackets installed according to drawings and specifications
105a8862-329d-4e07-91ac-4d1c28b02aba | checkpoint | Gutter lapped and sealed correctly according drawings and specifications
b93f2978-544b-4bfa-906e-4ec516472bc2 | checkpoint | All terminations and ends folded and sealed
fa0f0cdd-0eae-4148-870e-92db4995b00a | checkpoint | Expansion joints installed
4884a454-840e-41a7-bd7a-baa3234e4989 | checkpoint | Expansion joints roof flashings installed
964f12e9-6bef-4997-8900-bd2e2cc559ce | section | Downpipe install
c823fc7f-0b5e-430c-86ad-0f5d5d699d16 | checkpoint | Correct size dropper installed, riveted and sealed
b6113e63-5f76-4e1b-9c60-5ed3c2336e24 | checkpoint | Correct downpipe brackets installed with the correct spacings
69d681c6-0463-43a5-8113-1befdefb11f4 | checkpoint | Down pipe installed plumb and straight
61df9627-d34e-42f3-bb92-0ab776216fa2 | section | Review and sign off
39790635-700b-4cd8-97e6-f250cc3c048d | checkpoint | Area left clean and tidy
a469be7c-7846-47cd-a82e-e45f1247df20 | checkpoint | All installation work completed, checked and reviewed as per specifications
06c7f57e-aaa2-4246-9c3b-df7cf1c81ada | signoff | Client/main contractor sign off
29e64ff3-1386-4c2d-97ec-af1ebb50f637 | checklist | Metal Roof checklist |  | Metal Roof checklist
1565ac63-98f8-4ba0-a09b-18651c03feaa | section | Pre start
994a9b40-6d1b-4f18-95b6-0b057c68561e | checkpoint | Area accessible
4ef8129e-0369-46d7-bff2-47447e77626b | checkpoint | Edge protection and safety installed
87de23ac-29aa-4820-9479-62abd9b99264 | checkpoint | Purlins installed and QA / handover received from previous trade from main contractor
39b2ca05-5b14-4bef-82f0-3b3a5fb91591 | checkpoint | visual inspection by SWP
b70ff7fe-69ac-411c-acb6-357a4d7de449 | section | Safety Mesh install
52693c60-5518-4f72-8ebb-53cf1c9d9252 | checkpoint | Laid and secured perpendicular to the purlins
289be0a3-8c91-412b-aa19-daba4886bd08 | checkpoint | Lap side joins by min 1 grid section
a6a883a5-39e7-47c3-8152-ae0e760157a5 | section | Underlay installed
f3c6e32d-0516-4057-991c-4b2a5ea1f828 | checkpoint | Correct underlay installed as per specifications
d21ae71a-862b-49bf-bdb7-23b20d1cce6b | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
981be350-c685-44a0-9428-ba0c397f844d | checkpoint | All areas covered
d7888825-356d-4f14-aca9-7871c72d9e7a | checkpoint | Underlay installed as per specifications
f53d9676-9fa3-4819-bbbc-a71dc39d6686 | checkpoint | Joints taped together as per drawings and specifications
1d52a5f7-b317-407a-b628-16e9fbecd98f | section | Metal roof installation
af6446f1-6ceb-4966-bccd-b887964a3c29 | checkpoint | Drip edge installed as per drawings and specifications
9efdff5f-0d78-4b85-a6c0-535a9b5765d5 | checkpoint | Laid straight and perpendicular to gutter/purlins
4ee8ddb1-f909-4a46-8a33-87d5bee5bcf3 | checkpoint | Gutter overhang as per drawings and specifications
363a1380-8fc2-441e-a621-f0a9a6a57875 | checkpoint | Top end turned up
36727fd5-76e9-4634-a59e-2b9a31ad6d9d | checkpoint | Bottom ends turned down
c2238344-0567-4ba6-926d-52f54f220348 | checkpoint | Closure foam installed
7888265c-1dd9-45a1-8f5b-97e65cfa5dbe | checkpoint | Sheets fixed in to the purlins
652afb9e-26d1-4a54-8497-5d9349b49035 | checkpoint | Screw pattern according to plan/specs/best practice
0d92e665-4807-497d-8952-098561f08ca5 | section | Flashing install
d4d69e11-7421-478d-879e-9c2909a4565e | checkpoint | Sealant installed with 2 continues beads
35531233-a4ea-40fe-a7b5-2db04ed51250 | checkpoint | Clean excess sealant
ec285f08-0d87-4e03-951e-aeeef3572c7e | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
11bdd14b-8dbe-42f9-99fa-913b486aecb5 | checkpoint | Flashings installed as per drawings and specifications
484790de-8aa3-41e1-a606-b7f95c331a97 | checkpoint | Fixings installed as per drawings and specifications
187f88d9-d4d3-4146-a181-d2307a6fabc4 | section | Review and sign off
bd4cd95c-1f15-4e51-b396-6ab5d8f421ea | checkpoint | Area left clean and tidy
1f68367b-5bda-431a-8d54-11ea6e506edb | checkpoint | All installation work completed, checked and reviewed as per specifications
33228a13-436a-45f5-bfcc-2d3edc82d7b6 | signoff | Client/main contractor sign off
29cb532b-e35a-49b2-8bf6-437ebc144e9c | checklist | MSR checklist |  | MSR checklist
69c0d79e-d0e9-45a9-b2dc-3439ec2a3b6b | section | Pre start
47be664a-d3ef-496e-b54e-3ec57444c36d | checkpoint | Area accessible
f7811a3d-3cd2-4451-a8ec-b70c05dfa902 | checkpoint | Edge protection and safety installed
6195ca74-57bc-4a88-8ee3-3114d8244089 | checkpoint | Purlins installed and QA / handover received from main contractor
8afccb98-e887-4b11-a8bf-34f8c605be5f | checkpoint | visual inspection by SWP
785bf77d-f8ce-4a81-9e2a-8fde6dc3c43a | section | Liner deck
f09ef4fa-2627-4b6f-a863-272e641a54a7 | checkpoint | Liner deck fixed down in every purlin and every pan
e9f01717-c257-4fb7-8063-209c0817a9e0 | checkpoint | Correct fixing installed
9fcb2d2a-07f2-46fa-9d46-220786f57738 | section | Vapor control layer
c02e6a51-c231-430f-b5db-10c912088956 | checkpoint | Substrate clean, dry, free of debris
33c73d24-fdad-4760-9204-088c50230598 | checkpoint | Z flashing installed
a84da5d2-e687-4f3f-b369-fed60c3da273 | checkpoint | VCL installed and covered all surface
fa682389-fa02-4157-bbf5-b214b75e80c8 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
8abddd20-a69c-4c4a-9908-2824b58ab232 | section | Acoustic board install
8accac6b-7cbf-47be-9715-330dc73a6501 | checkpoint | VCL clean, no ponding water, free of debris prior to install
d482cf35-d536-460b-896d-0b461cc8e61f | checkpoint | VCL has been cheeked for damages
ad1059e4-9db8-4f70-882a-9808e22979e4 | checkpoint | All holes/penetrations patched
fa7152c3-7178-4e37-a232-4e2d2ef18875 | checkpoint | Acoustic board installed
0e12ced5-9899-453f-b276-430d7e4f7409 | section | Insulation
b2d3b770-b170-4f71-a8c3-1de635cd70df | checkpoint | Boards tightly butted all areas covered
792294a8-b43e-4b58-a86f-84cf0c07a322 | checkpoint | Correct insulation installed as per spec
984f2890-a670-4c69-b854-d8a82e1c1bc6 | section | Underlay installed
71f067b5-1048-472c-a280-8f29c2ee1b8c | checkpoint | Correct underlay installed as per specifications
868d5af9-d10d-4b40-b4ba-ae8b0757ec24 | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
365fce3f-7e1d-43e8-b08a-06aaaef1b3a3 | checkpoint | All areas covered
a223715e-a0fd-47cc-b188-98f5b1f647ba | checkpoint | Underlay installed as per specifications
1bfd41a6-0454-4cb3-a60a-46b6f9b319f2 | checkpoint | Joints taped together as per drawings and specifications
a7bf3f97-2d82-4afd-9dc0-663691256147 | section | Metal roof installation
36377b13-0cf3-4b23-97e2-18d200be8f75 | checkpoint | Drip edge installed as per drawings and specifications
e6cbdb14-dfad-4276-97b8-0dea46a6de65 | checkpoint | Laid straight and perpendicular to gutter/purlins
9807966a-8e25-4f44-90b1-55dba4bcdfa3 | checkpoint | Gutter overhang as per drawings and specifications
731943fc-dcd8-4896-9213-1e11fde7b41b | checkpoint | Top end turned up
9f8050b2-4ec8-4b6c-b03e-99c60493e82a | checkpoint | Bottom ends turned down
b3159a4a-3266-4bd0-b43f-f5f2fc9e4fd1 | checkpoint | Closure foam installed
cb86c705-4dd7-487d-9904-ffc015274d5a | checkpoint | Screw pattern according to plan/specs/fixing plan
d7977f0a-630b-4d3e-bde6-7c08c2a1e047 | section | Flashing install
f0bcf282-6fc0-4097-be0c-10fd72a6e850 | checkpoint | Sealant installed with 2 continues beads
4f06bc50-0866-4789-b9a5-4d367a5d863b | checkpoint | Clean excess sealant
d5a48a5b-fc30-4618-b43b-2d4b6f500e58 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
993488fe-9f8b-4723-91f2-a826c21c5e8d | checkpoint | Flashings installed as per drawings and specifications and facing away from waterflow
3a8abb72-a53e-4887-bf31-c06a5b920343 | checkpoint | Fixings installed as per drawings and specifications
e5bbbf24-1229-495a-9227-47c798bb8c7e | section | Review and sign off
3753e4ed-bedf-4c4e-b9f5-7da0f6ffe4bc | checkpoint | Area left clean and tidy
f78ea7d0-ee7c-43f5-809e-ab98cf5c6038 | checkpoint | All installation work completed, checked and reviewed as per specifications
ff9a4275-ffa4-44db-8e3b-c26ee2f01875 | signoff | Client/main contractor sign off
105b44ef-3bc1-4110-b17f-16931c95a39f | checklist | MSR cladding checklist |  | MSR cladding checklist
f507718d-9d30-452f-8b0a-229bcf7ef898 | section | Pre start
5e1dd5bb-849d-4438-aa96-df4f59e624a3 | checkpoint | Area accessible
9f00c449-d07a-461b-b623-8abd9fe90cde | checkpoint | Edge protection and safety installed
2f54bbf3-a4d3-44ad-b06b-d1a512949157 | checkpoint | Purlins installed and QA / handover received from previous trade from main contractor
df64cf1f-bfea-45ff-8132-5b8c12224382 | checkpoint | visual inspection by SWP
94447df7-bc72-41c0-bca2-7fc578181a34 | section | Vapor control layer
72737298-5431-4b06-8da6-a49e83b3302c | checkpoint | Substrate clean, dry, free of debris
dbbd8c46-fbd7-4a00-b389-22006b417e28 | checkpoint | VCL installed and covered all surface
6ef51e3b-b2be-4b9a-a0a8-4c25177ce622 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
4b3a5401-c6f0-4ca0-9d1b-34007c131d91 | section | Rohm rails Install
085f1c24-e0ad-4f07-8528-eb9af1b0e112 | checkpoint | C channel flashings installed
97b15fb6-6578-4099-a695-4446e7b4f0c7 | checkpoint | flashing tape installed check plans and specifications
96d4a899-4958-42c8-bfed-ab590c3e852a | checkpoint | Rohm rails installed with the correct spacings check plans and specifications
43857899-b380-4498-9d0a-8dec58807655 | checkpoint | Rohm rails installed to fixing plan
6c3d0553-22b6-4f59-9663-02b2d53cb7d8 | section | Insulation
5e12e342-1cf3-48af-9f9d-5df6b00911fb | checkpoint | Boards tightly butted all areas covered
102cd5e4-1752-4a98-99dd-ed1841e62a8c | checkpoint | Correct PIR installed as per spec
bf4d116e-396b-4f79-bfcc-a2bc7ceb94e5 | section | Underlay installed
09c5f462-f932-4b68-9238-cad7e9750644 | checkpoint | Correct underlay installed as per specifications
efa7eb2e-8434-4317-845f-df49f127bb8d | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
dc0b605c-5283-47d4-9546-27e936e41a41 | checkpoint | All areas covered
9d5909bb-6c05-4a3a-999d-a79f0088d704 | checkpoint | Underlay installed as per specifications
afc37b6f-6522-4c2b-9f20-b664afc985f1 | checkpoint | Joints taped together as per drawings and specifications
b4cc7a37-18ef-469a-bfbe-cc50ca528801 | section | Cladding installation
a9e1f821-7459-4f18-9a97-7053315f3a46 | checkpoint | Starter flashings installed
edbd4f1d-ca3c-44f6-ac59-ee2bee8616dd | checkpoint | Laid straight and perpendicular to gutter/purlins
d9b99364-3c64-424d-9870-5a704ed2c3ef | checkpoint | Top end turned up
f2d0160e-48ff-41ab-b9dd-89fce7b31082 | checkpoint | Closure foam installed
db7eb718-fd4a-466c-a7b0-1b4948eac014 | checkpoint | Screw pattern according to plan/specs/fixing plan
17f3be88-9689-46d3-84b9-55cb8102f33a | section | Flashing install
b1cc11e5-02b8-4996-a82b-87d5b90f3f86 | checkpoint | Sealant installed with 2 continues beads
b3f52a07-90ff-44f7-a29f-97722bed2933 | checkpoint | Clean excess sealant
7cb9b6cb-d6b6-4636-951e-7fa19fe59de0 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
c3746cbb-13c8-45de-b54b-da17f36592e6 | checkpoint | Flashings installed as per drawings and specifications
9082a23f-6eb5-44dd-a85d-9c92aa64a7ac | checkpoint | Fixings installed as per drawings and specifications
857d108b-b039-41ca-99fd-78a31cbffeb4 | section | Review and sign off
42baaa0c-935d-4b60-a80a-6da137d8a756 | checkpoint | Area left clean and tidy
590a62c0-95c0-4b4a-8b24-48efb3216983 | checkpoint | All installation work completed, checked and reviewed as per specifications
eb940d98-9c28-40c6-bfbc-e1f97b95a4d0 | signoff | Client/main contractor sign off
fbf6136d-618c-4aad-b3fb-ffed44870356 | checklist | New Files |  | New Files
f35dbf1f-b5c2-4a41-b901-e6c522b4633c | section | Details
5cadb7c4-4451-44e1-80a2-c2f1b7ea9fac | checkpoint | Upload Files
f1462c08-2d0b-4d87-a2c3-5a6ee11f9ae6 | checklist | QA - Carpark MMA Checklist |  | Carpark MMA Checklist
f000648e-38d2-4325-9ce5-2c54bb631d90 | section | Pre Start
aa84cd3a-665f-4f73-ba47-fcf40bba9803 | checkpoint | SSSP onsite
d98d94ef-9137-4588-8063-4c35c9a04bc6 | checkpoint | Fencing demarcation installed
f9e9b315-188a-45d5-b4ef-3da8cc55fc09 | checkpoint | Site signage installed
efabf73e-d327-4d54-9882-7659976b23e9 | checkpoint | Area Accessible
56e419a7-1115-45ab-b87f-41acb55af896 | checkpoint | Substrate complete and ready for SWP
ff8e0667-c6b7-4da2-b434-48e643f3cd8e | section | Surface Prep
72bf787a-3cf2-468f-9c20-2cd446d84d15 | checkpoint | Removal of coatings
301d147e-c306-4422-881b-65fcc764bfbe | checkpoint | Grind of substrate
c608ca1e-6191-4e31-bea0-054452a69c44 | checkpoint | Shotblast of substrate to achieve suitable profile
92ee635f-f61d-42d2-a895-aafc956456e9 | section | Pre-start of membrane install
9b0219ae-ccb8-41e0-a0a0-cd6d6d6fb3f5 | checkpoint | Substrate dry
d0258fad-e0bb-494d-afc5-aebc1e580413 | section | Membrane install
46adbccd-a75a-4f8d-8337-263ae3eb3a40 | checkpoint | Prime of substrate
674f756a-2429-4fb6-845a-dbe7a736b9ed | checkpoint | Stripe out cracks
85e02ab7-57c8-46e4-93ae-6f73393dcc1d | checkpoint | Map out areas based on coverage rates for install
725d2e7d-5a7d-429f-938b-15bebcdeaf77 | checkpoint | Membrane layer installed
e0f3d487-c3ff-4ef1-af4a-e2f9aea1840e | checkpoint | Wear layer installed and broadcast
e4c80ac6-cb1c-47da-98f4-ef89715405c9 | checkpoint | Excess broadcast swept and removed
65e235f5-453c-4324-89e3-bf0428dea8da | checkpoint | 1st Top coat
de65e489-5103-4cda-a2a0-08c9614fcfef | checkpoint | 2nd top coat
811d1961-d0ec-4e66-aafd-cf0247af21f3 | checkpoint | Site cleared and broken down
b3a291ce-8b19-454e-b38d-5aba355f9926 | checkpoint | Site cleared and broken down
9960c8d2-e757-40d1-b7a1-6ba241267bab | checklist | QA - Fiberglass System Checklist |  | Fiberglass System Checklist
7ebdb4ef-92ba-4911-be11-8bed2e707e7b | section | Prestart
a9cea67c-d744-489a-b14a-01e729ed3daa | checkpoint | Area accessible
a3f7e6a8-20dc-41f9-b26e-a673f8340a8d | checkpoint | Edge protection and safety installed
9e73589c-187d-41d8-9f6e-a3824dc149f6 | checkpoint | Substrate complete and ready for SWP
2b8a52e2-7ebe-4e0d-8a52-8fc108295781 | section | Surface Prep
d1679b2e-c10e-4b38-9518-ffd67c105742 | checkpoint | Concrete free of contaminants
1e327794-4fd8-417c-9daf-67d70ed42b80 | checkpoint | Concrete flat and smooth
b81713b8-fef5-42a2-837e-9c9447a45504 | checkpoint | Bug holes in plinths filled and smooth
25bd224b-5fde-4d9f-bf99-e9ad5275fa6e | section | Membrane install
507576a0-e135-4d43-a6fc-f81cfeee41d4 | checkpoint | Install sealant angle fillets to all wall floor junctions
07b5df80-bfc6-488a-b986-4c08db0d9dd1 | checkpoint | Prime surfaces with Epistixx
3a32592e-c364-4317-be59-bc3ed2b48a39 | checkpoint | 2nd body coat
1475ea42-de0a-44d3-a0f5-b317dafcfc22 | checkpoint | 3rd body coat
751eadf6-090a-4302-a689-b8783399cfab | checkpoint | Traxx 2000 wear coat.
e9f055eb-ddf8-47c4-9276-2c100fd37a5f | section | Review and Sign Off
167c9a92-2c5f-4115-ab4a-067312995828 | checkpoint | Area left clean and tidy
03a0d093-110d-4ed0-a7e7-5726bf923aa6 | checkpoint | All installation work complete, checked and reviewed as per specification
6203197a-e0d9-4600-8fb0-964075a7a58b | checkpoint | Client / Main Contractor sign off
9362e07c-0c2b-40d6-b7b7-3d6c65453531 | checklist | QA - Fibertherm Checklist |  | Fibertherm Checklist
0ca275a8-db72-4ed4-b841-b1c54eee1227 | section | Prestart
6caad23b-0398-4ee7-aba6-77f701fae595 | checkpoint | Area accessible
3af3cf04-d675-4819-8b76-47081f216579 | checkpoint | Edge protection and safety installed
43305ab3-5cb9-42bb-9ce9-c8e61d4730c0 | checkpoint | Substrate complete and ready for SWP
379c8342-3df9-4169-8ba7-000e3151a8f0 | section | Metal Deck
e9516556-2d81-4c9f-b225-b6e7436870fd | checkpoint | Timber to have separation
c581afa1-4c3e-4244-87d6-b24c37a8cd50 | checkpoint | End openings to have closure foam installed
3287dc56-2586-4111-ace4-f44409cff78b | checkpoint | Base deck screwed down in every pan
4d36755f-63ca-4189-b7ca-00ddda60af21 | checkpoint | VCL tape to be installed to all sheet laps
71f23648-d53a-488c-b311-2a092dd9a82a | checkpoint | VCL tape to all upstands
86a32cf6-c1f1-40b0-b48c-1f6ecea538ee | section | Post and Rail install
97fec4ae-99f8-412e-914e-8fe586bf539e | checkpoint | Post installed at correct fixing centers
4852bdff-290d-4387-a2c2-872592dd6617 | checkpoint | Thermal break pad under post foot
b25fa2a6-b33d-4baa-80fb-5fe5474c5a8f | checkpoint | Rail installed to posts
91a282a4-79c0-4368-adec-1d4cef748370 | section | Insulation install
540cdb62-2bab-43f7-a0af-8387a8eef0c3 | checkpoint | Specified Insulation installed
6fd9168a-04f6-45f7-b655-202e1088989a | checkpoint | No Gaps
82d06893-12c3-45ac-9bdf-baa9570b0e95 | section | Top Deck install
0f488e54-7f35-46bc-8140-8ac7baf2b717 | checkpoint | Lay sheets straight
9f848a43-ca88-4d6c-874b-ad08e5952f5d | checkpoint | Hang over into gutter min 75mm
4028dcd6-3277-4cb3-aa42-25f95e06f975 | checkpoint | Top end of sheets turned up
07efe7dd-20e8-4829-af6e-f9e9997b9054 | checkpoint | Bottom end of sheets turned down
0191d1ae-df98-4f53-87bc-0538099f9bf9 | checkpoint | Fixing back to rail
ecd20120-6bee-4296-af41-848656253b85 | checkpoint | Profile washers
e792b9bb-8b2b-4816-b626-6bbb44de38e9 | checkpoint | Screwed off as per fixing plan
c2690501-5461-4f53-9540-b68707da1a16 | section | Flashing install
c499b2f6-0cea-445b-b18d-ea5c40acff29 | checkpoint | Fixings according to specs & details
386a95ca-6f82-44b7-8b18-fd82256c7486 | section | Review and Sign Off
898a4122-6037-4c7a-a9ce-31a770856f68 | checkpoint | Area left clean and tidy
ea8aae3c-14f2-49ab-8d63-3d20cd111a9b | checkpoint | All installation work complete, checked and reviewed as per specification
b98e45e8-e6ce-4d80-ae5a-0e8551753b7e | checkpoint | Client / Main Contractor sign off
dabe5426-32e9-4802-9f45-a78bd715d12c | checklist | QA - Sheet Tanking System Checklist |  | Sheet Tanking System Checklist
217ac2e8-73f3-4206-923a-6a3a82cbf781 | section | Pre Start
22fd4119-c222-4127-96e4-e25a2792cd45 | checkpoint | Area Accessible
4033a781-ea8b-4932-b4ca-52cf9bdc33d2 | checkpoint | Edge protection and safety installed
5ef638c3-893b-4493-95a2-ee52dd359e2e | checkpoint | Substrate complete and ready for SWP
66a1fdbc-10c8-4589-8bb4-64118825162f | section | Primer
23d9bef8-d75d-4b7b-b76b-edbb520892ce | checkpoint | Applied as per specification on dry substrate at 5m2 per litre
41fcddbb-4d66-4281-97df-ea8692fe8a14 | section | Membrane
0bbb77f6-4f50-42cf-b7a0-a5b573891c4d | checkpoint | Temperature must be over 4 degrees for membrane install
c57c4bc9-3c0d-4d3e-a11d-a9d1c5404d2a | checkpoint | Is the substrate clean, dry and clear
01deb3e0-06c8-40a3-b36a-777009b5ef35 | checkpoint | Membrane applied with min 50mm overlap
91271878-4b9a-4404-a5b4-93e9bfef7edf | checkpoint | Overlap is to pressure applied or rolled for seal
6d22c7d0-6bad-478b-bdac-a9c1331829af | section | Protection
e1f8f7e0-568c-4aac-a373-a0924fa4c4ee | checkpoint | Works to be protected by main contractor
1cd02f0e-e0fc-4de7-b80d-ef976b1f99d6 | checklist | QA - Torch On to Concrete Checklist |  | Torch On to Concrete Checklist
2d0078a7-7a3b-4ff4-bee2-634599abe60a | section | Prestart
4de16901-ae47-4ea2-b1ed-b8db2b3e81dc | checkpoint | Area accessible
6db62080-489a-4908-a10a-44a6f2c75182 | checkpoint | Edge protection and safety installed
2417e325-20e8-4360-adc7-1f6035fbca26 | checkpoint | Substrate complete and ready for SWP
71d114d8-08f8-4765-870a-b600202a2d7a | section | Concrete Substrate
91e87009-266f-4288-8264-f4bed6e2234d | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
8fd04c50-3e7c-4525-9ccb-44decc76a742 | checkpoint | All lumps and sharp concrete bits ground/hammered down
1b3eec3f-bb91-44d0-a23a-557f1f0ca4fb | checkpoint | Large holes filled with grout
b9e91d9c-b209-495a-83f3-58f8559905a4 | section | Prime of Substrate
31bdf5af-97bf-4f62-a4b9-de9e71ee110a | checkpoint | Substrate clean and free from debris
f18ae96d-0ef4-4158-9842-2afb60075087 | checkpoint | Primer installed
fc67f380-2c26-42f1-aa0b-c9bd2909d2bc | section | Base Sheet
43f16188-b3d5-4928-a20e-2cdf0e8251bd | checkpoint | Install from low to high
2c1bd9d7-2e36-4242-adca-9241384bc755 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
391172d6-c3b9-4125-adc4-3853d41b7a97 | checkpoint | Check all welds at the end of the day
b1d6ae16-887a-4636-b5e1-a18d9b3a6db6 | section | Cap Sheet
5e292d7b-70bf-43ac-acf2-4013571eed85 | checkpoint | Install low to high
a74d667b-a7fc-46b9-9ec4-a902f4ade089 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
d71df172-bdd4-49e2-abe3-ee9f54c568b1 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
ec4fbff7-38e5-49c4-93b7-9dbc13c9cf46 | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
5b358b6a-a0a8-48de-9476-9f0b72acd7a8 | checkpoint | Membrane dressed into drains/outlets
90bbf13a-89ab-4b62-9b2e-cbbb3b8b9178 | checkpoint | Install clamps/rings/baskets
62f733d8-4718-4aed-a818-72d48520e6af | checkpoint | Flood/ILD test
75f7e783-a577-4d9e-81d5-3f3c77edb899 | section | Review and Sign Off
7173d1c4-fbaf-4c65-9f58-8081e1a15ea2 | checkpoint | Area left clean and tidy
542e825e-99f9-4340-8d1e-49dd6eeae10d | checkpoint | All installation work complete, checked and reviewed as per specification
eccaf011-bbf5-4019-a648-0821a1d9db76 | checkpoint | Client / Main Contractor sign off
4a267a82-a105-42cf-9417-c51f84032f60 | checklist | QA - Torch On to Plywood Checklist |  | Torch On to Plywood Checklist
4fb1a037-a864-4431-affb-3ace38d47d43 | section | Prestart
f061f10c-7556-4440-a870-f59d218dd697 | checkpoint | Area accessible
1c3278a7-3448-4276-a9f9-57b117d508cd | checkpoint | Edge protection and safety installed
5b6963e1-b903-4bea-9b2e-bf8ef0bf27cf | checkpoint | Substrate complete and ready for SWP
8461b8f3-ab68-4400-8b62-547092625f1a | section | Plywood Substrate
87ee0b0f-d6f6-497d-af68-73b00a7d7e1a | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
64674eea-afd0-4e19-9800-9fb1f6123ece | checkpoint | No Screws/nails/fixings popping up
33fc48d9-98e2-4242-8b9e-04d136c0c138 | checkpoint | Joints flush and even
f9256bdb-85da-4511-9e0a-a8eb0a73755d | section | Prime of Substrate
d54f7e35-9788-4b3f-bc81-02215b52fcd5 | checkpoint | Substrate clean and free from debris
9e00065a-17f4-454e-85b0-e6ca594ea71f | checkpoint | Primer installed
577f1cf7-0d7d-41a0-ade1-b77527b660cb | section | Base Sheet
1b44ae1c-8926-4041-bf6a-b54261db8ca2 | checkpoint | Install from low to high
418f9a22-b1cf-42d2-b009-61ceca51bbba | checkpoint | Side laps a minimum of 80mm and end laps 150mm
8758afcc-8118-4ce8-b245-bc8ef2b16a19 | checkpoint | Check all welds at the end of the day
890ae903-11ce-4df9-8502-06ed3b639547 | section | Cap Sheet
8e9948af-d0e5-4514-b6c9-9e77b2f2c3e7 | checkpoint | Install low to high
921637fb-207b-4155-82d6-b63a86da8b65 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
bcbc45d7-ac7e-4319-98bf-70099869df76 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
f2aee658-d239-40af-8783-55b91e4d6353 | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
ed5b5bd1-0f8d-4425-a3f1-f5806577cee5 | checkpoint | Membrane dressed into drains/outlets
a04cf00f-1702-4586-bb22-07c5d4f26940 | checkpoint | Install clamps/rings/baskets
409c54b4-913f-4ce6-b7b5-50b673f25199 | checkpoint | Flood/ILD test
5212f512-80b4-4884-b76a-94bc912b413b | section | Review and Sign Off
c286bd17-379b-4d9c-8b80-04f699f9fca2 | checkpoint | Area left clean and tidy
e4403cb2-4d91-4d97-815d-ada74a0d7acf | checkpoint | All installation work complete, checked and reviewed as per specification
9fca49eb-94ac-4ce5-b858-74c4b0ed83b9 | checkpoint | Client / Main Contractor sign off
c8ef6b71-8635-4877-b896-077b448451fd | checklist | QA - Torch on Warmroof Over Metal Deck Checklist |  | Torch on Warmroof Over Metal Deck Checklist
3a09ceda-f8ac-49dc-aea1-cb7fd9fbcc33 | section | Pre Start
145a0ffe-dce7-40a4-954c-b776107588b4 | checkpoint | Area accessible
573583c7-3e9b-4b8b-9e41-c20388acd542 | checkpoint | Edge protection and safety installed
85066a04-1ebb-4f61-b82d-242467d68ac0 | checkpoint | Substrate complete and ready for SWP
de38436e-7a4b-45b0-b062-e462848353f9 | section | Metal Deck
61f9f657-eca9-47bc-9019-b9f74f994958 | checkpoint | Timber to have separation barrier
8cf7f14b-8c00-4ec9-8706-13f6d7860d56 | checkpoint | Base deck screwed down in every pan
91b7ea3f-e706-429c-8143-be80a08989f2 | checkpoint | Sheet edges stitched together at 300mm centres
c5b21e62-1677-45ba-910c-c63491d0e64e | checkpoint | No sharp edges protruding
f2a50c0f-9e38-4bcf-86c9-d26a18457e9c | section | Vapour Control Layer
e3e5773e-ceba-4ccf-9568-5f4597e718dd | checkpoint | Is the substrate clean, dry and clear of swarf
aa180ab0-76e6-4447-b8b0-0dd7ad07231c | checkpoint | All areas covered and sheets lapped 50mm
0d249f98-f7fd-4a9c-a75a-c723aed33248 | checkpoint | All holes/penetrations patched and water tight
960ebb2f-598e-443c-887e-21340a7935a0 | section | Insulation
ea26b810-26ba-492e-9b5f-7468c4464518 | checkpoint | Surface is dry prior to install
af00be4a-6dd6-449c-bcb8-66271e2baf2d | checkpoint | Vapour control layer has been checked for no damage
e130a776-8e84-47b8-a1e2-013ee463fd5e | checkpoint | Insulation board installed
9b68b3c1-6dd3-493f-be84-ece67183ad09 | checkpoint | Joints flush (no gaps between boards on ends)
be35cb6d-8c97-4ab0-86a8-b7ad4a6fc01f | section | Securock
65d82745-a7d7-4d36-8f22-92296126b88f | checkpoint | Is the surface dry
a4cc0f1f-6948-4330-9db6-727e287b2f7c | checkpoint | Installed in brick pattern
dc79a874-62dd-4857-b79f-1ef4aed58b21 | checkpoint | Correct length screw with recessed flat plates
266f9e9a-aa7e-4176-aad9-eadf86da5ed1 | checkpoint | Installed as per wind uplift fixing plan
e34da0b2-ee31-4b3a-a8f7-74f50530c940 | checkpoint | Prime of Securrock
c8dfb9e7-bdf3-410f-a1dd-a9af430b2b01 | section | Base Sheet
3a6eccd0-f855-46c4-97b1-da98f4cb3f00 | checkpoint | Install from low to high
555360f7-c7cb-4273-aaee-2f74eb3ea128 | checkpoint | Bleed of bitumen on overlap should be up to 10mm
7beb8c6a-7d44-467a-b564-b6e4f1017c05 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
16c68db5-d1c5-4d5d-93d2-92dff901be0d | checkpoint | Check of all welds at the end of the day
a8153f5f-7a76-4215-bd79-915ec7ea3ce8 | section | Cap Sheet
2d9cfcde-ae86-476a-aa32-a1d543ee167e | checkpoint | Install from low to high
0ce18379-0d6a-422e-800f-a2b64a6f3425 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
6d705a42-038c-45fe-a8e9-5e18757e1a74 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
2bdbc694-48cf-4ca8-a4fb-d21fca763bbf | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
7798caac-4928-47aa-9696-3690358ecbdf | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
881acdd8-8c5e-4d14-ac94-9bb4c47fdf76 | checkpoint | Flood test / ILD tested
aa1ae16f-80d2-4ad2-a40e-ff88c044afdd | section | Review and Sign Off
6fa9e2b3-0189-48f5-96f4-1f101e3d5c32 | checkpoint | Area left clean and tidy
de3cc147-75cd-4467-b029-0feed51f64d4 | checkpoint | All installation work complete, checked and reviewed as per specification
87b43f88-937d-40a8-967e-ddb95570f665 | checkpoint | Client / Main Contractor sign off
ee8f53a2-56f8-46ca-abc4-9035c252b8e1 | checklist | QA - Torch on Warmroof Over Plywood Checklist |  | Torch on Warmroof Over Plywood Checklist
c4f91f7f-2bfd-4ec8-82a9-3a8a8b6f5173 | section | Pre Start
e394aede-c7f9-4995-8c83-1c1705759dbb | checkpoint | Area accessible
61823c5e-914f-4d99-aa66-56e4b1345acc | checkpoint | Edge protection and safety installed
b0830a4a-5bcc-4ec3-9b15-729e461daf4d | checkpoint | Substrate complete and ready for SWP
d6220039-7d9e-462a-a40e-10c38d227545 | section | Plywood
80ee1982-9759-463a-b230-482764d9ee7d | checkpoint | Plywood clean and dry. Free from dirt/debris and and ready for priming
2654b0ef-017f-4f2e-9b78-01d43f1dc871 | checkpoint | No screws/nails/fixings popping up
36887bfa-98f6-4509-8d97-ea9c37663fad | checkpoint | Plywood joints flush and even
b58a90ca-b02f-4d30-95c8-6e5a9dbe396f | section | Vapour Control Layer
228cba4b-8ef1-4f8d-94cf-c7e01a31984e | checkpoint | Is the substrate clean, dry and clear of swarf
58c6ead9-2b9f-44c7-8c8e-5a501708e515 | checkpoint | All areas covered and sheets lapped 50mm
fdaa1bef-3133-4603-8c45-187d13a3426d | checkpoint | All holes/penetrations patched and water tight
280c389a-490d-4413-9d8d-f02fad0f3e3a | section | Insulation
bc5278cd-b0a5-4ae9-92c0-4735f5fcbe50 | checkpoint | Surface is dry prior to install
25efc2c2-ff51-46e9-aa84-904de57946a0 | checkpoint | Vapour control layer has been checked for no damage
4437de7a-8207-4625-853b-e326d57b96ec | checkpoint | Insulation board installed
8d48bb99-467d-4921-aab0-d80cdc6b1577 | checkpoint | Joints flush (no gaps between boards on ends)
f90a9d84-bada-4415-8bee-182ee1aa3b0b | section | Securock
a2eefe27-bd5c-42dd-a914-e133495669db | checkpoint | Is the surface dry
ee9b7c1a-d10c-4bd0-a0cc-04f4dff21597 | checkpoint | Installed in brick pattern
5f87c1ce-fb45-4f83-87e4-cf4ee7f3d16f | checkpoint | Correct length screw with recessed flat plates
3e0e6f04-5b02-4cd8-aeff-b48dd250a852 | checkpoint | Prime of Securrock
1c746afe-7785-4d32-a35b-de42a44f5e5f | checkpoint | Installed as per wind uplift fixing plan
6d5898c3-0794-41d8-acd5-c94d796886f8 | section | Base Sheet
c15bea74-ff87-4af4-8b1c-c63cf7e71a51 | checkpoint | Install from low to high
cb554e49-1a42-401c-8adf-cfc1c01329e1 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
c0d374f2-5fb2-4392-b401-9e176b9ec6c3 | checkpoint | Check of all welds at the end of the day
5ea95bba-7eca-4a46-ba6a-8c30998085e1 | section | Cap Sheet
31daaa55-28c0-4e42-927c-216509a762a7 | checkpoint | Install from low to high
175079ee-03d6-4028-9672-528796eae9ac | checkpoint | Side laps a minimum of 80mm and end laps 150mm
11509291-db4a-43c6-a125-64176afca800 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
525d4bdc-4e4f-4545-aeda-ec4b1190f1bb | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
ae3e3979-f475-42ee-838e-5f4c8758dec0 | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
d4181486-01d7-4fc1-a2b8-7f1597146258 | checkpoint | Flood test / ILD checked
3e0d8562-e831-406b-a7df-2a52057d404d | section | Review and Sign Off
f2edc1f8-520e-4685-96e0-a015c720d871 | checkpoint | Area left clean and tidy
c096453b-013a-4db2-9da0-30603cbc4ea4 | checkpoint | All installation work complete, checked and reviewed as per specification
39570441-8fd3-4bf0-9de7-e5305bdd2583 | checkpoint | Client / Main Contractor sign off
b7a0c84e-ecdb-47b9-91b4-ac25b3ad28a6 | checklist | QA - Torch On Warmroof to Concrete Checklist |  | Torch On Warmroof to Concrete Checklist
e2baff71-7071-4324-81ad-6bc994efbffd | section | Pre Start
211970c4-8597-4181-b771-972a8d68a71f | checkpoint | Area accessible
b36cb3d4-1052-47c3-bb98-c9aa78ada471 | checkpoint | Edge protection and safety installed
0a8f4dac-b320-4921-97d8-30e968093ff3 | checkpoint | Substrate complete and ready for SWP
07665fa9-a834-4e3c-8641-c63ab07ae95e | section | Concrete
02989c77-d61c-4f96-9251-af925792a367 | checkpoint | Concrete clean and dry. Free from dirt/debris and ready for priming
a9853e6e-0d8a-43a7-be7f-f0d7d0028e03 | checkpoint | All lumps and sharp concrete bits ground down/hammered down
9df2177c-770a-4155-aa3e-bff7677cdcbc | checkpoint | Large holes filled with grout
19b8aed0-c471-4cc5-a445-f2a28934781b | section | Vapour Control Layer
32ac36cb-5d69-4ebc-9b57-69f97acff794 | checkpoint | Is the substrate clean, dry and clear of swarf
bdf7627c-8458-44ce-b797-a5c3b081429a | checkpoint | All areas covered and sheets lapped 50mm
9289959d-3e5b-4bd0-9e03-0bc91697b9af | checkpoint | All holes/penetrations patched and water tight
340044a2-4fc8-4205-b1d0-4b456b022f35 | section | Insulation
97cb2ff7-ff5c-4238-88fd-42705e08d35e | checkpoint | Surface is dry prior to install
3b1b811d-448d-4700-9355-db3f4ca2011a | checkpoint | Vapour control layer has been checked for no damage
bd545b9a-3f96-4516-a471-2f77864db8bd | checkpoint | Insulation board installed
3b59ecd8-ff3c-43c5-a480-abe2d9ca5ea8 | checkpoint | Joints flush (no gaps between boards on ends)
9948315e-1afb-4eda-97f4-fb77aa32e5e9 | section | Securock
14f16830-6e28-4d04-bf30-0440d6d4fe5c | checkpoint | Is the surface dry
072dbad1-f803-4219-a971-3cf57fefb413 | checkpoint | Installed in brick pattern
7f340cd5-d300-47a0-8d54-348b31fd2c5d | checkpoint | Correct length screw with load washer
4a4b26d9-4926-4888-b12f-e6d969f619ee | checkpoint | Prime of Securrock
19ced442-5b00-43e3-9507-ff3864fcb91f | checkpoint | Installed as per wind uplift fixing plan
fc3130fa-8dbb-4d0f-b2eb-1d68040a1509 | section | Base Sheet
71669c44-666a-4631-baa7-dbacc349e0fd | checkpoint | Install from low to high
b4fdb8b5-cfed-4c8d-b0ce-23aff80f5573 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
19ef7db9-6acc-47eb-9d95-f11dc54416c1 | checkpoint | Check of all welds at the end of the day
a8434d56-4db8-4932-adb7-bc4f364f277d | section | Cap Sheet
21d98494-b068-4da6-97d4-b5796298198f | checkpoint | Install from low to high
a3b06501-4abd-4a35-8edd-e2912205bb15 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
9d5e819b-3607-472d-8436-f8b3fa2bc42a | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
4b0efd51-887a-4491-98ff-b3070392ddf4 | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
10149eb4-d5bc-4f5a-a224-989c0302aeb4 | checkpoint | Clamps / rings / baskets press into overflows and outlets
9f6020ff-603e-494d-a792-01750458e6db | checkpoint | Flood test / ELD tested
bb24b4d3-e5a8-4440-87f4-2d6d52530d7f | section | Review and Sign Off
10926b36-adc1-4e1e-be94-960c5701ea6e | checkpoint | Area left clean and tidy
2ea97074-814b-451f-9fd5-01c2d64d7240 | checkpoint | All installation work complete, checked and reviewed as per specification
dbb27727-da3e-4ffb-9ec7-e275b9cd85b6 | checkpoint | Client / Main Contractor sign off
8bee4aff-0a8f-4372-92bb-10699479afa5 | checklist | Supplier Site Visit |  | Site Visit date:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c6381ae3-9864-4ee4-9e58-3e3063a0d2b9 | checkpoint-no-value | Site Details
6d41fa6a-4e1a-577e-a624-6bd736f97876 | textbox | Job Name
22044acf-ec81-5b86-a826-c71cabe41273 | textbox | Who is in attendance
1235194d-88da-53a0-854a-ce85145c2b1e | textbox | Area/Gridlines/Detail
7c20c549-2245-4611-9a13-c1202bdd3c39 | checkpoint | Photos
e4f72de6-232e-5c0f-a8f5-0b30ac9ea698 | textbox | Inspection Notes
46c409f1-29a0-44eb-b037-2ea6c1d02bf4 | signoff | Signoff Required
ae225fb3-9ad9-4149-ae2b-9de7a66c2e8a | checklist | SWP - QA - Fibertite Overlay Install Checklist |  | SWP - QA - Fibertite Overlay Install Checklist
69a03ed2-c42f-4ead-ab0e-953c9bb300e1 | section | Prestart
51740d88-776b-4771-a821-d0572776de18 | checkpoint | Area accessible
0562f0ef-d611-48f2-9733-705ffa41f8a1 | checkpoint | Edge protection and safety installed
711ba1bd-5f6a-4a04-b5f0-7385f2e7b202 | checkpoint | Substrate complete and ready for SWP
a55c359d-069e-4a3a-a565-8d434543fba7 | section | Substrate
4623f929-7fc6-4c30-b150-7ef32fe815e5 | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
b163d177-93ef-4f01-bd5d-b9267bba42d4 | checkpoint | Cut back existing roof edge at gutter
3cf478aa-cf4c-48f5-8797-5258317b11ed | checkpoint | Remove ridge as we go
08e5f3bc-955d-4504-82a7-c8ddac54db03 | section | VCL-Vapour Control Layer
5ee316aa-81fc-446c-9728-404ca5166cd1 | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
2af9f685-74d7-4b48-a5a0-2cc5e0eb6143 | checkpoint | All areas covered and lapped a minimum of 100mm
80dbeb04-342d-4dfc-a24a-c98858134eee | checkpoint | All holes/penetrations patched and made watertight
1459d4f1-ff49-441f-9c7b-b5bc12358d69 | section | Roof Pan Infills
0fc7f1c0-2038-468e-824f-32f5896070b6 | checkpoint | Surface is dry before installing Poly
9320b599-6c0a-4a92-b208-e5526c1f11b5 | checkpoint | Infills to be a minimum 5mm above ridges on roof
ca17e849-2d06-4ccf-8cd7-fdccab81f773 | checkpoint | Every pan has been infilled
a2d66e97-6f34-4cf6-8484-b83358d9b5a6 | section | Roofboard
685d1725-3ea5-490f-9e87-afe8780eebb9 | checkpoint | Substrate/surface dry & clean prior to being installed
30d619b3-5b62-4871-90d8-116beefb04db | checkpoint | Installed in brick pattern
4e4d6655-4e2d-4f35-912d-eb18e5ac8abf | checkpoint | Correct screws with load washer
113e6fb4-f3c1-427e-8d71-1927d098a48e | checkpoint | Installed as per wind uplift fixing plan
5483c944-e22a-41e2-a410-38b74f8043be | checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
9711814b-0d44-48f8-a1e4-0a24a1ba148b | section | Fibertite
a03e76c0-a094-4221-818d-7c4ad2eaa2bc | checkpoint | Correct Glue being used for substrate
9d2e1a3c-1612-4712-884b-2c09554d028f | checkpoint | Fibertite fully glued to substrate
84141ba0-a738-4541-935f-bd4e786fea00 | checkpoint | Broom/rolling of fibertite
730b38fa-2675-4675-a39a-3d98985fbb41 | checkpoint | Wipe/clean laps with acetone prior to welding
6edfa285-3c29-4430-849f-72e8d77421f1 | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
2c3ca352-240e-4f21-9886-e393ec2ce7c0 | checkpoint | Clamps / rings / baskets installed
82f6e9e4-7b90-486f-a1d1-61f38bd0e398 | checkpoint | Flooded / ILD checked
d2777793-20c0-4c49-9f5d-d4ee59e07dae | section | Fiberclad Flashings
0f0e094b-0581-41cc-b054-dbf839f5f155 | checkpoint | Installed correctly
adc384b3-c321-43a9-a4b6-d378122fcaf3 | checkpoint | Fixed down according to specification
e68febee-624c-4dbc-aba4-9499331398b9 | checkpoint | Cleaned down with acetone prior to welding
117c08bc-8ec1-446e-86ac-ac79bcc5d7cd | checkpoint | Fibertite fully welded to flashing and QA'd with hook
9f16ca42-8b5c-40fe-82d9-b1227730b329 | section | Review and Sign Off
8ef631f5-c2de-44e1-bea4-9164f7fb8f71 | checkpoint | Area left clean and tidy
7ba3b62b-56d0-49cd-81d9-a7e6cbc44c86 | checkpoint | All installation work complete, checked and reviewed as per specification
51d892b9-1470-45e7-8435-30a224cee7c1 | checkpoint | Client / Main Contractor sign off
146a4ffc-a8b3-4f42-8b36-63d44b8e70d5 | checklist | SYS - PT - Job Details |  | Job Details
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
afb9a02f-6bf2-4a99-9c08-acceac6d5b1d | checkpoint | Site Info
4e739149-fe6d-425d-b45e-4a4ff63e7c1e | textbox | Site Address
e326d577-6e3a-40b7-870a-8e178eda7195 | textbox | Main Contractor Details
6c1ef37c-4d31-4405-b668-f398c4ad1275 | textbox | Project Managers Details
351c3436-2ae9-42ae-9ee9-1146e81bffa2 | textbox | Site Manager Details
a839af8c-eaa6-42b7-81be-5dd0dd297a16 | checkpoint | Latest Drawings
837c43f5-d296-4ee8-b264-c9cd852abd11 | checkpoint | Scope of Works Attached
9429bd19-71e4-4e6a-ad33-ea830ae2ce51 | checkpoint | Additional Pre Start Docs
2cec505e-b871-4aa1-bcfe-6c0acd410174 | checkpoint | Fixing Plan Attached
95520c5a-fa33-49bb-85be-eb66b7e1378f | checklist | Weather Monitoring |  | Weather Monitoring
94cef617-c578-459c-b319-dd0aaf3fb8b7 | section | Current Weather
5868e3f2-a3ac-4303-a6e8-6552f560033b | checkpoint | Wind / weather conditions
08dd0521-722d-413b-8d73-dacfa88859d5 | checkpoint | Record any delays
b8e4c3c9-895e-4a12-b895-32c9bf1335d9 | checkpoint | area / gridlines
8d8543d9-7bc2-4b97-a70a-a2aeebd85d7a | checkpoint | Comments / issues / observations
8b700a01-de12-48ad-8bd5-3173824575b9 | section | Weather Forecast
f912e805-208f-4d30-a329-0597685bbc77 | checkpoint | What is the weather forecast this week
aefa88cf-4d61-4bbf-b3b1-cce3a48ed4ce | checkpoint | Record any delays
a0d8f8f5-8244-4230-9335-923ae2021beb | checkpoint | area / gridlines
e168c61b-bbf7-4ff1-a0a0-adfa63c0eaac | checkpoint | Comments / issues / observations
91df3875-f067-4beb-84b4-9d40bb5ee556 | checklist | Xtreme FibreTite Checklist |  | FiberTite Checklist - Area:
829e03e1-1ee6-4e70-a0ca-4f00f1fe93de | section | Pre Start
7b0b4539-cbdc-4944-b9a7-5b559131d859 | checkpoint | Area Accessible
45ed0251-0947-4c11-8826-e8615ac84cde | checkpoint | Edge protection and safety installed
f0607268-184d-4f79-aa13-ba8ea9d8564d | checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
7c86a380-b55e-412d-8b0c-784bd5e51959 | checkpoint | Perimeter support installed installed if metal deck substrate
6bdd7d9c-a395-426a-92ff-83da803ee367 | section | Metal Deck
e3d802da-b2d3-411e-af1a-4459f9316889 | checkpoint | Timber to have separation barrier
3ab81328-1c79-49df-b554-1c6026d0c783 | checkpoint | Base deck screwed down in every pan
34629d79-b776-4887-85b8-6e6fe4e6b4f3 | section | Vapour Control Layer
e2d75fa2-7933-4211-80e2-f06d98280942 | checkpoint | Is the substrate clean, dry and clear of swarf
832c33cb-05cb-478f-9648-59503c33a4b1 | checkpoint | All areas covered and sheets lapped 50mm
358f5e56-2152-4b1b-91ff-1371bdc1f070 | checkpoint | All holes/penetrations patched and water tight
551a0a6b-1e05-4898-a9dc-65cfe5dce357 | section | Acoustic Board
1e1cd78c-7e9d-4418-9a4d-043c5b237eb9 | checkpoint | Is the surface dry
0547b78b-d46f-4870-9788-928222efde7e | checkpoint | Installed in brick pattern
a252f951-9d80-41cb-953f-69cc0efae4c1 | checkpoint | correct length screw with recessed flat plates
5e90e4f9-7ebb-44b5-b6c2-43eaeb92172f | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
8531d4d9-0ce0-44c9-a9e2-401faa25e07a | section | Insulation
057d5f8c-1a84-48b0-92a8-132be45508b4 | checkpoint | Surface is dry prior to install
751052cb-8f1f-4270-aa2b-5b39fb9b1c80 | checkpoint | Vapour control layer has been checked for no damage
3bcb5a2d-58bd-4f2b-ac4c-f4156e223981 | checkpoint | Insulation board installed in a brick pattern
4c7f69c4-4d2a-4a10-b80a-4b4613b1c423 | checkpoint | Joints flush (no gaps between boards on ends)
3b2ed578-ec8e-45f5-80e6-89df89830165 | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
b257fb18-cfd4-420c-bc66-6a23466133f0 | section | HDP Roofboard
b2dd1798-0a0c-4429-935c-f3fcb8b5b1d9 | checkpoint | Is the surface dry
bf919665-5d90-470a-8160-c566ab2afc4d | checkpoint | Installed in brick pattern
5df31234-39d8-4722-b4ed-4704c3b4efc3 | checkpoint | correct length screw with recessed flat plates
1dad3c75-e3e8-43ee-8160-cafff6d2b92d | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
4384378e-516f-494f-9872-0679041d2f51 | section | FiberTite
426929de-ba6f-40db-99ad-6a18391e802d | checkpoint | Test weld with welding machine
9ce6912b-5c8d-44ce-9760-487126550702 | checkpoint | Adhesive installed to substrate
ecea925a-3f06-44c5-ad33-4171eb2a1c99 | checkpoint | Laying of membrane into the adhesive
2b143052-6951-4191-9b8d-be84f73aeadb | checkpoint | Broom/rolling of membrane
5f7b09e4-b6d6-4197-8c23-810cb7119ba2 | checkpoint | Wipe and clean of laps prior to welding
d913cd72-94c3-4a94-9531-f83351e96ea4 | checkpoint | Probe of seams with QA hook
91fe22cc-999f-44d7-a6fb-a47ca7de5172 | checkpoint | Clamp and weld of outlets and overflows
2089d265-e6a4-4ed0-a134-15edb6fc3441 | checkpoint | Flood test of outlets
69e906dc-6a65-46e9-982b-b8d478643c6b | section | Fiberclad flashings
4a3f587f-144d-42b8-9c15-913d8ab31d87 | checkpoint | Installed correctly according to specifications (Right way around)
f048689c-7b10-4259-80ee-91922d2e0485 | checkpoint | Fixings and welding done according to specifications and details
6dc415e0-0a1d-4389-8b6b-a3126633c0e4 | checkpoint | Probe of weld with QA hook
1017e738-cc49-4bca-93b7-0a8f7f5dbd1b | checkpoint | Area Complete (Request MC Signoff)

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
dbd4e19a-9cde-41e8-b9ee-a685fbaa7f25 | checklist | Fibertite Roof Overlay with PIR board (updated) |  | Fibertite Roof Overlay with PIR board
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
c0e9bd74-e7d8-5ee9-bae7-2272d9eaa5db | checkpoint | Area Accessible
0c87dabb-bb9c-53eb-a34b-a5354f8a9350 | checkpoint | Edge Protection in place
972a70d5-b3c3-5494-84a9-2f8250951f7c | checkpoint | Substrate ready for SWP
691ae12f-acc2-5904-80b8-90c3607eed06 | section | Substrate
4bbe7c4d-d166-5058-ac30-35970395face | checkpoint | Clean and wash down roof
743d695f-4269-5205-a9f2-153b9020999a | checkpoint | Mechanically fix existing roof pans to each purlin (1 fixing per pan 20mm class 4 steel tek)
f6c73b31-8ee0-5429-901f-6a6496757e86 | checkpoint | Skylights covered with plywood (by others)
aed7152d-8ab9-5172-b870-cb0253cef682 | checkpoint | Removal of ridge/old tray flashings
74992dd5-bd56-548b-8e51-da93d8ef1aa4 | section | VCL-Vapour Control Layer
cd888f55-8a1b-5d0c-8288-428e428a4d4b | checkpoint | Surface/substrate dry and clean
466eec61-37c9-5794-8df0-601bdb2e43f0 | checkpoint | All areas covered and lapped a minimum 100mm
c76f2066-dce6-5a14-95e0-1f0480ff3e3e | checkpoint | All holes/penetrations patched and made watertight
5b030369-a815-5423-9d64-e52a59fc1d21 | section | Roof pan infills
756b061c-3488-5273-b29f-3f96c74f542e | checkpoint | Surface is dry before installing PIR infills
5b609b25-2801-5de5-8547-7157a8e9cf08 | checkpoint | Butted together in every pan
56f3e634-b514-5240-8e08-cf3d021c39c4 | section | 80mm PIR
2477f1f4-2b6d-52de-a113-bf8fefbfbd00 | checkpoint | Substrate/surface dry & clean prior to being installed
d233c62e-d7fc-5559-a846-b8b60d11e882 | checkpoint | Boards tightly butted
c4e5c927-5e99-54f6-8c5b-29d460431864 | checkpoint | Correct Screws and load washer used
01d8a1da-0f1b-5d52-9816-77051de620b4 | checkpoint | Installed as per wind uplift fixing plan
a0251ca5-463c-4238-8f81-5cb4a7141c71 | checkpoint | Install PIR laminated plywood at gutter edge as per fixing plan
cf6cb777-e6df-403a-a5ec-b8e019f188f7 | checkpoint | Install zincalume flashing
b3098a4e-2d2d-5531-8d33-62cd3a06eec9 | section | Fibertite
4085aa83-c9b3-5afa-832b-39ce23bc81a9 | checkpoint | Correct Glue being used
d9f1de24-05fd-57db-81fd-a4868a881abf | checkpoint | Prime substrate where required
88678fa1-ad90-58bd-955c-52a39204d991 | checkpoint | Broom/rolling of Fibertite
cca6ba74-d669-5290-b383-3559ec5abb5b | checkpoint | Wipe/clean laps with acetone prior to welding
93ca56c0-5c85-472a-9484-efbad962ffce | checkpoint | Test weld with welding machine
cc20b976-2853-4532-a044-2bb0689c9c8c | checkpoint | Probe of seam with QA hook
ca24231d-3fc8-45f7-8327-b5bf609f6818 | section | Sumps
89a5f78a-87ca-4d95-92a1-cbbeef4b72f4 | checkpoint | Sealant installed to dropper flange under membrane
f2b69fd0-2017-422f-aba2-ffbb467aa8e9 | checkpoint | Membrane dressed in to outlets
9542b944-e161-452c-b9d2-b08bc6ff32fe | checkpoint | Clamp/rings/basket installed
78789b9a-1239-429b-8c10-0c0d7a6b1e8e | checkpoint | Flood test
81b0fc76-108f-49a6-9a94-385d2e138497 | checkpoint | Fibertite fully welded to flashing and QA'd with hook
899c239e-a307-4b2a-9689-f6f03d188602 | section | Smart bar installed
cf94e282-db19-4996-bdc0-1d332df6f75e | checkpoint | Smart bar installed as per fixing design
bcbdea37-934a-48ec-b24f-4e0537b3e4a3 | checkpoint | Wipe/clean laps with acetone prior to welding
73211c5e-9b36-4da1-8dd3-4212a0fa6a79 | checkpoint | Probe of seam with QA hook
40c697a3-1424-4249-a3de-3d28893726cf | section | Pressure bar installed
65c43686-c7fc-449f-bbe5-4796d2b59a25 | checkpoint | Installed correctly according to specifications ( right way around )
9bf64937-e22a-4281-b111-f0e76c25c9f8 | checkpoint | Fixings done according to specifications and details
665b86d1-088b-46d9-9b43-6bf726245f99 | checkpoint | Prime of Substrate where required
09e37594-0427-484a-8589-34de825b1925 | checkpoint | Sealant installed
f16eecf8-12c9-4484-85b9-23c01b5b88e0 | section | Over flashings
08bcdfb3-9cfb-4d28-b271-50cf5d766a25 | checkpoint | Over flashings has a separation barrier
ad900431-9609-4ff6-bf9a-ad6c9fe2f6d2 | checkpoint | Fixings done according to specifications and details
b2616b90-5aea-4279-a117-918771edb621 | checkpoint | Prime of Substrate where required
c13795e7-5688-4853-abc5-edc86ec03aae | checkpoint | Sealant installed
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
7522b949-ffcc-5857-970f-1d5304735f76 | checkpoint | All installation work completed, checked and reviewed as per specifications
b2a64aa1-bf30-568f-bbdc-39eae2319671 | checkpoint | Client/main contractor sign off
32d2f896-f3e8-4dd5-9cfd-63740b2eeb65 | checkpoint | All installation work completed, checked and reviewed as per specifications
2645322c-11b8-4eb1-99ff-f40553d038e5 | signoff | Client/main contractor sign off