## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Fibertite Roof Overlay with PIR board (updated) |  | Fibertite Roof Overlay with PIR board
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
c0e9bd74-e7d8-5ee9-bae7-2272d9eaa5db | checkpoint | Area Accessible
0c87dabb-bb9c-53eb-a34b-a5354f8a9350 | checkpoint | Edge Protection in place
972a70d5-b3c3-5494-84a9-2f8250951f7c | checkpoint | Substrate ready for SWP
691ae12f-acc2-5904-80b8-90c3607eed06 | section | Substrate
4bbe7c4d-d166-5058-ac30-35970395face | checkpoint | Clean and wash down roof
743d695f-4269-5205-a9f2-153b9020999a | checkpoint | Mechanically fix existing roof pans to each purlin (1 fixing per pan 20mm class 4 steel tek)
f6c73b31-8ee0-5429-901f-6a6496757e86 | checkpoint | Skylights covered with plywood (by others)
aed7152d-8ab9-5172-b870-cb0253cef682 | checkpoint | Removal of ridge/old tray flashings
74992dd5-bd56-548b-8e51-da93d8ef1aa4 | section | VCL-Vapour Control Layer
cd888f55-8a1b-5d0c-8288-428e428a4d4b | checkpoint | Surface/substrate dry and clean
466eec61-37c9-5794-8df0-601bdb2e43f0 | checkpoint | All areas covered and lapped a minimum 100mm
c76f2066-dce6-5a14-95e0-1f0480ff3e3e | checkpoint | All holes/penetrations patched and made watertight
5b030369-a815-5423-9d64-e52a59fc1d21 | section | Roof pan infills
756b061c-3488-5273-b29f-3f96c74f542e | checkpoint | Surface is dry before installing PIR infills
5b609b25-2801-5de5-8547-7157a8e9cf08 | checkpoint | Butted together in every pan
56f3e634-b514-5240-8e08-cf3d021c39c4 | section | 80mm PIR
2477f1f4-2b6d-52de-a113-bf8fefbfbd00 | checkpoint | Substrate/surface dry & clean prior to being installed
d233c62e-d7fc-5559-a846-b8b60d11e882 | checkpoint | Boards tightly butted
c4e5c927-5e99-54f6-8c5b-29d460431864 | checkpoint | Correct Screws and load washer used
01d8a1da-0f1b-5d52-9816-77051de620b4 | checkpoint | Installed as per wind uplift fixing plan
| checkpoint | Install PIR laminated plywood at gutter edge as per fixing plan
| checkpoint | Install zincalume flashing
b3098a4e-2d2d-5531-8d33-62cd3a06eec9 | section | Fibertite
4085aa83-c9b3-5afa-832b-39ce23bc81a9 | checkpoint | Correct Glue being used
d9f1de24-05fd-57db-81fd-a4868a881abf | checkpoint | Prime substrate where required
88678fa1-ad90-58bd-955c-52a39204d991 | checkpoint | Broom/rolling of Fibertite
cca6ba74-d669-5290-b383-3559ec5abb5b | checkpoint | Wipe/clean laps with acetone prior to welding
| checkpoint | Test weld with welding machine
| checkpoint | Probe of seam with QA hook
| section | Sumps
| checkpoint | Sealant installed to dropper flange under membrane
| checkpoint | Membrane dressed in to outlets
| checkpoint | Clamp/rings/basket installed
| checkpoint | Flood test
| checkpoint | Fibertite fully welded to flashing and QA'd with hook
| section | Smart bar installed
| checkpoint | Smart bar installed as per fixing design
| checkpoint | Wipe/clean laps with acetone prior to welding
| checkpoint | Probe of seam with QA hook
| section | Pressure bar installed
| checkpoint | Installed correctly according to specifications ( right way around )
| checkpoint | Fixings done according to specifications and details
| checkpoint | Prime of Substrate where required
| checkpoint | Sealant installed
| section | Over flashings
| checkpoint | Over flashings has a separation barrier
| checkpoint | Fixings done according to specifications and details
| checkpoint | Prime of Substrate where required
| checkpoint | Sealant installed
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
7522b949-ffcc-5857-970f-1d5304735f76 | checkpoint | All installation work completed, checked and reviewed as per specifications
b2a64aa1-bf30-568f-bbdc-39eae2319671 | checkpoint | Client/main contractor sign off
| checkpoint | All installation work completed, checked and reviewed as per specifications
| signoff | Client/main contractor sign off