## Sheet1
1 | Permits | H | Obtain Permits | As required | Document Review | Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place | Permit attached or permit number noted | 1 - Permits | ACTION (Hold, Monitor, Witness) - H | DETAIL - Obtain Permits | FREQUENCY - As required | INSPECTION - Document Review | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place | RECORDS - Permit attached or permit number noted | 1 - Permits
2 | Design (1) | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | 2 - Design (1) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Ensure that Design is approved and Drawings are of the latest revision | FREQUENCY - Prior to commencement | INSPECTION - Document Review | CONFORMANCE CRITERIA - | RECORDS - Check Drawing Register | ACTION (Hold, Monitor, Witness) - H
2 | Design (2) |  | Produce Shop Drawings and Submit for approval | Prior to Commencement | Document Review | Drawing Register | Check Drawing Register | 2 - Design (2) | ACTION (Hold, Monitor, Witness) - | DETAIL - Produce Shop Drawings and Submit for approval | FREQUENCY - Prior to Commencement | INSPECTION - Document Review | CONFORMANCE CRITERIA - Drawing Register | RECORDS - Check Drawing Register | DETAIL - Obtain Permits
3 | Survey Setout | H | Formwork / Mould to be setout to be inspected by Site Engineer prior to concrete being poured | Prior to commencement | Visual Inspection / Measure | Consistency with Construction Drawing | FHIMS-CS-4008 | 3 - Survey Setout | ACTION (Hold, Monitor, Witness) - H | DETAIL - Formwork / Mould to be setout to be inspected by Site Engineer prior to concrete being poured | FREQUENCY - Prior to commencement | INSPECTION - Visual Inspection / Measure | CONFORMANCE CRITERIA - Consistency with Construction Drawing | RECORDS - FHIMS-CS-4008 | FREQUENCY - As required
4 | Material Compliance (1) | H | Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete | Prior to commencement | Document review |  | Design Engineer Approval | 4 - Material Compliance (1) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete | FREQUENCY - Prior to commencement | INSPECTION - Document review | CONFORMANCE CRITERIA - | RECORDS - Design Engineer Approval | INSPECTION - Document Review
4 | Material Compliance (2) | H | All concrete delivered to site shall be produced strictly in accordance with the approved mix design | Prior to pouring concrete | Concrete Delivery Dockets |  | Concrete Delivery Dockets | 4 - Material Compliance (2) | ACTION (Hold, Monitor, Witness) - H | DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design | FREQUENCY - Prior to pouring concrete | INSPECTION - Concrete Delivery Dockets | CONFORMANCE CRITERIA - | RECORDS - Concrete Delivery Dockets | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place
4 | Material Compliance (3) | H | Steel Reinforcement shall comply with AS/NZS 4671 CHAR(AMP) NZS3109 and shall be the grade called up on the drawings | Prior to ordering steel | Document review | AS/NZS4671CHAR(AMP)NZS3109 | Detail Sheets and Mill Certificates | 4 - Material Compliance (3) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 CHAR(AMP) NZS3109 and shall be the grade called up on the drawings | FREQUENCY - Prior to ordering steel | INSPECTION - Document review | CONFORMANCE CRITERIA - AS/NZS4671CHAR(AMP)NZS3109 | RECORDS - Detail Sheets and Mill Certificates | RECORDS - Permit attached or permit number noted
4 | Material Compliance (4) | H | Any welding or mechanical splicing to be approved in writing by the Design Engineer | Prior to welding or splicing | Document review |  | Mark Up As Built Drawings | 4 - Material Compliance (4) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Any welding or mechanical splicing to be approved in writing by the Design Engineer | FREQUENCY - Prior to welding or splicing | INSPECTION - Document review | CONFORMANCE CRITERIA - | RECORDS - Mark Up As Built Drawings | 2 - Design (1)
4 | Material Compliance (5) | H | Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer | Prior to cutting or bending on site | Document review |  | Mark Up As Built Drawings | 4 - Material Compliance (5) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer | FREQUENCY - Prior to cutting or bending on site | INSPECTION - Document review | CONFORMANCE CRITERIA - | RECORDS - Mark Up As Built Drawings | ACTION (Hold, Monitor, Witness) - H
5 | Reinforcing (1) | W | Reinforcing steel shall be handled, placed and fixed as per NZS 3109 | Daily Visual Inspection | Document review | Concrete Inspection Record | FHIMS-CS-4008 | 5 - Reinforcing (1) | ACTION (Hold, Monitor, Witness) - W | DETAIL - Reinforcing steel shall be handled, placed and fixed as per NZS 3109 | FREQUENCY - Daily Visual Inspection | INSPECTION - Document review | CONFORMANCE CRITERIA - Concrete Inspection Record | RECORDS - FHIMS-CS-4008 | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
5 | Reinforcing (2) | H | Check Finished Reinforcing cage to ensure correct spacing, grade, diameter and number of bars | Prior to concrete pour | Visual inspection | Concrete Inspection Record | FHIMS-CS-4008 | 5 - Reinforcing (2) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Check Finished Reinforcing cage to ensure correct spacing, grade, diameter and number of bars | FREQUENCY - Prior to concrete pour | INSPECTION - Visual inspection | CONFORMANCE CRITERIA - Concrete Inspection Record | RECORDS - FHIMS-CS-4008 | FREQUENCY - Prior to commencement
5 | Reinforcing (3) | H | Check for any cast in items and ensure they are fixed correctly | Prior to concrete pour | Visual inspection | Concrete Inspection Record | FHIMS-CS-4008 | 5 - Reinforcing (3) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Check for any cast in items and ensure they are fixed correctly | FREQUENCY - Prior to concrete pour | INSPECTION - Visual inspection | CONFORMANCE CRITERIA - Concrete Inspection Record | RECORDS - FHIMS-CS-4008 | INSPECTION - Document Review
6 | Pre-tensioning (1) | H | Review Strand stressing / extension calculations comply with Specifications | Prior to concrete pour | Document Review |  | FHIMS-CS-4008 | 6 - Pre-tensioning (1) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Review Strand stressing / extension calculations comply with Specifications | FREQUENCY - Prior to concrete pour | INSPECTION - Document Review | CONFORMANCE CRITERIA - | RECORDS - FHIMS-CS-4008 | CONFORMANCE CRITERIA -
6 | Pre-tensioning (2) | H | Check Strand Size and type complies with Specifications | Prior to concrete pour | Visual Inspection |  | FHIMS-CS-4008 | 6 - Pre-tensioning (2) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Check Strand Size and type complies with Specifications | FREQUENCY - Prior to concrete pour | INSPECTION - Visual Inspection | CONFORMANCE CRITERIA - | RECORDS - FHIMS-CS-4008 | RECORDS - Check Drawing Register
6 | Pre-tensioning (3) | H | Check Debound lengths, and compliance with strand schedule | Prior to concrete pour | Visual Inspection |  | FHIMS-CS-4008 | 6 - Pre-tensioning (3) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Check Debound lengths, and compliance with strand schedule | FREQUENCY - Prior to concrete pour | INSPECTION - Visual Inspection | CONFORMANCE CRITERIA - | RECORDS - FHIMS-CS-4008 | 2 - Design (2)
6 | Pre-tensioning (4) | H | Check Actual Strand Stress/Extension with theoretical value. | Prior to concrete pour | Visual Inspection |  | FHIMS-CS-4008 | 6 - Pre-tensioning (4) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Check Actual Strand Stress/Extension with theoretical value. | FREQUENCY - Prior to concrete pour | INSPECTION - Visual Inspection | CONFORMANCE CRITERIA - | RECORDS - FHIMS-CS-4008 | ACTION (Hold, Monitor, Witness) -
7 | Concreting (1) | H | The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection |  | FHIMS-CS-4008 | 7 - Concreting (1) | ACTION (Hold, Monitor, Witness) - H | DETAIL - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | FREQUENCY - Prior to concrete pour | INSPECTION - Visual inspection | CONFORMANCE CRITERIA - | RECORDS - FHIMS-CS-4008 | DETAIL - Produce Shop Drawings and Submit for approval
7 | Concreting (2) | H | Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets | Prior to concrete pour | Test Results | NZS 3104 | FHIMS-CS-4090 | 7 - Concreting (2) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets | FREQUENCY - Prior to concrete pour | INSPECTION - Test Results | CONFORMANCE CRITERIA - NZS 3104 | RECORDS - FHIMS-CS-4090 | FREQUENCY - Prior to Commencement
7 | Concreting (3) | H | Concrete surfaces shall be F4 or better for formed surfaces and U2 or better for unformed surfaces, Bridge decks U5 (broom) finish | At completion of pour | Visual inspection | Concrete Inspection Record | FHIMS-CS-4008 | 7 - Concreting (3) | ACTION (Hold, Monitor, Witness) - H | DETAIL - Concrete surfaces shall be F4 or better for formed surfaces and U2 or better for unformed surfaces, Bridge decks U5 (broom) finish | FREQUENCY - At completion of pour | INSPECTION - Visual inspection | CONFORMANCE CRITERIA - Concrete Inspection Record | RECORDS - FHIMS-CS-4008 | INSPECTION - Document Review
8 | Striking of formwork and curing of Units | W | Striping of Beams shall only commence when Concrete has reached release strength and minimum 12 hours of curing | At completion of pour | Visual inspection | Concrete Inspection Record | FHIMS-CS-4008 | 8 - Striking of formwork and curing of Units | ACTION (Hold, Monitor, Witness) - W | DETAIL - Striping of Beams shall only commence when Concrete has reached release strength and minimum 12 hours of curing | FREQUENCY - At completion of pour | INSPECTION - Visual inspection | CONFORMANCE CRITERIA - Concrete Inspection Record | RECORDS - FHIMS-CS-4008 | CONFORMANCE CRITERIA - Drawing Register
9 | Beam Hog | M | To be Measured prior to site delivery. Deck slab thickness to be adjusted if required. | Prior to Precast Unit Delivery | Visual Inspection |  | FHIMS-CS-4008 | 9 - Beam Hog | ACTION (Hold, Monitor, Witness) - M | DETAIL - To be Measured prior to site delivery. Deck slab thickness to be adjusted if required. | FREQUENCY - Prior to Precast Unit Delivery | INSPECTION - Visual Inspection | CONFORMANCE CRITERIA - | RECORDS - FHIMS-CS-4008 | RECORDS - Check Drawing Register
10 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | 10 - As-builts | ACTION (Hold, Monitor, Witness) - H | DETAIL - Red pen mark up drawings to be included in QA file | FREQUENCY - At the completion of the Lot of work | INSPECTION - Drawings | CONFORMANCE CRITERIA - | RECORDS - Asbuilt Drawing | 3 - Survey Setout
11 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into M-Files | Delivery Dockets, Test Reports, Lab Testing Register | 11 - Lot Number QA File | ACTION (Hold, Monitor, Witness) - W | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | FREQUENCY - At completion of Lot | INSPECTION - Document Review | CONFORMANCE CRITERIA - Ensure all QA is uploaded into M-Files | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register | ACTION (Hold, Monitor, Witness) - H
DETAIL - Formwork / Mould to be setout to be inspected by Site Engineer prior to concrete being poured
FREQUENCY - Prior to commencement
INSPECTION - Visual Inspection / Measure
CONFORMANCE CRITERIA - Consistency with Construction Drawing
RECORDS - FHIMS-CS-4008
4 - Material Compliance (1)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete
FREQUENCY - Prior to commencement
INSPECTION - Document review
CONFORMANCE CRITERIA -
RECORDS - Design Engineer Approval
4 - Material Compliance (2)
ACTION (Hold, Monitor, Witness) - H
DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
FREQUENCY - Prior to pouring concrete
INSPECTION - Concrete Delivery Dockets
CONFORMANCE CRITERIA -
RECORDS - Concrete Delivery Dockets
4 - Material Compliance (3)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 CHAR(AMP) NZS3109 and shall be the grade called up on the drawings
FREQUENCY - Prior to ordering steel
INSPECTION - Document review
CONFORMANCE CRITERIA - AS/NZS4671CHAR(AMP)NZS3109
RECORDS - Detail Sheets and Mill Certificates
4 - Material Compliance (4)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Any welding or mechanical splicing to be approved in writing by the Design Engineer
FREQUENCY - Prior to welding or splicing
INSPECTION - Document review
CONFORMANCE CRITERIA -
RECORDS - Mark Up As Built Drawings
4 - Material Compliance (5)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
FREQUENCY - Prior to cutting or bending on site
INSPECTION - Document review
CONFORMANCE CRITERIA -
RECORDS - Mark Up As Built Drawings
5 - Reinforcing (1)
ACTION (Hold, Monitor, Witness) - W
DETAIL - Reinforcing steel shall be handled, placed and fixed as per NZS 3109
FREQUENCY - Daily Visual Inspection
INSPECTION - Document review
CONFORMANCE CRITERIA - Concrete Inspection Record
RECORDS - FHIMS-CS-4008
5 - Reinforcing (2)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Check Finished Reinforcing cage to ensure correct spacing, grade, diameter and number of bars
FREQUENCY - Prior to concrete pour
INSPECTION - Visual inspection
CONFORMANCE CRITERIA - Concrete Inspection Record
RECORDS - FHIMS-CS-4008
5 - Reinforcing (3)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Check for any cast in items and ensure they are fixed correctly
FREQUENCY - Prior to concrete pour
INSPECTION - Visual inspection
CONFORMANCE CRITERIA - Concrete Inspection Record
RECORDS - FHIMS-CS-4008
6 - Pre-tensioning (1)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Review Strand stressing / extension calculations comply with Specifications
FREQUENCY - Prior to concrete pour
INSPECTION - Document Review
CONFORMANCE CRITERIA -
RECORDS - FHIMS-CS-4008
6 - Pre-tensioning (2)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Check Strand Size and type complies with Specifications
FREQUENCY - Prior to concrete pour
INSPECTION - Visual Inspection
CONFORMANCE CRITERIA -
RECORDS - FHIMS-CS-4008
6 - Pre-tensioning (3)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Check Debound lengths, and compliance with strand schedule
FREQUENCY - Prior to concrete pour
INSPECTION - Visual Inspection
CONFORMANCE CRITERIA -
RECORDS - FHIMS-CS-4008
6 - Pre-tensioning (4)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Check Actual Strand Stress/Extension with theoretical value.
FREQUENCY - Prior to concrete pour
INSPECTION - Visual Inspection
CONFORMANCE CRITERIA -
RECORDS - FHIMS-CS-4008
7 - Concreting (1)
ACTION (Hold, Monitor, Witness) - H
DETAIL - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
FREQUENCY - Prior to concrete pour
INSPECTION - Visual inspection
CONFORMANCE CRITERIA -
RECORDS - FHIMS-CS-4008
7 - Concreting (2)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets
FREQUENCY - Prior to concrete pour
INSPECTION - Test Results
CONFORMANCE CRITERIA - NZS 3104
RECORDS - FHIMS-CS-4090
7 - Concreting (3)
ACTION (Hold, Monitor, Witness) - H
DETAIL - Concrete surfaces shall be F4 or better for formed surfaces and U2 or better for unformed surfaces, Bridge decks U5 (broom) finish
FREQUENCY - At completion of pour
INSPECTION - Visual inspection
CONFORMANCE CRITERIA - Concrete Inspection Record
RECORDS - FHIMS-CS-4008
8 - Striking of formwork and curing of Units
ACTION (Hold, Monitor, Witness) - W
DETAIL - Striping of Beams shall only commence when Concrete has reached release strength and minimum 12 hours of curing
FREQUENCY - At completion of pour
INSPECTION - Visual inspection
CONFORMANCE CRITERIA - Concrete Inspection Record
RECORDS - FHIMS-CS-4008
9 - Beam Hog
ACTION (Hold, Monitor, Witness) - M
DETAIL - To be Measured prior to site delivery. Deck slab thickness to be adjusted if required.
FREQUENCY - Prior to Precast Unit Delivery
INSPECTION - Visual Inspection
CONFORMANCE CRITERIA -
RECORDS - FHIMS-CS-4008
10 - As-builts
ACTION (Hold, Monitor, Witness) - H
DETAIL - Red pen mark up drawings to be included in QA file
FREQUENCY - At the completion of the Lot of work
INSPECTION - Drawings
CONFORMANCE CRITERIA -
RECORDS - Asbuilt Drawing
11 - Lot Number QA File
ACTION (Hold, Monitor, Witness) - W
DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
FREQUENCY - At completion of Lot
INSPECTION - Document Review
CONFORMANCE CRITERIA - Ensure all QA is uploaded into M-Files
RECORDS - Delivery Dockets, Test Reports, Lab Testing Register