## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b1abb6dc-5e0c-45c6-a5b7-5ef2382112ba | checklist | 03.02 - Supply and Installation of Precast Concrete Pipe | itp | 03.02 - Supply and Installation of Precast Concrete Pipe
e9c73d98-507c-41b4-af89-82416531324e | section | Details
63154636-6bbe-4521-a44d-752d9f62b5f6 | checkpoint | Lot Boundaries
58bbd35c-fdcc-51fd-9768-416096017c8f | note | Acceptance Criteria and Frequency (Project Specific) - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
29604530-d761-5676-abee-278f38692658 | note | Check Item - Check & Verify
23bd07e7-b0a6-4fee-9ebb-b05ab5fe5898 | checkpoint | Materials
612905fc-a320-50cb-a083-d5f0f95db67e | note | Acceptance Criteria and Frequency (Project Specific) - Bed Zone Material: 5mm or 10mm screenings. Embedment Zone Material: 5mm or 10mm screenings Backfill Material: Granular fill comprising rock (75mm maximum size, non plastic open graded material) or crusher run recycled concrete.
1144bd8b-43bf-5c65-802b-eff37590e142 | note | Check Item - Check Item
9ba44756-611e-572e-be76-019eeb1c88d2 | note | Reference - Note 2 IPEA STD DRW DS-030
9c2c2b43-75f0-4592-8b2b-450c86afb4d9 | checkpoint | Geometric Tolerances
42713209-c0c6-5790-9c16-4113ffffc50f | note | Acceptance Criteria and Frequency (Project Specific) - Pipes are laid from the discharge end upstream to the following tolerances: o invert levels–±50mm; o manhole locations–within 1,000mm of design; o gully locations–within 300mm of design.
1019116d-7863-5fdc-bfdc-5a3f01a88c22 | note | Check Item - Check & Verify
f964c8cf-b396-5bed-8bac-6d33a0c1a607 | note | Reference - Standard specification No. 3 Cl4.2
34386a8f-3ba1-4a72-808e-10c055ca9fad | checkpoint | Excavation
ffb42a95-2a55-51f6-a9e7-3b47c1b3ba1c | note | Acceptance Criteria and Frequency (Project Specific) - • Drainage lines and structures shall set out in accordance with the details shown in the Drawings • Excavation constructed to the shapes, alignment, and level shown on the drawings bottom of excavations shall be trimmed to the tolerances specified • Where excavation is carried out in asphalt pavement, the pavement has been cut 150mm beyond the limits of the trench excavation width • Trench not excavated wider than the trench width shown on the approved drawings. • All excavations are made in a careful manner to ensure they are rendered secure and safe by sheeting or other means
55ff1285-1a4b-591b-bcd5-b31ce612231f | note | Check Item - Check & Verify
69e85d0a-7926-5b39-9ea7-58ca02a9082a | note | Reference - Standard specification No. 3 Cl3.1
48ef5a67-0f97-4ef0-8108-88c4615b2220 | checkpoint | Trench Foundation
9a721b42-27b5-5b49-82da-0720f2e0e15a | note | Acceptance Criteria and Frequency (Project Specific) - Trench Foundation Inspected prior to placing of bedding material. Hold Point
d58704fb-da17-5df4-ba3c-61d84ec4584c | note | Check Item - Hold Point
29ec71cb-1333-53a8-8b08-0b8e6b0857db | note | Reference - RID/14/2018 & RID/15/2018 Cl 7.0
d4617003-d189-4377-9c64-c30c5e99e260 | signoff | Hold Point
745fc26f-c6e6-42e9-a3d6-7d81106d5414 | checkpoint | Unsuitable Trench Foundation
21ae44f4-7088-5960-8092-f5bec6fcbed3 | note | Acceptance Criteria and Frequency (Project Specific) - Where the excavation encounters ground water or other poor ground conditions at foundation, the depth of the bedding and surround material is to be increased to provide adequate support for the pipe as approved by the local government. Hold Point
6d448a87-a2ab-58f6-87d0-e7f8b84fab61 | note | Check Item - Hold Point
79e01b62-825d-5321-9d9e-c59c860ec039 | note | Reference - Standard specification No. 3 Cl3.3
ea027be8-25a0-4cc2-b8fe-1ad5c7a8ab55 | signoff | Hold Point
c750a697-fe36-456c-85e8-2df8b9d356f4 | checkpoint | Drainage of Bedding Material
0234d329-c84c-5db4-8f63-4c60163385af | note | Acceptance Criteria and Frequency (Project Specific) - Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material.
5a621b88-f8ef-5348-9c18-31c32db99504 | note | Check Item - Check & Verify
19d9fd90-8cc0-56ce-8bb7-34cc8c4d4bb4 | note | Reference - Standard specification No. 3 Cl3.2
76cc2cc9-fc81-4e13-97dd-ed01a354e79d | checkpoint | Pipe Laying
9e8bcfd5-4680-5d2c-b277-99e2ad920ab0 | note | Acceptance Criteria and Frequency (Project Specific) - • Pipes are laid true to line and grade, and are free draining and firmly bedded. • Circular pipes with elliptical reinforcement supplied with marked “Top” and “Bottom” to indicate the correct position when laid and such pipes are laid correctly according to the marking. • For pipes up to and including 600mm diameter, the socketed end of the pipe is laid upstream and a shallow excavation is made under the socket of each pipe so that the pipe fully rests for its full length of barrel upon the bedding material in the trench. • Elastomeric ring joints are carefully made ensuring the spigot and socket are clean, and the rubber ring is rolled evenly into place and elastomeric ring lubricant is used for fibre reinforced concrete pipes. • For concrete pipes greater than 600mm diameter, internal interlocking joints may be used and the pipes are laid generally as specified in section 4.2 (Pipe laying) of this standard specification. • Externally the pipe joint is sealed with an approved proprietary manufactured natural rubber jointing band. • Lifting holes in all pipes are plugged by a method approved by the local government.
6de2bf88-1981-5d1e-8409-f478abed442f | note | Check Item - Check & Verify
c76c000a-eaf8-5b5f-8e74-d1e88e8cbf4f | note | Reference - Standard specification No. 3 Cl4.2
b09bbee5-304d-4e28-b2d2-8d7e381c3a16 | checkpoint | Jointing Pipes - Spigot and Socket
f6d9f006-3ca9-5a38-a60e-8faac96aef35 | note | Acceptance Criteria and Frequency (Project Specific) - Where specified, spigot and socket pipes are joined by elastomeric ring joints which is in accordance with AS 1646–2007 Elastomeric seals for waterworks purposes–General requirements.
8a9e25d1-eaaf-513f-92f4-8f1f4d8cb188 | note | Check Item - Check & Verify
1b08e442-ee8c-59a2-ba10-3cfd5cdb5fbe | note | Reference - Standard specification No. 3 Cl4.3
eb5c399a-90df-4a28-bf6e-6d58d713938d | checkpoint | Jointing Pipes - Flush Joint
5dc623e6-7fd5-5856-b32b-4d043859ac4e | note | Acceptance Criteria and Frequency (Project Specific) - When a flush jointed pipe is used: • the first pipe (downstream) is bedded to established line and grade with the groove upstream; • the external band is installed after the joint is made, in accordance with manufacturer’s recommendations.
c05c4c1e-d71f-5f37-9e99-cd120054feec | note | Check Item - Check & Verify
9a6689ed-0e78-5e82-9a0a-40945977e1bc | note | Reference - Standard specification No. 3 Cl4.3
bab8e23b-3239-4d7f-ba7b-e38efb0e2448 | checkpoint | Pipe Backfill
c490910a-dfdb-5969-bcb2-703c0fed826d | note | Acceptance Criteria and Frequency (Project Specific) - Backfill is not placed until the Culvert pipe has been inspected and approved
b59a9152-93aa-5063-8ca6-c6a1492f6ac2 | note | Check Item - Hold Point
1b85da57-99b2-54c1-8050-c743e18663e2 | note | Reference - Standard specification No. 3 Cl5.1
0d7804c4-82b1-4c63-aed8-0ab74400cb89 | signoff | Hold Point
4a524551-1d43-4409-9a08-215e10c24aa5 | checkpoint | Pipe Backfill - Road Reserve
bcc8d0eb-7fbd-5b2d-8041-7cb1441bcbe6 | note | Acceptance Criteria and Frequency (Project Specific) - Where stormwater pipe is laid in a drainage easement or property other than the road reserve, backfill material may comply to the requirements of general fill providing that a minimum CBR of 5 is evidenced. 5 or 10mm drainage screenings are to be fully wrapped in A34 geofabric for all stormwater trenches located within a property easement or park land Compaction Testing: 1 test per 100 m³, 2 per Lot.
fa921723-3c58-581e-8534-6a8a352ad34b | note | Check Item - Check & Verify
a3d4e139-2432-53b3-bd73-a105a0387860 | note | Reference - RID/14/2018 & RID/15/2018 Cl 26.0
72650f32-7a5b-4071-9cdf-1aa1137280ed | checkpoint | Pipe Backfill - Drainage Easement
353a9687-abd9-5d97-9276-8f895a39cf0c | note | Acceptance Criteria and Frequency (Project Specific) - Where stormwater pipe is laid in a drainage easement or property other than the road reserve, backfill material may comply to the requirements of general fill providing that a minimum CBR of 5 is evidenced. 5 or 10mm drainage screenings are to be fully wrapped in A34 geofabric for all stormwater trenches located within a property easement or park land Compaction Testing: 1 test per 100 m³, 2 per Lot.
ed00e05f-7b14-53cf-a0d9-3301c7650ed9 | note | Check Item - Check & Verify
6631d1cc-1530-561e-9139-b2f1012559bb | note | Reference - RID/14/2018 & RID/15/2018 Cl 26.0
e878350b-95c4-4a6f-a7d6-b5bbb04b5af5 | checkpoint | Final Verification
2f510f7b-9585-582f-9d17-1cef2acf81c9 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
5d8fb252-d8d1-5890-9866-e531856fe386 | textbox | Print Name:
10d8df72-455a-547e-8d86-fa6e174b0f69 | date | Date:
020abb14-2ec7-55d0-a850-0588f9df70f9 | note | Client Verify that the Above has been Constructed according to Specification
0c6a8fdf-73a6-57b1-b453-52deba3fcdf0 | textbox | Print Name:
e1b86d7c-50b9-540d-b9ce-0ba030ea5e24 | date | Date:
0a93e514-14da-4cda-8bda-b2b540e064ac | signoff | Signature
8376d1f5-518b-40cd-b4b0-9d378ccf2e6c | checklist | Concrete Works | itp | Concrete Works
54ee2d6a-1729-4472-be8a-bf9f3e5bfbaf | section | Details
28ab83c4-c849-4ddb-9913-53273e5110d6 | checkpoint | Concrete batching
bdce59e5-dd9c-5305-894c-3f5a3896afe7 | note | Acceptance Criteria and Frequency (Project Specific) - Ready mixed concrete shall be supplied by a manufacturer: (a) approved by the local government; (b) which has an accredited quality assurance system.
29e59bbd-f67a-5a1c-9a73-3fb1e4c6f364 | note | Check Item - Check & Verify
54a40bbc-e7b0-5058-9a79-f3889eb5cf1f | note | Reference - Standard specification No. 7 Cl2.5
99f79fe9-cc91-4821-a3d4-53272d4cabc9 | checkpoint | Concrete testing
dc53cb4f-0f16-5389-a33a-4078d8b7387d | note | Acceptance Criteria and Frequency (Project Specific) - The frequency of sampling and testing to be in accordance with the Department of Transport and Main Roads – MRTS070 Concrete Technical Specification – Sampling Frequencies per Lot for 28 Day Strength Tests. However, For concrete footpath and driveway slab construction, the frequency of testing is to be reduced to one (1) batch per day. Testing is to provide one (1) 7 day test result and two (2) 28 day test results.
795b27bb-ce1d-58df-8e4e-09ea520d6086 | note | Check Item - Test Results
3ff9ab18-2c4e-5412-a154-6aa805aeda37 | note | Reference - Quotation Notes Cl25. & Cl40.
348475d1-537f-4dbf-b941-64ce353c6d29 | checkpoint | Concrete Slump
d772966e-9c44-56aa-8b4b-99b497f3bf14 | note | Acceptance Criteria and Frequency (Project Specific) - The consistency and workability of concrete shall be such that it complies with the Slump limits specified in Table 2.4.1 below. Any extra water that is added to concrete on site shall be measured and recorded and the concrete shall be thoroughly remixed and reslumped.
06e67726-2507-5524-9756-d9c5102e8a51 | note | Check Item - Check & Verify
810e1728-dfe5-51dd-85f9-745aad4e9902 | note | Reference - Standard specification No. 7 Cl2.4
23f59dc8-7d76-45f6-b697-4cc2ba10dc04 | checkpoint | Approval to place concrete
e0ebe542-395c-5f1f-9a8a-bf372b4e8adb | note | Acceptance Criteria and Frequency (Project Specific) - All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the Inspector. Hold Point
5b0106a4-da2e-52df-9b96-f267e0c3f9b0 | note | Check Item - Check & Verify
7f5e7828-5278-5557-9871-04aba55e410c | note | Reference - Standard specification No. 7 Cl4.1
9739a956-9ef1-4b9c-96e2-66845afc2a0f | signoff | HOLD POINT
75228dbb-eee9-4112-bc85-eae26d92d82a | checkpoint | Placing time limit
d66a4643-d921-5d3a-9c0e-66a7ab3dae23 | note | Acceptance Criteria and Frequency (Project Specific) - Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government.
b72cd4fd-b067-5dcf-bb5c-799797f8dd21 | note | Check Item - Check & Verify
7b711915-65c9-5a42-997e-a46dd9695a07 | note | Reference - Standard specification No. 7 Cl4.3
9c601c3c-9098-4394-a4f3-f71d5cd71830 | checkpoint | Finishing of concrete
abc0c114-dcfc-5fb5-a42c-ddc15ff8b13a | note | Acceptance Criteria and Frequency (Project Specific) - All surfaces of concrete that are exposed to view in the completed structure are finished such that: (a) immediately after the removal of forms, all fins and other projections are ground off, all pockets and honeycombs are cleaned and filled with a stiff cement mortar having the same proportion of cement and sand as the original concrete, and the surface of the patch is ground flush; (b) decks are roughened slightly by brooming or other approved method before initial set; (c) kerb and channel, invert crossings, vehicle crossings and industrial crossings are finished with an approved steel finishing tool; (d) footpaths and pram ramps are finished with a wooden float and broomed.
81fa16dd-ab77-50c7-941a-6cd6b2f82898 | note | Check Item - Check 7 Verify
311dc082-5ae2-5440-8393-b1203332f51b | note | Reference - Standard specification No. 7 Cl6.1
2658dcb3-8099-4b04-abc3-fdbd8e8fc149 | checkpoint | Curing of concrete
347ac154-2eb5-5436-a671-466717888d72 | note | Acceptance Criteria and Frequency (Project Specific) - Curing shall be commenced immediately on completion of the finishing of exposed surfaces or within 30 minutes of removal of the forms from other surfaces and shall be completed using either of the following method: (a) Spraying and approved curing compound; or (b) Using water sprays or wet sand in which case the surfaces are kept moist 24 hours a day for the full period specified
46340925-a92b-5ddb-87c5-2c29565c7d1a | note | Check Item - Check & Verify
8bc53868-6755-5794-812c-b54ba27f86d0 | note | Reference - Standard specification No. 7 Cl6.3
06ef425f-ddea-45e2-a731-34e518e7e1ec | signoff | HOLD POINT
f2bfbf44-8e01-4766-b133-e9a904b0ea06 | checkpoint | Removal of Forms / Falsework
231357bc-60a7-509e-b697-9bc63ef033b5 | note | Acceptance Criteria and Frequency (Project Specific) - Forms/Falsework shall not be removed from the concrete until the times specified the table below are met:
ad7e0534-319d-5482-8517-8c32d3636125 | note | Check Item - Check & Verify
cfa83f9f-66d9-5d2a-a36b-5dece64582df | note | Reference - Standard specification No. 7 Cl6.2
192e570a-2eb7-4313-b0f3-4feac7e876b6 | checkpoint | Final Verification
00c0f7d7-4438-5588-92a2-6be94e1777c9 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
e437d52d-f4ee-59af-a236-6f5fa3679474 | textbox | Print Name:
fa9b4f98-854c-5d79-8007-3d825018966e | date | Date:
9da76827-f9dd-5ef1-b1f1-173ca094abf2 | note | Client Verify that the Above has been Constructed according to Specification
63764302-14ec-567c-9e2d-83f087e4fcab | textbox | Print Name:
3a3bb839-1cc7-55b1-ba8a-d530f247a33b | date | Date:
8178037c-7d2a-4d12-b18a-ee2e0c5662af | signoff | Signature
ca691b8e-de90-4b03-bb19-3966fc9fa2ef | checklist | Installation of Insitu Stormwater Structures | itp | Installation of Insitu Stormwater Structures
c0615e7c-6364-41c2-8cea-d91124f05ef5 | section | Details
fc1b6c7b-f9f9-4e70-8010-9a988b5b8ea9 | checkpoint | Lot Boundaries
b29a69b1-7e6f-5311-8ce7-7401f25dc3a5 | note | Lot Size: Each Stormwater Structures
139867f8-5a74-5f1b-8ff3-7581f1c065ec | note | Check Item - Check & Verify
ef823457-0338-4954-bfba-57af2c08578b | checkpoint | Setout
1aea0c6c-3a9d-5083-9758-4ee9688b09e4 | note | Acceptance Criteria and Frequency (Project Specific) - Stormwater structures set out in accordance with the details shown in the drawing and within the following tolerances: o invert levels – ±50mm; o manhole locations – within 1,000mm of design;
e75e5140-6e4f-5e62-b994-3f65b074fa1f | note | Check Item - Check & Verify
24f716b7-5345-557a-aab5-793b0766c128 | note | Reference - Standard specification No. 3 Cl3.1
3a1d4d51-6283-46dd-93f4-7ecdbd507fe1 | checkpoint | Excavation
ad9928fb-1256-5910-92af-f1aeac6433d0 | note | Acceptance Criteria and Frequency (Project Specific) - Excavation constructed to the shapes, alignment, and level shown on the drawings. Where in situ material at the bottom of excavations is other than rock, the material has been compacted to not less than 95 percent standard compaction as determined by AS 1289.1-2000 Methods of testing soils for engineering purposes - General requirements and list of methods. Compaction Testing: 1 test per structure foundation
4627993a-e508-5f4e-8a5a-40f173a0956f | note | Check Item - Check and Verify
1c7ccd6e-e0bf-5687-a9ed-3560264b2e9d | note | Reference - Standard specification No. 3 Cl3.1
fdaf79c7-8a57-4191-84b3-34eac8dfef8f | checkpoint | Foundation
40ce62bb-9d98-5f46-b6e2-07b473d85442 | note | Acceptance Criteria and Frequency (Project Specific) - Trench Foundation inspected prior to placing of Structure. Hold Point If poor trench conditions exist, the pipe, or structure shall be supported by rock ballast which is • sound igneous or metamorphic material that does not disintegrate in water; • of a 50mm nominal size; • completely wrapped in a non-woven geotextile fabric 1.9mm minimum thickness; • tamped into place.
52cbfcf1-559a-559f-8e9e-d57bf2e6e7c4 | note | Check Item - Hold Point
947cc46a-8175-5bc2-9b43-334eb54b729d | note | Reference - RID/15/2018 Cl 7.0 & Standard specification No. 3 Cl3.3
3f08a552-5707-4de2-b34f-7df6a11c0d4b | signoff | Hold Point
53fa80d9-c057-4e47-b130-474684358506 | checkpoint | Formwork Walls
c9debfe4-a115-53b2-a6be-28d1c087e5e5 | note | Acceptance Criteria and Frequency (Project Specific) - Where the sides of excavations are in solid ground, the manhole shafts may be constructed without the use of backforms. Where concrete is placed without the use of backforms, the specified wall thicknesses is increased by not less than 50mm
b98be779-69c3-5c07-b60a-a9cea64c7f07 | note | Check Item - Check & Verify
f6df349c-ec3d-5701-b965-6cb8f8a9723c | note | Reference - Standard specification No. 6 Cl6.3
c5fd00cb-cccb-4622-9634-9847ac9c5862 | checkpoint | Access Chamber/Gully Pit Walls
9adb130a-7a9e-50bb-b221-02a451165f3a | note | Acceptance Criteria and Frequency (Project Specific) - The walls of gullies and manholes are constructed so the thickness is nowhere less than the minimum shown on the plans nor greater than 300mm above the design thickness.
52050fdc-5ecb-5094-aef4-fabd6f69d340 | note | Check Item - Check & Verify
4214d116-efc1-54eb-8180-463b0e4c7f91 | note | Reference - Standard specification No. 3 Cl6.3
b63be4ff-3983-4413-b62e-1495ec3aeea2 | checkpoint | Concrete Batching
b63c030b-58a7-5722-b5ab-14368014ba18 | note | Acceptance Criteria and Frequency (Project Specific) - Ready mixed concrete is supplied by a manufacturer: (a) approved by the local government; (b) which has an accredited quality assurance system.
dbe18992-9ed0-56dc-b5d4-cbb0b9035d23 | note | Check Item - Check and Verify
983af1d1-3038-5a62-a512-d5559bff97f6 | note | Reference - Standard specification No. 8 Cl2.5
355b473f-f425-4dc4-abb9-1e6b8e349dd3 | checkpoint | Concrete Testing
5b360e77-5b45-588a-8831-5f051c7d917d | note | Acceptance Criteria and Frequency (Project Specific) - The frequency of sampling and testing to be in accordance with the Department of Transport and Main Roads – MRTS070 Concrete Technical Specification – Sampling Frequencies per Lot for 28 Day Strength Tests.
ba8af93b-f47a-57e1-81da-3b574f99ca03 | note | Check Item - Test Results
a8c6f8ec-f95d-5cd9-a6a2-fb4018cce485 | note | Reference - Quotation Notes Cl25.0
a69983bd-7eb5-466e-9efd-7fcf7d88f371 | checkpoint | Concrete Slump
d15a4c5c-3763-59b4-bf8c-b14d59743469 | note | Acceptance Criteria and Frequency (Project Specific) - The consistency and workability of concrete shall be such that it complies with the Slump limits specified in Table 2.4.1 below. Any extra water that is added to concrete on site shall be measured and recorded and the concrete shall be thoroughly remixed and reslumped.
a7993e44-4bd0-572c-a5fe-9c19daccf550 | note | Check Item - Check & Verify
a70a6c49-157c-5353-ad2d-a58e9decd7a4 | note | Reference - Standard specification No. 7 Cl2.4
3fd14542-7f55-45b3-aec2-c86050785d9d | checkpoint | Approval to place concrete
1d3e8e1e-a721-528c-bfde-938b19d4b746 | note | Acceptance Criteria and Frequency (Project Specific) - All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the Inspector. Hold Point
372a964e-1a87-5b54-baac-f8f38584dfe0 | note | Check Item - Hold Point
f6b15388-6027-5020-aa3a-a2cc8a20ccc6 | note | Reference - Standard specification No. 8 Cl4.1
8e98c01d-7d13-49c2-a920-ddfa38d04700 | signoff | Hold Point
777423cd-01bf-4f38-bc3b-682a68a660c2 | checkpoint | Placing time limit
3a81fd4b-85c2-5c88-842f-b0cb58d80973 | note | Acceptance Criteria and Frequency (Project Specific) - Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government.
60bc8203-5881-5fa6-a7a3-63700fff3420 | note | Check Item - Check & Verify
e1ed36fa-d522-51c6-87e1-442c8ea0a276 | note | Reference - Standard specification No. 8 Cl4.3
3a106dbb-5ad2-4cea-8c72-869eadc01a86 | checkpoint | Removal of Forms/Falsework
0d49e749-9bd1-5934-958c-0fbc9e40c6a7 | note | Acceptance Criteria and Frequency (Project Specific) - Forms/Falswork shall not be removed from the concrete until the times specified the table below are met:
761c4019-0915-57fc-adb3-b0be73ea0903 | note | Check Item - Check & Verify
a3979b9d-7921-56ef-8f2d-2fa76a6cf68a | note | Reference - Standard specification No. 8 Cl6.2
3106a610-dd57-4a75-bece-da371067fbe6 | checkpoint | Concrete Benching
2d54aacb-b354-5297-a7c5-ff378ed9f02c | note | Acceptance Criteria and Frequency (Project Specific) - Concrete benching is provided to manholes, gullies and inlet pits and is shaped to the shape specified and has smooth, even surfaces and neat edges.
700c61ab-e356-5f1c-9fbd-58dfe711ee27 | note | Check Item - Check & Verify
abc35c8e-c6fc-57ef-a855-ed03786d8df9 | note | Reference - Standard specification No. 3 Cl6.3
4aeba786-6296-4f75-84f6-f9e05e428f5d | checkpoint | Pipe Joint
d57f2f39-8820-5123-9266-bde8f34923bb | note | Acceptance Criteria and Frequency (Project Specific) - The joints between access chambers/gully pits and pipes shall be made water tight using cement mortar and shall be finished to provide smooth surfaces, uniform with the inner surfaces of the chamber/pits.
90122abd-55ff-5f0f-9118-9a4d95152514 | note | Check Item - Check & Verify
b79d9a06-0036-5f3b-9945-755be14ca532 | note | Reference - Standard specification No. 3 Cl6.3
5ed284f7-0749-4013-a479-dffc6c28ed2c | checkpoint | Concrete Top Slab/Entry Units
a96d41b2-5e51-596f-94b5-96c3a342b744 | note | Acceptance Criteria and Frequency (Project Specific) - Concrete top slabs, inlet units and converter slabs shall be joined to the access champers/gully pits using cement mortar or epoxy mortar.
cb34131f-e81c-5f52-92bb-448eca3ccfad | note | Check Item - Check & Verify
ed8540e0-a800-5db2-a2e0-54e0ff5a2dc8 | note | Reference - Standard specification No. 3 Cl6.3
9cad611e-9331-4f52-ba5b-138b9414e3ae | checkpoint | Backfilling
3bfaab13-7531-5c6b-bc36-401f5d26f37c | note | Acceptance Criteria and Frequency (Project Specific) - Backfilling has been completed in accordance with Stormwater Pipe Installation - ITP
c7e39f49-d44f-5218-9184-a6156df21f45 | note | Check Item - Check & Verify
57d0c654-c6a9-52d9-af80-0388517a87cc | note | Reference - Stormwater Pipe Installation ITP
e06cc5d0-ccf3-4e30-94ba-4ead0e5df5ea | checkpoint | Final Verification
6fec827b-207d-52d9-8140-c37033c5468f | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
a8b6f6c9-cced-5f5a-b2b8-438a9762943b | textbox | Print Name:
178c6389-1819-5a49-8b75-b1a07a08b5eb | date | Date:
95d34784-7f12-5f31-9e03-59232cc04606 | note | Client Verify that the Above has been Constructed according to Specification
c92906ea-d7f9-5094-bc53-379b61ec6a12 | textbox | Print Name:
84d35d38-69c2-5d25-9774-51898ae2a06b | date | Date:
c23965a7-9e9b-45b5-8096-45e737fb864c | signoff | Signature
7f8c5d4e-91b8-4ecb-8cfe-61c65b9a1adb | checklist | Installation of Precast Access Chambers / Gully Pits | itp | Installation of Precast Access Chambers / Gully Pits
74da47b5-7e48-45d6-ba2a-b615c82f49cd | section | Details
07af6f9b-e729-487e-b89c-204cf7d44808 | checkpoint | Lot Boundaries
c3e05094-bbfe-5136-b3d6-437ad977501a | note | Lot Size: Each Stormwater Structure
85ac0a17-4c0a-5c14-af4a-ddd94214ae46 | note | Check Item - Check & Verify
15e055a4-6597-418e-95fc-3fe3c2b28200 | checkpoint | Setout
6c66ebd0-99ee-5510-b67a-eceff952f1da | note | Acceptance Criteria and Frequency (Project Specific) - Stormwater structures set out in accordance with the details shown in the drawing.
a2c93f44-ed24-5880-bb97-3f438beec674 | note | Check Item - Check & Verify
b90b5ac8-3689-502c-877e-d0271e7fa442 | note | Reference - Standard specification No. 3 Cl3.1
62b79b87-32fb-4f54-86c3-ead25b619190 | checkpoint | Excavation
0b822ee3-bc26-51a8-bf51-1b253813ebe9 | note | Acceptance Criteria and Frequency (Project Specific) - Excavation constructed to the shapes, alignment, and level shown on the drawings. Where in situ material at the bottom of excavations is other than rock, the material has been compacted to not less than 95 percent standard compaction as determined by AS 1289.1-2000 Methods of testing soils for engineering purposes - General requirements and list of methods. Compaction Testing: 1 test per structure foundation
d43a9684-200a-592b-a49f-239db3c19a59 | note | Check Item - Check & Verify
135a5ee1-9b07-515f-b410-d869fb133933 | note | Reference - Standard specification No. 3 Cl3.1
d6997f14-bada-4adc-8fcf-005b2315c98b | checkpoint | Foundation
dd31896b-c548-5f48-a68b-937a9db5f8a8 | note | Acceptance Criteria and Frequency (Project Specific) - Trench Foundation inspected prior to placing of Structure. Hold Point If poor trench conditions exist, the pipe, or structure shall be supported by rock ballast which is • sound igneous or metamorphic material that does not disintegrate in water; • of a 50mm nominal size; • completely wrapped in a non-woven geotextile fabric 1.9mm minimum thickness; • tamped into place.
c7b27c88-eacb-5618-b041-80af5197db8f | note | Check Item - Hold Point
14340202-fbde-51a4-9332-a71d5edc513f | note | Reference - RID/15/2018 Cl 7.0 & Standard specification No. 3 Cl3.3
51ece6a5-3040-4731-aa40-165ea8804874 | signoff | Hold Point
866841be-b317-49a7-96c3-e164b3a22e5f | checkpoint | Installation Precast Base
5eb9fcc7-7f71-534d-98dc-eea7a7d1add4 | note | Acceptance Criteria and Frequency (Project Specific) - Precast base installed in the location and levels shown in drawing within the following tolerances: o invert levels–±50mm; o manhole locations–within 1,000mm of design; o gully locations–within 300mm of design
244c65f7-3f64-5bd6-a49d-cc382cc60c59 | note | Check Item - Check and Verify
8d9ceba3-9b09-52e3-aab5-541571d7f3e1 | note | Reference - Standard specification No. 3 Cl3.2
a398db79-1086-4943-a153-cb4db78c48d6 | checkpoint | Concrete Benching
d8446a9a-aca4-5aea-93e4-dc2f3f457027 | note | Acceptance Criteria and Frequency (Project Specific) - Concrete benching has been provided to manholes, gullies and inlet pits and is shaped to the shapes specified and has smooth, even surfaces and neat edges
5f2ffbe7-dd19-5548-a54b-59075952d6b1 | note | Check Item - Check and Verify
a721778b-0edc-5c66-adba-90af7eff155f | note | Reference - Standard specification No. 3 Cl6.3
9ced05dc-0a88-4264-8c00-d198ec2762c1 | checkpoint | Joining of Precast Sections
b2556eec-ba11-580d-9340-b44f388d89bc | note | Acceptance Criteria and Frequency (Project Specific) - Where Pre-cast systems are constructed by lowering the precast shaft section onto a precast base and a converter slab onto the precast shaft. In accordance with manufacturers' instructions, an Epoxy resin has be applied to both joint surfaces prior to joining.
7fb2565f-c6db-5a50-9559-2716258e6c31 | note | Check Item - Check and Verify
2ce0a8b6-e27f-58ad-974f-778b4d8e9b58 | note | Reference - Humes Installation instructions
d01818b0-14b5-4d75-aa56-8e32b9adb658 | checkpoint | Pipe Penetration Cut Outs
c37c3493-52eb-5400-9c53-e9f26101c900 | note | Acceptance Criteria and Frequency (Project Specific) - Cut outs for pipe penetrations have been made using concrete saws or drills in such a manner as to minimise damage to the pre-cast units. Precast concrete shaft sections joints have been made watertight using an epoxy compound or using cement mortar and the joints have been be finished to provide smooth surfaces, uniform with the inner surfaces of the structures
75fe8b31-165f-52fa-b4c6-1698877fb64e | note | Check Item - Check and Verify
c8bf1597-7571-5867-91a7-a019c99e4f3a | note | Reference - Standard specification No. 3 Cl7.3
cd77c1b5-dbce-418b-8102-372b50607909 | checkpoint | Concrete Top Slab/Entry Units
3797b333-545b-5e76-ace3-75e274f8ffea | note | Acceptance Criteria and Frequency (Project Specific) - Concrete top slabs, inlet units and converter slabs shall be joined to the access champers/gully pits using cement mortar or epoxy mortar.
23d973a9-d781-551d-a0c1-8175978211ac | note | Check Item - Check and Verify
8c420eee-ae50-54cd-bbf9-5ef1741838b9 | note | Reference - Standard specification No. 3 Cl6.3
0c07be6c-970d-484f-9a97-d48579e73f53 | checkpoint | Backfilling
a1fb9a00-3707-5f53-920b-347847063412 | note | Acceptance Criteria and Frequency (Project Specific) - Backfilling has been completed in accordance with Stormwater Pipe Installation - ITP
e1e3fbc1-3e6f-58ac-ae5a-24f7df306e76 | note | Check Item - Check and Verify
f6674c75-c334-5479-b3da-f4f9c057d8ba | note | Reference - Stormwater Pipe Installation ITP
5ab09342-d2e0-4aec-bde0-57798b6cf15c | checkpoint | Final Verification
38c3204d-6237-53fd-a551-32e87572cb11 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
9155bc98-3e05-5453-9c8e-6d4ea1238d9b | textbox | Print Name:
ddc85a8a-4b1b-547b-b5a9-79684f7d0f89 | date | Date:
85f30b02-d1c0-5214-9cbc-fa1c00facb58 | note | Client Verify that the Above has been Constructed according to Specification
ea6a19de-8a14-57cf-a204-ca9e903133b5 | textbox | Print Name:
b567b34a-83e7-5c4a-a313-f47a8451c2ba | date | Date:
9bb2953c-4e74-4612-aef1-061ac5d9e995 | signoff | Signature
ceb5533f-576e-4e9d-b6d4-707e5f165f84 | checklist | Landscaping | itp | Landscaping
2d82a79e-9c32-47fc-83a7-15201bd0caa1 | section | Details
3904c545-0f47-4be8-8249-d44e1183392c | checkpoint | Landscaping Materials
5b7e0f46-bdab-5d6c-b3f5-274253737777 | note | Acceptance Criteria and Frequency (Project Specific) - Materials and workmanship comply with the relevant Australian Standards. Manufactured items used in accordance with manufacturer's specification. All landscape materials (soil, plants and mulch) free from fire ants, certificate or legislation.
942b61ae-dd01-5eb5-a1b1-828966145b3c | note | Check Item - Check & Verify
6154db24-ed16-56f8-a0d8-78314e3373b6 | note | Reference - Standard specification No. 2 Cl2.1
08b3f791-5196-4788-85dd-da659306d1fe | checkpoint | Landscaping Commencement
5818274d-3175-5e9f-a483-b45d5c8850d9 | note | Acceptance Criteria and Frequency (Project Specific) - Prior to landscaping works commencement, the Contractor shall liase with LCC Site Representative to confirm locations / spacing of plants.
ac2c71d5-ecbb-5872-a792-a3eb594f050f | note | Check Item - Hold Point
ccb6ec1b-b6aa-565c-bfcd-805269f8ecbe | note | Reference - Quotation Note No. 85
1af3d839-7c88-4027-a9a1-043838b32171 | signoff | HOLD POINT
d26d77a2-13a5-4bd0-bb8e-0699972f38e3 | checkpoint | Plant Management
39d76c2f-9af1-57a6-96dc-8afe20573d46 | note | Acceptance Criteria and Frequency (Project Specific) - Plant protection, works near trees, damage, maintenance, removal and weed eradication to be in accordance with Standard Specification No. 3 Cl 3.
69178cd1-0b06-583d-ae9b-8bb65be52365 | note | Check Item - Check & Verify
d92afac5-028b-558c-a949-12c92cb0be24 | note | Reference - Standard specification No. 2 Cl 3
5c8ab4ed-aea4-4842-a9ec-b5f39c7658bc | checkpoint | Earthworks
13f8ffaf-84cc-53ba-92fc-68ac64712962 | note | Acceptance Criteria and Frequency (Project Specific) - Erosion and sediment control, clearing and grubbing, stockpiles, softworks grades and earth mounds to be in accordance with Standard Specification No. 3 Cl 4. The maximum grade for a garden bed is 1 in 3. The maximum grade for a garden bed is 1 in 4.
4d65dc86-a1f5-50bf-b2b8-ea65d24dc82c | note | Check Item - Check & Verify
f2dc7e65-eb92-5cba-aa23-1917da294e41 | note | Reference - Standard specification No. 2 Cl 4
e4f3498f-cc91-4dce-af75-e70189963e3e | checkpoint | Hardworks
37c4adf1-46de-524d-bc2e-9696b2a7993f | note | Acceptance Criteria and Frequency (Project Specific) - Edges to garden areas, outdoor furniture, play areas, and bollards to be in accordance with Standard specification No. 3 Cl 5
cb493a93-c37a-509b-a449-4fe1240e1210 | note | Check Item - Check & Verify
7e03c6bf-29f6-535f-94cd-5cb0df47e2c8 | note | Reference - Standard specification No. 2 Cl 5
fb35acc5-9f4a-450a-a7ef-19ae04138424 | checkpoint | Softworks
72ac0af5-f4c4-593f-9315-48631a7cbb67 | note | Acceptance Criteria and Frequency (Project Specific) - Cultivation, soil, fertiliser, plant material, tree planting, transplanting, plant size, mulch, organic stabilisation matting, turfing and grassing and rehabilitation planting to be in accordance with Standard Specification No. 3 Cl6
4e7a7980-1cc2-5a74-8484-6025b68814cc | note | Check Item - Check & Verify
d8a3c8e4-cea1-5b46-9e3e-5c0df40988a5 | note | Reference - Standard specification No. 2 Cl 6
3f15581b-9144-47da-bc2f-d51fe9cf4d63 | checkpoint | Maintenance
ce98037c-e94d-5ed8-9674-71d87712e5a9 | note | Acceptance Criteria and Frequency (Project Specific) - Maintenance works and spraying of plants to be in accordance with Standard specification No. 3, Cl 7.
a30e28b1-1841-54ce-8420-69284489d9a4 | note | Check Item - Check & Verify
ce887c09-ec27-5248-9ced-0ea4c2fa44a0 | note | Reference - Maintenance works and spraying of plants to be in accordance with Standard specification No. 2, Cl 7.
6df0095d-9b7c-497b-a121-dbedb215d185 | checkpoint | Revegetation (Topsoil)
f7ae1257-5fd3-503c-be2c-3856be043911 | note | Acceptance Criteria and Frequency (Project Specific) - All embankment batters are to be topsoiles with a minimum 75mm of topsoil. Prior to topsoil being placed, the batters shall be lightly tyned to a depth of 75mm.
092e9859-69aa-5dfc-9cf4-a7d558965ef9 | note | Check Item - Check & Verify
e8ee2821-4c65-5396-bc3b-e419a66b1499 | note | Reference - Operations Specification RID/14/2018 and RID/15/2018 Civil Construction Services Part 32.
dd387968-e3b9-44da-8303-b477f4a0f8f0 | checkpoint | Revegetation (Grassing)
5c3dbeb3-3933-547e-a15a-ddd0a969f0f6 | note | Acceptance Criteria and Frequency (Project Specific) - Unless directed otherwise by the Superintendent, grassing shall be rolled turfed (not seed or hydromulched products). Sufficient allowance made by Contractor to maintain turf with watering such that turf does not brown off and until such time that turf has taken root in topsoil and is not able to be lifted away from the ground by hand.
4356cf5f-3eab-52d7-9d3b-af6d854ff837 | note | Check Item - Check & Verify
958863a5-93b9-5166-b317-55a72b88dda6 | note | Reference - Operations Specification RID/14/2018 and RID/15/2018 Civil Construction Services Part 32.
6c27b29c-ae28-41ce-a297-6e19a9ba9d65 | checkpoint | Contractual Provisions
44a95ee9-6ff1-54b2-b2d3-15c9b2fd70e8 | note | Acceptance Criteria and Frequency (Project Specific) - The Contractor must obtain written approval of the Superintendent before ordering alternative materials.
16b9c710-ad29-5c82-bcc8-6cae53ab5d9f | note | Check Item - Hold Point
ec229407-192a-57d2-8bd1-32d1fed82804 | note | Reference - Standard specification No. 2 Cl8
c726e357-1b6c-4389-8067-52aef5222872 | signoff | HOLD POINT
9e9409ef-f2ff-44e6-941b-872144b1eb10 | checkpoint | Final Verification
9fca7e51-5607-5cf4-a5ee-05d918c37804 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
19fbcaa1-8d9c-53de-806e-99bec37b494e | textbox | Print Name:
999fd193-3aca-50d1-aa31-44ed1c44b793 | date | Date:
8dc1d265-826b-5d24-918c-5a9e3d3e7a3b | note | Client Verify that the Above has been Constructed according to Specification
e111d87b-6b5c-561a-80e8-fdda2ea8c16b | textbox | Print Name:
f38b9036-8ee3-5751-8158-85bafc30109e | date | Date:
d9ccc7fe-0587-4a11-a197-ef724ee0500c | signoff | Signature
c6dc35f7-bb26-4f34-919e-3c5212d6c053 | checklist | Linemarking | itp | Linemarking
cd28edd1-60b3-42bd-bbd6-56fab53ccc41 | section | Details
abfaeab7-bbac-4887-a0a1-a7568eb48d7f | checkpoint | Linemarking Accordance
f4742210-caca-5ceb-bb6f-79213ca8962e | note | Acceptance Criteria and Frequency (Project Specific) - All Linemarking shall be in accordance with manual of uniform traffic control devices. Surplus pavement markings shall be removed by a method approved Council
be0d8fe5-7f1e-5641-8973-e856fc1b0734 | note | Check Item - Check & verify
cbed5631-918d-5aed-9506-c07df488df2b | note | Reference - Project Drawings General Notes Cl11.
4ea77bf7-34bc-4894-b437-b2555293b69c | checkpoint | Minimum Placement Period between Operations
18603720-398c-5f6a-8228-0e404f29cdee | note | Acceptance Criteria and Frequency (Project Specific) - The Contractor to ensure that there is a minimum period of 72 hours between the placement of asphalt wearing course/spray seal surfacing and line marking installation.
a76c094b-4704-557f-a768-283a422b74cf | note | Check Item - Check & Verify
a95f7a66-79d9-596a-8cb0-b66c46b23f22 | note | Reference - Quotation Notes Cl63.
ea33159e-97a0-4189-8e5b-051f4b78185e | checkpoint | Application of Linemarking
f47aac49-d871-5434-a5e6-0c251c2ae000 | note | Acceptance Criteria and Frequency (Project Specific) - Linemarking (excluding thermoplastic) shall be marked at an application rate of 0.375 litres/m2 +/- 0.025 litres/m2. All transverse Linemarking and arrows are to be placed in Thermoplastic unless otherwise directed by the Superintendent.
d284361b-1394-5f00-b62a-a036db24eb77 | note | Check Item - Check & Verify
2af7dcde-4cce-557a-bcb2-882b22658032 | note | Reference - Operations Specification Cl31.
42c9a678-fad9-48de-873d-f5b2599f439e | checkpoint | Final Verification
6674b8e9-a97c-508e-9fad-28e076e0b294 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
7903968c-a041-57f7-96c8-87c7846861ff | textbox | Print Name:
e4c3e984-cc41-5c7d-b06e-1b23bbb2890b | date | Date:
b1bd9f86-2da2-5ef0-95b4-a58c4ad045df | note | Client Verify that the Above has been Constructed according to Specification
8b262f35-69a3-5eec-89d2-aa46bd286abc | textbox | Print Name:
73fabd39-c4ea-5b33-bcf3-0c079f8df4b2 | date | Date:
87ef3f22-993d-412b-9a10-6edab57cf089 | signoff | Signature
3665ab96-e35f-41de-a871-af60d6fdc99f | checklist | Minor Concrete Works (Kerb & Channel) | itp | Minor Concrete Works (Kerb & Channel)
ed74a11b-b49b-4ffd-b610-0a8c34438a5c | section | Details
3561ba87-a242-4bb0-ac69-701e84579063 | checkpoint | Kerb and channel
3393ea05-6c13-5fd4-ba60-1a43328013bf | note | Acceptance Criteria and Frequency (Project Specific) - kerb and channel rehabilitation works, the kerb and channel are to be constructed in accordance to the LCC Supplementary Specification for Kerb & Channel Rehabilitation Projects
edf8537e-393b-5ca7-acc7-4a8011aee615 | note | Check Item - Check & Verify
7c7ac645-8f93-518b-88e0-e816d6059f74 | note | Reference - Quotation Notes Cl41.
adf9598e-708c-46ba-b657-c8eb73d5799b | checkpoint | Pavement under kerb and channel
79af41d8-9775-5927-9d43-1eaab9563a68 | note | Acceptance Criteria and Frequency (Project Specific) - Where pavement thickness exceeds 175mm in depth, the pavement shall extends under the kerb. Where the pavement thickness does not exceed 175mm in depth, the kerb and channel shall be firmly bedded on 100mm road base aggregate compacted to 95 percent modified dry density
991aebf9-35af-59e2-9987-52693968d141 | note | Check Item - Check & Verify
15fed348-137d-5546-86a4-cf1cee85c254 | note | Reference - Standard specification No. 8 Cl6.2
313932cb-9d7b-4cba-b0f5-5c90d01d4f35 | checkpoint | Machine placed kerb and channel
e934c8e3-c94e-573a-9dd1-f19f33123ace | note | Acceptance Criteria and Frequency (Project Specific) - 1. Where a kerb and channel machine is used to place the replacement kerb and channel, a 20MPa kerb mix with maximum aggregate size of between 5mm and 10mm shall be used. 2. A minimum slump of 12mm shall be adopted for this mix. The concrete shall be fully compacted and finished with a high strength sand/cement slurry to the profile as specified
6e0de378-e607-5c7e-b2d3-baaa93e3605e | note | Check Item - Check & verify
c5c2647c-3b37-528f-988d-d21e9bafb3b6 | note | Reference - Standard specification No. 8 Cl6.4.1
37b363d2-5e64-4e59-827f-a99954f577a2 | checkpoint | Hand placed kerb and channel
cb61eb27-8ca4-59d2-b74d-962e786ab0ad | note | Acceptance Criteria and Frequency (Project Specific) - 1. Where the replacement kerb and channel is placed and finished by "hand" an N25/20 grade concrete shall be used with a minimum 40mm and maximum 80mm slump. 2. The concrete shall be fully compacted with vibratory equipment, shaped and trowel finished to match the profile of the adjoining kerb and channel or to a profile as otherwise specified. 3. Transitions between different kerb types shall be done over a distance of at least 2.0 metres.
38e5668f-eadb-5e40-97a3-2035bbdafaab | note | Check Item - Check & Verify
28b70e17-b374-50da-a951-48294ac6e0eb | note | Reference - Standard specification No. 8 Cl6.4.2
a9715fc1-abb1-47d9-85ef-bc0bbc389c46 | checkpoint | Backfill behind kerb & channel
0a5e5ea6-b3bd-57e6-a4b9-cd8ebaf93627 | note | Acceptance Criteria and Frequency (Project Specific) - When suitably cured, the kerb and channel shall be backfilled with a suitable granular material, compacted and finished with 50mm of topsoil and turfed with a minimum 'B' grade couch turf. Excavated pavement material may be reused as kerb backfill.
cdb42509-74d3-5ad8-9e09-80421ec8f8d0 | note | Check Item - Check & Verify
33fb3b31-f297-5e05-a0aa-29be1adeccc0 | note | Reference - Standard specification No. 8 Cl6.5.1
3258ac33-7557-49d8-8457-0c397368a233 | signoff | HOLD POINT
d2ae0a0f-2bed-4383-af06-c0a2e874bbf6 | checkpoint | Final Verification
39681c5e-205c-5425-a22d-8c32369b0b47 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
1e2933f4-e594-5819-a03a-3ea81c7122a0 | textbox | Print Name:
74c4e0c6-3b07-590a-aaa7-e391765152da | date | Date:
443c9083-cdad-50f7-9b32-a8c21066bf1b | note | Client Verify that the Above has been Constructed according to Specification
7f23cb58-26f5-56df-a066-62e09a249ecf | textbox | Print Name:
5981e60c-5c5c-5d05-b920-5a6cd232f334 | date | Date:
66a25be4-d368-4669-a1b9-13246412a0e2 | signoff | Signature
4635ee48-5472-4fe0-bbce-d39bc24bc00f | checklist | Reinforcement for Drainage Structures | itp | Reinforcement for Drainage Structures
8ea3694d-6960-437b-b580-4b9153d5777a | section | Details
cbe182ac-1855-4ffd-9485-753215ac4853 | checkpoint | Material for Reinforcement
0e85117f-aecc-5938-ba5d-3ddc5721eb83 | note | Acceptance Criteria and Frequency (Project Specific) - All materials for reinforcement comply with the relevant Australian Standards as per Standard Specification No. 9 Cl 2.1
112db7b6-ed69-51c7-8216-f61791adeb43 | note | Check Item - Check & Verify
0887e2c4-94b2-524e-a432-03b799de18af | note | Reference - All materials for reinforcement comply with the relevant Australian Standards as per Standard Specification No. 9 Cl 2.1
bbc2f011-b473-42bd-8db8-4096573ac881 | checkpoint | Protection
295ba288-186a-56b0-be55-8212e3f720b7 | note | Acceptance Criteria and Frequency (Project Specific) - Reinforcement is to be protected from damage at all times. Reinforcement is stacked in racks or on timber above ground, kept clear of contamination and cleaned if accidental contamination occurs.
47f54d70-5794-5677-8509-37a0fcd02d91 | note | Check Item - Check & verify
b415779d-5ef7-5e83-9e49-11a96d1acbca | note | Reference - Standard Specification No. 9 Cl 3.1
1618dee9-94ed-47de-a9aa-3b75993b6a47 | checkpoint | Cutting & Bending
d1689b0e-6262-582e-80b9-b874a21715b3 | note | Acceptance Criteria and Frequency (Project Specific) - Approval to hot bend reinforcement on site.
92a3acf4-3cb8-5286-9f86-01d8085f181a | note | Check Item - Hold Point
54782d4f-0216-506a-8225-cc6afd6abc6f | note | Reference - Standard Specification No. 9 Cl 4.1
11610816-f0b6-4c58-9232-828ba90f5452 | signoff | Hold Point
5078b6a8-185b-4511-9eab-e64daa21205d | checkpoint | Cutting & Bending
bc1df7c2-f37e-552f-bd9a-79a32603cc48 | note | Acceptance Criteria and Frequency (Project Specific) - Reinforcment is fabricated to the shape and dimensions shown on the approved drawings and within the following tolerances: (a) on any overall dimension for bars and fabric except where used as a fitment (i) length up to 600mm, 25mm, +0; or (ii) length over 600mm, 40mm, +0; or (b) on any overall dimension of bars or fabric used as a fitment: (i) for deformed bars and fabric, 15mm, +0; or (ii) for plain round bars and wire, 10mm, +0; or (c) on the overall offset dimension of a cranked column bar -0, +10mm; or (d) for the sawn or machined end of a straight bar intended for use as an end-bearing splice, the angular deviation from the square measured in relation to the end 300mm is within 2 degrees.
92a09df4-6d69-5827-a856-cbab31eb8c2d | note | Check Item - Check & Verify
dfc3fe55-f552-586e-9ca3-0c78e6d3f16c | note | Reference - Standard Specification No. 9 Cl 4.1
fc328f78-f4d6-49d0-ba60-d716f1ec618b | checkpoint | Surface Condition of Reinforcement
85a29ac5-b4f6-5454-afb5-51829a2a11e9 | note | Acceptance Criteria and Frequency (Project Specific) - Reinforcement projecting from a previous concreting operation is cleaned free of adhering concrete or loose slurry prior to any further embedment.
f571eb63-d883-52b3-a93f-9ce83ea48bbe | note | Check Item - Check & Verify
0a3be9eb-5382-5529-a772-7e384ee2cd6d | note | Reference - Standard Specification No. 9 Cl 5
d2831f24-9bc7-4eab-973c-eea33a28b93b | checkpoint | Placing & Fixing
f1f1982e-cb03-5537-930e-814584f9ea8a | note | Acceptance Criteria and Frequency (Project Specific) - Reinforcement is placed in position as shown in the approved drawings
d41ea3bc-22d2-5aaf-ab4f-80a38f8c3e53 | note | Check Item - Check & verify
bc51cb1f-7359-590a-a41d-8e8a3fcb0105 | note | Reference - Standard Specification No. 9 Cl 6
8dc9138d-5201-4b97-be4b-80fb10eababf | checkpoint | Tolerance on Position of Reinforcement
bf392927-5118-52bc-8d1a-d8cbbfb16978 | note | Acceptance Criteria and Frequency (Project Specific) - The deviation from the specified position of reinforcement and densons do not exceed: (a) for positions controlled by cover: (i) in beams, girders, slabs, columns and walls, -5mm and +10mm; (ii) in slabs-on-ground including foorings of walls and culverts, -10mm and +20mm; (iii) in footings cast in the ground where the depth of the footing is 500mm or more, -20mm and +40mm; (b) for positions not controlled by cover: (i) the location of reinforcement on a profile, 10mm; (ii) the position of the ends of reinforcement along the line of the bar, 50mm; (iii) the spacing of bars in walls and slabs and of fitments in beams and columns, whichever is the greater of: (A) 10 percent of the specified spacing; or (B) 15mm, whichever is the greater.
74ce7a50-b0fd-5a16-9d7f-bcc0c4fc335a | note | Check Item - Check & Verify
fe4dd580-4ebe-5804-9ca9-871af560238e | note | Reference - Standard Specification No. 9 Cl 7.1
b9f424a9-8a82-4ee7-bc84-d068a87aecef | checkpoint | Splicing
ce8f7410-dafe-5774-9b0b-9bf3a86a941b | note | Acceptance Criteria and Frequency (Project Specific) - The splicing of reinforcement occurs only in the locations shown in the approved drawings.
5623dbe6-8872-593d-b42f-b862ba996194 | note | Check Item - Hold Point
040ca54c-3647-5e65-8283-4f1dbd9750f8 | note | Reference - Standard Specification No. 9 Cl 8.1
6328fb92-e4a7-4f8e-abb8-57f16d639ed0 | signoff | Hold Point
aa5f6d9b-2099-4895-9f99-a2dea3e761e9 | checkpoint | Substitution
22ded3cc-5b1b-54e2-a129-3543f6bffac0 | note | Acceptance Criteria and Frequency (Project Specific) - Approval for the substitution of reinforcement.
bcde16c1-6432-5eeb-ae9b-379e106e5124 | note | Check Item - Hold Point
ef40e15b-d444-58ba-b91d-d900451cd21a | note | Reference - Standard Specification No. 9 Cl 9.1
73bea13a-f34c-4968-921a-a6e00f169570 | signoff | Hold Point
98994c9f-c172-478b-b9c1-5b3c257c494f | checkpoint | Fibre Reinforcement
850e42ef-39ce-5ec3-9ceb-bedbbe29d07a | note | Acceptance Criteria and Frequency (Project Specific) - Approval to incorporate fibre reinforcement into the works.
b7193671-7ee0-5f6e-95c9-adcec142fc29 | note | Check Item - Hold Point
05806c23-fec7-53c2-869f-b8decb9134b6 | note | Reference - Standard Specification No. 9 Cl 10.1
74962dd1-4789-4efd-81b6-ee018bf38edd | signoff | Hold Point
d4f0154c-f8ae-4add-9716-78c396c88007 | checkpoint | Final Verification
06025294-1930-54cb-8a1a-39c46785640d | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
f5080aae-2ecc-5298-9220-7ba038a70aaa | textbox | Print Name:
32cf05ed-f3bd-53fa-8955-224cb69f24c0 | date | Date:
f84c82a7-0c4d-5e78-871b-17ddd13e5445 | note | Client Verify that the Above has been Constructed according to Specification
985abaf6-cf19-58f1-96a4-6197cd140720 | textbox | Print Name:
249067a2-8acb-5ff7-8e1a-4915b5050c5f | date | Date:
27bae33c-bd2d-476e-9c76-be196204ea45 | signoff | Signature
495aaed8-6d5c-490f-b709-c0b28bd92782 | checklist | Unbound Granular Pavements | itp | Unbound Granular Pavements
ab7aa2a9-296c-4c8c-a6f2-818b02742231 | section | Details
8b65af8a-438c-4719-bfb4-01e5a0b0359c | checkpoint | Materials
0f95b5bf-2993-5efe-b28e-502d47252b08 | note | Acceptance Criteria and Frequency (Project Specific) - Subgrade Replacement - Type 2.5 CBR > 15 Sub-Base Course - Type 2.3 CBR > 45 Base Course - Type 2.1 CBR > 60 Equivalent unbound gravel materials for road pavements as per MRTS05 are considered acceptable for use in this project, should the Contractor determine materials adhering to MRTS05, are more readily available. Contractor is to advise the Superintendent of MRTS05 materials proposed including grading envelopes, prior to use in the contract.
9de6cf3f-746f-59e9-986f-771128c210e9 | note | Check Item - Check Item
ed4d9bf4-698b-562e-bace-1b172a916197 | note | Reference - Quotation Notes Cl 57.0
1bc26b0a-1737-429b-ae75-aa9ac4a5a937 | checkpoint | Submission of material Testing
2e60307a-6ee6-56a0-999a-6476b18dbf4f | note | Acceptance Criteria and Frequency (Project Specific) - Pavement material compliance testing is carried out by a NATA registered or equivalent accredited soils testing laboratory. Prior to the use of road base material, the developer is to submit current certified evidence obtained within the last twelve months
e85e38dc-e956-5a98-bb1c-9b27406fc92b | note | Check Item - Material Submission
f67a855c-daf4-5aa9-ad1c-aeccdd32c9f0 | note | Reference - Standard specification No. 1 Cl3.1
326b8c61-e48f-4093-8d09-ff27d5e46f57 | checkpoint | Layer Placement Thickness
cfc6abf7-21e2-537c-a562-599cab41d514 | note | Acceptance Criteria and Frequency (Project Specific) - Where the required compacted thickness of any pavement course is 200mm or less, the pavement material is spread and compacted in one layer. Where the required compacted thickness of any pavement course is more than 200mm, the pavement material is compacted in two or more layers each not less than 75mm compacted thickness and not greater than 150mm compacted thickness.
3e73db92-c1e8-56e5-81d6-fe569233252f | note | Check Item - Check & Verify
b6ba3509-1fcb-5cc4-a1c5-16661aebc163 | note | Reference - Standard specification No. 6 Cl4.2
5a59dec5-eacf-4c8b-a9e9-ee514fd5dd58 | checkpoint | Compaction
80942297-52f4-5c6b-883a-8deb4474b309 | note | Acceptance Criteria and Frequency (Project Specific) - On all transverse stormwater road crossings, field density testing must be carried out at a frequency of one test per layer of granular pavement material over each section of new pipeline. On all subsequent roads, field density tests must be carried out at a frequency of one test per layer every 50m of new pipeline unless directed otherwise by the Superintendent Transverse Lines: 1 test per Stormwater Section Longitudinal Lines: 1 test per 50m of pipeline
c326ffb5-803e-5e3d-afc0-abc9de14aa3c | note | Check Item - Test Results
a8535783-e6f3-5044-be69-079caf4afc59 | note | Reference - Standard specification No. 6 Cl6.1
3fddd52e-b860-4272-a7d3-c677a8d9338a | checkpoint | Geometrics
85595766-2df1-5e84-83d5-b74a9fff19ee | note | Acceptance Criteria and Frequency (Project Specific) - The finished pavement complies with the alignment and dimensions shown on the approved drawings or within the tolerances specified in Table 5.1.1 - Tolerance on the alignment, grade and crossfall of this standard specification.
f2e6ba8b-e4b4-52c9-b97d-1d322c4e94f7 | note | Check Item - Survey
70f61faa-6491-502e-8e22-2d3e3829a438 | note | Reference - Standard specification No. 6 Cl5.1
655c16cc-1a66-4a48-914c-76a4274038a6 | checkpoint | Proof Roll
b5d72617-4053-58a7-b48b-e67ac76d5804 | note | Acceptance Criteria and Frequency (Project Specific) - Proof rolling of the base course layer prior to placement of Asphaltic Concrete(AC) or Concrete kerb and channel shall constitute a Hold Point Proof rolling of all other intermediate layers of pavement materials shall constitute a Witness Point
faa01a83-30a9-5a09-9d50-ba87f053fb3d | note | Check Item - Hold Point / Witness point
cbdec6ac-ab76-5d95-94a8-39b6db66a90b | note | Reference - Quotation Notes Cl 59.0
ae482620-3daa-4b3e-a950-a675d9c702b0 | signoff | Hold Point / Witness Point
f7a9b942-f0b5-491a-9e31-61f18353fd6b | checkpoint | Approval to Place Subsequent Layer
5f12510a-9544-5d90-b003-3ce864d57215 | note | Acceptance Criteria and Frequency (Project Specific) - No subsequent pavement course shall be placed until the previous course, that is the subgrade, sub-base, base or existing pavement, has been inspected by the local government.
0e7f52cc-5766-579c-b519-115c2bc04703 | note | Check Item - Hold Point
0d006b36-0fad-5991-ae0b-2df833004e72 | note | Reference - Standard specification No. 6 Cl4.2
4ad0edba-9b70-4997-a189-32bfe611b13d | signoff | Hold Point
df928157-c2fb-43ad-9fe4-90f8b2f2b4b3 | checkpoint | Final Verification
da51a42b-7809-5246-a76c-73fa891efdb6 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
0fe5b221-edcc-572d-bfa1-3c12b137c45c | textbox | Print Name:
ccce793a-c6c0-5547-a526-f4c2aa632961 | date | Date:
e0c5d890-11dd-5354-a74d-be7cd645ea6e | note | Client Verify that the Above has been Constructed according to Specification
63c9f9ef-c53d-51e0-92c0-8b3b37dec1ba | textbox | Print Name:
13a79ce2-dc40-5d0d-8677-781b519845d1 | date | Date:
ff8132b0-5304-4216-a092-a5a75387fc57 | signoff | Signature