## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
ceb5533f-576e-4e9d-b6d4-707e5f165f84 | checklist | Landscaping | itp | Landscaping
2d82a79e-9c32-47fc-83a7-15201bd0caa1 | section | Details
3904c545-0f47-4be8-8249-d44e1183392c | checkpoint | Landscaping Materials
5b7e0f46-bdab-5d6c-b3f5-274253737777 | note | Acceptance Criteria and Frequency (Project Specific) - Materials and workmanship comply with the relevant Australian Standards. Manufactured items used in accordance with manufacturer's specification. All landscape materials (soil, plants and mulch) free from fire ants, certificate or legislation.
942b61ae-dd01-5eb5-a1b1-828966145b3c | note | Check Item - Check & Verify
6154db24-ed16-56f8-a0d8-78314e3373b6 | note | Reference - Standard specification No. 2 Cl2.1
08b3f791-5196-4788-85dd-da659306d1fe | checkpoint | Landscaping Commencement
5818274d-3175-5e9f-a483-b45d5c8850d9 | note | Acceptance Criteria and Frequency (Project Specific) - Prior to landscaping works commencement, the Contractor shall liase with LCC Site Representative to confirm locations / spacing of plants.
ac2c71d5-ecbb-5872-a792-a3eb594f050f | note | Check Item - Hold Point
ccb6ec1b-b6aa-565c-bfcd-805269f8ecbe | note | Reference - Quotation Note No. 85
1af3d839-7c88-4027-a9a1-043838b32171 | signoff | HOLD POINT
d26d77a2-13a5-4bd0-bb8e-0699972f38e3 | checkpoint | Plant Management
39d76c2f-9af1-57a6-96dc-8afe20573d46 | note | Acceptance Criteria and Frequency (Project Specific) - Plant protection, works near trees, damage, maintenance, removal and weed eradication to be in accordance with Standard Specification No. 3 Cl 3.
69178cd1-0b06-583d-ae9b-8bb65be52365 | note | Check Item - Check & Verify
d92afac5-028b-558c-a949-12c92cb0be24 | note | Reference - Standard specification No. 2 Cl 3
5c8ab4ed-aea4-4842-a9ec-b5f39c7658bc | checkpoint | Earthworks
13f8ffaf-84cc-53ba-92fc-68ac64712962 | note | Acceptance Criteria and Frequency (Project Specific) - Erosion and sediment control, clearing and grubbing, stockpiles, softworks grades and earth mounds to be in accordance with Standard Specification No. 3 Cl 4. The maximum grade for a garden bed is 1 in 3. The maximum grade for a garden bed is 1 in 4.
4d65dc86-a1f5-50bf-b2b8-ea65d24dc82c | note | Check Item - Check & Verify
f2dc7e65-eb92-5cba-aa23-1917da294e41 | note | Reference - Standard specification No. 2 Cl 4
e4f3498f-cc91-4dce-af75-e70189963e3e | checkpoint | Hardworks
37c4adf1-46de-524d-bc2e-9696b2a7993f | note | Acceptance Criteria and Frequency (Project Specific) - Edges to garden areas, outdoor furniture, play areas, and bollards to be in accordance with Standard specification No. 3 Cl 5
cb493a93-c37a-509b-a449-4fe1240e1210 | note | Check Item - Check & Verify
7e03c6bf-29f6-535f-94cd-5cb0df47e2c8 | note | Reference - Standard specification No. 2 Cl 5
fb35acc5-9f4a-450a-a7ef-19ae04138424 | checkpoint | Softworks
72ac0af5-f4c4-593f-9315-48631a7cbb67 | note | Acceptance Criteria and Frequency (Project Specific) - Cultivation, soil, fertiliser, plant material, tree planting, transplanting, plant size, mulch, organic stabilisation matting, turfing and grassing and rehabilitation planting to be in accordance with Standard Specification No. 3 Cl6
4e7a7980-1cc2-5a74-8484-6025b68814cc | note | Check Item - Check & Verify
d8a3c8e4-cea1-5b46-9e3e-5c0df40988a5 | note | Reference - Standard specification No. 2 Cl 6
3f15581b-9144-47da-bc2f-d51fe9cf4d63 | checkpoint | Maintenance
ce98037c-e94d-5ed8-9674-71d87712e5a9 | note | Acceptance Criteria and Frequency (Project Specific) - Maintenance works and spraying of plants to be in accordance with Standard specification No. 3, Cl 7.
a30e28b1-1841-54ce-8420-69284489d9a4 | note | Check Item - Check & Verify
ce887c09-ec27-5248-9ced-0ea4c2fa44a0 | note | Reference - Maintenance works and spraying of plants to be in accordance with Standard specification No. 2, Cl 7.
6df0095d-9b7c-497b-a121-dbedb215d185 | checkpoint | Revegetation (Topsoil)
f7ae1257-5fd3-503c-be2c-3856be043911 | note | Acceptance Criteria and Frequency (Project Specific) - All embankment batters are to be topsoiles with a minimum 75mm of topsoil. Prior to topsoil being placed, the batters shall be lightly tyned to a depth of 75mm.
092e9859-69aa-5dfc-9cf4-a7d558965ef9 | note | Check Item - Check & Verify
e8ee2821-4c65-5396-bc3b-e419a66b1499 | note | Reference - Operations Specification RID/14/2018 and RID/15/2018 Civil Construction Services Part 32.
dd387968-e3b9-44da-8303-b477f4a0f8f0 | checkpoint | Revegetation (Grassing)
5c3dbeb3-3933-547e-a15a-ddd0a969f0f6 | note | Acceptance Criteria and Frequency (Project Specific) - Unless directed otherwise by the Superintendent, grassing shall be rolled turfed (not seed or hydromulched products). Sufficient allowance made by Contractor to maintain turf with watering such that turf does not brown off and until such time that turf has taken root in topsoil and is not able to be lifted away from the ground by hand.
4356cf5f-3eab-52d7-9d3b-af6d854ff837 | note | Check Item - Check & Verify
958863a5-93b9-5166-b317-55a72b88dda6 | note | Reference - Operations Specification RID/14/2018 and RID/15/2018 Civil Construction Services Part 32.
6c27b29c-ae28-41ce-a297-6e19a9ba9d65 | checkpoint | Contractual Provisions
44a95ee9-6ff1-54b2-b2d3-15c9b2fd70e8 | note | Acceptance Criteria and Frequency (Project Specific) - The Contractor must obtain written approval of the Superintendent before ordering alternative materials.
16b9c710-ad29-5c82-bcc8-6cae53ab5d9f | note | Check Item - Hold Point
ec229407-192a-57d2-8bd1-32d1fed82804 | note | Reference - Standard specification No. 2 Cl8
c726e357-1b6c-4389-8067-52aef5222872 | signoff | HOLD POINT
9e9409ef-f2ff-44e6-941b-872144b1eb10 | checkpoint | Final Verification
9fca7e51-5607-5cf4-a5ee-05d918c37804 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
19fbcaa1-8d9c-53de-806e-99bec37b494e | textbox | Print Name:
999fd193-3aca-50d1-aa31-44ed1c44b793 | date | Date:
8dc1d265-826b-5d24-918c-5a9e3d3e7a3b | note | Client Verify that the Above has been Constructed according to Specification
e111d87b-6b5c-561a-80e8-fdda2ea8c16b | textbox | Print Name:
f38b9036-8ee3-5751-8158-85bafc30109e | date | Date:
d9ccc7fe-0587-4a11-a197-ef724ee0500c | signoff | Signature